## Map
Posession Indicator Tool
| Year | Week
| 2023 | 1
Section marked with RED = total closure on the section
Section marked with YELLOW = reduced capacity on the section
Budapest
Bratislava
Praha
Wien
Bucuresti
Constanta
Burgas
Thessaloniki
Alexandroupolis
Vidin
Sofia
Svilengrad
Athens
Principal line
Diversionary line
Berlin
Hamburg
Bremerhaven
Wilhelmshaven
Rostock
Dresden
Děčín
Kolín
Česká Třebová
Brno
Břeclav
Kúty
Nové Zámky
Štúrovo
Komárom
Györ
Sopron
Szajol
Vác
Biharkeresztes
Curtici
Timisoara
Filiasi
Simeria
Brasov
Craiova
Orsova
Coslariu
Plovdiv
Dimitrovgrad
Mezdra
Nova Zagora
Ruse
Stara Zagora
Promachon
Bremen
Hannover/Lehrte
Magdeburg
Falkenberg
Hegyeshalom
Arad
Karnobat
Újszász
Indicate possessions
2023. 02. 21.
Updated
Strymonas

## Schedule
10000
IM | ID | Section | Direction | Line |  | Year |  | Week |  | Period from |  | Period to |  | Duration | Time of Day | Reason for restriction | Traffic impact |  |  |  |  | Traffic measures |  |  |  |  | Description | International coordination | In yearly timetable | IM Project ID | Date of first publication | Date of last change | Lately announced | Re-routing possibilities
|  |  |  | From | To | From | To | From | To | Date from | Time from | Date to | Time to |  |  |  | Total Closure | Reduced Track Availability | Speed Restrictions | Weight, Length, Profile | Diesel only | Cancellation | Re-routing | Train replacement | Delays | Other
DB Netz AG | A45-011 | Hannover - Magdeburg | > | Waldhausen | Hannover-Wülfel | 2023 | 2023 | 13 | 14 | 2023-04-01 | 12:00 | 2023-04-03 | 15:00 | 2d, 3h | Continuous | Switch |  | LT | [9 empty] | 80 | N | A45-011 |  | 2021-05-11
DB Netz AG | A4E-008 | Bremerhaven - Bremen | <> | Brh-Wulsdorf | Stubben | 2023 | 2023 | 19 | 19 | 2023-05-08 | 6:00 | 2023-05-12 | 18:00 | 4d, 12h | Periodical | Miscellaneous |  |  | S | [8 empty] | 80 | N | A4E-008 |  | 2021-05-20
DB Netz AG | A4E-006 | Bremerhaven - Bremen | <> | Brh-Wulsdorf | Stubben | 2023 | 2023 | 11 | 12 | 2023-03-18 | 0:00 | 2023-03-20 | 5:00 | 2d, 5h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | A4E-006 |  | 2021-07-08
DB Netz AG | A4F-002 | Rostock - Berlin | > | Lalendorf Ost | Kavelstorf | 2023 | 2023 | 17 | 18 | 2023-04-28 | 21:00 | 2023-05-05 | 5:00 | 6d, 8h | Periodical | Maintenance |  | LT | [9 empty] | 80 | N | A4F-002 |  | 2021-06-08
DB Netz AG | AA4-001 | Wilhelmshaven - Bremen | > | Osnabrück Hbf Po | Bremen Hbf | 2022 | 2022 | 50 | 52 | 2022-12-17 | 23:00 | 2022-12-31 | 5:00 | 350d, 6h | Periodical | Maintenance |  | LT | [9 empty] | 80 | Y | AA4-001 |  | 2022-04-20
DB Netz AG | AA4-001 | Wilhelmshaven - Bremen | > | Osnabrück Hbf Po | Bremen Hbf | 2023 | 2023 | 1 | 48 | 2023-01-01 | 23:00 | 2023-12-03 | 5:00 | 350d, 6h | Periodical | Maintenance |  | LT | [9 empty] | 80 | Y | AA4-001 |  | 2022-04-20
DB Netz AG | AA9-001 | Rostock - Berlin | <> | Priemerbg-NUP Gü | Plaaz Abzw | 2023 | 2023 | 10 | 24 | 2023-03-06 | 8:00 | 2023-06-16 | 17:00 | 102d, 8h | Continuous | Bridge | T | [10 empty] | 80 | Y | AA9-001 |  | 2021-04-19
DB Netz AG | AE6-007 | Bremerhaven - Bremen | < | Brh-Wulsdorf | Stubben | 2023 | 2023 | 10 | 20 | 2023-03-11 | 14:00 | 2023-05-15 | 5:00 | 64d, 14h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | Y | AE6-007 |  | 2021-05-04
DB Netz AG | AE6-001 | Bremerhaven - Bremen | <> | Stubben | Brh-Wulsdorf | 2023 | 2023 | 10 | 20 | 2023-03-11 | 14:00 | 2023-05-15 | 5:00 | 64d, 14h | Periodical | Miscellaneous |  |  | S | [8 empty] | 80 | N | AE6-001 |  | 2021-07-05
DB Netz AG | AE6-008 | Bremerhaven - Bremen | <> | Stubben | Brh-Wulsdorf | 2023 | 2023 | 10 | 20 | 2023-03-09 | 23:00 | 2023-05-17 | 5:00 | 68d, 5h | Periodical | Miscellaneous |  |  | S | [8 empty] | 80 | N | AE6-008 |  | 2021-07-06
DB Netz AG | AE6-006 | Bremerhaven - Bremen | < | Brh-Wulsdorf | Stubben | 2023 | 2023 | 10 | 20 | 2023-03-09 | 23:00 | 2023-05-17 | 5:00 | 68d, 5h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | AE6-006 |  | 2021-07-06
DB Netz AG | AED-001 | Hamburg - Magdeburg | <> | Wieren | Salzwedel | 2023 | 2023 | 10 | 10 | 2023-03-06 | 22:00 | 2023-03-11 | 5:00 | 4d, 7h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | AED-001 |  | 2021-06-03
DB Netz AG | AED-003 | Hamburg - Magdeburg | <> | Schnega | Schnega | 2023 | 2023 | 10 | 11 | 2023-03-06 | 5:00 | 2023-03-17 | 21:00 | 11d, 16h | Continuous | Miscellaneous |  |  | S | [8 empty] | 80 | Y | AED-003 |  | 2021-06-03
DB Netz AG | AED-008 | Hamburg - Magdeburg | <> | Schnega | Wieren | 2023 | 2023 | 10 | 11 | 2023-03-06 | 19:30 | 2023-03-17 | 20:00 | 11d, 0h | Periodical | Miscellaneous | T | [10 empty] | 80 | Y | AED-008 |  | 2021-05-26
DB Netz AG | AED-005 | Hamburg - Magdeburg | <> | Schnega | Wieren | 2023 | 2023 | 10 | 11 | 2023-03-06 | 8:15 | 2023-03-17 | 8:45 | 11d, 0h | Periodical | Miscellaneous | T | [10 empty] | 80 | Y | AED-005 |  | 2021-05-26
DB Netz AG | AED-006 | Hamburg - Magdeburg | <> | Schnega | Schnega | 2023 | 2023 | 10 | 11 | 2023-03-06 | 5:00 | 2023-03-17 | 21:00 | 11d, 16h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | Y | AED-006 |  | 2021-05-26
DB Netz AG | B49-047 | Hamburg - Magdeburg | > | Meckelfeld | Hmb-Harburg | 2023 | 2023 | 16 | 16 | 2023-04-23 | 1:00 | 2023-04-23 | 6:00 | 0d, 5h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | B49-047 |  | 2021-07-26
DB Netz AG | 15B7-001 | Hamburg - Magdeburg | < | Hmb-Wlb Abzw | Hmb-Harburg | 2023 | 2023 | 15 | 15 | 2023-04-15 | 2:00 | 2023-04-15 | 6:00 | 0d, 4h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 15B7-001 |  | 2021-05-27
DB Netz AG | 15B7-002 | Hamburg - Magdeburg | > | Hmb-Harburg | Hmb-Wlb Abzw | 2023 | 2023 | 15 | 15 | 2023-04-15 | 2:00 | 2023-04-15 | 6:00 | 0d, 4h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 15B7-002 |  | 2021-07-26
DB Netz AG | 15B5-001 | Hamburg - Magdeburg | > | Hmb-Harb Bbf Süd | Hmb-Harburg | 2023 | 2023 | 14 | 14 | 2023-04-06 | 4:00 | 2023-04-06 | 6:00 | 0d, 2h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 15B5-001 |  | 2021-05-27
DB Netz AG | B49-048 | Hamburg - Magdeburg | <> | Hmb-Harburg | Hmb-Harburg | 2023 | 2023 | 17 | 17 | 2023-04-24 | 23:00 | 2023-04-25 | 5:00 | 0d, 6h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | B49-048 |  | 2021-07-26
DB Netz AG | 15B6-001 | Hamburg - Magdeburg | < | Hmb-Harburg | Hmb-Harburg | 2023 | 2023 | 15 | 15 | 2023-04-11 | 4:00 | 2023-04-11 | 5:30 | 0d, 1h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 15B6-001 |  | 2021-05-27
DB Netz AG | 15B8-001 | Hamburg - Magdeburg | <> | Hmb-Harburg | Hmb-Harburg | 2023 | 2023 | 16 | 16 | 2023-04-17 | 2:00 | 2023-04-17 | 6:00 | 0d, 4h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 15B8-001 |  | 2021-05-27
DB Netz AG | 15B8-002 | Hamburg - Magdeburg | < | Hmb-Harburg | Hmb-Harburg | 2023 | 2023 | 16 | 16 | 2023-04-19 | 3:00 | 2023-04-19 | 6:00 | 0d, 3h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 15B8-002 |  | 2021-05-27
DB Netz AG | 15B6-002 | Hamburg - Magdeburg | > | Hmb-Harb Bbf Süd | Hmb Unterelbe | 2023 | 2023 | 14 | 14 | 2023-04-08 | 0:00 | 2023-04-08 | 6:00 | 0d, 6h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 15B6-002 |  | 2021-05-28
DB Netz AG | 15B7-003 | Hamburg - Magdeburg | > | Hmb-Harburg | Hmb-Harburg | 2023 | 2023 | 15 | 15 | 2023-04-12 | 20:00 | 2023-04-13 | 6:00 | 0d, 10h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 15B7-003 |  | 2021-07-26
DB Netz AG | B49-018 | Hamburg - Magdeburg | < | Hmb-Wlb Abzw | Meckelfeld | 2023 | 2023 | 16 | 16 | 2023-04-21 | 22:00 | 2023-04-22 | 6:00 | 0d, 8h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | B49-018 |  | 2021-05-27
DB Netz AG | 15B6-003 | Hamburg - Magdeburg | <> | Hmb-Harburg | Hmb-Harburg | 2023 | 2023 | 14 | 14 | 2023-04-09 | 5:00 | 2023-04-09 | 23:00 | 0d, 18h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 15B6-003 |  | 2021-05-27
DB Netz AG | 15B6-004 | Hamburg - Magdeburg | < | Hmb-Harburg | Hmb-Harburg | 2023 | 2023 | 14 | 14 | 2023-04-08 | 4:00 | 2023-04-08 | 6:00 | 0d, 2h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 15B6-004 |  | 2021-05-27
DB Netz AG | 15B5-002 | Hamburg - Magdeburg | > | Hmb-Harburg | Hmb-Harburg | 2023 | 2023 | 14 | 14 | 2023-04-03 | 3:00 | 2023-04-03 | 6:00 | 0d, 3h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 15B5-002 |  | 2021-05-27
DB Netz AG | 15B7-004 | Hamburg - Magdeburg | > | Meckelfeld | Hmb-Harburg | 2023 | 2023 | 15 | 15 | 2023-04-15 | 20:00 | 2023-04-16 | 2:00 | 0d, 6h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 15B7-004 |  | 2021-07-26
DB Netz AG | 15B7-005 | Hamburg - Magdeburg | <> | Hmb-Harburg | Meckelfeld | 2023 | 2023 | 15 | 15 | 2023-04-16 | 2:00 | 2023-04-16 | 6:00 | 0d, 4h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | 15B7-005 |  | 2021-07-26
DB Netz AG | 15B5-003 | Hamburg - Magdeburg | > | Hmb-Harburg | Hmb-Harburg | 2023 | 2023 | 13 | 13 | 2023-04-01 | 23:00 | 2023-04-02 | 6:00 | 0d, 7h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 15B5-003 |  | 2021-07-26
DB Netz AG | B49-021 | Hamburg - Magdeburg | > | Meckelfeld | Hmb-Wlb Abzw | 2023 | 2023 | 16 | 16 | 2023-04-20 | 22:00 | 2023-04-21 | 6:00 | 0d, 8h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | B49-021 |  | 2021-07-26
DB Netz AG | 15B8-003 | Hamburg - Magdeburg | <> | Hmb-Harburg | Hmb-Harburg | 2023 | 2023 | 16 | 16 | 2023-04-20 | 0:00 | 2023-04-20 | 6:00 | 0d, 6h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 15B8-003 |  | 2021-07-26
DB Netz AG | 15B6-005 | Hamburg - Magdeburg | <> | Hmb-Harburg | Hmb-Harburg | 2023 | 2023 | 15 | 15 | 2023-04-11 | 6:00 | 2023-04-11 | 20:00 | 0d, 14h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 15B6-005 |  | 2021-07-26
DB Netz AG | B49-022 | Hamburg - Magdeburg | <> | Hmb-Harburg | Hmb-Harburg | 2023 | 2023 | 16 | 16 | 2023-04-22 | 22:00 | 2023-04-23 | 6:00 | 0d, 8h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | B49-022 |  | 2021-05-27
DB Netz AG | B49-067 | Hamburg - Magdeburg | <> | Hmb-Harburg | Hmb-Harburg | 2023 | 2023 | 17 | 17 | 2023-04-25 | 23:00 | 2023-04-26 | 6:00 | 0d, 7h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | B49-067 |  | 2021-07-26
DB Netz AG | 15B7-006 | Hamburg - Magdeburg | <> | Hmb-Harburg | Hmb-Harburg | 2023 | 2023 | 15 | 15 | 2023-04-11 | 20:00 | 2023-04-12 | 6:00 | 0d, 10h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 15B7-006 |  | 2021-07-26
DB Netz AG | 15B7-007 | Hamburg - Magdeburg | <> | Hmb-Harburg | Hmb-Wlb Abzw | 2023 | 2023 | 15 | 15 | 2023-04-14 | 20:00 | 2023-04-15 | 2:00 | 0d, 6h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | 15B7-007 |  | 2021-05-27
DB Netz AG | 15B5-004 | Hamburg - Magdeburg | > | Buchholz (Nordh) | Hmb-Harburg | 2023 | 2023 | 14 | 14 | 2023-04-03 | 22:00 | 2023-04-04 | 6:00 | 0d, 8h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 15B5-004 |  | 2021-05-27
DB Netz AG | B49-038 | Hamburg - Magdeburg | <> | Hmb-Harburg | Hmb-Harburg | 2023 | 2023 | 16 | 17 | 2023-04-23 | 23:00 | 2023-04-24 | 2:00 | 0d, 3h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | B49-038 |  | 2021-07-26
DB Netz AG | 15B8-004 | Hamburg - Magdeburg | <> | Hmb-Harburg | Hmb-Harburg | 2023 | 2023 | 15 | 16 | 2023-04-16 | 22:00 | 2023-04-17 | 6:00 | 0d, 8h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 15B8-004 |  | 2021-05-27
DB Netz AG | 15B5-005 | Hamburg - Magdeburg | < | Hmb-Harburg | Buchholz (Nordh) | 2023 | 2023 | 14 | 14 | 2023-04-06 | 2:00 | 2023-04-06 | 6:00 | 0d, 4h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 15B5-005 |  | 2021-05-27
DB Netz AG | 15B6-006 | Hamburg - Magdeburg | > | Hmb-Harb Bbf Süd | Hmb-Harburg | 2023 | 2023 | 14 | 14 | 2023-04-08 | 23:00 | 2023-04-09 | 5:00 | 0d, 6h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 15B6-006 |  | 2021-05-27
DB Netz AG | B49-058 | Hamburg - Magdeburg | <> | Hmb-Harburg | Hmb-Harburg | 2023 | 2023 | 17 | 17 | 2023-04-24 | 2:00 | 2023-04-24 | 5:00 | 0d, 3h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | B49-058 |  | 2021-05-27
DB Netz AG | 15B6-007 | Hamburg - Magdeburg | <> | Hmb-Harburg | Hmb-Harburg | 2023 | 2023 | 14 | 14 | 2023-04-07 | 18:00 | 2023-04-08 | 6:00 | 0d, 12h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 15B6-007 |  | 2021-07-26
DB Netz AG | 15B6-008 | Hamburg - Magdeburg | > | Hmb-Harb Bbf Süd | Hmb-Harburg | 2023 | 2023 | 14 | 14 | 2023-04-07 | 18:00 | 2023-04-08 | 0:00 | 0d, 6h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 15B6-008 |  | 2021-05-27
DB Netz AG | 15B5-006 | Hamburg - Magdeburg | <> | Hmb-Harburg | Hmb-Harburg | 2023 | 2023 | 14 | 14 | 2023-04-06 | 22:00 | 2023-04-07 | 6:00 | 0d, 8h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 15B5-006 |  | 2021-05-27
DB Netz AG | 15B5-007 | Hamburg - Magdeburg | <> | Hmb-Harburg | Hmb-Harburg | 2023 | 2023 | 14 | 14 | 2023-04-03 | 6:00 | 2023-04-04 | 19:00 | 1d, 13h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 15B5-007 |  | 2021-05-27
DB Netz AG | 15B7-008 | Hamburg - Magdeburg | <> | Hmb-Harburg | Hmb-Harburg | 2023 | 2023 | 15 | 15 | 2023-04-12 | 6:00 | 2023-04-12 | 20:00 | 0d, 14h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 15B7-008 |  | 2021-05-27
DB Netz AG | 15B6-009 | Hamburg - Magdeburg | < | Hmb-Harburg | Meckelfeld | 2023 | 2023 | 14 | 14 | 2023-04-09 | 2:30 | 2023-04-09 | 4:30 | 0d, 2h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 15B6-009 |  | 2021-05-27
DB Netz AG | 15B8-005 | Hamburg - Magdeburg | <> | Hmb-Harburg | Hmb-Harburg | 2023 | 2023 | 16 | 16 | 2023-04-18 | 0:00 | 2023-04-18 | 6:00 | 0d, 6h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 15B8-005 |  | 2021-05-27
DB Netz AG | 15B5-008 | Hamburg - Magdeburg | <> | Hmb-Harburg | Hmb-Harburg | 2023 | 2023 | 14 | 14 | 2023-04-05 | 6:00 | 2023-04-06 | 22:00 | 1d, 16h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 15B5-008 |  | 2021-07-26
DB Netz AG | 15B5-009 | Hamburg - Magdeburg | <> | Hmb-Harburg | Hmb-Harburg | 2023 | 2023 | 14 | 14 | 2023-04-07 | 6:00 | 2023-04-07 | 18:00 | 0d, 12h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 15B5-009 |  | 2021-05-27
DB Netz AG | 15B5-010 | Hamburg - Magdeburg | > | Hmb-Harburg | Hmb-Harburg | 2023 | 2023 | 13 | 14 | 2023-04-02 | 23:00 | 2023-04-03 | 6:00 | 0d, 7h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 15B5-010 |  | 2021-05-27
DB Netz AG | 15B8-006 | Hamburg - Magdeburg | <> | Hmb-Harburg | Hmb-Harburg | 2023 | 2023 | 16 | 16 | 2023-04-19 | 22:00 | 2023-04-20 | 0:00 | 0d, 2h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 15B8-006 |  | 2021-07-26
DB Netz AG | B49-070 | Hamburg - Magdeburg | > | Hmb-Harburg | Hmb-Harburg | 2023 | 2023 | 16 | 16 | 2023-04-22 | 22:00 | 2023-04-23 | 1:00 | 0d, 3h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | B49-070 |  | 2021-05-27
DB Netz AG | 15B5-011 | Hamburg - Magdeburg | < | Hmb-Harburg | Buchholz (Nordh) | 2023 | 2023 | 14 | 14 | 2023-04-07 | 2:00 | 2023-04-07 | 6:00 | 0d, 4h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 15B5-011 |  | 2021-05-27
DB Netz AG | B49-071 | Hamburg - Magdeburg | <> | Hmb-Harburg | Hmb-Harburg | 2023 | 2023 | 16 | 17 | 2023-04-23 | 23:00 | 2023-04-24 | 5:00 | 0d, 6h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | B49-071 |  | 2021-05-27
DB Netz AG | 15B8-007 | Hamburg - Magdeburg | <> | Hmb-Harburg | Hmb-Harburg | 2023 | 2023 | 16 | 16 | 2023-04-17 | 20:00 | 2023-04-18 | 6:00 | 0d, 10h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 15B8-007 |  | 2021-05-27
DB Netz AG | 15B5-012 | Hamburg - Magdeburg | <> | Hmb-Harburg | Hmb-Harburg | 2023 | 2023 | 14 | 14 | 2023-04-05 | 6:00 | 2023-04-05 | 20:00 | 0d, 14h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 15B5-012 |  | 2021-07-26
DB Netz AG | 15B5-013 | Hamburg - Magdeburg | > | Meckelfeld | Hmb-Harburg | 2023 | 2023 | 14 | 14 | 2023-04-04 | 2:00 | 2023-04-04 | 6:00 | 0d, 4h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 15B5-013 |  | 2021-07-26
DB Netz AG | 15B6-010 | Hamburg - Magdeburg | > | Meckelfeld | Hmb-Harburg | 2023 | 2023 | 15 | 15 | 2023-04-10 | 2:30 | 2023-04-10 | 4:30 | 0d, 2h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 15B6-010 |  | 2021-05-27
DB Netz AG | 15B8-008 | Hamburg - Magdeburg | < | Hmb-Harburg | Meckelfeld | 2023 | 2023 | 15 | 16 | 2023-04-16 | 20:00 | 2023-04-17 | 2:00 | 0d, 6h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 15B8-008 |  | 2021-05-27
DB Netz AG | 15B6-011 | Hamburg - Magdeburg | < | Süderelbbrücke | Hmb-Harburg | 2023 | 2023 | 15 | 15 | 2023-04-10 | 20:00 | 2023-04-10 | 22:00 | 0d, 2h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 15B6-011 |  | 2021-05-27
DB Netz AG | 15B6-012 | Hamburg - Magdeburg | <> | Hmb-Harburg | Süderelbbrücke | 2023 | 2023 | 15 | 15 | 2023-04-10 | 22:00 | 2023-04-11 | 5:00 | 0d, 7h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | 15B6-012 |  | 2021-07-26
DB Netz AG | 15B7-009 | Hamburg - Magdeburg | < | Hmb-Harburg | Hmb-Harburg | 2023 | 2023 | 15 | 15 | 2023-04-13 | 3:00 | 2023-04-13 | 6:00 | 0d, 3h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 15B7-009 |  | 2021-07-26
DB Netz AG | 15B7-010 | Hamburg - Magdeburg | > | Hmb-Harburg | Hmb-Wilhelmsbg | 2023 | 2023 | 15 | 15 | 2023-04-13 | 3:00 | 2023-04-13 | 6:00 | 0d, 3h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 15B7-010 |  | 2021-05-27
DB Netz AG | 15B5-014 | Wilhelmshaven - Bremen | < | Hmb-Harburg | Buchholz (Nordh) | 2023 | 2023 | 14 | 14 | 2023-04-04 | 19:00 | 2023-04-05 | 6:00 | 0d, 11h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 15B5-014 |  | 2021-05-27
DB Netz AG | 15B6-013 | Hamburg - Magdeburg | < | Hmb-Harburg | Hmb-Harb Bbf Süd | 2023 | 2023 | 14 | 15 | 2023-04-09 | 23:00 | 2023-04-10 | 5:00 | 0d, 6h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 15B6-013 |  | 2021-05-27
DB Netz AG | 15B5-015 | Hamburg - Magdeburg | < | Hmb-Harburg | Meckelfeld | 2023 | 2023 | 13 | 13 | 2023-04-02 | 3:00 | 2023-04-02 | 6:00 | 0d, 3h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 15B5-015 |  | 2021-05-27
DB Netz AG | 15B7-011 | Hamburg - Magdeburg | <> | Hmb-Harburg | Hmb-Wlb Abzw | 2023 | 2023 | 15 | 15 | 2023-04-13 | 20:00 | 2023-04-14 | 6:00 | 0d, 10h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | 15B7-011 |  | 2021-05-27
DB Netz AG | 15B5-016 | Hamburg - Magdeburg | < | Hmb-Harburg | Meckelfeld | 2023 | 2023 | 14 | 14 | 2023-04-05 | 20:00 | 2023-04-06 | 6:00 | 0d, 10h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 15B5-016 |  | 2021-05-27
DB Netz AG | 15B7-012 | Hamburg - Magdeburg | > | Hmb-Harburg | Hmb-Wilhelmsbg | 2023 | 2023 | 15 | 15 | 2023-04-12 | 3:00 | 2023-04-12 | 6:00 | 0d, 3h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 15B7-012 |  | 2021-05-27
DB Netz AG | 15B5-017 | Hamburg - Magdeburg | <> | Buchholz (Nordh) | Hmb-Harburg | 2023 | 2023 | 14 | 14 | 2023-04-05 | 2:00 | 2023-04-05 | 6:00 | 0d, 4h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | 15B5-017 |  | 2021-05-27
DB Netz AG | 15B5-018 | Hamburg - Magdeburg | <> | Hmb-Harburg | Hmb-Harburg | 2023 | 2023 | 13 | 13 | 2023-04-02 | 6:00 | 2023-04-02 | 23:00 | 0d, 17h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 15B5-018 |  | 2021-05-27
DB Netz AG | B49-063 | Hamburg - Magdeburg | <> | Hmb-Harburg | Hmb-Harburg | 2023 | 2023 | 17 | 17 | 2023-04-26 | 3:00 | 2023-04-26 | 6:00 | 0d, 3h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | B49-063 |  | 2021-05-27
DB Netz AG | 15B8-010 | Hamburg - Magdeburg | <> | Hmb-Harburg | Hmb-Harburg | 2023 | 2023 | 16 | 16 | 2023-04-19 | 0:00 | 2023-04-19 | 3:00 | 0d, 3h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 15B8-010 |  | 2021-05-27
DB Netz AG | B49-015 | Hamburg - Magdeburg | <> | Hmb-Harburg | Hmb-Harburg | 2023 | 2023 | 17 | 17 | 2023-04-25 | 2:00 | 2023-04-25 | 5:00 | 0d, 3h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | B49-015 |  | 2021-05-27
DB Netz AG | 15B6-014 | Hamburg - Magdeburg | > | Hmb-Harburg | Hmb-Wilhelmsbg | 2023 | 2023 | 15 | 15 | 2023-04-11 | 5:00 | 2023-04-11 | 6:00 | 0d, 1h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 15B6-014 |  | 2021-07-26
DB Netz AG | 15B8-011 | Hamburg - Magdeburg | > | Hmb-Harburg | Hmb Unterelbe | 2023 | 2023 | 16 | 16 | 2023-04-20 | 4:00 | 2023-04-20 | 6:00 | 0d, 2h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 15B8-011 |  | 2021-05-27
DB Netz AG | B58-001 | Hamburg - Magdeburg | <> | Salzwedel | Wieren | 2023 | 2023 | 11 | 12 | 2023-03-17 | 21:00 | 2023-03-20 | 5:00 | 2d, 8h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | B58-001 |  | 2021-06-08
DB Netz AG | B93-006 | Hamburg - Magdeburg | <> | Brunau-Packeb | Salzwedel | 2023 | 2023 | 11 | 12 | 2023-03-19 | 19:00 | 2023-03-20 | 5:00 | 0d, 10h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | B93-006 |  | 2021-05-17
DB Netz AG | B93-001 | Hamburg - Magdeburg | <> | Ritze DB-Grenze | Salzwedel Gbf | 2023 | 2023 | 11 | 12 | 2023-03-19 | 19:00 | 2023-03-20 | 5:00 | 0d, 10h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | B93-001 |  | 2021-05-17
DB Netz AG | B93-002 | Hamburg - Magdeburg | <> | Brunau-Packeb | Salzwedel | 2023 | 2023 | 13 | 14 | 2023-04-02 | 21:00 | 2023-04-03 | 5:00 | 0d, 8h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | B93-002 |  | 2021-05-17
DB Netz AG | B93-004 | Hamburg - Magdeburg | <> | Salzwedel Gbf | Ritze DB-Grenze | 2023 | 2023 | 13 | 14 | 2023-04-02 | 21:00 | 2023-04-03 | 5:00 | 0d, 8h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | B93-004 |  | 2021-05-17
DB Netz AG | B93-005 | Hamburg - Magdeburg | <> | Salzwedel Gbf | Salzwedel | 2023 | 2023 | 9 | 19 | 2023-03-04 | 5:00 | 2023-05-12 | 21:00 | 69d, 15h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | Y | B93-005 |  | 2021-05-17
DB Netz AG | BA3-016 | Bremerhaven - Bremen | <> | Stubben | Stubben | 2023 | 2023 | 17 | 19 | 2023-04-29 | 0:00 | 2023-05-08 | 4:00 | 9d, 4h | Periodical | Track & Rail |  |  | S | [8 empty] | 80 | N | BA3-016 |  | 2021-05-26
DB Netz AG | BA3-022 | Bremerhaven - Bremen | < | Brh-Wulsdorf | Lübberstedt | 2023 | 2023 | 17 | 19 | 2023-04-29 | 0:00 | 2023-05-08 | 4:00 | 9d, 4h | Periodical | Track & Rail |  | LT | [9 empty] | 80 | N | BA3-022 |  | 2021-07-14
DB Netz AG | BC3-002 | Hamburg - Magdeburg | < | Celle | Lehrte | 2023 | 2023 | 5 | 7 | 2023-01-30 | 23:00 | 2023-02-16 | 5:00 | 16d, 6h | Periodical | Maintenance |  | LT | [9 empty] | 80 | N | BC3-002 |  | 2021-05-12
DB Netz AG | BC4-002 | Hamburg - Magdeburg | < | Hmb-Harburg | Celle | 2023 | 2023 | 5 | 7 | 2023-01-30 | 23:00 | 2023-02-16 | 5:00 | 16d, 6h | Periodical | Maintenance |  | LT | [9 empty] | 80 | N | BC4-002 |  | 2021-05-12
DB Netz AG | BD8-001 | Hamburg - Magdeburg | > | Hmb-Harburg | Hmb-Roth Tk | 2022 | 2022 | 49 | 52 | 2022-12-11 | 23:00 | 2022-12-31 | 5:00 | 357d, 6h | Periodical | Maintenance |  | LT | [9 empty] | 80 | Y | BD8-001 |  | 2021-05-12
DB Netz AG | BD8-001 | Hamburg - Magdeburg | > | Hmb-Harburg | Hmb-Roth Tk | 2023 | 2023 | 1 | 49 | 2023-01-01 | 23:00 | 2023-12-04 | 5:00 | 357d, 6h | Periodical | Maintenance |  | LT | [9 empty] | 80 | Y | BD8-001 |  | 2021-05-12
DB Netz AG | BD9-001 | Hamburg - Magdeburg | < | Buchholz (Nordh) | Maschen Rbf Msof | 2022 | 2022 | 50 | 52 | 2022-12-12 | 6:00 | 2022-12-31 | 14:00 | 357d, 8h | Periodical | Maintenance |  | LT | [9 empty] | 80 | Y | BD9-001 |  | 2021-06-18
DB Netz AG | BD9-001 | Hamburg - Magdeburg | < | Buchholz (Nordh) | Maschen Rbf Msof | 2023 | 2023 | 1 | 49 | 2023-01-01 | 6:00 | 2023-12-04 | 14:00 | 357d, 8h | Periodical | Maintenance |  | LT | [9 empty] | 80 | Y | BD9-001 |  | 2021-06-18
DB Netz AG | C05-001 | Bremerhaven - Bremen | > | Bremen Hbf | Brh-Speckenbütt | 2022 | 2022 | 49 | 52 | 2022-12-11 | 23:00 | 2022-12-31 | 5:00 | 357d, 6h | Periodical | Maintenance |  | LT | [9 empty] | 80 | Y | C05-001 |  | 2021-05-11
DB Netz AG | C05-001 | Bremerhaven - Bremen | > | Bremen Hbf | Brh-Speckenbütt | 2023 | 2023 | 1 | 49 | 2023-01-01 | 23:00 | 2023-12-04 | 5:00 | 357d, 6h | Periodical | Maintenance |  | LT | [9 empty] | 80 | Y | C05-001 |  | 2021-05-11
DB Netz AG | C24-046 | Bremerhaven - Bremen | <> | Stubben | Brh-Wulsdorf | 2023 | 2023 | 12 | 12 | 2023-03-24 | 23:00 | 2023-03-25 | 5:00 | 0d, 6h | Continuous | Track & Rail |  |  | S | [8 empty] | 80 | N | C24-046 |  | 2021-07-09
DB Netz AG | C24-012 | Bremerhaven - Bremen | < | Brh-Wulsdorf | Stubben | 2023 | 2023 | 13 | 14 | 2023-03-31 | 23:00 | 2023-04-03 | 5:00 | 2d, 6h | Periodical | Track & Rail |  | LT | [9 empty] | 80 | N | C24-012 |  | 2021-05-25
DB Netz AG | C24-029 | Bremerhaven - Bremen | < | Brh-Wulsdorf | Stubben | 2023 | 2023 | 12 | 13 | 2023-03-26 | 23:00 | 2023-03-27 | 5:00 | 0d, 6h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | C24-029 |  | 2021-05-25
DB Netz AG | C24-053 | Bremerhaven - Bremen | <> | Stubben | Brh-Wulsdorf | 2023 | 2023 | 12 | 12 | 2023-03-25 | 23:00 | 2023-03-26 | 5:00 | 0d, 5h | Continuous | Track & Rail |  |  | S | [8 empty] | 80 | N | C24-053 |  | 2021-07-12
DB Netz AG | C24-016 | Bremerhaven - Bremen | <> | Stubben | Brh-Wulsdorf | 2023 | 2023 | 12 | 13 | 2023-03-26 | 23:00 | 2023-03-27 | 5:00 | 0d, 6h | Continuous | Track & Rail |  |  | S | [8 empty] | 80 | N | C24-016 |  | 2021-07-12
DB Netz AG | C24-003 | Bremerhaven - Bremen | <> | Stubben | Brh-Wulsdorf | 2023 | 2023 | 11 | 12 | 2023-03-18 | 23:00 | 2023-03-20 | 5:00 | 1d, 6h | Periodical | Track & Rail |  |  | S | [8 empty] | 80 | N | C24-003 |  | 2021-07-12
DB Netz AG | C24-042 | Bremerhaven - Bremen | <> | Stubben | Brh-Wulsdorf | 2023 | 2023 | 11 | 11 | 2023-03-17 | 23:00 | 2023-03-18 | 5:00 | 0d, 6h | Continuous | Track & Rail |  |  | S | [8 empty] | 80 | N | C24-042 |  | 2021-07-21
DB Netz AG | C24-006 | Bremerhaven - Bremen | <> | Stubben | Brh-Wulsdorf | 2023 | 2023 | 14 | 15 | 2023-04-07 | 23:00 | 2023-04-10 | 5:00 | 2d, 6h | Periodical | Track & Rail |  |  | S | [8 empty] | 80 | N | C24-006 |  | 2021-07-12
DB Netz AG | C24-007 | Bremerhaven - Bremen | <> | Stubben | Brh-Wulsdorf | 2023 | 2023 | 13 | 13 | 2023-03-31 | 23:00 | 2023-04-01 | 5:00 | 0d, 6h | Continuous | Track & Rail |  |  | S | [8 empty] | 80 | N | C24-007 |  | 2021-07-12
DB Netz AG | C24-026 | Bremerhaven - Bremen | < | Brh-Wulsdorf | Stubben | 2023 | 2023 | 14 | 15 | 2023-04-07 | 23:00 | 2023-04-10 | 5:00 | 2d, 6h | Periodical | Track & Rail |  | LT | [9 empty] | 80 | N | C24-026 |  | 2021-05-25
DB Netz AG | C24-009 | Bremerhaven - Bremen | < | Brh-Wulsdorf | Stubben | 2023 | 2023 | 12 | 12 | 2023-03-24 | 23:00 | 2023-03-25 | 5:00 | 0d, 6h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | C24-009 |  | 2021-05-25
DB Netz AG | C24-051 | Bremerhaven - Bremen | <> | Stubben | Brh-Wulsdorf | 2023 | 2023 | 13 | 14 | 2023-04-01 | 23:00 | 2023-04-03 | 5:00 | 1d, 6h | Periodical | Track & Rail |  |  | S | [8 empty] | 80 | N | C24-051 |  | 2021-07-13
DB Netz AG | C24-011 | Bremerhaven - Bremen | < | Brh-Wulsdorf | Stubben | 2023 | 2023 | 11 | 12 | 2023-03-17 | 23:00 | 2023-03-20 | 5:00 | 2d, 6h | Periodical | Track & Rail |  | LT | [9 empty] | 80 | N | C24-011 |  | 2021-05-25
DB Netz AG | C24-067 | Bremerhaven - Bremen | < | Brh-Wulsdorf | Stubben | 2023 | 2023 | 12 | 12 | 2023-03-25 | 23:00 | 2023-03-26 | 5:00 | 0d, 5h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | C24-067 |  | 2021-07-13
DB Netz AG | C4B-001 | Hamburg - Magdeburg | <> | Salzwedel | Wieren | 2023 | 2023 | 9 | 10 | 2023-03-03 | 21:00 | 2023-03-06 | 5:00 | 2d, 8h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | C4B-001 |  | 2021-05-11
DB Netz AG | CA7-010 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 11 | 18 | 2023-03-13 | 5:30 | 2023-05-01 | 5:30 | 48d, 23h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | CA7-010 |  | 2021-05-25
DB Netz AG | CA7-019 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 11 | 18 | 2023-03-13 | 5:30 | 2023-05-01 | 5:30 | 48d, 23h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | CA7-019 |  | 2021-05-25
DB Netz AG | CA7-002 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 11 | 18 | 2023-03-13 | 5:30 | 2023-05-01 | 5:30 | 48d, 23h | Continuous | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | CA7-002 |  | 2021-05-25
DB Netz AG | CA7-025 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 18 | 20 | 2023-05-04 | 21:30 | 2023-05-20 | 5:30 | 15d, 8h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | CA7-025 |  | 2021-05-26
DB Netz AG | CA7-024 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 18 | 20 | 2023-05-04 | 21:30 | 2023-05-20 | 5:30 | 15d, 8h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | CA7-024 |  | 2021-05-26
DB Netz AG | CA7-011 | Dresden - Děčín | <> | Dresden Hbf | Dresden Mitte | 2023 | 2023 | 18 | 20 | 2023-05-04 | 21:30 | 2023-05-20 | 5:30 | 15d, 8h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | CA7-011 |  | 2021-05-26
DB Netz AG | CA7-013 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 18 | 20 | 2023-05-04 | 21:30 | 2023-05-20 | 5:30 | 15d, 8h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | CA7-013 |  | 2021-05-26
DB Netz AG | CA7-005 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 11 | 17 | 2023-03-14 | 21:30 | 2023-04-29 | 5:30 | 45d, 7h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | CA7-005 |  | 2021-05-25
DB Netz AG | CA7-029 | Dresden - Děčín | <> | Dresden Hbf | Dresden Mitte | 2023 | 2023 | 11 | 17 | 2023-03-14 | 21:30 | 2023-04-29 | 5:30 | 45d, 7h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | CA7-029 |  | 2021-05-25
DB Netz AG | CA7-021 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 11 | 17 | 2023-03-14 | 21:30 | 2023-04-29 | 5:30 | 45d, 7h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | CA7-021 |  | 2021-05-25
DB Netz AG | CA7-030 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 11 | 17 | 2023-03-14 | 21:30 | 2023-04-29 | 5:30 | 45d, 7h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | CA7-030 |  | 2021-05-25
DB Netz AG | CA7-014 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 18 | 21 | 2023-05-01 | 5:30 | 2023-05-22 | 5:30 | 21d, 0h | Continuous | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | CA7-014 |  | 2021-05-26
DB Netz AG | CA7-028 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 18 | 21 | 2023-05-01 | 5:30 | 2023-05-22 | 5:30 | 21d, 0h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | CA7-028 |  | 2021-05-26
DB Netz AG | CA7-017 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 10 | 10 | 2023-03-06 | 7:00 | 2023-03-10 | 20:00 | 4d, 13h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | CA7-017 |  | 2021-05-25
DB Netz AG | CA7-007 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 10 | 10 | 2023-03-06 | 7:00 | 2023-03-10 | 20:00 | 4d, 13h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | CA7-007 |  | 2021-05-25
DB Netz AG | 1308-001 | Rostock - Berlin | <> | Birkenwerd b Bln | Oranienburg | 2022 | 2022 | 49 | 52 | 2022-12-11 | 0:00 | 2022-12-31 | 4:00 | 295d, 3h | Continuous | Signal |  |  |  | P | [7 empty] | 80 | N | 1308-001 |  | 2021-08-12
DB Netz AG | 1308-001 | Rostock - Berlin | <> | Birkenwerd b Bln | Oranienburg | 2023 | 2023 | 1 | 40 | 2023-01-01 | 0:00 | 2023-10-02 | 4:00 | 295d, 3h | Continuous | Signal |  |  |  | P | [7 empty] | 80 | N | 1308-001 |  | 2021-08-12
DB Netz AG | D02-002 | Dresden - Děčín | <> | Bad Schandau | Schöna | 2023 | 2023 | 12 | 12 | 2023-03-20 | 23:00 | 2023-03-24 | 5:00 | 3d, 6h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | D02-002 |  | 2021-05-27
DB Netz AG | D02-001 | Dresden - Děčín | <> | Bad Schandau | Bad Schandau Gr | 2023 | 2023 | 12 | 12 | 2023-03-20 | 23:00 | 2023-03-24 | 5:00 | 3d, 6h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80,54 | N | D02-001 |  | 2021-05-27
DB Netz AG | D0E-001 | Falkenberg - Dresden | <> | Weißig (b Groß) | Weißig (b Groß) | 2023 | 2023 | 15 | 49 | 2023-04-10 | 14:00 | 2023-12-09 | 23:59 | 243d, 10h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | Y | D0E-001 |  | 2021-05-21
DB Netz AG | D0E-002 | Falkenberg - Dresden | <> | Zeithain Bogendr | Leckwitz | 2023 | 2023 | 15 | 49 | 2023-04-10 | 14:00 | 2023-12-09 | 23:59 | 243d, 10h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | Y | D0E-002 |  | 2021-05-21
DB Netz AG | D6F-001 | Magdeburg - Falkenberg | <> | Fermerswalde | Jessen (Elster) | 2023 | 2023 | 11 | 13 | 2023-03-17 | 23:00 | 2023-03-29 | 4:00 | 11d, 4h | Continuous | Catenary | T | [10 empty] | 80 | N | D6F-001 |  | 2021-04-27
DB Netz AG | D6F-002 | Magdeburg - Falkenberg | <> | Fermerswalde | Fermerswalde | 2023 | 2023 | 17 | 20 | 2023-04-27 | 18:00 | 2023-05-19 | 21:00 | 22d, 3h | Continuous | Catenary |  | ST | [9 empty] | 80 | N | D6F-002 |  | 2021-04-27
DB Netz AG | D6F-003 | Magdeburg - Falkenberg | <> | Fermerswalde | Jessen (Elster) | 2023 | 2023 | 17 | 20 | 2023-04-28 | 22:00 | 2023-05-19 | 21:00 | 20d, 23h | Continuous | Catenary | T | [10 empty] | 80 | N | D6F-003 |  | 2021-04-27
DB Netz AG | D9E-006 | Dresden - Děčín | < | Bad Schandau | Bad Schandau Gr | 2022 | 2022 | 49 | 52 | 2022-12-11 | 0:01 | 2022-12-31 | 23:59 | 69d, 23h | Continuous | Catenary |  | LT | [9 empty] | 80,54 | Y | D9E-006 |  | 2021-05-25
DB Netz AG | D9E-006 | Dresden - Děčín | < | Bad Schandau | Bad Schandau Gr | 2023 | 2023 | 1 | 7 | 2023-01-01 | 0:01 | 2023-02-18 | 23:59 | 69d, 23h | Continuous | Catenary |  | LT | [9 empty] | 80,54 | Y | D9E-006 |  | 2021-05-25
DB Netz AG | D9E-001 | Dresden - Děčín | < | Bad Schandau Ost | Bad Schandau Ost | 2022 | 2022 | 49 | 52 | 2022-12-11 | 0:01 | 2022-12-31 | 23:59 | 69d, 23h | Continuous | Catenary |  | ST | [9 empty] | 80 | Y | D9E-001 |  | 2021-05-25
DB Netz AG | D9E-001 | Dresden - Děčín | < | Bad Schandau Ost | Bad Schandau Ost | 2023 | 2023 | 1 | 7 | 2023-01-01 | 0:01 | 2023-02-18 | 23:59 | 69d, 23h | Continuous | Catenary |  | ST | [9 empty] | 80 | Y | D9E-001 |  | 2021-05-25
DB Netz AG | D9E-007 | Dresden - Děčín | <> | Schöna | Schöna | 2022 | 2022 | 49 | 52 | 2022-12-11 | 0:01 | 2022-12-31 | 23:59 | 69d, 23h | Continuous | Catenary |  | ST | [9 empty] | 80 | Y | D9E-007 |  | 2021-06-30
DB Netz AG | D9E-007 | Dresden - Děčín | <> | Schöna | Schöna | 2023 | 2023 | 1 | 7 | 2023-01-01 | 0:01 | 2023-02-18 | 23:59 | 69d, 23h | Continuous | Catenary |  | ST | [9 empty] | 80 | Y | D9E-007 |  | 2021-06-30
DB Netz AG | D9E-005 | Dresden - Děčín | <> | Bad Schandau Gr | Bad Schandau | 2022 | 2022 | 49 | 52 | 2022-12-11 | 0:01 | 2022-12-31 | 23:59 | 69d, 23h | Continuous | Catenary |  |  |  | P | [7 empty] | 80,54 | Y | D9E-005 |  | 2021-05-25
DB Netz AG | D9E-005 | Dresden - Děčín | <> | Bad Schandau Gr | Bad Schandau | 2023 | 2023 | 1 | 7 | 2023-01-01 | 0:01 | 2023-02-18 | 23:59 | 69d, 23h | Continuous | Catenary |  |  |  | P | [7 empty] | 80,54 | Y | D9E-005 |  | 2021-05-25
DB Netz AG | D9E-004 | Dresden - Děčín | < | Bad Schandau | Bad Schandau Gr | 2022 | 2022 | 49 | 52 | 2022-12-11 | 0:01 | 2022-12-31 | 23:59 | 69d, 23h | Continuous | Catenary |  |  |  |  | X | [6 empty] | 80,54 | Y | D9E-004 |  | 2021-05-25
DB Netz AG | D9E-004 | Dresden - Děčín | < | Bad Schandau | Bad Schandau Gr | 2023 | 2023 | 1 | 7 | 2023-01-01 | 0:01 | 2023-02-18 | 23:59 | 69d, 23h | Continuous | Catenary |  |  |  |  | X | [6 empty] | 80,54 | Y | D9E-004 |  | 2021-05-25
DB Netz AG | DB9-002 | Falkenberg - Dresden | < | Weißig (b Groß) | Leckwitz | 2023 | 2023 | 15 | 15 | 2023-04-10 | 14:00 | 2023-04-11 | 14:00 | 1d, 0h | Continuous | Miscellaneous |  |  | S | [8 empty] | 80 | N | DB9-002 |  | 2021-05-20
DB Netz AG | DB9-003 | Falkenberg - Dresden | > | Leckwitz | Leckwitz | 2023 | 2023 | 15 | 15 | 2023-04-10 | 14:00 | 2023-04-11 | 14:00 | 1d, 0h | Continuous | Miscellaneous |  |  | S | [8 empty] | 80 | N | DB9-003 |  | 2021-05-20
DB Netz AG | DB9-001 | Falkenberg - Dresden | < | Weißig (b Groß) | Zeithain Bogendr | 2023 | 2023 | 15 | 15 | 2023-04-10 | 14:00 | 2023-04-11 | 14:00 | 1d, 0h | Continuous | Miscellaneous |  |  | S | [8 empty] | 80 | N | DB9-001 |  | 2021-05-20
DB Netz AG | E50-006 | Falkenberg - Dresden | <> | Leckwitz | Coswig Stw 1 | 2023 | 2023 | 14 | 14 | 2023-04-07 | 8:00 | 2023-04-07 | 18:00 | 0d, 10h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | E50-006 |  | 2021-05-20
DB Netz AG | E50-005 | Berlin - Dresden | <> | Priestewitz | Großenh Cott Bf | 2023 | 2023 | 14 | 14 | 2023-04-07 | 8:00 | 2023-04-07 | 18:00 | 0d, 10h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | E50-005 |  | 2021-05-20
DB Netz AG | E50-001 | Falkenberg - Dresden | <> | Leckwitz | Kottewitz | 2023 | 2023 | 14 | 15 | 2023-04-07 | 8:00 | 2023-04-10 | 14:00 | 3d, 6h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | E50-001 |  | 2021-05-20
DB Netz AG | E50-003 | Falkenberg - Dresden | <> | Rohrwerk | Zeithain Bogendr | 2023 | 2023 | 14 | 14 | 2023-04-07 | 8:00 | 2023-04-08 | 8:00 | 1d, 0h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | E50-003 |  | 2021-05-20
DB Netz AG | E50-007 | Falkenberg - Dresden | <> | Zeithain Bogendr | Röderau | 2023 | 2023 | 14 | 14 | 2023-04-07 | 8:00 | 2023-04-08 | 8:00 | 1d, 0h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | E50-007 |  | 2021-06-03
DB Netz AG | E50-008 | Falkenberg - Dresden | <> | Röderau Bogendr | Zeithain Bogendr | 2023 | 2023 | 14 | 14 | 2023-04-07 | 8:00 | 2023-04-08 | 8:00 | 1d, 0h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | E50-008 |  | 2021-05-20
DB Netz AG | E50-009 | Falkenberg - Dresden | <> | Zeithain Bogendr | Priestewitz | 2023 | 2023 | 14 | 15 | 2023-04-07 | 8:00 | 2023-04-10 | 14:00 | 3d, 6h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | E50-009 |  | 2021-05-20
DB Netz AG | ED2-004 | Dresden - Děčín | <> | Bad Schandau Gr | Bad Schandau | 2022 | 2022 | 50 | 52 | 2022-12-12 | 8:50 | 2022-12-31 | 16:40 | 64d, 7h | Periodical | Catenary | T | [10 empty] | 80,54 | N | ED2-004 |  | 2021-05-25
DB Netz AG | ED2-004 | Dresden - Děčín | <> | Bad Schandau Gr | Bad Schandau | 2023 | 2023 | 1 | 7 | 2023-01-01 | 8:50 | 2023-02-14 | 16:40 | 64d, 7h | Periodical | Catenary | T | [10 empty] | 80,54 | N | ED2-004 |  | 2021-05-25
DB Netz AG | ED2-006 | Dresden - Děčín | <> | Bad Schandau Ost | Bad Schandau Ost | 2022 | 2022 | 50 | 52 | 2022-12-12 | 8:50 | 2022-12-31 | 16:40 | 64d, 7h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | ED2-006 |  | 2021-05-25
DB Netz AG | ED2-006 | Dresden - Děčín | <> | Bad Schandau Ost | Bad Schandau Ost | 2023 | 2023 | 1 | 7 | 2023-01-01 | 8:50 | 2023-02-14 | 16:40 | 64d, 7h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | ED2-006 |  | 2021-05-25
DB Netz AG | ED2-001 | Dresden - Děčín | <> | Bad Schandau Gr | Bad Schandau | 2022 | 2022 | 50 | 52 | 2022-12-12 | 8:50 | 2022-12-31 | 16:40 | 64d, 7h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80,54 | N | ED2-001 |  | 2021-11-12
DB Netz AG | ED2-001 | Dresden - Děčín | <> | Bad Schandau Gr | Bad Schandau | 2023 | 2023 | 1 | 7 | 2023-01-01 | 8:50 | 2023-02-14 | 16:40 | 64d, 7h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80,54 | N | ED2-001 |  | 2021-11-12
DB Netz AG | F29-001 | Hamburg - Magdeburg | <> | Hamburg Hbf | Hmb-Wlb Abzw | 2023 | 2023 | 18 | 19 | 2023-05-06 | 22:00 | 2023-05-11 | 5:00 | 4d, 7h | Continuous | Switch | T | [10 empty] | 80 | N | F29-001 |  | 2021-05-23
DB Netz AG | F29-009 | Hamburg - Magdeburg | <> | Veddel | Hmb-Wlb Abzw | 2023 | 2023 | 18 | 18 | 2023-05-06 | 2:00 | 2023-05-06 | 5:00 | 0d, 3h | Continuous | Switch | T | [10 empty] | 80 | N | F29-009 |  | 2021-07-21
DB Netz AG | F29-002 | Hamburg - Magdeburg | > | Hmb-Wlb Abzw | Veddel | 2023 | 2023 | 18 | 18 | 2023-05-05 | 23:00 | 2023-05-06 | 2:00 | 0d, 3h | Continuous | Switch |  | LT | [9 empty] | 80 | N | F29-002 |  | 2021-05-23
DB Netz AG | F29-003 | Hamburg - Magdeburg | < | Hmb-Roth Ro | Hmb-Wlb Abzw | 2023 | 2023 | 18 | 19 | 2023-05-06 | 23:00 | 2023-05-11 | 5:00 | 4d, 6h | Periodical | Switch |  | LT | [9 empty] | 80 | N | F29-003 |  | 2021-05-23
DB Netz AG | F5A-013 | Hamburg - Magdeburg | < | Glindenberg | Mg-Neustadt | 2023 | 2023 | 17 | 18 | 2023-04-24 | 6:30 | 2023-05-04 | 20:30 | 10d, 14h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | F5A-013 |  | 2021-05-05
DB Netz AG | F5A-007 | Hamburg - Magdeburg | > | Mg-Neustadt | Glindenberg | 2023 | 2023 | 16 | 16 | 2023-04-21 | 6:30 | 2023-04-22 | 20:30 | 1d, 14h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | F5A-007 |  | 2021-05-06
DB Netz AG | F5A-009 | Hamburg - Magdeburg | < | Mg-Eichenw Üst | Mg-Neustadt | 2023 | 2023 | 18 | 21 | 2023-05-05 | 6:30 | 2023-05-24 | 20:30 | 19d, 14h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | F5A-009 |  | 2021-05-06
DB Netz AG | F5A-010 | Hamburg - Magdeburg | < | Glindenberg | Mg-Neustadt | 2023 | 2023 | 15 | 16 | 2023-04-14 | 6:30 | 2023-04-20 | 20:30 | 6d, 14h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | F5A-010 |  | 2021-05-06
DB Netz AG | F72-006 | Dresden - Děčín | <> | Bad Schandau Ost | Königst (Sä) Üst | 2023 | 2023 | 11 | 11 | 2023-03-16 | 16:40 | 2023-03-16 | 17:40 | 0d, 1h | Continuous | Track & Rail | T | [10 empty] | 80 | N | F72-006 |  | 2021-05-27
DB Netz AG | F72-007 | Dresden - Děčín | < | Bad Schandau | Bad Schandau Gr | 2023 | 2023 | 11 | 11 | 2023-03-16 | 7:40 | 2023-03-16 | 17:40 | 0d, 10h | Continuous | Track & Rail |  | LT | [9 empty] | 80,54 | N | F72-007 |  | 2021-05-27
DB Netz AG | F72-002 | Dresden - Děčín | < | Bad Schandau Ost | Bad Schandau Ost | 2023 | 2023 | 11 | 11 | 2023-03-16 | 7:40 | 2023-03-16 | 17:40 | 0d, 10h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | F72-002 |  | 2021-05-27
DB Netz AG | F72-008 | Dresden - Děčín | < | Bad Schandau | Bad Schandau Gr | 2023 | 2023 | 11 | 11 | 2023-03-16 | 7:40 | 2023-03-16 | 17:40 | 0d, 10h | Continuous | Track & Rail |  |  |  |  | X | [6 empty] | 80,54 | N | F72-008 |  | 2021-05-27
DB Netz AG | F72-009 | Dresden - Děčín | <> | Bad Schandau | Bad Schandau Gr | 2023 | 2023 | 11 | 11 | 2023-03-16 | 7:40 | 2023-03-16 | 17:40 | 0d, 10h | Continuous | Track & Rail |  |  |  | P | [7 empty] | 80,54 | N | F72-009 |  | 2021-05-27
DB Netz AG | F72-003 | Dresden - Děčín | < | Schöna | Schöna | 2023 | 2023 | 11 | 11 | 2023-03-16 | 7:40 | 2023-03-16 | 17:40 | 0d, 10h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | F72-003 |  | 2021-05-27
DB Netz AG | FCB-006 | Dresden - Děčín | <> | Bad Schandau Ost | Königst (Sä) Üst | 2023 | 2023 | 11 | 11 | 2023-03-15 | 16:40 | 2023-03-15 | 17:40 | 0d, 1h | Continuous | Track & Rail | T | [10 empty] | 80 | N | FCB-006 |  | 2021-05-27
DB Netz AG | FCB-001 | Dresden - Děčín | <> | Bad Schandau Gr | Bad Schandau | 2023 | 2023 | 11 | 11 | 2023-03-15 | 7:40 | 2023-03-15 | 17:40 | 0d, 10h | Continuous | Track & Rail |  |  |  |  | X | [6 empty] | 80,54 | N | FCB-001 |  | 2021-05-27
DB Netz AG | FCB-002 | Dresden - Děčín | <> | Bad Schandau Gr | Bad Schandau | 2023 | 2023 | 11 | 11 | 2023-03-15 | 7:40 | 2023-03-15 | 17:40 | 0d, 10h | Continuous | Track & Rail |  |  |  | P | [7 empty] | 80,54 | N | FCB-002 |  | 2021-05-27
DB Netz AG | FCB-008 | Dresden - Děčín | <> | Schöna | Schöna | 2023 | 2023 | 11 | 11 | 2023-03-15 | 7:40 | 2023-03-15 | 17:40 | 0d, 10h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | FCB-008 |  | 2021-06-30
DB Netz AG | FCB-005 | Dresden - Děčín | <> | Bad Schandau Ost | Bad Schandau Ost | 2023 | 2023 | 11 | 11 | 2023-03-15 | 7:40 | 2023-03-15 | 17:40 | 0d, 10h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | FCB-005 |  | 2021-06-30
DB Netz AG | FCB-003 | Dresden - Děčín | > | Bad Schandau Gr | Bad Schandau | 2023 | 2023 | 11 | 11 | 2023-03-15 | 7:40 | 2023-03-15 | 17:40 | 0d, 10h | Continuous | Track & Rail |  | LT | [9 empty] | 80,54 | N | FCB-003 |  | 2021-05-27
DB Netz AG | 1030-003 | Bremen - Hannover | > | Verden (Aller) | Langwedel | 2023 | 2023 | 13 | 13 | 2023-03-30 | 0:00 | 2023-03-30 | 4:00 | 0d, 4h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1030-003 |  | 2021-05-06
DB Netz AG | 1030-001 | Bremen - Hannover | > | Verden (Aller) | Langwedel | 2023 | 2023 | 8 | 13 | 2023-02-22 | 4:00 | 2023-03-30 | 0:00 | 35d, 19h | Continuous | Track & Rail |  |  | S | [8 empty] | 80 | N | 1030-001 |  | 2021-05-06
DB Netz AG | 1030-006 | Bremen - Hannover | <> | Langwedel | Verden (Aller) | 2023 | 2023 | 8 | 8 | 2023-02-22 | 0:00 | 2023-02-22 | 4:00 | 0d, 4h | Continuous | Track & Rail |  |  | S | [8 empty] | 80 | N | 1030-006 |  | 2021-05-06
DB Netz AG | 1030-007 | Bremen - Hannover | <> | Verden (Aller) | Verden (Aller) | 2023 | 2023 | 8 | 13 | 2023-02-21 | 8:00 | 2023-03-30 | 18:00 | 37d, 9h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1030-007 |  | 2021-05-19
DB Netz AG | 1030-009 | Bremen - Hannover | <> | Verden (Aller) | Walle/Verden | 2023 | 2023 | 8 | 8 | 2023-02-22 | 0:00 | 2023-02-22 | 4:00 | 0d, 4h | Continuous | Track & Rail | T | [10 empty] | 80 | N | 1030-009 |  | 2021-05-19
DB Netz AG | 1030-013 | Bremen - Hannover | <> | Verden (Aller) | Verden (Aller) | 2023 | 2023 | 8 | 8 | 2023-02-22 | 0:00 | 2023-02-22 | 4:00 | 0d, 4h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1030-013 |  | 2021-05-19
DB Netz AG | 1030-008 | Bremen - Hannover | <> | Verden (Aller) | Verden (Aller) | 2023 | 2023 | 8 | 13 | 2023-02-22 | 21:00 | 2023-03-29 | 5:00 | 34d, 7h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1030-008 |  | 2021-06-28
DB Netz AG | 1030-010 | Bremen - Hannover | <> | Verden (Aller) | Rotenburg(Wümme) | 2023 | 2023 | 8 | 13 | 2023-02-22 | 21:00 | 2023-03-29 | 5:00 | 34d, 7h | Continuous | Track & Rail | T | [10 empty] | 80 | N | 1030-010 |  | 2021-05-19
DB Netz AG | 1030-005 | Bremen - Hannover | <> | Verden (Aller) | Walle/Verden | 2023 | 2023 | 13 | 13 | 2023-03-30 | 0:00 | 2023-03-30 | 4:00 | 0d, 4h | Continuous | Track & Rail | T | [10 empty] | 80 | N | 1030-005 |  | 2021-05-19
DB Netz AG | 1030-004 | Bremen - Hannover | <> | Verden (Aller) | Verden (Aller) | 2023 | 2023 | 13 | 13 | 2023-03-30 | 0:00 | 2023-03-30 | 4:00 | 0d, 4h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1030-004 |  | 2021-05-06
DB Netz AG | 1030-011 | Bremen - Hannover | <> | Langwedel | Verden (Aller) | 2023 | 2023 | 13 | 13 | 2023-03-30 | 0:00 | 2023-03-30 | 4:00 | 0d, 4h | Continuous | Track & Rail |  |  | S | [8 empty] | 80 | N | 1030-011 |  | 2021-05-06
DB Netz AG | 1030-002 | Bremen - Hannover | > | Verden (Aller) | Langwedel | 2023 | 2023 | 8 | 8 | 2023-02-22 | 0:00 | 2023-02-22 | 4:00 | 0d, 4h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1030-002 |  | 2021-05-06
DB Netz AG | 1030-012 | Bremen - Hannover | <> | Verden (Aller) | Unterstedt | 2023 | 2023 | 13 | 13 | 2023-03-29 | 5:00 | 2023-03-31 | 5:00 | 2d, 0h | Continuous | Track & Rail |  |  | S | [8 empty] | 80 | N | 1030-012 |  | 2021-05-06
DB Netz AG | 1082-023 | Bremen - Hannover | <> | Brm-Sebaldsbrück | Brm-Sebaldsbrück | 2023 | 2023 | 9 | 38 | 2023-03-05 | 20:00 | 2023-09-24 | 6:00 | 202d, 9h | Continuous | Bridge |  | ST | [9 empty] | 80 | N | 1082-023 |  | 2021-05-27
DB Netz AG | 1.37 | Rostock - Berlin | <> | Eichgestell | Stadtforst | 2023 | 2023 | 12 | 13 | 2023-03-24 | 22:40 | 2023-03-30 | 4:50 | 5d, 5h | Periodical | Track & Rail | T | [10 empty] | 80 | N | 1.37 |  | 2021-04-30
DB Netz AG | 10BB-001 | Rostock - Berlin | <> | Eichgestell | Ostendgestell | 2023 | 2023 | 16 | 16 | 2023-04-17 | 22:40 | 2023-04-21 | 4:50 | 3d, 6h | Periodical | Track & Rail | T | [10 empty] | 80 | N | 10BB-001 |  | 2021-04-30
DB Netz AG | 0.137 | Rostock - Berlin | <> | Eichgestell Nord | Stadtforst | 2023 | 2023 | 12 | 13 | 2023-03-24 | 22:40 | 2023-03-30 | 4:50 | 5d, 5h | Periodical | Track & Rail | T | [10 empty] | 80 | N | 0.137 |  | 2021-04-30
DB Netz AG | 10F1-002 | Falkenberg - Dresden | < | Leckwitz | Zeithain Bogendr | 2022 | 2022 | 49 | 52 | 2022-12-11 | 0:00 | 2022-12-31 | 8:00 | 117d, 7h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | Y | 10F1-002 |  | 2021-04-23
DB Netz AG | 10F1-002 | Falkenberg - Dresden | < | Leckwitz | Zeithain Bogendr | 2023 | 2023 | 1 | 14 | 2023-01-01 | 0:00 | 2023-04-07 | 8:00 | 117d, 7h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | Y | 10F1-002 |  | 2021-04-23
DB Netz AG | 10F1-001 | Falkenberg - Dresden | <> | Weißig (b Groß) | Weißig (b Groß) | 2022 | 2022 | 49 | 52 | 2022-12-11 | 0:00 | 2022-12-31 | 8:00 | 117d, 7h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | Y | 10F1-001 |  | 2021-05-20
DB Netz AG | 10F1-001 | Falkenberg - Dresden | <> | Weißig (b Groß) | Weißig (b Groß) | 2023 | 2023 | 1 | 14 | 2023-01-01 | 0:00 | 2023-04-07 | 8:00 | 117d, 7h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | Y | 10F1-001 |  | 2021-05-20
DB Netz AG | 10FD-001 | Magdeburg - Falkenberg | > | Lu Wittenberg | Elster (Elbe) | 2023 | 2023 | 18 | 20 | 2023-05-01 | 10:00 | 2023-05-19 | 18:00 | 18d, 8h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 10FD-001 |  | 2021-04-13
DB Netz AG | 10FD-002 | Magdeburg - Falkenberg | < | Elster (Elbe) | Lu Wittenberg | 2023 | 2023 | 11 | 13 | 2023-03-17 | 10:00 | 2023-03-31 | 18:00 | 14d, 7h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 10FD-002 |  | 2021-04-13
DB Netz AG | 10FE-002 | Dresden - Děčín | > | Obervogelgesang | Pirna | 2023 | 2023 | 9 | 22 | 2023-03-03 | 23:00 | 2023-05-29 | 4:00 | 86d, 4h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | Y | 10FE-002 |  | 2021-05-21
DB Netz AG | 10FE-003 | Dresden - Děčín | <> | Pirna Gbf | Pirna Gbf | 2023 | 2023 | 9 | 22 | 2023-03-03 | 8:00 | 2023-05-29 | 18:00 | 87d, 9h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | Y | 10FE-003 |  | 2021-05-25
DB Netz AG | 10FE-001 | Dresden - Děčín | <> | Pirna | Obervogelgesang | 2023 | 2023 | 9 | 22 | 2023-03-03 | 23:00 | 2023-05-29 | 4:00 | 86d, 4h | Continuous | Miscellaneous |  |  | S | [8 empty] | 80 | Y | 10FE-001 |  | 2021-05-21
DB Netz AG | 1113-011 | Dresden - Děčín | > | Schöna | Bad Schandau Ost | 2023 | 2023 | 16 | 17 | 2023-04-23 | 23:00 | 2023-04-28 | 5:00 | 4d, 6h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | 1113-011 |  | 2021-06-03
DB Netz AG | 1113-005 | Dresden - Děčín | > | Schöna | Bad Schandau Ost | 2023 | 2023 | 16 | 17 | 2023-04-23 | 23:00 | 2023-04-28 | 5:00 | 4d, 6h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 1113-005 |  | 2021-05-28
DB Netz AG | 1113-017 | Dresden - Děčín | <> | Schöna | Bad Schandau Ost | 2023 | 2023 | 16 | 17 | 2023-04-23 | 23:00 | 2023-04-28 | 5:00 | 4d, 6h | Periodical | Miscellaneous |  |  |  | P | [7 empty] | 80 | N | 1113-017 |  | 2021-05-28
DB Netz AG | 1113-012 | Dresden - Děčín | > | Bad Schandau Gr | Bad Schandau Ost | 2023 | 2023 | 17 | 18 | 2023-04-30 | 23:00 | 2023-05-03 | 5:00 | 2d, 6h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80,54 | N | 1113-012 |  | 2021-05-28
DB Netz AG | 1113-001 | Dresden - Děčín | > | Bad Schandau Gr | Bad Schandau Ost | 2023 | 2023 | 17 | 18 | 2023-04-30 | 23:00 | 2023-05-03 | 5:00 | 2d, 6h | Periodical | Miscellaneous |  | LT | [9 empty] | 80,54 | N | 1113-001 |  | 2021-05-28
DB Netz AG | 1113-006 | Dresden - Děčín | <> | Bad Schandau Gr | Bad Schandau Ost | 2023 | 2023 | 17 | 18 | 2023-04-30 | 23:00 | 2023-05-03 | 5:00 | 2d, 6h | Periodical | Miscellaneous |  |  |  | P | [7 empty] | 80,54 | N | 1113-006 |  | 2021-05-28
DB Netz AG | 1113-003 | Dresden - Děčín | <> | Bad Schandau Gr | Bad Schandau | 2023 | 2023 | 18 | 19 | 2023-05-07 | 23:00 | 2023-05-10 | 5:00 | 2d, 6h | Periodical | Miscellaneous |  |  |  | P | [7 empty] | 80,54 | N | 1113-003 |  | 2021-05-28
DB Netz AG | 1113-008 | Dresden - Děčín | > | Bad Schandau Ost | Bad Schandau | 2023 | 2023 | 18 | 19 | 2023-05-07 | 23:00 | 2023-05-10 | 5:00 | 2d, 6h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | 1113-008 |  | 2021-05-28
DB Netz AG | 1113-004 | Dresden - Děčín | > | Bad Schandau Ost | Bad Schandau | 2023 | 2023 | 18 | 19 | 2023-05-07 | 23:00 | 2023-05-10 | 5:00 | 2d, 6h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 1113-004 |  | 2021-05-28
DB Netz AG | 1113-015 | Dresden - Děčín | <> | Bad Schandau Ost | Bad Schandau Gr | 2023 | 2023 | 18 | 18 | 2023-05-03 | 23:00 | 2023-05-05 | 5:00 | 1d, 6h | Periodical | Miscellaneous |  |  |  | P | [7 empty] | 80,54 | N | 1113-015 |  | 2021-05-28
DB Netz AG | 1113-009 | Dresden - Děčín | < | Bad Schandau Ost | Bad Schandau Ost | 2023 | 2023 | 18 | 18 | 2023-05-03 | 23:00 | 2023-05-05 | 5:00 | 1d, 6h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 1113-009 |  | 2021-05-28
DB Netz AG | 1113-016 | Dresden - Děčín | < | Bad Schandau Ost | Bad Schandau Ost | 2023 | 2023 | 18 | 18 | 2023-05-03 | 23:00 | 2023-05-05 | 5:00 | 1d, 6h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1113-016 |  | 2021-05-28
DB Netz AG | 1113-010 | Dresden - Děčín | < | Bad Schandau Ost | Schöna | 2023 | 2023 | 18 | 18 | 2023-05-03 | 23:00 | 2023-05-05 | 5:00 | 1d, 6h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | 1113-010 |  | 2021-05-28
DB Netz AG | 11B8-002 | Hannover - Magdeburg | > | Lehrte | Groß Gleidingen | 2023 | 2023 | 16 | 17 | 2023-04-21 | 23:00 | 2023-04-28 | 5:00 | 6d, 6h | Periodical | Maintenance |  | LT | [9 empty] | 80 | N | 11B8-002 |  | 2021-11-25
DB Netz AG | 11EE-001 | Bremen - Hannover | > | Wunstorf | Bremen Hbf | 2023 | 2023 | 13 | 14 | 2023-03-27 | 23:00 | 2023-04-07 | 5:00 | 10d, 6h | Periodical | Maintenance |  | LT | [9 empty] | 80 | N | 11EE-001 |  | 2021-07-23
DB Netz AG | 1250-001 | Hannover - Magdeburg | > | Waldheim | Lehrte West | 2023 | 2023 | 15 | 17 | 2023-04-14 | 23:00 | 2023-04-28 | 5:00 | 13d, 6h | Periodical | Maintenance |  | LT | [9 empty] | 80 | N | 1250-001 |  | 2021-01-12
DB Netz AG | A4F-001 | Rostock - Berlin | <> | Kavelstorf | Dalwitzhof | 2023 | 2023 | 17 | 18 | 2023-04-28 | 21:00 | 2023-05-05 | 5:00 | 6d, 8h | Periodical | Maintenance | T | [10 empty] | 80 | N | A4F-001
DB Netz AG | 1289-001 | Magdeburg - Falkenberg | <> | Fermerswalde | Fermerswalde | 2023 | 2023 | 19 | 19 | 2023-05-08 | 8:00 | 2023-05-13 | 18:00 | 5d, 10h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1289-001 |  | 2021-04-29
DB Netz AG | 1289-004 | Magdeburg - Falkenberg | <> | Fermerswalde | Fermerswalde | 2023 | 2023 | 18 | 19 | 2023-05-07 | 22:00 | 2023-05-08 | 4:00 | 0d, 6h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1289-004 |  | 2021-04-06
DB Netz AG | 1289-005 | Falkenberg - Dresden | <> | Fak unt Bf W 26 | Fak unt Bf W 26 | 2023 | 2023 | 19 | 19 | 2023-05-08 | 8:00 | 2023-05-13 | 18:00 | 5d, 10h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1289-005 |  | 2021-04-29
DB Netz AG | 1289-003 | Falkenberg - Dresden | <> | Fak unt Bf B 20 | Fak unt Bf B 20 | 2023 | 2023 | 19 | 19 | 2023-05-08 | 8:00 | 2023-05-13 | 18:00 | 5d, 10h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1289-003 |  | 2021-04-06
DB Netz AG | 1289-002 | Magdeburg - Falkenberg | < | Annaburg | Fak unt Bf W 26 | 2023 | 2023 | 19 | 19 | 2023-05-08 | 22:00 | 2023-05-13 | 4:00 | 4d, 6h | Periodical | Track & Rail |  | LT | [9 empty] | 80 | N | 1289-002 |  | 2021-04-06
DB Netz AG | 1289-007 | Magdeburg - Falkenberg | < | Fermerswalde | Fermerswalde | 2023 | 2023 | 19 | 19 | 2023-05-08 | 8:00 | 2023-05-13 | 18:00 | 5d, 10h | Continuous | Track & Rail |  |  | S | [8 empty] | 80 | N | 1289-007 |  | 2021-04-29
DB Netz AG | 0.129 | Magdeburg - Falkenberg | <> | Roßlau(Elbe) Gbf | Roßlau(Elbe) Gbf | 2023 | 2023 | 16 | 22 | 2023-04-22 | 0:00 | 2023-06-03 | 23:59 | 42d, 23h | Continuous | Catenary |  | ST | [9 empty] | 80 | N | 0.129 |  | 2021-10-28
DB Netz AG | 12A2-001 | Magdeburg - Falkenberg | <> | Rodleben | Güterglück | 2023 | 2023 | 9 | 10 | 2023-03-05 | 20:00 | 2023-03-12 | 4:00 | 6d, 8h | Periodical | Maintenance |  | LT | [9 empty] | 80 | N | 12A2-001 |  | 2021-11-01
DB Netz AG | 1300-001 | Magdeburg - Falkenberg | < | Elster (Elbe) | Lu Wittenberg | 2023 | 2023 | 11 | 12 | 2023-03-17 | 10:00 | 2023-03-21 | 22:00 | 4d, 12h | Continuous | Signal |  | LT | [9 empty] | 80 | N | 1300-001 |  | 2021-05-18
DB Netz AG | 1300-002 | Magdeburg - Falkenberg | <> | Lu Wittenberg | Lu Wittenberg | 2023 | 2023 | 11 | 12 | 2023-03-17 | 10:00 | 2023-03-21 | 16:00 | 4d, 6h | Periodical | Signal |  | ST | [9 empty] | 80 | N | 1300-002 |  | 2022-01-07
DB Netz AG | 1300-003 | Magdeburg - Falkenberg | <> | Lu Wittenberg | Lu Wittenberg | 2023 | 2023 | 11 | 12 | 2023-03-17 | 10:00 | 2023-03-21 | 16:00 | 4d, 6h | Periodical | Signal |  | ST | [9 empty] | 80 | N | 1300-003 |  | 2021-05-19
DB Netz AG | 1301-001 | Magdeburg - Falkenberg | > | Lu Wittenberg | Lu Wb-Piesteritz | 2023 | 2023 | 17 | 18 | 2023-04-28 | 21:00 | 2023-05-01 | 10:00 | 2d, 13h | Continuous | Signal |  | LT | [9 empty] | 80 | N | 1301-001 |  | 2021-05-13
DB Netz AG | 130C-001 | Magdeburg - Falkenberg | < | Lu Wb-Piesteritz | Elster (Elbe) | 2023 | 2023 | 18 | 18 | 2023-05-01 | 10:00 | 2023-05-03 | 5:00 | 1d, 19h | Continuous | Signal |  | LT | [9 empty] | 80 | N | 130C-001 |  | 2021-05-14
DB Netz AG | 130D-003 | Magdeburg - Falkenberg | < | Lu Wittenberg | Elster (Elbe) | 2023 | 2023 | 18 | 19 | 2023-05-05 | 6:00 | 2023-05-10 | 22:00 | 5d, 16h | Continuous | Signal |  | LT | [9 empty] | 80 | N | 130D-003 |  | 2022-01-24
DB Netz AG | D9E-003 | Dresden - Děčín | <> | Bad Schandau | Bad Schandau Gr | 2022 | 2022 | 49 | 52 | 2022-12-11 | 0:01 | 2022-12-31 | 23:59 | 69d, 23h | Continuous | Catenary |  | ST | [9 empty] | 80,54 | Y | D9E-003 |  | 2021-05-25
DB Netz AG | D9E-003 | Dresden - Děčín | <> | Bad Schandau | Bad Schandau Gr | 2023 | 2023 | 1 | 7 | 2023-01-01 | 0:01 | 2023-02-18 | 23:59 | 69d, 23h | Continuous | Catenary |  | ST | [9 empty] | 80,54 | Y | D9E-003 |  | 2021-05-25
DB Netz AG | D9E-008 | Dresden - Děčín | <> | Bad Schandau Gr | Dolni Zleb | 2022 | 2022 | 49 | 52 | 2022-12-11 | 0:01 | 2022-12-31 | 23:59 | 69d, 23h | Continuous | Catenary |  |  |  | P | [7 empty] | 80,54,80,54 | Y | D9E-008 |  | 2022-04-29
DB Netz AG | D9E-008 | Dresden - Děčín | <> | Bad Schandau Gr | Dolni Zleb | 2023 | 2023 | 1 | 7 | 2023-01-01 | 0:01 | 2023-02-18 | 23:59 | 69d, 23h | Continuous | Catenary |  |  |  | P | [7 empty] | 80,54,80,54 | Y | D9E-008 |  | 2022-04-29
DB Netz AG | B58-002 | Hamburg - Magdeburg | <> | Schnega | Schnega | 2023 | 2023 | 11 | 12 | 2023-03-17 | 21:00 | 2023-03-20 | 5:00 | 2d, 8h | Continuous | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | B58-002
DB Netz AG | ED2-002 | Dresden - Děčín | <> | Bad Schandau Gr | Bad Schandau | 2022 | 2022 | 50 | 52 | 2022-12-12 | 8:50 | 2022-12-31 | 16:40 | 64d, 7h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80,54 | N | ED2-002 |  | 2022-04-29
DB Netz AG | ED2-002 | Dresden - Děčín | <> | Bad Schandau Gr | Bad Schandau | 2023 | 2023 | 1 | 7 | 2023-01-01 | 8:50 | 2023-02-14 | 16:40 | 64d, 7h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80,54 | N | ED2-002 |  | 2022-04-29
DB Netz AG | ED2-005 | Dresden - Děčín | <> | Bad Schandau Gr | Dolni Zleb | 2022 | 2022 | 50 | 52 | 2022-12-12 | 8:50 | 2022-12-31 | 16:40 | 64d, 7h | Periodical | Catenary | T | [10 empty] | 80,54,80,54 | N | ED2-005 |  | 2022-04-29
DB Netz AG | ED2-005 | Dresden - Děčín | <> | Bad Schandau Gr | Dolni Zleb | 2023 | 2023 | 1 | 7 | 2023-01-01 | 8:50 | 2023-02-14 | 16:40 | 64d, 7h | Periodical | Catenary | T | [10 empty] | 80,54,80,54 | N | ED2-005 |  | 2022-04-29
DB Netz AG | ED2-003 | Dresden - Děčín | <> | Bad Schandau Gr | Bad Schandau Gr | 2022 | 2022 | 50 | 52 | 2022-12-12 | 8:50 | 2022-12-31 | 16:40 | 64d, 7h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80,54 | N | ED2-003 |  | 2022-04-29
DB Netz AG | ED2-003 | Dresden - Děčín | <> | Bad Schandau Gr | Bad Schandau Gr | 2023 | 2023 | 1 | 7 | 2023-01-01 | 8:50 | 2023-02-14 | 16:40 | 64d, 7h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80,54 | N | ED2-003 |  | 2022-04-29
DB Netz AG | AED-002 | Hamburg - Magdeburg | <> | Salzwedel | Wieren | 2023 | 2023 | 10 | 10 | 2023-03-06 | 22:00 | 2023-03-11 | 5:00 | 4d, 7h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | AED-002
DB Netz AG | AED-004 | Hamburg - Magdeburg | <> | Schnega | Schnega | 2023 | 2023 | 10 | 11 | 2023-03-06 | 5:00 | 2023-03-17 | 21:00 | 11d, 16h | Continuous | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | AED-004
DB Netz AG | AED-007 | Hamburg - Magdeburg | <> | Schnega | Schnega | 2023 | 2023 | 10 | 11 | 2023-03-06 | 5:00 | 2023-03-17 | 21:00 | 11d, 16h | Continuous | Miscellaneous |  |  |  | P | [7 empty] | 80 | Y | AED-007
DB Netz AG | FCB-009 | Dresden - Děčín | > | Dolni Zleb | Bad Schandau Gr | 2023 | 2023 | 11 | 11 | 2023-03-15 | 7:40 | 2023-03-15 | 17:40 | 0d, 10h | Continuous | Track & Rail |  | LT | [9 empty] | 80,54,80,54 | N | FCB-009 |  | 2021-05-27
DB Netz AG | FCB-007 | Dresden - Děčín | <> | Bad Schandau Gr | Dolni Zleb | 2023 | 2023 | 11 | 11 | 2023-03-15 | 7:40 | 2023-03-15 | 17:40 | 0d, 10h | Continuous | Track & Rail |  |  |  | P | [7 empty] | 80,54,80,54 | N | FCB-007 |  | 2021-05-27
DB Netz AG | F72-005 | Dresden - Děčín | < | Bad Schandau Gr | Bad Schandau Gr | 2023 | 2023 | 11 | 11 | 2023-03-16 | 7:40 | 2023-03-16 | 17:40 | 0d, 10h | Continuous | Track & Rail |  | LT | [9 empty] | 80,54 | N | F72-005 |  | 2020-09-29
DB Netz AG | F72-004 | Dresden - Děčín | <> | Bad Schandau Gr | Dolni Zleb | 2023 | 2023 | 11 | 11 | 2023-03-16 | 7:40 | 2023-03-16 | 17:40 | 0d, 10h | Continuous | Track & Rail |  |  |  | P | [7 empty] | 80,54,80,54 | N | F72-004 |  | 2020-09-29
DB Netz AG | 1405-001 | Magdeburg - Falkenberg | > | Bad Liebenwerda | Fak unt Bf W 15 | 2023 | 2023 | 16 | 16 | 2023-04-18 | 22:00 | 2023-04-20 | 6:00 | 1d, 8h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | 1405-001 |  | 2021-09-17
DB Netz AG | 1405-002 | Magdeburg - Falkenberg | > | Bad Liebenwerda | Fak unt Bf B 20 | 2023 | 2023 | 16 | 16 | 2023-04-20 | 22:00 | 2023-04-21 | 6:00 | 0d, 8h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 1405-002 |  | 2021-09-17
DB Netz AG | 1424-001 | Magdeburg - Falkenberg | > | Fak unt Bf W 17 | Fermerswalde | 2023 | 2023 | 18 | 18 | 2023-05-02 | 10:00 | 2023-05-03 | 16:00 | 1d, 6h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | 1424-001 |  | 2022-01-25
DB Netz AG | 1424-002 | Magdeburg - Falkenberg | > | Fak unt Bf W 26 | Fermerswalde | 2023 | 2023 | 18 | 18 | 2023-05-04 | 10:00 | 2023-05-04 | 16:00 | 0d, 6h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 1424-002 |  | 2022-01-25
DB Netz AG | 1402-002 | Magdeburg - Falkenberg | > | Fak unt Bf W 26 | Annaburg | 2023 | 2023 | 18 | 18 | 2023-05-05 | 10:00 | 2023-05-05 | 16:00 | 0d, 6h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 1402-002 |  | 2021-07-15
DB Netz AG | 1402-003 | Magdeburg - Falkenberg | > | Fak unt Bf W 26 | Annaburg | 2023 | 2023 | 18 | 18 | 2023-05-06 | 10:00 | 2023-05-07 | 16:00 | 1d, 6h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | 1402-003 |  | 2021-05-21
DB Netz AG | 1402-004 | Magdeburg - Falkenberg | > | Annaburg | Jessen (Elster) | 2023 | 2023 | 19 | 19 | 2023-05-08 | 10:00 | 2023-05-09 | 16:00 | 1d, 6h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | 1402-004 |  | 2021-10-08
DB Netz AG | 1441-001 | Magdeburg - Falkenberg | < | Fak unt Bf W 17 | Wahrenbrück | 2023 | 2023 | 16 | 16 | 2023-04-21 | 22:00 | 2023-04-23 | 6:00 | 1d, 8h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | 1441-001 |  | 2021-09-14
DB Netz AG | 1441-002 | Magdeburg - Falkenberg | < | Fak unt Bf W 17 | Fak unt Bf W 15 | 2023 | 2023 | 16 | 17 | 2023-04-23 | 22:00 | 2023-04-24 | 6:00 | 0d, 8h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 1441-002 |  | 2021-09-14
DB Netz AG | 1437-006 | Magdeburg - Falkenberg | < | Lu Wb-Piesteritz | Lu Wittenberg | 2023 | 2023 | 18 | 18 | 2023-05-01 | 10:00 | 2023-05-01 | 16:00 | 0d, 6h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 1437-006 |  | 2021-05-21
DB Netz AG | 1402-005 | Magdeburg - Falkenberg | > | Lu Wittenberg | Lu Wb-Piesteritz | 2023 | 2023 | 17 | 17 | 2023-04-29 | 10:00 | 2023-04-29 | 16:00 | 0d, 6h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 1402-005 |  | 2021-05-21
DB Netz AG | 1405-005 | Magdeburg - Falkenberg | <> | Fak unt Bf W 17 | Fak unt Bf W 17 | 2023 | 2023 | 16 | 16 | 2023-04-20 | 22:00 | 2023-04-21 | 6:00 | 0d, 8h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | 1405-005 |  | 2021-09-17
DB Netz AG | 1424-003 | Magdeburg - Falkenberg | <> | Fak unt Bf B 20 | Fak unt Bf B 20 | 2023 | 2023 | 18 | 18 | 2023-05-02 | 10:00 | 2023-05-03 | 16:00 | 1d, 6h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | 1424-003 |  | 2021-05-21
DB Netz AG | 1485-005 | Hannover - Magdeburg | <> | Weddel/Braunschw | Weddel/Braunschw | 2022 | 2022 | 49 | 50 | 2022-12-11 | 0:00 | 2022-12-13 | 22:00 | 2d, 22h | Continuous | Miscellaneous |  |  | S | [8 empty] | 80 | N | 1485-005 |  | 2022-05-10
DB Netz AG | 1485-006 | Hannover - Magdeburg | <> | Weddel/Braunschw | Weddel/Braunschw | 2022 | 2022 | 49 | 50 | 2022-12-11 | 0:00 | 2022-12-13 | 22:00 | 2d, 22h | Continuous | Miscellaneous |  |  | S | [8 empty] | 80 | N | 1485-006 |  | 2022-05-10
DB Netz AG | 1485-007 | Hannover - Magdeburg | <> | Weddel/Braunschw | Weddel/Braunschw | 2022 | 2022 | 50 | 50 | 2022-12-13 | 22:00 | 2022-12-15 | 12:00 | 1d, 14h | Continuous | Miscellaneous |  |  | S | [8 empty] | 80 | N | 1485-007 |  | 2022-05-10
DB Netz AG | 1485-008 | Hannover - Magdeburg | <> | Weddel Abzw | Weddel Abzw | 2022 | 2022 | 50 | 50 | 2022-12-13 | 22:00 | 2022-12-15 | 12:00 | 1d, 14h | Continuous | Miscellaneous |  |  | S | [8 empty] | 80 | N | 1485-008 |  | 2022-05-30
DB Netz AG | 1082-057 | Bremen - Hannover | <> | Brm-Sebaldsbrück | Brm-Sebaldsbrück | 2023 | 2023 | 7 | 8 | 2023-02-17 | 22:00 | 2023-02-20 | 5:00 | 2d, 7h | Continuous | Bridge |  | ST | [9 empty] | 80 | N | 1082-057 |  | 2022-05-02
DB Netz AG | 1532-001 | Hannover - Magdeburg | <> | Braunschweig Rbf | Braunschweig Hbf | 2023 | 2023 | 9 | 9 | 2023-03-03 | 21:10 | 2023-03-04 | 0:00 | 0d, 2h | Continuous | Track & Rail | T | [10 empty] | 80 | N | 1532-001
DB Netz AG | 1532-002 | Hannover - Magdeburg | < | Buchhorst Abzw | Braunschweig Hbf | 2023 | 2023 | 9 | 9 | 2023-03-04 | 0:00 | 2023-03-04 | 3:00 | 0d, 3h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1532-002
DB Netz AG | 1532-003 | Hannover - Magdeburg | > | Braunschweig Hbf | Schandelah | 2023 | 2023 | 9 | 9 | 2023-03-04 | 3:00 | 2023-03-04 | 6:00 | 0d, 3h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1532-003
DB Netz AG | 15B5-019 | Hamburg - Magdeburg | <> | Hmb-Harburg | Hmb-Harburg | 2023 | 2023 | 14 | 14 | 2023-04-04 | 6:00 | 2023-04-04 | 19:00 | 0d, 13h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 15B5-019 |  | 2021-07-26
DB Netz AG | 15B5-020 | Hamburg - Magdeburg | > | Hmb-Harburg | Hmb-Harburg | 2023 | 2023 | 14 | 14 | 2023-04-04 | 2:00 | 2023-04-04 | 6:00 | 0d, 4h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 15B5-020
DB Netz AG | 15B6-015 | Hamburg - Magdeburg | > | Hmb-Harburg | Hmb-Harburg | 2023 | 2023 | 14 | 14 | 2023-04-08 | 0:00 | 2023-04-08 | 6:00 | 0d, 6h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 15B6-015
DB Netz AG | 15B6-016 | Hamburg - Magdeburg | > | Hmb-Harburg | Hmb-Harburg | 2023 | 2023 | 14 | 14 | 2023-04-07 | 18:00 | 2023-04-08 | 6:00 | 0d, 12h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 15B6-016
DB Netz AG | 15B7-013 | Hamburg - Magdeburg | > | Hmb-Harburg | Hmb-Harburg | 2023 | 2023 | 15 | 15 | 2023-04-12 | 3:00 | 2023-04-12 | 6:00 | 0d, 3h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 15B7-013
DB Netz AG | B49-072 | Hamburg - Magdeburg | > | Hmb-Harburg | Hmb-Harburg | 2023 | 2023 | 16 | 16 | 2023-04-23 | 1:00 | 2023-04-23 | 6:00 | 0d, 5h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | B49-072 |  | 2021-07-26
DB Netz AG | 1614-001 | Dresden - Děčín | < | Dresden-Altstadt | Dresden Hbf | 2023 | 2023 | 9 | 9 | 2023-03-01 | 22:00 | 2023-03-03 | 5:00 | 1d, 7h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 1614-001
DB Netz AG | 1614-002 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 9 | 9 | 2023-03-01 | 22:00 | 2023-03-03 | 5:00 | 1d, 7h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 1614-002
DB Netz AG | 1614-003 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 9 | 9 | 2023-03-01 | 22:00 | 2023-03-03 | 5:00 | 1d, 7h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 1614-003
DB Netz AG | 1614-004 | Dresden - Děčín | > | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 9 | 9 | 2023-03-03 | 22:00 | 2023-03-04 | 5:00 | 0d, 7h | Continuous | Catenary |  | ST | [9 empty] | 80 | N | 1614-004
DB Netz AG | 1614-005 | Dresden - Děčín | <> | Dresden Hbf | Dre Freibg Str | 2023 | 2023 | 9 | 9 | 2023-03-03 | 22:00 | 2023-03-04 | 5:00 | 0d, 7h | Continuous | Catenary |  | ST | [9 empty] | 80 | N | 1614-005
DB Netz AG | 1614-006 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 9 | 9 | 2023-03-03 | 22:00 | 2023-03-04 | 5:00 | 0d, 7h | Continuous | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 1614-006
DB Netz AG | 1614-007 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 9 | 9 | 2023-03-03 | 22:00 | 2023-03-04 | 5:00 | 0d, 7h | Continuous | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 1614-007
DB Netz AG | 1614-008 | Dresden - Děčín | > | Dre-Friedrichst | Dre Freibg Str | 2023 | 2023 | 9 | 9 | 2023-02-27 | 22:00 | 2023-03-01 | 5:00 | 1d, 7h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 1614-008
DB Netz AG | 1614-009 | Dresden - Děčín | <> | Dresden Mitte | Dresden Hbf | 2023 | 2023 | 9 | 9 | 2023-02-27 | 22:00 | 2023-03-01 | 5:00 | 1d, 7h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 1614-009
DB Netz AG | 1614-010 | Dresden - Děčín | > | Dre-Friedrichst | Dre Freibg Str | 2023 | 2023 | 9 | 9 | 2023-02-27 | 22:00 | 2023-03-01 | 5:00 | 1d, 7h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 1614-010
DB Netz AG | 1614-011 | Dresden - Děčín | <> | Dresden Mitte | Dresden Hbf | 2023 | 2023 | 9 | 9 | 2023-02-27 | 22:00 | 2023-03-01 | 5:00 | 1d, 7h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 1614-011
DB Netz AG | 1614-012 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 9 | 9 | 2023-02-27 | 22:00 | 2023-03-01 | 5:00 | 1d, 7h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 1614-012
DB Netz AG | 1614-013 | Dresden - Děčín | <> | Dre Freibg Str | Dre Freibg Str | 2023 | 2023 | 9 | 9 | 2023-02-27 | 22:00 | 2023-03-01 | 5:00 | 1d, 7h | Periodical | Catenary | T | [10 empty] | 80 | N | 1614-013
DB Netz AG | 1614-014 | Dresden - Děčín | <> | Dre Freibg Str | Dre Freibg Str | 2023 | 2023 | 9 | 9 | 2023-02-27 | 22:00 | 2023-03-01 | 5:00 | 1d, 7h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 1614-014
DB Netz AG | 1614-015 | Dresden - Děčín | <> | Dre-Friedrichst | Dre Freibg Str | 2023 | 2023 | 9 | 9 | 2023-02-27 | 22:00 | 2023-03-01 | 5:00 | 1d, 7h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 1614-015
DB Netz AG | 1614-016 | Dresden - Děčín | <> | Dre Freibg Str | Dre Freibg Str | 2023 | 2023 | 9 | 9 | 2023-02-27 | 22:00 | 2023-03-01 | 5:00 | 1d, 7h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 1614-016
DB Netz AG | 1640-001 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 13 | 13 | 2023-03-27 | 21:00 | 2023-04-01 | 5:00 | 4d, 8h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 1640-001
DB Netz AG | 1640-002 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 13 | 13 | 2023-03-27 | 21:00 | 2023-04-01 | 5:00 | 4d, 8h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 1640-002
DB Netz AG | 1640-003 | Dresden - Děčín | > | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 13 | 13 | 2023-03-27 | 21:00 | 2023-04-01 | 5:00 | 4d, 8h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 1640-003
DB Netz AG | 1640-004 | Dresden - Děčín | > | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 13 | 13 | 2023-03-27 | 21:00 | 2023-04-01 | 5:00 | 4d, 8h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 1640-004
DB Netz AG | 1640-005 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 13 | 13 | 2023-03-27 | 21:00 | 2023-04-01 | 5:00 | 4d, 8h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 1640-005
DB Netz AG | 1640-006 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 13 | 13 | 2023-03-27 | 21:00 | 2023-04-01 | 5:00 | 4d, 8h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 1640-006
DB Netz AG | 1640-007 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 16 | 16 | 2023-04-17 | 20:00 | 2023-04-22 | 5:00 | 4d, 9h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 1640-007
DB Netz AG | 1640-008 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 16 | 16 | 2023-04-17 | 20:00 | 2023-04-22 | 5:00 | 4d, 9h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 1640-008
DB Netz AG | 1640-009 | Dresden - Děčín | > | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 16 | 16 | 2023-04-17 | 20:00 | 2023-04-22 | 5:00 | 4d, 9h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 1640-009
DB Netz AG | 1640-010 | Dresden - Děčín | > | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 16 | 16 | 2023-04-17 | 20:00 | 2023-04-22 | 5:00 | 4d, 9h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 1640-010
DB Netz AG | 1640-011 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 16 | 16 | 2023-04-17 | 20:00 | 2023-04-22 | 5:00 | 4d, 9h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 1640-011
DB Netz AG | 1640-012 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 16 | 16 | 2023-04-17 | 20:00 | 2023-04-22 | 5:00 | 4d, 9h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 1640-012
DB Netz AG | 16D7-001 | Dresden - Děčín | <> | Pirna | Coswig (bei Dre) | 2023 | 2023 | 7 | 7 | 2023-02-18 | 23:00 | 2023-02-19 | 3:00 | 0d, 4h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 16D7-001
DB Netz AG | 16D7-002 | Falkenberg - Dresden | <> | Dre-Neustadt | Weißig (b Groß) | 2023 | 2023 | 7 | 7 | 2023-02-18 | 23:00 | 2023-02-19 | 3:00 | 0d, 4h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 16D7-002
DB Netz AG | 16D7-003 | Dresden - Děčín | <> | Pirna | Dre-Neustadt | 2023 | 2023 | 7 | 7 | 2023-02-18 | 23:00 | 2023-02-19 | 3:00 | 0d, 4h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 16D7-003
DB Netz AG | 16D7-004 | Dresden - Děčín | <> | Dresden Hbf | Dre-Neustadt | 2023 | 2023 | 7 | 7 | 2023-02-18 | 23:00 | 2023-02-19 | 3:00 | 0d, 4h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 16D7-004
DB Netz AG | 16D7-005 | Dresden - Děčín | <> | Dresden Hbf | Freit-Hainsbg Hp | 2023 | 2023 | 7 | 7 | 2023-02-18 | 23:00 | 2023-02-19 | 3:00 | 0d, 4h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 16D7-005
DB Netz AG | 16D7-006 | Berlin - Dresden | <> | Az | Radebeul Nord | 2023 | 2023 | 7 | 7 | 2023-02-18 | 23:00 | 2023-02-19 | 3:00 | 0d, 4h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 16D7-006
DB Netz AG | 16D7-008 | Falkenberg - Dresden | <> | Zeithain Bogendr | Elsterwerda | 2023 | 2023 | 7 | 7 | 2023-02-18 | 23:00 | 2023-02-19 | 3:00 | 0d, 4h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 16D7-008
DB Netz AG | 16D7-010 | Dresden - Děčín | <> | Bad Schandau | Bad Schandau | 2023 | 2023 | 7 | 7 | 2023-02-18 | 23:00 | 2023-02-19 | 3:00 | 0d, 4h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 16D7-010
DB Netz AG | 16D7-011 | Falkenberg - Dresden | <> | Leckwitz | Kottewitz | 2023 | 2023 | 7 | 7 | 2023-02-18 | 23:00 | 2023-02-19 | 3:00 | 0d, 4h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 16D7-011
DB Netz AG | 16D7-012 | Berlin - Dresden | <> | Dre-Pieschen Abz | Dre-Neustadt | 2023 | 2023 | 7 | 7 | 2023-02-18 | 23:00 | 2023-02-19 | 3:00 | 0d, 4h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 16D7-012
DB Netz AG | 16D7-014 | Berlin - Dresden | <> | Elsterwerda | Elsterw-Biehla | 2023 | 2023 | 7 | 7 | 2023-02-18 | 23:00 | 2023-02-19 | 3:00 | 0d, 4h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 16D7-014
DB Netz AG | 16D7-015 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 7 | 7 | 2023-02-18 | 23:00 | 2023-02-19 | 3:00 | 0d, 4h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 16D7-015
DB Netz AG | 16D7-016 | Falkenberg - Dresden | <> | Großenh Cott Bf | Priestewitz | 2023 | 2023 | 7 | 7 | 2023-02-18 | 23:00 | 2023-02-19 | 3:00 | 0d, 4h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 16D7-016
DB Netz AG | 16D7-017 | Dresden - Děčín | <> | Dre-Friedrichst | Dresden Mitte | 2023 | 2023 | 7 | 7 | 2023-02-18 | 23:00 | 2023-02-19 | 3:00 | 0d, 4h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 16D7-017
DB Netz AG | 16D7-018 | Berlin - Dresden | <> | Großenh Berl Bf | Großenh Cott Bf | 2023 | 2023 | 7 | 7 | 2023-02-18 | 23:00 | 2023-02-19 | 3:00 | 0d, 4h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 16D7-018
DB Netz AG | 16D7-019 | Falkenberg - Dresden | <> | Dre-Friedrichst | Elsterwerda Strw | 2023 | 2023 | 7 | 7 | 2023-02-18 | 23:00 | 2023-02-19 | 3:00 | 0d, 4h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 16D7-019
DB Netz AG | 16D7-020 | Berlin - Dresden | <> | Elsterwerda Strw | Hohenleipisch | 2023 | 2023 | 7 | 7 | 2023-02-18 | 23:00 | 2023-02-19 | 3:00 | 0d, 4h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 16D7-020
DB Netz AG | 16FB-002 | Dresden - Děčín | <> | Bad Schandau | Bad Schandau | 2023 | 2023 | 8 | 8 | 2023-02-24 | 7:00 | 2023-02-24 | 13:00 | 0d, 6h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 16FB-002 |  | 2021-04-30
DB Netz AG | 16FB-003 | Dresden - Děčín | <> | Bad Schandau | Bad Schandau | 2023 | 2023 | 8 | 8 | 2023-02-24 | 7:00 | 2023-02-24 | 13:00 | 0d, 6h | Continuous | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 16FB-003 |  | 2021-04-30
DB Netz AG | 1779-004 | Rostock - Berlin | <> | Biesdf Kr Nord | Bln Nordost | 2023 | 2023 | 2 | 2 | 2023-01-09 | 8:00 | 2023-01-09 | 14:00 | 0d, 6h | Continuous | Bridge | T | [10 empty] | 80 | N | 1779-004
DB Netz AG | 1779-008 | Rostock - Berlin | <> | Biesdf Kr Nord | Bln Nordost | 2023 | 2023 | 6 | 6 | 2023-02-06 | 8:00 | 2023-02-07 | 14:00 | 1d, 6h | Continuous | Bridge | T | [10 empty] | 80 | N | 1779-008
DB Netz AG | 1308-008 | Rostock - Berlin | <> | Hohen Neuend W | Birkenwerd b Bln | 2022 | 2022 | 49 | 52 | 2022-12-11 | 0:00 | 2022-12-31 | 4:00 | 295d, 3h | Continuous | Signal |  |  |  | P | [7 empty] | 80 | N | 1308-008 |  | 2022-05-16
DB Netz AG | 1308-008 | Rostock - Berlin | <> | Hohen Neuend W | Birkenwerd b Bln | 2023 | 2023 | 1 | 40 | 2023-01-01 | 0:00 | 2023-10-02 | 4:00 | 295d, 3h | Continuous | Signal |  |  |  | P | [7 empty] | 80 | N | 1308-008 |  | 2022-05-16
DB Netz AG | 1308-009 | Rostock - Berlin | <> | Birkenwerd b Bln | Schönfließ West | 2022 | 2022 | 49 | 52 | 2022-12-11 | 0:00 | 2022-12-31 | 4:00 | 295d, 3h | Continuous | Signal |  |  |  | P | [7 empty] | 80 | N | 1308-009 |  | 2022-05-16
DB Netz AG | 1308-009 | Rostock - Berlin | <> | Birkenwerd b Bln | Schönfließ West | 2023 | 2023 | 1 | 40 | 2023-01-01 | 0:00 | 2023-10-02 | 4:00 | 295d, 3h | Continuous | Signal |  |  |  | P | [7 empty] | 80 | N | 1308-009 |  | 2022-05-16
DB Netz AG | 1308-010 | Rostock - Berlin | <> | Hohen Neuend Sw | Schönfließ West | 2022 | 2022 | 49 | 52 | 2022-12-11 | 0:00 | 2022-12-31 | 4:00 | 295d, 3h | Continuous | Signal |  |  |  | P | [7 empty] | 80 | N | 1308-010 |  | 2022-05-16
DB Netz AG | 1308-010 | Rostock - Berlin | <> | Hohen Neuend Sw | Schönfließ West | 2023 | 2023 | 1 | 40 | 2023-01-01 | 0:00 | 2023-10-02 | 4:00 | 295d, 3h | Continuous | Signal |  |  |  | P | [7 empty] | 80 | N | 1308-010 |  | 2022-05-16
DB Netz AG | 1801-005 | Hannover - Magdeburg | > | Waldhausen | Hannover-Wülfel | 2023 | 2023 | 10 | 10 | 2023-03-06 | 22:35 | 2023-03-07 | 0:20 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1801-005 |  | 2022-04-25
DB Netz AG | 181C-001 | Bremerhaven - Bremen | <> | Brh-Wulsdorf | Brh-Speckenbütt | 2023 | 2023 | 14 | 14 | 2023-04-03 | 4:00 | 2023-04-03 | 5:00 | 0d, 1h | Continuous | Bridge |  |  |  |  | X | [6 empty] | 80 | N | 181C-001 |  | 2021-08-16
DB Netz AG | 1841-001 | Falkenberg - Dresden | <> | Großenh Cott Bf | Priestewitz | 2023 | 2023 | 18 | 18 | 2023-05-02 | 21:00 | 2023-05-03 | 4:00 | 0d, 7h | Continuous | Track & Rail | T | [10 empty] | 80 | N | 1841-001 |  | 2022-07-15
DB Netz AG | 1841-002 | Berlin - Dresden | <> | Großenh Cott Bf | Großenh Cott Bf | 2023 | 2023 | 18 | 18 | 2023-05-02 | 21:00 | 2023-05-03 | 4:00 | 0d, 7h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1841-002 |  | 2022-07-15
DB Netz AG | 1841-003 | Falkenberg - Dresden | < | Priestewitz | Leckwitz | 2023 | 2023 | 18 | 18 | 2023-05-03 | 1:00 | 2023-05-03 | 4:00 | 0d, 3h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1841-003 |  | 2022-07-15
DB Netz AG | 1841-004 | Falkenberg - Dresden | <> | Priestewitz | Priestewitz | 2023 | 2023 | 18 | 18 | 2023-05-03 | 1:00 | 2023-05-03 | 4:00 | 0d, 3h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1841-004 |  | 2022-07-15
DB Netz AG | 1846-001 | Berlin - Dresden | <> | Großenh Cott Bf | Lampertswalde | 2023 | 2023 | 18 | 18 | 2023-05-03 | 21:30 | 2023-05-05 | 4:30 | 1d, 7h | Periodical | Track & Rail | T | [10 empty] | 80 | N | 1846-001
DB Netz AG | 1846-002 | Berlin - Dresden | <> | Großenh Cott Bf | Lampertswalde | 2023 | 2023 | 18 | 18 | 2023-05-03 | 21:30 | 2023-05-05 | 4:30 | 1d, 7h | Periodical | Track & Rail |  | ST | [9 empty] | 80 | N | 1846-002
DB Netz AG | 1849-002 | Falkenberg - Dresden | <> | Priestewitz | Niederau | 2023 | 2023 | 18 | 18 | 2023-05-02 | 21:00 | 2023-05-04 | 5:00 | 1d, 8h | Periodical | Track & Rail | T | [10 empty] | 80 | N | 1849-002 |  | 2021-05-05
DB Netz AG | 1849-003 | Falkenberg - Dresden | <> | Priestewitz | Niederau | 2023 | 2023 | 18 | 18 | 2023-05-02 | 21:00 | 2023-05-04 | 5:00 | 1d, 8h | Periodical | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | 1849-003 |  | 2021-05-05
DB Netz AG | 1849-004 | Falkenberg - Dresden | <> | Priestewitz | Niederau | 2023 | 2023 | 18 | 19 | 2023-05-02 | 21:00 | 2023-05-12 | 5:00 | 9d, 8h | Continuous | Track & Rail |  |  |  | P | [7 empty] | 80 | N | 1849-004 |  | 2021-05-05
DB Netz AG | 1849-005 | Falkenberg - Dresden | < | Niederau | Priestewitz | 2023 | 2023 | 18 | 19 | 2023-05-04 | 5:00 | 2023-05-10 | 21:00 | 6d, 16h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1849-005 |  | 2021-05-05
DB Netz AG | 1849-006 | Falkenberg - Dresden | < | Niederau | Priestewitz | 2023 | 2023 | 18 | 19 | 2023-05-04 | 5:00 | 2023-05-10 | 21:00 | 6d, 16h | Continuous | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | 1849-006 |  | 2021-05-05
DB Netz AG | 1849-007 | Falkenberg - Dresden | <> | Niederau | Priestewitz | 2023 | 2023 | 18 | 19 | 2023-05-04 | 5:00 | 2023-05-10 | 21:00 | 6d, 16h | Continuous | Track & Rail |  |  | S | [8 empty] | 80 | N | 1849-007 |  | 2021-05-05
DB Netz AG | 1849-008 | Falkenberg - Dresden | <> | Priestewitz | Niederau | 2023 | 2023 | 18 | 19 | 2023-05-05 | 1:00 | 2023-05-10 | 4:00 | 5d, 3h | Periodical | Track & Rail | T | [10 empty] | 80 | N | 1849-008 |  | 2021-05-05
DB Netz AG | 1849-009 | Falkenberg - Dresden | <> | Priestewitz | Niederau | 2023 | 2023 | 18 | 19 | 2023-05-05 | 1:00 | 2023-05-10 | 4:00 | 5d, 3h | Periodical | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | 1849-009 |  | 2021-05-05
DB Netz AG | 1856-001 | Falkenberg - Dresden | > | Großenh Berl Bf | Frauenhain | 2023 | 2023 | 7 | 8 | 2023-02-19 | 21:30 | 2023-02-20 | 2:00 | 0d, 4h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1856-001
DB Netz AG | 1856-002 | Berlin - Dresden | <> | Großenh Berl Bf | Großenh Cott Bf | 2023 | 2023 | 7 | 8 | 2023-02-19 | 21:30 | 2023-02-20 | 2:00 | 0d, 4h | Continuous | Maintenance | T | [10 empty] | 80 | N | 1856-002
DB Netz AG | 1856-003 | Falkenberg - Dresden | > | Großenh Berl Bf | Elsterwerda | 2023 | 2023 | 8 | 8 | 2023-02-20 | 2:00 | 2023-02-20 | 5:30 | 0d, 3h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1856-003
DB Netz AG | 1856-004 | Falkenberg - Dresden | <> | Frauenhain | Frauenhain | 2023 | 2023 | 8 | 8 | 2023-02-20 | 2:00 | 2023-02-20 | 5:30 | 0d, 3h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 1856-004
DB Netz AG | 1856-005 | Berlin - Dresden | > | Elsterwerda | Elsterwerda | 2023 | 2023 | 8 | 8 | 2023-02-20 | 2:00 | 2023-02-20 | 5:30 | 0d, 3h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 1856-005 |  | 2021-11-15
DB Netz AG | 1856-006 | Berlin - Dresden | < | Elsterwerda | Frauenhain | 2023 | 2023 | 8 | 8 | 2023-02-20 | 21:30 | 2023-02-21 | 1:30 | 0d, 4h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1856-006 |  | 2022-01-10
DB Netz AG | 1856-007 | Falkenberg - Dresden | < | Großenh Berl Bf | Kottewitz | 2023 | 2023 | 8 | 8 | 2023-02-21 | 1:30 | 2023-02-21 | 5:30 | 0d, 4h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1856-007 |  | 2022-01-10
DB Netz AG | 1856-008 | Falkenberg - Dresden | <> | Frauenhain | Frauenhain | 2023 | 2023 | 8 | 8 | 2023-02-20 | 21:30 | 2023-02-21 | 1:30 | 0d, 4h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 1856-008 |  | 2022-01-10
DB Netz AG | 1856-009 | Berlin - Dresden | < | Elsterwerda | Elsterwerda | 2023 | 2023 | 8 | 8 | 2023-02-20 | 21:30 | 2023-02-21 | 1:30 | 0d, 4h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 1856-009 |  | 2022-01-10
DB Netz AG | 1872-001 | Falkenberg - Dresden | > | Weinböhla | Kottewitz | 2023 | 2023 | 11 | 12 | 2023-03-19 | 21:00 | 2023-03-20 | 4:30 | 0d, 7h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1872-001 |  | 2022-04-10
DB Netz AG | 1872-002 | Falkenberg - Dresden | > | Weinböhla | Kottewitz | 2023 | 2023 | 11 | 12 | 2023-03-19 | 21:00 | 2023-03-20 | 4:30 | 0d, 7h | Continuous | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | 1872-002 |  | 2022-04-10
DB Netz AG | 1872-003 | Falkenberg - Dresden | <> | Weinböhla | Kottewitz | 2023 | 2023 | 11 | 12 | 2023-03-19 | 21:00 | 2023-03-20 | 4:30 | 0d, 7h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1872-003 |  | 2022-04-10
DB Netz AG | 1872-004 | Falkenberg - Dresden | <> | Weinböhla | Kottewitz | 2023 | 2023 | 11 | 12 | 2023-03-19 | 21:00 | 2023-03-20 | 4:30 | 0d, 7h | Continuous | Track & Rail |  |  |  | P | [7 empty] | 80 | N | 1872-004 |  | 2022-05-03
DB Netz AG | 1872-005 | Falkenberg - Dresden | > | Az | Weinböhla | 2023 | 2023 | 11 | 11 | 2023-03-19 | 21:00 | 2023-03-19 | 23:00 | 0d, 2h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1872-005 |  | 2022-05-03
DB Netz AG | 1872-006 | Falkenberg - Dresden | <> | Weinböhla | Weinböhla | 2023 | 2023 | 11 | 11 | 2023-03-19 | 21:00 | 2023-03-19 | 23:00 | 0d, 2h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1872-006 |  | 2022-05-03
DB Netz AG | 1872-007 | Berlin - Dresden | < | Radebeul Nord | Az | 2023 | 2023 | 11 | 11 | 2023-03-19 | 21:00 | 2023-03-19 | 23:00 | 0d, 2h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1872-007 |  | 2022-05-03
DB Netz AG | 1872-008 | Falkenberg - Dresden | > | Weinböhla | Kottewitz | 2023 | 2023 | 11 | 11 | 2023-03-19 | 21:00 | 2023-03-19 | 23:00 | 0d, 2h | Continuous | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | 1872-008 |  | 2022-05-03
DB Netz AG | 1872-009 | Falkenberg - Dresden | < | Kottewitz | Weinböhla | 2023 | 2023 | 12 | 12 | 2023-03-20 | 21:00 | 2023-03-22 | 4:00 | 1d, 7h | Periodical | Track & Rail |  | LT | [9 empty] | 80 | N | 1872-009 |  | 2022-05-03
DB Netz AG | 1872-010 | Falkenberg - Dresden | <> | Weinböhla | Weinböhla | 2023 | 2023 | 12 | 12 | 2023-03-20 | 21:00 | 2023-03-22 | 4:00 | 1d, 7h | Periodical | Track & Rail |  | ST | [9 empty] | 80 | N | 1872-010 |  | 2022-05-03
DB Netz AG | 1872-011 | Falkenberg - Dresden | < | Kottewitz | Weinböhla | 2023 | 2023 | 12 | 12 | 2023-03-20 | 21:00 | 2023-03-22 | 4:00 | 1d, 7h | Periodical | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | 1872-011 |  | 2022-05-03
DB Netz AG | 1872-012 | Falkenberg - Dresden | <> | Weinböhla | Kottewitz | 2023 | 2023 | 12 | 12 | 2023-03-20 | 21:00 | 2023-03-22 | 4:00 | 1d, 7h | Periodical | Track & Rail |  |  |  | P | [7 empty] | 80 | N | 1872-012 |  | 2022-05-03
DB Netz AG | 1872-013 | Falkenberg - Dresden | < | Weinböhla | Kottewitz | 2023 | 2023 | 12 | 12 | 2023-03-20 | 21:00 | 2023-03-21 | 4:00 | 0d, 7h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1872-013 |  | 2022-05-03
DB Netz AG | 1878-001 | Bremerhaven - Bremen | < | Brm-Sebaldsbrück | Achim | 2023 | 2023 | 13 | 13 | 2023-03-31 | 23:00 | 2023-04-01 | 3:00 | 0d, 4h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 1878-001 |  | 2021-08-19
DB Netz AG | 1878-002 | Bremerhaven - Bremen | > | Achim | Brm-Sebaldsbrück | 2023 | 2023 | 13 | 13 | 2023-04-01 | 3:00 | 2023-04-01 | 5:00 | 0d, 2h | Continuous | Catenary |  | LT | [9 empty] | 80 | N | 1878-002 |  | 2021-08-19
DB Netz AG | 1878-003 | Bremerhaven - Bremen | <> | Bremen-Mahndorf | Bremen-Mahndorf | 2023 | 2023 | 13 | 13 | 2023-03-31 | 23:00 | 2023-04-01 | 3:00 | 0d, 4h | Continuous | Catenary |  |  | S | [8 empty] | 80 | N | 1878-003 |  | 2022-05-24
DB Netz AG | 1878-004 | Bremerhaven - Bremen | <> | Bremen-Mahndorf | Bremen-Mahndorf | 2023 | 2023 | 13 | 13 | 2023-04-01 | 3:00 | 2023-04-01 | 5:00 | 0d, 2h | Periodical | Catenary |  |  | S | [8 empty] | 80 | N | 1878-004 |  | 2022-05-24
DB Netz AG | 1899-001 | Rostock - Berlin | > | Kavelstorf | Laage (Meckl) | 2023 | 2023 | 18 | 18 | 2023-05-02 | 7:00 | 2023-05-03 | 15:45 | 1d, 8h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | 1899-001 |  | 2021-08-21
DB Netz AG | 1899-002 | Rostock - Berlin | < | Laage (Meckl) | Kavelstorf | 2023 | 2023 | 18 | 18 | 2023-05-02 | 7:00 | 2023-05-03 | 15:45 | 1d, 8h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | 1899-002 |  | 2021-08-21
DB Netz AG | 1914-005 | Magdeburg - Falkenberg | <> | Herzberg(Elster) | Fak unt Bf W 26 | 2023 | 2023 | 14 | 14 | 2023-04-03 | 22:00 | 2023-04-04 | 6:00 | 0d, 8h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | 1914-005 |  | 2021-09-29
DB Netz AG | 1914-007 | Magdeburg - Falkenberg | <> | Herzberg(Elster) | Fak unt Bf B 20 | 2023 | 2023 | 13 | 14 | 2023-04-02 | 22:00 | 2023-04-03 | 6:00 | 0d, 8h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | 1914-007 |  | 2021-09-29
DB Netz AG | 18AB-001 | Bremen - Hannover | > | Baden /Kr Verden | Bremen-Mahndorf | 2023 | 2023 | 9 | 9 | 2023-03-02 | 22:00 | 2023-03-02 | 23:40 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 18AB-001 |  | 2022-06-27
DB Netz AG | 18AB-002 | Bremen - Hannover | > | Achim | Brm-Sebaldsbrück | 2023 | 2023 | 9 | 9 | 2023-03-02 | 23:40 | 2023-03-03 | 1:40 | 0d, 2h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 18AB-002 |  | 2022-06-27
DB Netz AG | 1914-008 | Magdeburg - Falkenberg | <> | Fak unt Bf B 20 | Fak unt Bf B 20 | 2023 | 2023 | 13 | 14 | 2023-04-02 | 22:00 | 2023-04-03 | 6:00 | 0d, 8h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 1914-008 |  | 2021-09-29
DB Netz AG | 18AB-003 | Bremen - Hannover | <> | Brm-Sebaldsbrück | Brm-Sebaldsbrück | 2023 | 2023 | 9 | 9 | 2023-03-03 | 1:40 | 2023-03-03 | 2:30 | 0d, 0h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 18AB-003 |  | 2022-06-27
DB Netz AG | 18AB-004 | Bremen - Hannover | > | Bremen-Mahndorf | Bremen Hbf | 2023 | 2023 | 9 | 9 | 2023-03-03 | 1:40 | 2023-03-03 | 2:30 | 0d, 0h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 18AB-004 |  | 2022-06-27
DB Netz AG | 18AB-006 | Bremen - Hannover | <> | Brm-Sebaldsbrück | Bremen Hbf | 2023 | 2023 | 9 | 9 | 2023-03-03 | 1:40 | 2023-03-03 | 2:30 | 0d, 0h | Continuous | Maintenance | T | [10 empty] | 80 | N | 18AB-006 |  | 2022-06-27
DB Netz AG | 18AB-007 | Bremen - Hannover | > | Brm-Sebaldsbrück | Bremen Hbf | 2023 | 2023 | 9 | 9 | 2023-03-03 | 2:30 | 2023-03-03 | 3:45 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 18AB-007 |  | 2022-06-27
DB Netz AG | 18AB-008 | Bremen - Hannover | < | Bremen Hbf | Hastedt | 2023 | 2023 | 9 | 9 | 2023-03-03 | 2:30 | 2023-03-03 | 3:45 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 18AB-008 |  | 2022-06-27
DB Netz AG | 1914-009 | Magdeburg - Falkenberg | <> | Fak unt Bf W 26 | Fak unt Bf W 26 | 2023 | 2023 | 14 | 14 | 2023-04-03 | 22:00 | 2023-04-04 | 6:00 | 0d, 8h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 1914-009 |  | 2021-09-29
DB Netz AG | 18AB-009 | Bremerhaven - Bremen | > | Bremen Hbf | Bremen Rbf Abzw | 2023 | 2023 | 9 | 9 | 2023-03-03 | 3:45 | 2023-03-03 | 4:30 | 0d, 0h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 18AB-009 |  | 2022-06-27
DB Netz AG | 1978-001 | Falkenberg - Dresden | <> | Coswig Stw 1 | Coswig (bei Dre) | 2023 | 2023 | 15 | 17 | 2023-04-11 | 8:00 | 2023-04-27 | 17:00 | 16d, 9h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1978-001 |  | 2021-04-20
DB Netz AG | 1978-003 | Falkenberg - Dresden | <> | Coswig (bei Dre) | Coswig (bei Dre) | 2023 | 2023 | 15 | 17 | 2023-04-11 | 8:00 | 2023-04-27 | 17:00 | 16d, 9h | Continuous | Track & Rail |  |  |  | P | [7 empty] | 80 | N | 1978-003 |  | 2021-04-20
DB Netz AG | 1978-004 | Falkenberg - Dresden | <> | Coswig Stw 1 | Coswig (bei Dre) | 2023 | 2023 | 15 | 16 | 2023-04-14 | 8:00 | 2023-04-23 | 17:00 | 9d, 9h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1978-004 |  | 2021-04-20
DB Netz AG | 1978-006 | Falkenberg - Dresden | <> | Coswig (bei Dre) | Coswig (bei Dre) | 2023 | 2023 | 16 | 16 | 2023-04-20 | 16:00 | 2023-04-20 | 17:00 | 0d, 1h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1978-006 |  | 2021-04-20
DB Netz AG | 1978-007 | Falkenberg - Dresden | <> | Coswig (bei Dre) | Coswig (bei Dre) | 2023 | 2023 | 16 | 16 | 2023-04-20 | 16:00 | 2023-04-20 | 17:00 | 0d, 1h | Continuous | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | 1978-007 |  | 2021-04-20
DB Netz AG | 1978-008 | Falkenberg - Dresden | <> | Coswig (bei Dre) | Coswig (bei Dre) | 2023 | 2023 | 16 | 16 | 2023-04-20 | 17:00 | 2023-04-23 | 17:00 | 3d, 0h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1978-008 |  | 2021-04-20
DB Netz AG | 1978-010 | Falkenberg - Dresden | <> | Coswig (bei Dre) | Coswig (bei Dre) | 2023 | 2023 | 16 | 16 | 2023-04-20 | 17:00 | 2023-04-23 | 17:00 | 3d, 0h | Continuous | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | 1978-010 |  | 2021-04-20
DB Netz AG | 1978-011 | Falkenberg - Dresden | <> | Coswig (bei Dre) | Coswig (bei Dre) | 2023 | 2023 | 16 | 16 | 2023-04-22 | 23:00 | 2023-04-23 | 5:00 | 0d, 6h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1978-011 |  | 2021-04-20
DB Netz AG | 1978-012 | Falkenberg - Dresden | < | Coswig (bei Dre) | Radeb-Naundf Abz | 2023 | 2023 | 16 | 16 | 2023-04-22 | 23:00 | 2023-04-23 | 5:00 | 0d, 6h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1978-012 |  | 2021-04-20
DB Netz AG | 1978-013 | Falkenberg - Dresden | < | Radebeul-Naundf | Radebeul-Naundf | 2023 | 2023 | 16 | 16 | 2023-04-22 | 23:00 | 2023-04-23 | 5:00 | 0d, 6h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1978-013 |  | 2021-04-20
DB Netz AG | 1978-014 | Falkenberg - Dresden | <> | Coswig (bei Dre) | Coswig (bei Dre) | 2023 | 2023 | 16 | 17 | 2023-04-23 | 17:00 | 2023-04-27 | 17:00 | 4d, 0h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1978-014 |  | 2021-04-20
DB Netz AG | 1978-016 | Falkenberg - Dresden | <> | Coswig (bei Dre) | Coswig (bei Dre) | 2023 | 2023 | 16 | 17 | 2023-04-23 | 17:00 | 2023-04-27 | 17:00 | 4d, 0h | Continuous | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | 1978-016 |  | 2021-04-20
DB Netz AG | 1978-017 | Falkenberg - Dresden | <> | Coswig (bei Dre) | Coswig (bei Dre) | 2023 | 2023 | 17 | 17 | 2023-04-27 | 8:00 | 2023-04-27 | 12:00 | 0d, 4h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1978-017 |  | 2021-04-20
DB Netz AG | 1978-018 | Falkenberg - Dresden | <> | Coswig (bei Dre) | Coswig (bei Dre) | 2023 | 2023 | 17 | 17 | 2023-04-27 | 16:00 | 2023-04-27 | 17:00 | 0d, 1h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1978-018 |  | 2021-04-20
DB Netz AG | 1978-019 | Falkenberg - Dresden | <> | Coswig (bei Dre) | Coswig (bei Dre) | 2023 | 2023 | 17 | 17 | 2023-04-27 | 16:00 | 2023-04-27 | 17:00 | 0d, 1h | Continuous | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | 1978-019 |  | 2021-04-20
DB Netz AG | 19A4-001 | Berlin - Dresden | <> | Gensh Heide Mitt | Glasow Damm Ost | 2023 | 2023 | 15 | 16 | 2023-04-14 | 22:00 | 2023-04-17 | 4:00 | 2d, 6h | Continuous | Switch | T | [10 empty] | 80 | N | 19A4-001 |  | 2022-03-21
DB Netz AG | 1918-001 | Magdeburg - Falkenberg | < | Neuburxdorf | Fak unt Bf W 26 | 2023 | 2023 | 12 | 13 | 2023-03-26 | 22:00 | 2023-03-27 | 6:00 | 0d, 8h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 1918-001 |  | 2022-01-28
DB Netz AG | 1918-002 | Magdeburg - Falkenberg | < | Röderau | Neuburxdorf | 2023 | 2023 | 12 | 12 | 2023-03-25 | 22:00 | 2023-03-26 | 6:00 | 0d, 7h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 1918-002 |  | 2022-01-28
DB Netz AG | 19A4-003 | Berlin - Dresden | <> | Glasow Damm West | Glasow Damm Süd | 2023 | 2023 | 15 | 16 | 2023-04-14 | 22:00 | 2023-04-17 | 4:00 | 2d, 6h | Continuous | Switch | T | [10 empty] | 80 | N | 19A4-003 |  | 2021-11-29
DB Netz AG | 19A4-004 | Berlin - Dresden | <> | Gensh Heide Ost | Birkengrund Süd | 2023 | 2023 | 15 | 16 | 2023-04-14 | 22:00 | 2023-04-17 | 4:00 | 2d, 6h | Continuous | Switch | T | [10 empty] | 80 | N | 19A4-004 |  | 2021-11-29
DB Netz AG | 19D6-001 | Rostock - Berlin | <> | Kavelstorf | Laage (Meckl) | 2023 | 2023 | 19 | 19 | 2023-05-08 | 22:00 | 2023-05-10 | 6:00 | 1d, 8h | Periodical | Catenary | T | [10 empty] | 80 | N | 19D6-001 |  | 2021-10-27
DB Netz AG | 1A10-001 | Bremerhaven - Bremen | < | Neustadt a Rbg | Wunstorf | 2023 | 2023 | 13 | 14 | 2023-04-02 | 21:40 | 2023-04-03 | 5:15 | 0d, 7h | Continuous | Catenary |  | LT | [9 empty] | 80 | N | 1A10-001 |  | 2022-07-15
DB Netz AG | 1A10-002 | Bremerhaven - Bremen | <> | Poggenhagen | Poggenhagen | 2023 | 2023 | 13 | 14 | 2023-04-02 | 21:40 | 2023-04-03 | 5:15 | 0d, 7h | Continuous | Catenary |  |  |  | P | [7 empty] | 80 | N | 1A10-002 |  | 2022-07-15
DB Netz AG | 1A10-003 | Bremerhaven - Bremen | <> | Wunstorf | Neustadt a Rbg | 2023 | 2023 | 14 | 14 | 2023-04-03 | 1:35 | 2023-04-03 | 4:25 | 0d, 2h | Continuous | Catenary | T | [10 empty] | 80 | N | 1A10-003 |  | 2022-07-15
DB Netz AG | 1A22-001 | Bremerhaven - Bremen | < | Hagen (Han) | Neustadt a Rbg | 2023 | 2023 | 14 | 14 | 2023-04-03 | 21:35 | 2023-04-04 | 5:20 | 0d, 7h | Continuous | Catenary |  | LT | [9 empty] | 80 | N | 1A22-001 |  | 2022-07-15
DB Netz AG | 1A22-002 | Bremerhaven - Bremen | <> | Neustadt a Rbg | Hagen (Han) | 2023 | 2023 | 14 | 14 | 2023-04-03 | 21:35 | 2023-04-04 | 5:20 | 0d, 7h | Continuous | Catenary |  |  |  | P | [7 empty] | 80 | N | 1A22-002 |  | 2022-07-15
DB Netz AG | 1A28-001 | Bremerhaven - Bremen | < | Hagen (Han) | Neustadt a Rbg | 2023 | 2023 | 14 | 14 | 2023-04-04 | 21:35 | 2023-04-05 | 5:20 | 0d, 7h | Continuous | Catenary |  | LT | [9 empty] | 80 | N | 1A28-001 |  | 2022-07-15
DB Netz AG | 1A28-002 | Bremerhaven - Bremen | <> | Neustadt a Rbg | Hagen (Han) | 2023 | 2023 | 14 | 14 | 2023-04-04 | 21:35 | 2023-04-05 | 5:20 | 0d, 7h | Continuous | Catenary |  |  |  | P | [7 empty] | 80 | N | 1A28-002 |  | 2022-07-15
DB Netz AG | 1A2E-001 | Rostock - Berlin | > | Langhagen | Plaaz Abzw | 2023 | 2023 | 19 | 19 | 2023-05-09 | 21:30 | 2023-05-11 | 5:00 | 1d, 7h | Periodical | Track & Rail |  | LT | [9 empty] | 80 | N | 1A2E-001 |  | 2021-05-21
DB Netz AG | 1A2E-002 | Rostock - Berlin | < | Langhagen | Lalendorf Ost | 2023 | 2023 | 19 | 19 | 2023-05-09 | 21:30 | 2023-05-11 | 5:00 | 1d, 7h | Periodical | Track & Rail |  |  |  | P | [7 empty] | 80 | N | 1A2E-002 |  | 2021-05-21
DB Netz AG | 1A2E-003 | Rostock - Berlin | > | Langhagen | Langhagen | 2023 | 2023 | 19 | 19 | 2023-05-09 | 21:30 | 2023-05-10 | 1:30 | 0d, 4h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1A2E-003 |  | 2021-05-21
DB Netz AG | 1A2E-005 | Rostock - Berlin | > | Vollrathsruhe | Langhagen | 2023 | 2023 | 19 | 19 | 2023-05-09 | 21:30 | 2023-05-10 | 1:30 | 0d, 4h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1A2E-005 |  | 2021-05-21
DB Netz AG | 1A2E-006 | Rostock - Berlin | > | Vollrathsruhe | Vollrathsruhe | 2023 | 2023 | 19 | 19 | 2023-05-09 | 21:30 | 2023-05-10 | 1:30 | 0d, 4h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1A2E-006 |  | 2021-05-21
DB Netz AG | 1A45-001 | Bremerhaven - Bremen | < | Hagen (Han) | Neustadt a Rbg | 2023 | 2023 | 14 | 14 | 2023-04-05 | 21:35 | 2023-04-06 | 5:20 | 0d, 7h | Continuous | Catenary |  | LT | [9 empty] | 80 | N | 1A45-001 |  | 2022-07-19
DB Netz AG | 1A45-002 | Bremerhaven - Bremen | <> | Neustadt a Rbg | Hagen (Han) | 2023 | 2023 | 14 | 14 | 2023-04-05 | 21:35 | 2023-04-06 | 5:20 | 0d, 7h | Continuous | Catenary |  |  |  | P | [7 empty] | 80 | N | 1A45-002 |  | 2022-07-19
DB Netz AG | 1A2E-007 | Rostock - Berlin | <> | Langhagen | Langhagen | 2023 | 2023 | 19 | 19 | 2023-05-09 | 21:30 | 2023-05-10 | 1:30 | 0d, 4h | Continuous | Track & Rail |  |  |  | P | [7 empty] | 80 | N | 1A2E-007 |  | 2021-05-21
DB Netz AG | 1A4C-001 | Bremerhaven - Bremen | < | Linsburg | Neustadt a Rbg | 2023 | 2023 | 14 | 14 | 2023-04-06 | 22:25 | 2023-04-07 | 6:05 | 0d, 7h | Continuous | Catenary |  | LT | [9 empty] | 80 | N | 1A4C-001 |  | 2022-07-15
DB Netz AG | 1A4C-002 | Bremerhaven - Bremen | <> | Neustadt a Rbg | Hagen (Han) | 2023 | 2023 | 14 | 14 | 2023-04-06 | 22:25 | 2023-04-07 | 6:05 | 0d, 7h | Continuous | Catenary |  |  |  | P | [7 empty] | 80 | N | 1A4C-002 |  | 2022-07-15
DB Netz AG | 1981-001 | Magdeburg - Falkenberg | > | Güterglück | Dessau Hbf | 2023 | 2023 | 13 | 14 | 2023-03-27 | 8:00 | 2023-04-03 | 8:00 | 7d, 0h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1981-001 |  | 2022-03-01
DB Netz AG | 1981-004 | Magdeburg - Falkenberg | > | Rodleben | Roßlau (Elbe) | 2023 | 2023 | 13 | 14 | 2023-03-27 | 8:00 | 2023-04-03 | 8:00 | 7d, 0h | Continuous | Track & Rail |  |  | S | [8 empty] | 80 | N | 1981-004 |  | 2021-05-20
DB Netz AG | 1981-005 | Magdeburg - Falkenberg | > | Rodleben | Roßlau (Elbe) | 2023 | 2023 | 13 | 14 | 2023-03-27 | 8:00 | 2023-04-03 | 8:00 | 7d, 0h | Continuous | Track & Rail |  |  |  | P | [7 empty] | 80 | N | 1981-005 |  | 2021-05-20
DB Netz AG | 1981-006 | Magdeburg - Falkenberg | > | Güterglück | Dessau Hbf | 2023 | 2023 | 13 | 14 | 2023-04-01 | 8:00 | 2023-04-03 | 8:00 | 2d, 0h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1981-006 |  | 2021-05-20
DB Netz AG | 1981-007 | Magdeburg - Falkenberg | <> | Roßlau (Elbe) | Roßlau (Elbe) | 2023 | 2023 | 13 | 13 | 2023-04-02 | 1:00 | 2023-04-02 | 4:00 | 0d, 3h | Continuous | Track & Rail | T | [10 empty] | 80 | N | 1981-007 |  | 2021-05-20
DB Netz AG | 1A72-001 | Rostock - Berlin | <> | Laage (Meckl) | Lalendorf Ost | 2023 | 2023 | 18 | 18 | 2023-05-04 | 23:00 | 2023-05-05 | 4:00 | 0d, 5h | Continuous | Switch | T | [10 empty] | 80 | N | 1A72-001 |  | 2021-05-21
DB Netz AG | 1A72-002 | Rostock - Berlin | <> | Priemerbg-NUP Gü | Plaaz Abzw | 2023 | 2023 | 18 | 18 | 2023-05-04 | 23:00 | 2023-05-05 | 4:00 | 0d, 5h | Continuous | Switch | T | [10 empty] | 80 | N | 1A72-002 |  | 2021-05-21
DB Netz AG | 1A72-004 | Rostock - Berlin | <> | Laage (Meckl) | Lalendorf Ost | 2023 | 2023 | 18 | 18 | 2023-05-06 | 22:40 | 2023-05-07 | 6:20 | 0d, 7h | Continuous | Switch | T | [10 empty] | 80 | N | 1A72-004 |  | 2021-05-21
DB Netz AG | 1A72-005 | Rostock - Berlin | <> | Priemerbg-NUP Gü | Plaaz Abzw | 2023 | 2023 | 18 | 18 | 2023-05-06 | 22:40 | 2023-05-07 | 6:20 | 0d, 7h | Continuous | Switch | T | [10 empty] | 80 | N | 1A72-005 |  | 2021-05-21
DB Netz AG | 1A72-007 | Rostock - Berlin | > | Lalendorf Ost | Laage (Meckl) | 2023 | 2023 | 18 | 18 | 2023-05-06 | 21:50 | 2023-05-06 | 22:40 | 0d, 0h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 1A72-007 |  | 2021-05-21
DB Netz AG | 19D6-010 | Rostock - Berlin | <> | Kavelstorf | Ro Seehf Süd | 2023 | 2023 | 19 | 19 | 2023-05-08 | 22:00 | 2023-05-10 | 6:00 | 1d, 8h | Periodical | Catenary | T | [10 empty] | 80 | N | 19D6-010 |  | 2021-10-27
DB Netz AG | 19D6-011 | Rostock - Berlin | <> | Kavelstorf | Dalwitzhof | 2023 | 2023 | 19 | 19 | 2023-05-08 | 22:00 | 2023-05-10 | 6:00 | 1d, 8h | Periodical | Catenary | T | [10 empty] | 80 | N | 19D6-011 |  | 2021-10-27
DB Netz AG | 1AC5-001 | Bremen - Hannover | > | Seelze West | Ahlem | 2023 | 2023 | 16 | 17 | 2023-04-17 | 6:00 | 2023-04-24 | 14:00 | 7d, 8h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | 1AC5-001 |  | 2021-05-03
DB Netz AG | 1AC5-002 | Bremen - Hannover | > | Seelze West | Ahlem | 2023 | 2023 | 14 | 14 | 2023-04-03 | 1:15 | 2023-04-03 | 9:15 | 0d, 8h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | 1AC5-002 |  | 2021-05-03
DB Netz AG | 1AC5-004 | Bremen - Hannover | < | Seelze Ost | Letter Abzw | 2023 | 2023 | 19 | 19 | 2023-05-09 | 23:00 | 2023-05-11 | 5:00 | 1d, 6h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | 1AC5-004 |  | 2021-05-03
DB Netz AG | 1AC5-005 | Bremen - Hannover | <> | Seelze Ost | Seelze Ost | 2023 | 2023 | 19 | 19 | 2023-05-09 | 23:00 | 2023-05-11 | 5:00 | 1d, 6h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1AC5-005 |  | 2021-05-03
DB Netz AG | 1B05-001 | Berlin - Dresden | <> | Glasow Damm Ost | Grün Kreuz Süd | 2023 | 2023 | 17 | 17 | 2023-04-25 | 22:00 | 2023-04-28 | 4:00 | 2d, 6h | Continuous | Track & Rail | T | [10 empty] | 80 | N | 1B05-001 |  | 2022-03-22
DB Netz AG | 1B05-002 | Berlin - Dresden | <> | Grün Kreuz West | Grün Kreuz Süd | 2023 | 2023 | 17 | 17 | 2023-04-25 | 22:00 | 2023-04-28 | 4:00 | 2d, 6h | Continuous | Track & Rail | T | [10 empty] | 80 | N | 1B05-002 |  | 2022-03-18
DB Netz AG | 1B05-003 | Berlin - Dresden | <> | Bln-Grünau | Grün Kreuz Süd | 2023 | 2023 | 17 | 17 | 2023-04-25 | 22:00 | 2023-04-28 | 4:00 | 2d, 6h | Continuous | Track & Rail | T | [10 empty] | 80 | N | 1B05-003 |  | 2022-03-18
DB Netz AG | 1AC5-012 | Bremen - Hannover | > | Seelze West | Ahlem | 2023 | 2023 | 15 | 15 | 2023-04-11 | 6:00 | 2023-04-11 | 14:00 | 0d, 8h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 1AC5-012 |  | 2021-05-03
DB Netz AG | 1B21-001 | Hamburg - Magdeburg | <> | Uelzen Gbf | Uelzen Gbf | 2023 | 2023 | 15 | 15 | 2023-04-11 | 23:00 | 2023-04-16 | 5:00 | 4d, 6h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1B21-001 |  | 2022-05-03
DB Netz AG | 1B21-002 | Hamburg - Magdeburg | <> | Uelzen | Uelzen Gbf | 2023 | 2023 | 15 | 15 | 2023-04-11 | 23:00 | 2023-04-16 | 5:00 | 4d, 6h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1B21-002 |  | 2022-05-03
DB Netz AG | 1981-010 | Magdeburg - Falkenberg | <> | Roßlau(Elbe) Gbf | Roßlau(Elbe) Gbf | 2023 | 2023 | 12 | 14 | 2023-03-24 | 8:00 | 2023-04-04 | 8:00 | 10d, 23h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1981-010 |  | 2021-05-20
DB Netz AG | 1B21-003 | Hamburg - Magdeburg | <> | Uelzen Gbf | Uelzen | 2023 | 2023 | 15 | 17 | 2023-04-16 | 23:00 | 2023-04-24 | 5:00 | 7d, 6h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1B21-003 |  | 2022-05-03
DB Netz AG | 1B21-004 | Hamburg - Magdeburg | <> | Uelzen Gbf | Uelzen Gbf | 2023 | 2023 | 15 | 17 | 2023-04-16 | 23:00 | 2023-04-24 | 5:00 | 7d, 6h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1B21-004 |  | 2022-05-03
DB Netz AG | 1B21-005 | Hamburg - Magdeburg | <> | Uelzen Gbf | Uelzen Gbf | 2023 | 2023 | 15 | 17 | 2023-04-16 | 23:00 | 2023-04-24 | 5:00 | 7d, 6h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 1B21-005 |  | 2022-05-03
DB Netz AG | 1B21-006 | Hamburg - Magdeburg | <> | Uelzen Gbf | Uelzen | 2023 | 2023 | 17 | 18 | 2023-04-24 | 23:00 | 2023-05-02 | 5:00 | 7d, 6h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1B21-006 |  | 2022-05-03
DB Netz AG | 1B21-007 | Hamburg - Magdeburg | <> | Uelzen Gbf | Uelzen Gbf | 2023 | 2023 | 17 | 18 | 2023-04-24 | 23:00 | 2023-05-02 | 5:00 | 7d, 6h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1B21-007 |  | 2022-05-03
DB Netz AG | 1B21-008 | Hamburg - Magdeburg | <> | Uelzen Gbf | Uelzen Gbf | 2023 | 2023 | 17 | 18 | 2023-04-24 | 23:00 | 2023-05-02 | 5:00 | 7d, 6h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 1B21-008 |  | 2022-05-03
DB Netz AG | 1B39-004 | Hamburg - Magdeburg | <> | Uelzen Gbf | Uelzen | 2023 | 2023 | 19 | 19 | 2023-05-08 | 23:00 | 2023-05-12 | 5:00 | 3d, 6h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1B39-004 |  | 2022-05-03
DB Netz AG | 1BC7-001 | Rostock - Berlin | > | Lalendorf Ost | Laage (Meckl) | 2023 | 2023 | 17 | 17 | 2023-04-28 | 22:30 | 2023-04-30 | 6:00 | 1d, 7h | Periodical | Track & Rail |  | LT | [9 empty] | 80 | N | 1BC7-001 |  | 2021-09-21
DB Netz AG | 1BC7-003 | Rostock - Berlin | <> | Lalendorf Ost | Kavelstorf | 2023 | 2023 | 17 | 17 | 2023-04-28 | 22:30 | 2023-04-30 | 6:00 | 1d, 7h | Periodical | Track & Rail |  |  |  | P | [7 empty] | 80 | N | 1BC7-003 |  | 2021-09-21
DB Netz AG | 1BD3-001 | Rostock - Berlin | <> | Lalendorf Ost | Kavelstorf | 2023 | 2023 | 18 | 18 | 2023-05-01 | 22:15 | 2023-05-04 | 6:00 | 2d, 7h | Periodical | Track & Rail |  |  |  | P | [7 empty] | 80 | N | 1BD3-001 |  | 2022-02-04
DB Netz AG | 1BC7-005 | Rostock - Berlin | > | Laage (Meckl) | Kavelstorf | 2023 | 2023 | 17 | 17 | 2023-04-30 | 3:00 | 2023-04-30 | 6:00 | 0d, 3h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1BC7-005 |  | 2021-09-21
DB Netz AG | 1BC7-006 | Rostock - Berlin | <> | Laage (Meckl) | Laage (Meckl) | 2023 | 2023 | 17 | 17 | 2023-04-30 | 3:00 | 2023-04-30 | 6:00 | 0d, 3h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1BC7-006 |  | 2021-09-21
DB Netz AG | 1BD3-002 | Rostock - Berlin | > | Lalendorf Ost | Laage (Meckl) | 2023 | 2023 | 18 | 18 | 2023-05-01 | 22:15 | 2023-05-04 | 6:00 | 2d, 7h | Periodical | Track & Rail |  | LT | [9 empty] | 80 | N | 1BD3-002 |  | 2022-02-04
DB Netz AG | 1BD3-004 | Rostock - Berlin | > | Laage (Meckl) | Kavelstorf | 2023 | 2023 | 18 | 18 | 2023-05-01 | 22:15 | 2023-05-02 | 2:45 | 0d, 4h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1BD3-004 |  | 2022-02-04
DB Netz AG | 1BD3-005 | Rostock - Berlin | <> | Laage (Meckl) | Laage (Meckl) | 2023 | 2023 | 18 | 18 | 2023-05-01 | 22:15 | 2023-05-02 | 2:45 | 0d, 4h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1BD3-005 |  | 2022-02-04
DB Netz AG | 1BD7-001 | Bremen - Hannover | > | Hannover-Linden | Misburg | 2022 | 2022 | 49 | 50 | 2022-12-11 | 22:50 | 2022-12-12 | 5:50 | 0d, 7h | Continuous | Catenary |  | LT | [9 empty] | 80 | N | 1BD7-001 |  | 2022-04-27
DB Netz AG | 1BD7-007 | Bremen - Hannover | > | Hannover-Linden | Misburg | 2022 | 2022 | 51 | 51 | 2022-12-19 | 22:20 | 2022-12-20 | 5:05 | 0d, 6h | Continuous | Catenary |  | LT | [9 empty] | 80 | N | 1BD7-007 |  | 2022-04-27
DB Netz AG | 1BD7-010 | Bremen - Hannover | > | Hannover-Linden | Misburg | 2022 | 2022 | 50 | 51 | 2022-12-18 | 23:45 | 2022-12-19 | 6:45 | 0d, 7h | Continuous | Catenary |  | LT | [9 empty] | 80 | N | 1BD7-010 |  | 2022-04-27
DB Netz AG | 1980-001 | Magdeburg - Falkenberg | <> | Neuburxdorf | Röderau | 2023 | 2023 | 14 | 14 | 2023-04-07 | 9:00 | 2023-04-07 | 19:00 | 0d, 10h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | 1980-001 |  | 2021-09-29
DB Netz AG | 1C93-001 | Berlin - Dresden | > | Doberlug-K ob Bf | Doberlug-K ob Bf | 2023 | 2023 | 18 | 18 | 2023-05-05 | 9:00 | 2023-05-05 | 12:00 | 0d, 3h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 1C93-001 |  | 2022-07-19
DB Netz AG | 1C93-002 | Berlin - Dresden | <> | Doberlug-K ob Bf | Doberlug-K untBf | 2023 | 2023 | 18 | 18 | 2023-05-05 | 9:00 | 2023-05-05 | 12:00 | 0d, 3h | Continuous | Signal | T | [10 empty] | 80 | N | 1C93-002 |  | 2022-07-19
DB Netz AG | 1C93-003 | Berlin - Dresden | <> | Doberlug-Kh Nord | Rückersdorf NL | 2023 | 2023 | 18 | 18 | 2023-05-05 | 11:00 | 2023-05-05 | 12:00 | 0d, 1h | Continuous | Signal | T | [10 empty] | 80 | N | 1C93-003 |  | 2022-07-19
DB Netz AG | 1C93-004 | Berlin - Dresden | <> | Doberlug-K ob Bf | Doberlug-K untBf | 2023 | 2023 | 18 | 18 | 2023-05-05 | 11:00 | 2023-05-05 | 12:00 | 0d, 1h | Continuous | Signal | T | [10 empty] | 80 | N | 1C93-004 |  | 2022-07-19
DB Netz AG | 1DBD-001 | Bremen - Hannover | <> | Verden (Aller) | Walle/Verden | 2023 | 2023 | 11 | 11 | 2023-03-13 | 8:00 | 2023-03-14 | 14:00 | 1d, 6h | Periodical | Catenary | T | [10 empty] | 80 | N | 1DBD-001 |  | 2022-06-01
DB Netz AG | 1DBD-002 | Bremen - Hannover | <> | Verden (Aller) | Walle/Verden | 2023 | 2023 | 11 | 11 | 2023-03-13 | 8:00 | 2023-03-14 | 14:00 | 1d, 6h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 1DBD-002 |  | 2022-06-01
DB Netz AG | 1DC0-001 | Bremen - Hannover | > | Hagen (Han) | Linsburg | 2023 | 2023 | 19 | 19 | 2023-05-08 | 23:10 | 2023-05-10 | 5:10 | 1d, 6h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 1DC0-001
DB Netz AG | 1DCC-001 | Bremen - Hannover | > | Linsburg | Rohrsen/Nienburg | 2023 | 2023 | 11 | 11 | 2023-03-13 | 0:30 | 2023-03-13 | 6:30 | 0d, 6h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 1DCC-001 |  | 2022-03-31
DB Netz AG | 1DDA-001 | Bremerhaven - Bremen | < | Brh-Speckenbütt | Brh-L Abstellbf | 2023 | 2023 | 14 | 14 | 2023-04-03 | 8:00 | 2023-04-03 | 15:00 | 0d, 7h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 1DDA-001 |  | 2022-07-20
DB Netz AG | 1DDC-001 | Bremen - Hannover | < | Wahnebergen | Verden (Aller) | 2023 | 2023 | 11 | 11 | 2023-03-13 | 22:30 | 2023-03-14 | 5:00 | 0d, 6h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 1DDC-001 |  | 2022-06-01
DB Netz AG | 1DDE-001 | Bremen - Hannover | < | Verden (Aller) | Dörverden | 2023 | 2023 | 11 | 11 | 2023-03-14 | 22:30 | 2023-03-15 | 5:00 | 0d, 6h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 1DDE-001 |  | 2022-06-01
DB Netz AG | 1DDF-001 | Bremen - Hannover | > | Baden /Kr Verden | Bremen-Mahndorf | 2023 | 2023 | 18 | 19 | 2023-05-07 | 23:00 | 2023-05-08 | 5:00 | 0d, 6h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 1DDF-001 |  | 2022-07-21
DB Netz AG | 1DE1-001 | Bremen - Hannover | < | Eystrup | Wahnebergen | 2023 | 2023 | 10 | 10 | 2023-03-11 | 22:30 | 2023-03-12 | 5:00 | 0d, 6h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 1DE1-001 |  | 2022-06-01
DB Netz AG | 1DE1-002 | Bremen - Hannover | <> | Eystrup | Wahnebergen | 2023 | 2023 | 10 | 10 | 2023-03-12 | 0:00 | 2023-03-12 | 4:00 | 0d, 4h | Periodical | Catenary | T | [10 empty] | 80 | N | 1DE1-002 |  | 2022-06-01
DB Netz AG | 1E1E-001 | Hannover - Magdeburg | <> | Braunschweig Hbf | Lünischteich | 2023 | 2023 | 10 | 11 | 2023-03-10 | 22:10 | 2023-03-18 | 23:45 | 8d, 1h | Continuous | Track & Rail | T | [10 empty] | 80 | N | 1E1E-001 |  | 2021-05-21
DB Netz AG | 1E1E-002 | Hannover - Magdeburg | <> | Braunschweig Hbf | Braunschweig Hbf | 2023 | 2023 | 10 | 10 | 2023-03-10 | 22:10 | 2023-03-11 | 0:10 | 0d, 2h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1E1E-002 |  | 2021-05-21
DB Netz AG | 1E1E-003 | Hannover - Magdeburg | <> | Braunschweig Hbf | Braunschweig Hbf | 2023 | 2023 | 10 | 10 | 2023-03-10 | 22:10 | 2023-03-11 | 0:10 | 0d, 2h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1E1E-003 |  | 2021-05-21
DB Netz AG | 1E1E-004 | Hannover - Magdeburg | <> | Braunschweig Hbf | Braunschweig Hbf | 2023 | 2023 | 11 | 11 | 2023-03-18 | 21:45 | 2023-03-18 | 23:45 | 0d, 2h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1E1E-004 |  | 2021-05-21
DB Netz AG | 1E1E-005 | Hannover - Magdeburg | <> | Braunschweig Hbf | Braunschweig Hbf | 2023 | 2023 | 11 | 11 | 2023-03-18 | 21:45 | 2023-03-18 | 23:45 | 0d, 2h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1E1E-005 |  | 2021-05-21
DB Netz AG | 1E1E-006 | Hannover - Magdeburg | <> | Braunschweig Hbf | Braunschweig Hbf | 2023 | 2023 | 10 | 11 | 2023-03-12 | 0:20 | 2023-03-18 | 5:10 | 6d, 4h | Periodical | Track & Rail |  | ST | [9 empty] | 80 | N | 1E1E-006 |  | 2021-05-21
DB Netz AG | 1E1E-007 | Hannover - Magdeburg | <> | Braunschweig Hbf | Braunschweig Hbf | 2023 | 2023 | 10 | 11 | 2023-03-12 | 0:20 | 2023-03-18 | 5:10 | 6d, 4h | Periodical | Track & Rail |  | ST | [9 empty] | 80 | N | 1E1E-007 |  | 2021-05-21
DB Netz AG | 1E1E-009 | Hannover - Magdeburg | <> | Schmiedekamp | Lünischteich | 2023 | 2023 | 10 | 11 | 2023-03-12 | 23:55 | 2023-03-18 | 4:55 | 5d, 5h | Periodical | Track & Rail | T | [10 empty] | 80 | N | 1E1E-009 |  | 2021-05-21
DB Netz AG | 1EB8-001 | Hamburg - Magdeburg | > | Hmb-Wlb Abzw | Hmb-Roth Ro | 2023 | 2023 | 13 | 14 | 2023-04-02 | 23:00 | 2023-04-03 | 2:00 | 0d, 3h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1EB8-001 |  | 2022-07-22
DB Netz AG | 1EF3-001 | Berlin - Dresden | < | Schoenef.T5(F-B) | Glasow Damm Ost | 2023 | 2023 | 15 | 15 | 2023-04-10 | 21:00 | 2023-04-11 | 1:00 | 0d, 4h | Periodical | Switch |  | LT | [9 empty] | 80 | N | 1EF3-001 |  | 2021-10-08
DB Netz AG | 1EF3-002 | Berlin - Dresden | > | Schoenef.T5(F-B) | Schoenef.T5(F-B) | 2023 | 2023 | 15 | 15 | 2023-04-10 | 21:00 | 2023-04-11 | 1:00 | 0d, 4h | Periodical | Switch |  | ST | [9 empty] | 80 | N | 1EF3-002 |  | 2021-10-08
DB Netz AG | 1EF3-003 | Berlin - Dresden | <> | Schoenef.T5(F-B) | Glasow Damm Ost | 2023 | 2023 | 15 | 15 | 2023-04-11 | 0:30 | 2023-04-11 | 5:00 | 0d, 4h | Periodical | Switch | T | [10 empty] | 80 | N | 1EF3-003 |  | 2021-10-08
DB Netz AG | 1EF3-004 | Berlin - Dresden | <> | Schoenef.T5(F-B) | Schoenef.T5(F-B) | 2023 | 2023 | 15 | 15 | 2023-04-11 | 0:30 | 2023-04-11 | 5:00 | 0d, 4h | Periodical | Switch |  | ST | [9 empty] | 80 | N | 1EF3-004 |  | 2021-10-08
DB Netz AG | 1EF3-005 | Berlin - Dresden | < | Schoenef.T5(F-B) | Glasow Damm Ost | 2023 | 2023 | 15 | 15 | 2023-04-11 | 20:00 | 2023-04-12 | 1:00 | 0d, 5h | Periodical | Switch |  | LT | [9 empty] | 80 | N | 1EF3-005 |  | 2021-10-08
DB Netz AG | 1EF3-006 | Berlin - Dresden | < | Schoenef.T5(F-B) | Schoenef.T5(F-B) | 2023 | 2023 | 15 | 15 | 2023-04-11 | 20:00 | 2023-04-12 | 1:00 | 0d, 5h | Periodical | Switch |  | ST | [9 empty] | 80 | N | 1EF3-006 |  | 2021-10-08
DB Netz AG | 1EF3-007 | Berlin - Dresden | <> | Schoenef.T5(F-B) | Glasow Damm Ost | 2023 | 2023 | 15 | 15 | 2023-04-12 | 0:30 | 2023-04-12 | 5:00 | 0d, 4h | Periodical | Switch | T | [10 empty] | 80 | N | 1EF3-007 |  | 2021-10-08
DB Netz AG | 1EF3-008 | Berlin - Dresden | < | Schoenef.T5(F-B) | Schoenef.T5(F-B) | 2023 | 2023 | 15 | 15 | 2023-04-12 | 0:30 | 2023-04-12 | 5:00 | 0d, 4h | Periodical | Switch |  | ST | [9 empty] | 80 | N | 1EF3-008 |  | 2021-10-08
DB Netz AG | 1EF9-001 | Berlin - Dresden | < | Schoenef.T5(F-B) | Glasow Damm Ost | 2023 | 2023 | 15 | 15 | 2023-04-12 | 21:00 | 2023-04-13 | 1:00 | 0d, 4h | Periodical | Switch |  | LT | [9 empty] | 80 | N | 1EF9-001 |  | 2021-04-12
DB Netz AG | 1EF9-002 | Berlin - Dresden | < | Schoenef.T5(F-B) | Schoenef.T5(F-B) | 2023 | 2023 | 15 | 15 | 2023-04-12 | 21:00 | 2023-04-13 | 1:00 | 0d, 4h | Periodical | Switch |  | ST | [9 empty] | 80 | N | 1EF9-002 |  | 2021-04-12
DB Netz AG | 1EF9-003 | Berlin - Dresden | < | Grün Kreuz Süd | Schoenef.T5(F-B) | 2023 | 2023 | 15 | 15 | 2023-04-13 | 0:30 | 2023-04-13 | 5:00 | 0d, 4h | Periodical | Switch |  | LT | [9 empty] | 80 | N | 1EF9-003 |  | 2021-04-12
DB Netz AG | 1EF9-004 | Berlin - Dresden | < | Schoenef.T5(F-B) | Schoenef.T5(F-B) | 2023 | 2023 | 15 | 15 | 2023-04-13 | 0:30 | 2023-04-13 | 5:00 | 0d, 4h | Periodical | Switch |  | ST | [9 empty] | 80 | N | 1EF9-004 |  | 2021-04-12
DB Netz AG | 1EF9-005 | Berlin - Dresden | > | Glasow Damm Ost | Schoenef.T5(F-B) | 2023 | 2023 | 15 | 15 | 2023-04-13 | 21:00 | 2023-04-14 | 1:00 | 0d, 4h | Periodical | Switch |  | LT | [9 empty] | 80 | N | 1EF9-005 |  | 2021-04-12
DB Netz AG | 1EF9-006 | Berlin - Dresden | > | Schoenef.T5(F-B) | Schoenef.T5(F-B) | 2023 | 2023 | 15 | 15 | 2023-04-13 | 21:00 | 2023-04-14 | 1:00 | 0d, 4h | Periodical | Switch |  | ST | [9 empty] | 80 | N | 1EF9-006 |  | 2021-04-12
DB Netz AG | 1EF9-007 | Berlin - Dresden | > | Schoenef.T5(F-B) | Grün Kreuz Süd | 2023 | 2023 | 15 | 15 | 2023-04-14 | 0:30 | 2023-04-14 | 5:00 | 0d, 4h | Periodical | Switch |  | LT | [9 empty] | 80 | N | 1EF9-007 |  | 2021-04-12
DB Netz AG | 1EF9-008 | Berlin - Dresden | > | Schoenef.T5(F-B) | Schoenef.T5(F-B) | 2023 | 2023 | 15 | 15 | 2023-04-14 | 0:30 | 2023-04-14 | 5:00 | 0d, 4h | Periodical | Switch |  | ST | [9 empty] | 80 | N | 1EF9-008 |  | 2021-04-12
DB Netz AG | 1F1E-001 | Hamburg - Magdeburg | <> | Hohenwulsch | Hohenwulsch | 2023 | 2023 | 9 | 9 | 2023-03-04 | 22:20 | 2023-03-05 | 6:30 | 0d, 8h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1F1E-001 |  | 2022-05-09
DB Netz AG | 1F1E-002 | Hamburg - Magdeburg | > | Hohenwulsch | Brunau-Packeb | 2023 | 2023 | 9 | 9 | 2023-03-04 | 22:30 | 2023-03-05 | 6:30 | 0d, 8h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1F1E-002 |  | 2022-05-09
DB Netz AG | 1F1E-003 | Hamburg - Magdeburg | > | Hohenwulsch | Brunau-Packeb | 2023 | 2023 | 9 | 9 | 2023-03-04 | 22:30 | 2023-03-05 | 6:30 | 0d, 8h | Continuous | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | 1F1E-003 |  | 2022-05-09
DB Netz AG | 1F1E-004 | Hamburg - Magdeburg | <> | Brunau-Packeb | Hohenwulsch | 2023 | 2023 | 9 | 9 | 2023-03-04 | 22:30 | 2023-03-05 | 6:30 | 0d, 8h | Continuous | Track & Rail |  |  |  | P | [7 empty] | 80 | N | 1F1E-004 |  | 2022-05-09
DB Netz AG | 1F32-002 | Bremerhaven - Bremen | < | Verden (Aller) | Wahnebergen | 2023 | 2023 | 17 | 17 | 2023-04-26 | 23:00 | 2023-04-28 | 5:00 | 1d, 6h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 1F32-002 |  | 2022-07-20
DB Netz AG | 1F9B-001 | Hamburg - Magdeburg | < | Veddel | Hmb-Wlb Abzw | 2022 | 2022 | 49 | 52 | 2022-12-11 | 0:00 | 2022-12-31 | 23:59 | 363d, 23h | Continuous | Signal |  |  | S | [8 empty] | 80 | N | 1F9B-001 |  | 2022-04-24
DB Netz AG | 1F9B-001 | Hamburg - Magdeburg | < | Veddel | Hmb-Wlb Abzw | 2023 | 2023 | 1 | 49 | 2023-01-01 | 0:00 | 2023-12-09 | 23:59 | 363d, 23h | Continuous | Signal |  |  | S | [8 empty] | 80 | N | 1F9B-001 |  | 2022-04-24
DB Netz AG | 1F9B-002 | Hamburg - Magdeburg | > | Hmb-Wlb Abzw | Veddel | 2022 | 2022 | 49 | 52 | 2022-12-11 | 0:00 | 2022-12-31 | 23:59 | 363d, 23h | Continuous | Signal |  |  | S | [8 empty] | 80 | N | 1F9B-002 |  | 2022-04-24
DB Netz AG | 1F9B-002 | Hamburg - Magdeburg | > | Hmb-Wlb Abzw | Veddel | 2023 | 2023 | 1 | 49 | 2023-01-01 | 0:00 | 2023-12-09 | 23:59 | 363d, 23h | Continuous | Signal |  |  | S | [8 empty] | 80 | N | 1F9B-002 |  | 2022-04-24
DB Netz AG | 1F9B-003 | Wilhelmshaven - Bremen | < | Veddel | Hmb-Wlb Abzw | 2022 | 2022 | 49 | 52 | 2022-12-11 | 0:00 | 2022-12-31 | 23:59 | 363d, 23h | Continuous | Signal |  |  | S | [8 empty] | 80 | N | 1F9B-003 |  | 2022-04-24
DB Netz AG | 1F9B-003 | Wilhelmshaven - Bremen | < | Veddel | Hmb-Wlb Abzw | 2023 | 2023 | 1 | 49 | 2023-01-01 | 0:00 | 2023-12-09 | 23:59 | 363d, 23h | Continuous | Signal |  |  | S | [8 empty] | 80 | N | 1F9B-003 |  | 2022-04-24
DB Netz AG | 1F9B-004 | Wilhelmshaven - Bremen | > | Hmb-Wlb Abzw | Veddel | 2022 | 2022 | 49 | 52 | 2022-12-11 | 0:00 | 2022-12-31 | 23:59 | 363d, 23h | Continuous | Signal |  |  | S | [8 empty] | 80 | N | 1F9B-004 |  | 2022-04-24
DB Netz AG | 1F9B-004 | Wilhelmshaven - Bremen | > | Hmb-Wlb Abzw | Veddel | 2023 | 2023 | 1 | 49 | 2023-01-01 | 0:00 | 2023-12-09 | 23:59 | 363d, 23h | Continuous | Signal |  |  | S | [8 empty] | 80 | N | 1F9B-004 |  | 2022-04-24
DB Netz AG | 1FAD-001 | Hamburg - Magdeburg | <> | Zielitz Stw B2 | Zielitz Stw B2 | 2023 | 2023 | 9 | 10 | 2023-03-05 | 18:00 | 2023-03-07 | 18:00 | 2d, 0h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1FAD-001 |  | 2022-05-09
DB Netz AG | 1FAD-002 | Hamburg - Magdeburg | > | Zielitz | Zielitz Stw B2 | 2023 | 2023 | 9 | 9 | 2023-03-05 | 20:35 | 2023-03-05 | 22:35 | 0d, 2h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1FAD-002 |  | 2022-01-10
DB Netz AG | 1FAD-003 | Hamburg - Magdeburg | > | Zielitz | Zielitz Stw B2 | 2023 | 2023 | 9 | 9 | 2023-03-05 | 20:35 | 2023-03-05 | 22:35 | 0d, 2h | Continuous | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | 1FAD-003 |  | 2022-05-09
DB Netz AG | 1FAD-004 | Hamburg - Magdeburg | > | Zielitz | Angern-Rogätz | 2023 | 2023 | 9 | 10 | 2023-03-05 | 22:35 | 2023-03-06 | 4:15 | 0d, 5h | Continuous | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | 1FAD-004 |  | 2021-10-13
DB Netz AG | 1FAD-005 | Hamburg - Magdeburg | > | Zielitz | Angern-Rogätz | 2023 | 2023 | 9 | 10 | 2023-03-05 | 22:35 | 2023-03-06 | 4:15 | 0d, 5h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1FAD-005 |  | 2021-10-13
DB Netz AG | 1FAD-006 | Hamburg - Magdeburg | <> | Angern-Rogätz | Zielitz | 2023 | 2023 | 9 | 10 | 2023-03-05 | 20:35 | 2023-03-07 | 4:15 | 1d, 7h | Periodical | Track & Rail |  |  |  | P | [7 empty] | 80 | N | 1FAD-006 |  | 2022-05-09
DB Netz AG | 1FAD-007 | Hamburg - Magdeburg | > | Zielitz Stw B2 | Angern-Rogätz | 2023 | 2023 | 10 | 10 | 2023-03-06 | 20:35 | 2023-03-07 | 4:15 | 0d, 7h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1FAD-007 |  | 2022-05-09
DB Netz AG | 1FAD-008 | Hamburg - Magdeburg | > | Zielitz Stw B2 | Angern-Rogätz | 2023 | 2023 | 10 | 10 | 2023-03-06 | 20:35 | 2023-03-07 | 4:15 | 0d, 7h | Continuous | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | 1FAD-008 |  | 2022-05-09
DB Netz AG | 2034-001 | Rostock - Berlin | <> | Rostock Seehafen | Rostock Seehafen | 2023 | 2023 | 15 | 49 | 2023-04-14 | 6:59 | 2023-12-09 | 23:59 | 239d, 18h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 2034-001
DB Netz AG | 2034-002 | Rostock - Berlin | <> | Ro Seehf Süd | Ro Seehf Süd | 2023 | 2023 | 15 | 39 | 2023-04-14 | 7:00 | 2023-09-30 | 23:59 | 169d, 16h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 2034-002
DB Netz AG | 2034-003 | Rostock - Berlin | <> | Rostock Seehafen | Rostock Seehafen | 2023 | 2023 | 15 | 39 | 2023-04-14 | 7:00 | 2023-09-30 | 23:59 | 169d, 16h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 2034-003
DB Netz AG | 2034-004 | Rostock - Berlin | <> | Bentwisch | Ro Seehf Süd | 2023 | 2023 | 15 | 17 | 2023-04-14 | 7:00 | 2023-04-24 | 18:00 | 10d, 11h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | 2034-004
DB Netz AG | 2034-005 | Rostock - Berlin | <> | Ro Seehf Süd | Ro Seehf Süd | 2023 | 2023 | 15 | 17 | 2023-04-14 | 7:00 | 2023-04-24 | 18:00 | 10d, 11h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 2034-005
DB Netz AG | 2034-006 | Rostock - Berlin | <> | Ro Seehf Süd | Rostock Seehafen | 2023 | 2023 | 17 | 26 | 2023-04-24 | 18:00 | 2023-06-26 | 6:00 | 62d, 12h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 2034-006
DB Netz AG | 2034-007 | Rostock - Berlin | <> | Ro Seehf Süd | Rostock Seehafen | 2023 | 2023 | 17 | 26 | 2023-04-24 | 18:00 | 2023-06-26 | 6:00 | 62d, 12h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 2034-007
DB Netz AG | 2044-001 | Wilhelmshaven - Bremen | < | Delmenhorst | Bookholzberg | 2023 | 2023 | 16 | 16 | 2023-04-17 | 22:10 | 2023-04-22 | 5:00 | 4d, 6h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 2044-001
DB Netz AG | 2046-001 | Hamburg - Magdeburg | > | Mg-Neustadt | Glindenberg | 2023 | 2023 | 14 | 14 | 2023-04-08 | 21:00 | 2023-04-09 | 5:00 | 0d, 8h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 2046-001 |  | 2021-05-14
DB Netz AG | 2046-002 | Hamburg - Magdeburg | <> | Glindenberg | Mg-Neustadt | 2023 | 2023 | 14 | 14 | 2023-04-08 | 21:00 | 2023-04-09 | 5:00 | 0d, 8h | Continuous | Track & Rail |  |  |  | P | [7 empty] | 80 | N | 2046-002 |  | 2021-05-14
DB Netz AG | 2046-003 | Hamburg - Magdeburg | > | Mg-Neustadt | Wolmirstedt | 2023 | 2023 | 14 | 14 | 2023-04-09 | 3:00 | 2023-04-09 | 5:00 | 0d, 2h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 2046-003 |  | 2021-05-14
DB Netz AG | 2046-004 | Hamburg - Magdeburg | > | Mg-Neustadt | Glindenberg | 2023 | 2023 | 14 | 14 | 2023-04-08 | 21:00 | 2023-04-09 | 5:00 | 0d, 8h | Continuous | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | 2046-004 |  | 2021-05-14
DB Netz AG | 2046-005 | Hamburg - Magdeburg | > | Mg-Rothensee Hp | Glindenberg | 2023 | 2023 | 14 | 14 | 2023-04-09 | 3:00 | 2023-04-09 | 5:00 | 0d, 2h | Continuous | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | 2046-005 |  | 2021-05-14
DB Netz AG | 20.4 | Hamburg - Magdeburg | < | Glindenberg | Mg-Neustadt | 2023 | 2023 | 14 | 15 | 2023-04-09 | 21:00 | 2023-04-10 | 5:00 | 0d, 8h | Continuous | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | 20.4 |  | 2021-05-14
DB Netz AG | 2.04 | Hamburg - Magdeburg | <> | Mg-Neustadt | Glindenberg | 2023 | 2023 | 14 | 15 | 2023-04-09 | 21:00 | 2023-04-10 | 5:00 | 0d, 8h | Continuous | Track & Rail |  |  |  | P | [7 empty] | 80 | N | 2.04 |  | 2021-05-14
DB Netz AG | 0.204 | Hamburg - Magdeburg | < | Glindenberg | Mg-Neustadt | 2023 | 2023 | 14 | 15 | 2023-04-09 | 21:00 | 2023-04-10 | 5:00 | 0d, 8h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 0.204 |  | 2021-05-14
DB Netz AG | 0.0204 | Hamburg - Magdeburg | < | Glindenberg | Mg-Neustadt | 2023 | 2023 | 15 | 15 | 2023-04-10 | 3:00 | 2023-04-10 | 5:00 | 0d, 2h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 0.0204 |  | 2021-05-14
DB Netz AG | 2047-001 | Wilhelmshaven - Bremen | < | Bremen-Neustadt | Delmenhorst | 2023 | 2023 | 18 | 19 | 2023-05-07 | 22:10 | 2023-05-09 | 5:00 | 1d, 6h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 2047-001 |  | 2021-10-14
DB Netz AG | 2047-002 | Wilhelmshaven - Bremen | < | Delmenhorst Df | Bookholzberg | 2023 | 2023 | 19 | 19 | 2023-05-09 | 22:10 | 2023-05-10 | 5:00 | 0d, 6h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 2047-002 |  | 2021-10-14
DB Netz AG | 2053-001 | Rostock - Berlin | <> | Biesdf Kr Nord | Biesdf Kr Nord | 2023 | 2023 | 18 | 19 | 2023-05-02 | 22:00 | 2023-05-12 | 4:00 | 9d, 6h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 2053-001 |  | 2021-05-20
DB Netz AG | 2068-001 | Bremen - Hannover | <> | Nienburg (Weser) | Nienburg (Weser) | 2023 | 2023 | 16 | 16 | 2023-04-17 | 8:00 | 2023-04-20 | 14:45 | 3d, 6h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 2068-001 |  | 2022-07-20
DB Netz AG | 201D-001 | Hamburg - Magdeburg | < | Hmb-Harb Bbf Süd | Meckelfeld | 2022 | 2022 | 50 | 50 | 2022-12-12 | 8:00 | 2022-12-16 | 15:00 | 4d, 7h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | 201D-001 |  | 2022-04-27
DB Netz AG | 201D-002 | Hamburg - Magdeburg | < | Hmb-Harburg | Meckelfeld | 2022 | 2022 | 50 | 51 | 2022-12-17 | 8:00 | 2022-12-19 | 15:00 | 2d, 7h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | 201D-002 |  | 2022-04-27
DB Netz AG | 20.1 | Hamburg - Magdeburg | < | Hmb-Harb Bbf Süd | Meckelfeld | 2023 | 2023 | 14 | 14 | 2023-04-03 | 8:00 | 2023-04-03 | 15:00 | 0d, 7h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 20.1 |  | 2022-04-27
DB Netz AG | 2089-001 | Hamburg - Magdeburg | <> | Stelle | Stelle | 2023 | 2023 | 17 | 17 | 2023-04-27 | 22:00 | 2023-04-28 | 6:00 | 0d, 8h | Continuous | Catenary |  |  | S | [8 empty] | 80 | N | 2089-001 |  | 2021-07-13
DB Netz AG | 2089-002 | Hamburg - Magdeburg | <> | Ashausen | Maschen Rbf Msof | 2023 | 2023 | 17 | 17 | 2023-04-27 | 22:00 | 2023-04-28 | 6:00 | 0d, 8h | Continuous | Catenary | T | [10 empty] | 80 | N | 2089-002 |  | 2021-07-13
DB Netz AG | 2089-003 | Hamburg - Magdeburg | > | Winsen (Luhe) | Maschen Pbf | 2023 | 2023 | 17 | 17 | 2023-04-27 | 22:00 | 2023-04-28 | 6:00 | 0d, 8h | Continuous | Catenary |  | LT | [9 empty] | 80 | N | 2089-003 |  | 2021-07-13
DB Netz AG | 2089-004 | Hamburg - Magdeburg | <> | Winsen (Luhe) | Stelle | 2023 | 2023 | 17 | 17 | 2023-04-27 | 22:00 | 2023-04-28 | 6:00 | 0d, 8h | Continuous | Catenary |  | ST | [9 empty] | 80 | N | 2089-004 |  | 2021-07-13
DB Netz AG | 2089-005 | Hamburg - Magdeburg | <> | Winsen (Luhe) | Stelle | 2023 | 2023 | 17 | 17 | 2023-04-29 | 22:00 | 2023-04-30 | 5:00 | 0d, 7h | Continuous | Catenary |  | ST | [9 empty] | 80 | N | 2089-005 |  | 2021-07-13
DB Netz AG | 2089-007 | Hamburg - Magdeburg | <> | Stelle | Stelle | 2023 | 2023 | 17 | 17 | 2023-04-29 | 22:00 | 2023-04-30 | 5:00 | 0d, 7h | Continuous | Catenary |  |  | S | [8 empty] | 80 | N | 2089-007 |  | 2021-07-13
DB Netz AG | 2089-008 | Hamburg - Magdeburg | > | Winsen (Luhe) | Maschen Pbf | 2023 | 2023 | 17 | 17 | 2023-04-29 | 22:00 | 2023-04-30 | 5:00 | 0d, 7h | Continuous | Catenary |  | LT | [9 empty] | 80 | N | 2089-008 |  | 2021-07-13
DB Netz AG | 2089-009 | Hamburg - Magdeburg | <> | Ashausen Abzw | Maschen Rbf Msof | 2023 | 2023 | 17 | 17 | 2023-04-29 | 22:00 | 2023-04-30 | 5:00 | 0d, 7h | Continuous | Catenary | T | [10 empty] | 80 | N | 2089-009 |  | 2021-07-13
DB Netz AG | 2089-010 | Hamburg - Magdeburg | <> | Winsen (Luhe) | Stelle | 2023 | 2023 | 17 | 17 | 2023-04-29 | 22:00 | 2023-04-30 | 5:00 | 0d, 7h | Continuous | Catenary |  | ST | [9 empty] | 80 | N | 2089-010 |  | 2021-07-13
DB Netz AG | 2089-011 | Hamburg - Magdeburg | > | Winsen (Luhe) | Maschen Pbf | 2023 | 2023 | 17 | 18 | 2023-04-30 | 22:00 | 2023-05-01 | 5:00 | 0d, 7h | Continuous | Catenary |  | LT | [9 empty] | 80 | N | 2089-011 |  | 2021-07-13
DB Netz AG | 2089-012 | Hamburg - Magdeburg | <> | Ashausen | Maschen Rbf Msof | 2023 | 2023 | 17 | 18 | 2023-04-30 | 22:00 | 2023-05-01 | 5:00 | 0d, 7h | Continuous | Catenary | T | [10 empty] | 80 | N | 2089-012 |  | 2021-07-13
DB Netz AG | 2089-013 | Hamburg - Magdeburg | <> | Winsen (Luhe) | Stelle | 2023 | 2023 | 17 | 18 | 2023-04-30 | 22:00 | 2023-05-01 | 5:00 | 0d, 7h | Continuous | Catenary |  | ST | [9 empty] | 80 | N | 2089-013 |  | 2021-07-13
DB Netz AG | 2089-014 | Hamburg - Magdeburg | <> | Stelle | Stelle | 2023 | 2023 | 17 | 18 | 2023-04-30 | 22:00 | 2023-05-01 | 5:00 | 0d, 7h | Continuous | Catenary |  |  | S | [8 empty] | 80 | N | 2089-014 |  | 2021-07-13
DB Netz AG | 2089-015 | Hamburg - Magdeburg | < | Stelle | Lüneburg Nordk | 2023 | 2023 | 18 | 18 | 2023-05-03 | 23:00 | 2023-05-04 | 6:00 | 0d, 7h | Continuous | Catenary |  | LT | [9 empty] | 80 | N | 2089-015 |  | 2021-07-13
DB Netz AG | 2089-016 | Hamburg - Magdeburg | > | Winsen (Luhe) | Ashausen Abzw | 2023 | 2023 | 18 | 18 | 2023-05-03 | 23:00 | 2023-05-04 | 6:00 | 0d, 7h | Continuous | Catenary |  |  | S | [8 empty] | 80 | N | 2089-016 |  | 2021-07-13
DB Netz AG | 2096-001 | Bremen - Hannover | <> | Bremen Hbf | Bremen Hbf | 2023 | 2023 | 12 | 12 | 2023-03-20 | 8:00 | 2023-03-20 | 15:00 | 0d, 7h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 2096-001 |  | 2022-06-01
DB Netz AG | 2096-002 | Bremen - Hannover | <> | Bremen Hbf | Bremen Hbf | 2023 | 2023 | 12 | 12 | 2023-03-20 | 8:00 | 2023-03-20 | 15:00 | 0d, 7h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 2096-002 |  | 2022-06-01
DB Netz AG | 2089-017 | Hamburg - Magdeburg | <> | Winsen (Luhe) | Stelle | 2023 | 2023 | 18 | 18 | 2023-05-04 | 22:00 | 2023-05-05 | 5:00 | 0d, 7h | Continuous | Catenary | T | [10 empty] | 80 | N | 2089-017 |  | 2021-07-13
DB Netz AG | 2089-018 | Hamburg - Magdeburg | <> | Winsen (Luhe) | Winsen (Luhe) | 2023 | 2023 | 18 | 19 | 2023-05-06 | 23:00 | 2023-05-08 | 5:00 | 1d, 6h | Periodical | Catenary | T | [10 empty] | 80 | N | 2089-018 |  | 2021-07-13
DB Netz AG | 209A-001 | Bremen - Hannover | <> | Nienburg (Weser) | Nienburg (Weser) | 2023 | 2023 | 19 | 19 | 2023-05-09 | 8:00 | 2023-05-11 | 14:45 | 2d, 6h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 209A-001 |  | 2022-07-26
DB Netz AG | 209A-002 | Bremen - Hannover | <> | Nienburg (Weser) | Nienburg (Weser) | 2023 | 2023 | 19 | 19 | 2023-05-09 | 8:00 | 2023-05-11 | 14:45 | 2d, 6h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 209A-002 |  | 2022-07-26
DB Netz AG | 209F-001 | Bremen - Hannover | <> | Nienburg (Weser) | Nienburg (Weser) | 2023 | 2023 | 18 | 18 | 2023-05-02 | 8:00 | 2023-05-04 | 14:45 | 2d, 6h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 209F-001 |  | 2022-07-20
DB Netz AG | 2250-001 | Berlin - Dresden | <> | Schönfließ | Schönfließ | 2023 | 2023 | 18 | 19 | 2023-05-05 | 8:00 | 2023-05-08 | 16:00 | 3d, 8h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 2250-001 |  | 2022-07-20
DB Netz AG | 2250-002 | Rostock - Berlin | <> | Oranienburg | Oranienburg | 2023 | 2023 | 18 | 19 | 2023-05-05 | 8:00 | 2023-05-08 | 16:00 | 3d, 8h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 2250-002 |  | 2022-07-20
DB Netz AG | 228F-001 | Rostock - Berlin | > | Grabowhöfe | Vollrathsruhe | 2023 | 2023 | 16 | 16 | 2023-04-17 | 7:00 | 2023-04-17 | 15:45 | 0d, 8h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | 228F-001 |  | 2021-05-21
DB Netz AG | 228F-002 | Rostock - Berlin | <> | Vollrathsruhe | Vollrathsruhe | 2023 | 2023 | 16 | 16 | 2023-04-17 | 7:00 | 2023-04-17 | 15:45 | 0d, 8h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 228F-002 |  | 2021-05-21
DB Netz AG | 228F-003 | Rostock - Berlin | > | Waren (Müritz) | Vollrathsruhe | 2023 | 2023 | 16 | 16 | 2023-04-18 | 7:00 | 2023-04-18 | 15:45 | 0d, 8h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | 228F-003 |  | 2021-05-21
DB Netz AG | 228F-004 | Rostock - Berlin | > | Vollrathsruhe | Vollrathsruhe | 2023 | 2023 | 16 | 16 | 2023-04-18 | 7:00 | 2023-04-18 | 15:45 | 0d, 8h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 228F-004 |  | 2021-05-21
DB Netz AG | 228F-005 | Rostock - Berlin | < | Vollrathsruhe | Grabowhöfe | 2023 | 2023 | 16 | 16 | 2023-04-19 | 7:00 | 2023-04-19 | 15:45 | 0d, 8h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | 228F-005 |  | 2021-05-21
DB Netz AG | 228F-006 | Rostock - Berlin | < | Vollrathsruhe | Waren (Müritz) | 2023 | 2023 | 16 | 16 | 2023-04-20 | 7:00 | 2023-04-20 | 15:45 | 0d, 8h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | 228F-006 |  | 2021-05-21
DB Netz AG | 23D0-001 | Rostock - Berlin | < | Vollrathsruhe | Langhagen | 2023 | 2023 | 17 | 17 | 2023-04-24 | 7:00 | 2023-04-24 | 15:45 | 0d, 8h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 23D0-001 |  | 2021-11-11
DB Netz AG | 23D0-002 | Rostock - Berlin | < | Langhagen | Langhagen | 2023 | 2023 | 17 | 17 | 2023-04-24 | 7:00 | 2023-04-24 | 15:45 | 0d, 8h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 23D0-002 |  | 2021-11-11
DB Netz AG | 23D0-003 | Rostock - Berlin | > | Vollrathsruhe | Langhagen | 2023 | 2023 | 17 | 17 | 2023-04-25 | 7:00 | 2023-04-25 | 15:45 | 0d, 8h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 23D0-003 |  | 2021-11-11
DB Netz AG | 23D0-004 | Rostock - Berlin | > | Vollrathsruhe | Vollrathsruhe | 2023 | 2023 | 17 | 17 | 2023-04-25 | 7:00 | 2023-04-25 | 15:45 | 0d, 8h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 23D0-004 |  | 2021-11-11
DB Netz AG | 2482-001 | Rostock - Berlin | <> | Oranienburg | Oranienburg | 2022 | 2022 | 49 | 52 | 2022-12-11 | 0:00 | 2022-12-31 | 4:00 | 358d, 4h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 2482-001 |  | 2022-05-02
DB Netz AG | 2482-001 | Rostock - Berlin | <> | Oranienburg | Oranienburg | 2023 | 2023 | 1 | 49 | 2023-01-01 | 0:00 | 2023-12-04 | 4:00 | 358d, 4h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 2482-001 |  | 2022-05-02
DB Netz AG | 2729-001 | Rostock - Berlin | <> | Kavelstorf | Dalwitzhof | 2023 | 2023 | 16 | 17 | 2023-04-17 | 23:00 | 2023-04-27 | 5:00 | 9d, 6h | Periodical | Bridge | T | [10 empty] | 80 | N | 2729-001 |  | 2021-08-18
DB Netz AG | 2729-002 | Rostock - Berlin | <> | Kavelstorf | Dalwitzhof | 2023 | 2023 | 16 | 16 | 2023-04-21 | 23:00 | 2023-04-22 | 6:00 | 0d, 7h | Continuous | Bridge | T | [10 empty] | 80 | N | 2729-002 |  | 2021-08-18
DB Netz AG | 2729-003 | Rostock - Berlin | <> | Kavelstorf | Dalwitzhof | 2023 | 2023 | 16 | 16 | 2023-04-22 | 22:20 | 2023-04-23 | 6:00 | 0d, 7h | Continuous | Bridge | T | [10 empty] | 80 | N | 2729-003 |  | 2021-08-18
DB Netz AG | 2729-004 | Rostock - Berlin | <> | Kavelstorf | Dalwitzhof | 2023 | 2023 | 16 | 17 | 2023-04-23 | 23:40 | 2023-04-24 | 5:00 | 0d, 5h | Continuous | Bridge | T | [10 empty] | 80 | N | 2729-004 |  | 2021-08-18
DB Netz AG | 1300-004 | Magdeburg - Falkenberg | < | Elster (Elbe) | Lu Wittenberg | 2023 | 2023 | 11 | 12 | 2023-03-17 | 10:00 | 2023-03-21 | 22:00 | 4d, 12h | Continuous | Signal |  |  |  |  | X | [6 empty] | 80 | N | 1300-004 |  | 2021-05-18
DB Netz AG | 1856-010 | Berlin - Dresden | < | Elsterwerda | Großenh Berl Bf | 2023 | 2023 | 8 | 8 | 2023-02-21 | 1:30 | 2023-02-21 | 5:30 | 0d, 4h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1856-010
DB Netz AG | 1856-011 | Falkenberg - Dresden | <> | Frauenhain | Großenh Berl Bf | 2023 | 2023 | 8 | 8 | 2023-02-21 | 1:30 | 2023-02-21 | 5:30 | 0d, 4h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 1856-011
DB Netz AG | 1981-011 | Magdeburg - Falkenberg | > | Meinsdorf | Dessau Hbf | 2023 | 2023 | 13 | 14 | 2023-04-01 | 8:00 | 2023-04-03 | 8:00 | 2d, 0h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1981-011 |  | 2021-05-20
DB Netz AG | 1981-012 | Magdeburg - Falkenberg | <> | Roßlau (Elbe) | Roßlau (Elbe) | 2023 | 2023 | 13 | 13 | 2023-04-02 | 1:00 | 2023-04-02 | 4:00 | 0d, 3h | Continuous | Track & Rail | T | [10 empty] | 80 | N | 1981-012 |  | 2021-05-20
DB Netz AG | 1981-013 | Magdeburg - Falkenberg | > | Meinsdorf | Dessau Hbf | 2023 | 2023 | 13 | 14 | 2023-04-01 | 8:00 | 2023-04-03 | 8:00 | 2d, 0h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1981-013 |  | 2021-05-20
DB Netz AG | 1981-014 | Magdeburg - Falkenberg | <> | Roßlau (Elbe) | Roßlau (Elbe) | 2023 | 2023 | 13 | 13 | 2023-04-02 | 1:00 | 2023-04-02 | 4:00 | 0d, 3h | Continuous | Track & Rail | T | [10 empty] | 80 | N | 1981-014 |  | 2021-05-20
DB Netz AG | 34C1-001 | Wilhelmshaven - Bremen | <> | Oldb (Oldb) Hbf | Oldb (Oldb) Hbf | 2022 | 2022 | 49 | 52 | 2022-12-11 | 0:00 | 2022-12-31 | 23:59 | 363d, 23h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 34C1-001 |  | 2022-04-21
DB Netz AG | 34C1-001 | Wilhelmshaven - Bremen | <> | Oldb (Oldb) Hbf | Oldb (Oldb) Hbf | 2023 | 2023 | 1 | 49 | 2023-01-01 | 0:00 | 2023-12-09 | 23:59 | 363d, 23h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 34C1-001 |  | 2022-04-21
DB Netz AG | 3582-001 | Hamburg - Magdeburg | > | Stelle | Winsen (Luhe) | 2022 | 2022 | 49 | 50 | 2022-12-11 | 23:00 | 2022-12-12 | 2:00 | 0d, 3h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 3582-001 |  | 2022-05-10
DB Netz AG | 3582-002 | Hamburg - Magdeburg | > | Winsen (Luhe) | Winsen (Luhe) | 2022 | 2022 | 49 | 50 | 2022-12-11 | 23:00 | 2022-12-12 | 5:00 | 0d, 6h | Continuous | Switch |  |  | S | [8 empty] | 80 | N | 3582-002 |  | 2022-05-10
DB Netz AG | 3582-003 | Hamburg - Magdeburg | > | Winsen (Luhe) | Winsen (Luhe) | 2022 | 2022 | 50 | 50 | 2022-12-12 | 1:30 | 2022-12-12 | 2:00 | 0d, 0h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 3582-003 |  | 2022-05-10
DB Netz AG | 3582-004 | Hamburg - Magdeburg | > | Stelle | Lüneburg | 2022 | 2022 | 50 | 50 | 2022-12-12 | 1:30 | 2022-12-12 | 2:00 | 0d, 0h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 3582-004 |  | 2022-05-10
DB Netz AG | 3582-005 | Hamburg - Magdeburg | > | Winsen (Luhe) | Lüneburg | 2022 | 2022 | 50 | 50 | 2022-12-12 | 2:00 | 2022-12-12 | 4:30 | 0d, 2h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 3582-005 |  | 2022-05-10
DB Netz AG | 3582-006 | Hamburg - Magdeburg | > | Winsen (Luhe) | Winsen (Luhe) | 2022 | 2022 | 50 | 50 | 2022-12-12 | 4:30 | 2022-12-12 | 5:00 | 0d, 0h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 3582-006 |  | 2022-05-10
DB Netz AG | 1E1E-014 | Hannover - Magdeburg | <> | Braunschweig Hbf | Braunschweig Hbf | 2023 | 2023 | 10 | 10 | 2023-03-10 | 22:10 | 2023-03-11 | 0:10 | 0d, 2h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1E1E-014 |  | 2021-05-21
DB Netz AG | 1E1E-015 | Hannover - Magdeburg | <> | Braunschweig Hbf | Braunschweig Hbf | 2023 | 2023 | 10 | 11 | 2023-03-12 | 0:20 | 2023-03-18 | 5:10 | 6d, 4h | Periodical | Track & Rail |  | ST | [9 empty] | 80 | N | 1E1E-015 |  | 2021-05-21
DB Netz AG | 1E1E-016 | Hannover - Magdeburg | <> | Braunschweig Hbf | Braunschweig Hbf | 2023 | 2023 | 11 | 11 | 2023-03-18 | 21:45 | 2023-03-18 | 23:45 | 0d, 2h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1E1E-016 |  | 2021-05-21
DB Netz AG | A43-001 | Bremerhaven - Bremen | <> | Bremen-Burg | Bremen Rbf Abzw | 2023 | 2023 | 26 | 28 | 2023-06-26 | 23:30 | 2023-07-13 | 5:00 | 16d, 5h | Periodical | Miscellaneous |  |  | S | [8 empty] | 80 | N | A43-001 |  | 2021-05-28
DB Netz AG | A43-006 | Bremerhaven - Bremen | > | Bremen Hbf | Bremen-Burg | 2023 | 2023 | 26 | 28 | 2023-06-26 | 23:00 | 2023-07-13 | 5:00 | 16d, 6h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | A43-006 |  | 2021-05-11
DB Netz AG | A45-028 | Hannover - Magdeburg | > | Waldhausen | Hannover-Wülfel | 2023 | 2023 | 19 | 19 | 2023-05-13 | 8:00 | 2023-05-13 | 12:00 | 0d, 4h | Continuous | Switch |  | LT | [9 empty] | 80 | N | A45-028 |  | 2021-05-11
DB Netz AG | A45-021 | Hannover - Magdeburg | > | Waldhausen | Hannover-Wülfel | 2023 | 2023 | 20 | 20 | 2023-05-20 | 8:00 | 2023-05-20 | 12:00 | 0d, 4h | Continuous | Switch |  | LT | [9 empty] | 80 | N | A45-021 |  | 2021-05-11
DB Netz AG | A4E-009 | Bremerhaven - Bremen | <> | Brh-Wulsdorf | Stubben | 2023 | 2023 | 21 | 21 | 2023-05-23 | 0:00 | 2023-05-24 | 5:00 | 1d, 5h | Periodical | Miscellaneous |  |  | S | [8 empty] | 80 | N | A4E-009 |  | 2021-05-20
DB Netz AG | A4E-002 | Bremerhaven - Bremen | <> | Stubben | Brh-Wulsdorf | 2023 | 2023 | 19 | 19 | 2023-05-11 | 0:00 | 2023-05-13 | 5:00 | 2d, 5h | Periodical | Miscellaneous |  |  | S | [8 empty] | 80 | N | A4E-002 |  | 2021-05-20
DB Netz AG | A4E-021 | Bremerhaven - Bremen | <> | Brh-Wulsdorf | Brh-Wulsdorf | 2023 | 2023 | 20 | 21 | 2023-05-15 | 12:00 | 2023-05-22 | 18:00 | 7d, 6h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | A4E-021 |  | 2021-07-07
DB Netz AG | A4E-003 | Bremerhaven - Bremen | < | Brh-Wulsdorf | Stubben | 2023 | 2023 | 19 | 19 | 2023-05-11 | 0:00 | 2023-05-13 | 5:00 | 2d, 5h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | A4E-003 |  | 2021-05-20
DB Netz AG | A4E-010 | Bremerhaven - Bremen | <> | Brh-Wulsdorf | Stubben | 2023 | 2023 | 27 | 27 | 2023-07-03 | 6:00 | 2023-07-05 | 18:00 | 2d, 12h | Periodical | Miscellaneous |  |  | S | [8 empty] | 80 | N | A4E-010 |  | 2021-05-20
DB Netz AG | A4E-011 | Bremerhaven - Bremen | <> | Brh-Wulsdorf | Stubben | 2023 | 2023 | 21 | 21 | 2023-05-22 | 6:00 | 2023-05-26 | 18:00 | 4d, 12h | Periodical | Miscellaneous |  |  | S | [8 empty] | 80 | N | A4E-011 |  | 2021-05-20
DB Netz AG | A4E-024 | Bremerhaven - Bremen | <> | Brh-Wulsdorf | Brh-Wulsdorf | 2023 | 2023 | 20 | 21 | 2023-05-15 | 12:00 | 2023-05-22 | 18:00 | 7d, 6h | Continuous | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | A4E-024 |  | 2021-07-07
DB Netz AG | A4E-026 | Bremerhaven - Bremen | <> | Brh-Wulsdorf | Stubben | 2023 | 2023 | 21 | 22 | 2023-05-27 | 0:00 | 2023-05-29 | 5:00 | 2d, 5h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | A4E-026 |  | 2021-07-07
DB Netz AG | A4E-015 | Bremerhaven - Bremen | <> | Stubben | Brh-Wulsdorf | 2023 | 2023 | 19 | 20 | 2023-05-14 | 0:00 | 2023-05-15 | 5:00 | 1d, 5h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | A4E-015 |  | 2021-05-20
DB Netz AG | A4E-004 | Bremerhaven - Bremen | <> | Stubben | Brh-Wulsdorf | 2023 | 2023 | 20 | 20 | 2023-05-16 | 0:00 | 2023-05-17 | 5:00 | 1d, 5h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | A4E-004 |  | 2021-05-20
DB Netz AG | A4E-016 | Bremerhaven - Bremen | > | Stubben | Brh-Wulsdorf | 2023 | 2023 | 20 | 21 | 2023-05-18 | 0:00 | 2023-05-22 | 4:00 | 4d, 4h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | A4E-016 |  | 2021-05-20
DB Netz AG | A4E-017 | Bremerhaven - Bremen | <> | Brh-Wulsdorf | Stubben | 2023 | 2023 | 20 | 20 | 2023-05-18 | 0:00 | 2023-05-18 | 8:00 | 0d, 8h | Continuous | Miscellaneous |  |  | S | [8 empty] | 80 | N | A4E-017 |  | 2021-07-07
DB Netz AG | A4E-025 | Bremerhaven - Bremen | <> | Brh-Wulsdorf | Brh-Wulsdorf | 2023 | 2023 | 19 | 21 | 2023-05-11 | 8:00 | 2023-05-22 | 18:00 | 11d, 10h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | A4E-025 |  | 2021-05-20
DB Netz AG | A4E-013 | Bremerhaven - Bremen | <> | Brh-Wulsdorf | Stubben | 2023 | 2023 | 19 | 19 | 2023-05-10 | 0:00 | 2023-05-10 | 5:00 | 0d, 5h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | A4E-013 |  | 2021-07-07
DB Netz AG | A4E-001 | Bremerhaven - Bremen | <> | Brh-Wulsdorf | Stubben | 2023 | 2023 | 20 | 21 | 2023-05-20 | 8:00 | 2023-05-22 | 4:00 | 1d, 20h | Continuous | Miscellaneous |  |  | S | [8 empty] | 80 | N | A4E-001 |  | 2021-07-07
DB Netz AG | A4E-027 | Bremerhaven - Bremen | > | Stubben | Brh-Wulsdorf | 2023 | 2023 | 27 | 27 | 2023-07-09 | 0:00 | 2023-07-09 | 6:00 | 0d, 6h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | A4E-027 |  | 2021-05-20
DB Netz AG | A4E-005 | Bremerhaven - Bremen | > | Stubben | Brh-Wulsdorf | 2023 | 2023 | 21 | 21 | 2023-05-23 | 0:00 | 2023-05-24 | 5:00 | 1d, 5h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | A4E-005 |  | 2021-05-20
DB Netz AG | A4E-018 | Bremerhaven - Bremen | > | Stubben | Brh-Wulsdorf | 2023 | 2023 | 21 | 21 | 2023-05-23 | 4:00 | 2023-05-24 | 4:00 | 1d, 0h | Continuous | Miscellaneous |  |  | S | [8 empty] | 80 | N | A4E-018 |  | 2021-07-07
DB Netz AG | A4E-014 | Bremerhaven - Bremen | <> | Brh-Wulsdorf | Stubben | 2023 | 2023 | 20 | 20 | 2023-05-16 | 0:00 | 2023-05-17 | 5:00 | 1d, 5h | Periodical | Miscellaneous |  |  | S | [8 empty] | 80 | N | A4E-014 |  | 2021-05-20
DB Netz AG | A4E-028 | Bremerhaven - Bremen | <> | Brh-Wulsdorf | Stubben | 2023 | 2023 | 20 | 20 | 2023-05-18 | 8:00 | 2023-05-20 | 8:00 | 2d, 0h | Continuous | Miscellaneous |  |  | S | [8 empty] | 80 | N | A4E-028 |  | 2021-07-08
DB Netz AG | A4E-023 | Bremerhaven - Bremen | <> | Brh-Wulsdorf | Stubben | 2023 | 2023 | 27 | 27 | 2023-07-09 | 0:00 | 2023-07-09 | 6:00 | 0d, 6h | Continuous | Miscellaneous |  |  | S | [8 empty] | 80 | N | A4E-023 |  | 2021-07-08
DB Netz AG | A4E-020 | Bremerhaven - Bremen | <> | Brh-Wulsdorf | Stubben | 2023 | 2023 | 19 | 20 | 2023-05-14 | 0:00 | 2023-05-15 | 5:00 | 1d, 5h | Periodical | Miscellaneous |  |  | S | [8 empty] | 80 | N | A4E-020 |  | 2021-07-08
DB Netz AG | A4E-007 | Bremerhaven - Bremen | > | Stubben | Brh-Wulsdorf | 2023 | 2023 | 21 | 21 | 2023-05-22 | 4:00 | 2023-05-23 | 4:00 | 1d, 0h | Continuous | Miscellaneous |  |  | S | [8 empty] | 80 | N | A4E-007 |  | 2021-07-08
DB Netz AG | A9D-002 | Hamburg - Magdeburg | <> | Schnega | Schnega | 2023 | 2023 | 21 | 21 | 2023-05-22 | 8:00 | 2023-05-22 | 19:00 | 0d, 11h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | A9D-002 |  | 2021-06-03
DB Netz AG | A9D-004 | Hamburg - Magdeburg | <> | Schnega | Schnega | 2023 | 2023 | 20 | 21 | 2023-05-15 | 5:00 | 2023-05-22 | 8:00 | 7d, 3h | Continuous | Miscellaneous |  |  | S | [8 empty] | 80 | N | A9D-004 |  | 2021-06-03
DB Netz AG | A9D-001 | Hamburg - Magdeburg | <> | Schnega | Schnega | 2023 | 2023 | 21 | 21 | 2023-05-22 | 8:00 | 2023-05-22 | 19:00 | 0d, 11h | Continuous | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | A9D-001 |  | 2021-06-04
DB Netz AG | ACE-002 | Bremen - Hannover | < | Bremen Hbf | Bremen Hbf | 2023 | 2023 | 21 | 22 | 2023-05-28 | 0:00 | 2023-05-29 | 5:00 | 1d, 5h | Periodical | Signal |  | ST | [9 empty] | 80 | N | ACE-002 |  | 2021-05-27
DB Netz AG | ACE-009 | Bremen - Hannover | < | Bremen Hbf | Brm-Hemelingen | 2023 | 2023 | 21 | 21 | 2023-05-22 | 0:00 | 2023-05-23 | 5:00 | 1d, 5h | Periodical | Signal |  | LT | [9 empty] | 80 | N | ACE-009 |  | 2021-05-27
DB Netz AG | ACE-011 | Bremen - Hannover | < | Bremen Hbf | Bremen Hbf | 2023 | 2023 | 21 | 21 | 2023-05-22 | 0:00 | 2023-05-23 | 5:00 | 1d, 5h | Periodical | Signal |  | ST | [9 empty] | 80 | N | ACE-011 |  | 2021-07-22
DB Netz AG | ACE-001 | Bremen - Hannover | <> | Bremen Hbf | Bremen Hbf | 2023 | 2023 | 22 | 22 | 2023-06-02 | 0:00 | 2023-06-04 | 5:00 | 2d, 5h | Periodical | Signal | T | [10 empty] | 80 | N | ACE-001 |  | 2021-05-27
DB Netz AG | ACE-010 | Bremen - Hannover | > | Bremen Hbf | Bremen Hbf | 2023 | 2023 | 23 | 23 | 2023-06-05 | 0:00 | 2023-06-06 | 5:00 | 1d, 5h | Periodical | Signal |  | ST | [9 empty] | 80 | N | ACE-010 |  | 2021-05-27
DB Netz AG | ACE-003 | Bremen - Hannover | <> | Bremen Hbf | Bremen Hbf | 2023 | 2023 | 22 | 22 | 2023-05-30 | 0:00 | 2023-06-01 | 5:00 | 2d, 5h | Periodical | Signal |  | ST | [9 empty] | 80 | N | ACE-003 |  | 2021-05-27
DB Netz AG | ACE-007 | Bremen - Hannover | <> | Bremen Hbf | Bremen Hbf | 2023 | 2023 | 23 | 23 | 2023-06-05 | 0:00 | 2023-06-08 | 5:00 | 3d, 5h | Periodical | Signal | T | [10 empty] | 80 | N | ACE-007 |  | 2021-05-27
DB Netz AG | ACE-012 | Bremen - Hannover | < | Bremen Hbf | Bremen Hbf | 2023 | 2023 | 21 | 22 | 2023-05-28 | 0:00 | 2023-05-29 | 5:00 | 1d, 5h | Periodical | Signal |  | ST | [9 empty] | 80 | N | ACE-012 |  | 2021-05-27
DB Netz AG | ACE-008 | Bremen - Hannover | <> | Bremen Hbf | Bremen Hbf | 2023 | 2023 | 21 | 21 | 2023-05-26 | 0:00 | 2023-05-27 | 5:00 | 1d, 5h | Periodical | Signal |  | ST | [9 empty] | 80 | N | ACE-008 |  | 2021-05-27
DB Netz AG | ACE-004 | Bremen - Hannover | <> | Bremen Hbf | Bremen Hbf | 2023 | 2023 | 21 | 21 | 2023-05-24 | 0:00 | 2023-05-25 | 5:00 | 1d, 5h | Periodical | Signal |  | ST | [9 empty] | 80 | N | ACE-004 |  | 2021-05-27
DB Netz AG | ACE-013 | Bremen - Hannover | > | Bremen Hbf | Bremen Hbf | 2023 | 2023 | 21 | 21 | 2023-05-22 | 0:00 | 2023-05-23 | 5:00 | 1d, 5h | Periodical | Signal |  | ST | [9 empty] | 80 | N | ACE-013 |  | 2021-07-22
DB Netz AG | ACE-005 | Bremen - Hannover | < | Bremen Hbf | Bremen Hbf | 2023 | 2023 | 21 | 21 | 2023-05-24 | 0:00 | 2023-05-25 | 5:00 | 1d, 5h | Periodical | Signal |  | ST | [9 empty] | 80 | N | ACE-005 |  | 2021-05-27
DB Netz AG | AE6-005 | Bremerhaven - Bremen | <> | Brh-Wulsdorf | Stubben | 2023 | 2023 | 26 | 35 | 2023-06-26 | 23:00 | 2023-09-01 | 5:00 | 66d, 6h | Periodical | Miscellaneous |  |  | S | [8 empty] | 80 | N | AE6-005 |  | 2021-05-04
DB Netz AG | AE6-003 | Bremerhaven - Bremen | > | Stubben | Brh-Wulsdorf | 2023 | 2023 | 26 | 35 | 2023-06-26 | 23:00 | 2023-09-01 | 5:00 | 66d, 6h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | AE6-003 |  | 2021-05-04
DB Netz AG | AE6-009 | Bremerhaven - Bremen | > | Stubben | Brh-Wulsdorf | 2023 | 2023 | 25 | 35 | 2023-06-24 | 14:00 | 2023-08-28 | 5:00 | 64d, 15h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | Y | AE6-009 |  | 2021-05-04
DB Netz AG | AE6-004 | Bremerhaven - Bremen | <> | Brh-Wulsdorf | Stubben | 2023 | 2023 | 25 | 35 | 2023-06-24 | 14:00 | 2023-08-28 | 5:00 | 64d, 15h | Periodical | Miscellaneous |  |  | S | [8 empty] | 80 | N | AE6-004 |  | 2021-05-04
DB Netz AG | B85-012 | Hamburg - Magdeburg | < | Hmb-Neugraben | Hmb-Hausbruch | 2023 | 2023 | 27 | 28 | 2023-07-08 | 14:00 | 2023-07-10 | 4:00 | 1d, 14h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | B85-012 |  | 2021-05-05
DB Netz AG | B85-009 | Hamburg - Magdeburg | > | Hmb-Hausbruch | Hmb-Neugraben | 2023 | 2023 | 26 | 26 | 2023-06-26 | 23:00 | 2023-06-30 | 6:00 | 3d, 7h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | B85-009 |  | 2021-05-05
DB Netz AG | B85-005 | Hamburg - Magdeburg | > | Hmb-Hausbruch | Hmb-Neugraben | 2023 | 2023 | 26 | 27 | 2023-07-01 | 9:00 | 2023-07-03 | 3:00 | 1d, 18h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | B85-005 |  | 2021-05-04
DB Netz AG | B85-010 | Hamburg - Magdeburg | > | Hmb-Hausbruch | Hmb-Neugraben | 2023 | 2023 | 25 | 26 | 2023-06-23 | 22:00 | 2023-06-26 | 4:00 | 2d, 6h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | B85-010 |  | 2021-05-04
DB Netz AG | BA3-001 | Bremerhaven - Bremen | > | Lübberstedt | Brh-Wulsdorf | 2023 | 2023 | 21 | 21 | 2023-05-22 | 0:00 | 2023-05-22 | 3:00 | 0d, 3h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | BA3-001 |  | 2021-05-26
DB Netz AG | BA3-003 | Bremerhaven - Bremen | <> | Brh-Wulsdorf | Lübberstedt | 2023 | 2023 | 21 | 21 | 2023-05-22 | 1:30 | 2023-05-22 | 3:00 | 0d, 1h | Continuous | Track & Rail | T | [10 empty] | 80 | N | BA3-003 |  | 2021-05-26
DB Netz AG | BA3-013 | Bremerhaven - Bremen | > | Lübberstedt | Brh-Wulsdorf | 2023 | 2023 | 22 | 22 | 2023-05-30 | 1:00 | 2023-05-30 | 4:00 | 0d, 3h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | BA3-013 |  | 2021-05-26
DB Netz AG | BA3-017 | Bremerhaven - Bremen | <> | Stubben | Stubben | 2023 | 2023 | 20 | 20 | 2023-05-15 | 6:00 | 2023-05-19 | 18:00 | 4d, 12h | Periodical | Track & Rail |  |  | S | [8 empty] | 80 | N | BA3-017 |  | 2021-07-14
DB Netz AG | BA3-011 | Bremerhaven - Bremen | <> | Stubben | Stubben | 2023 | 2023 | 22 | 22 | 2023-05-30 | 6:00 | 2023-06-02 | 18:00 | 3d, 12h | Periodical | Track & Rail |  |  | S | [8 empty] | 80 | N | BA3-011 |  | 2021-07-14
DB Netz AG | BA3-004 | Bremerhaven - Bremen | <> | Stubben | Stubben | 2023 | 2023 | 21 | 22 | 2023-05-22 | 0:00 | 2023-05-30 | 4:00 | 8d, 4h | Continuous | Track & Rail |  |  | S | [8 empty] | 80 | N | BA3-004 |  | 2021-05-26
DB Netz AG | BA3-007 | Bremerhaven - Bremen | < | Brh-Wulsdorf | Lübberstedt | 2023 | 2023 | 22 | 22 | 2023-05-31 | 0:00 | 2023-06-02 | 4:00 | 2d, 4h | Periodical | Track & Rail |  | LT | [9 empty] | 80 | N | BA3-007 |  | 2021-07-14
DB Netz AG | BA3-019 | Bremerhaven - Bremen | <> | Stubben | Stubben | 2023 | 2023 | 22 | 22 | 2023-05-29 | 0:00 | 2023-05-29 | 5:00 | 0d, 5h | Continuous | Track & Rail | T | [10 empty] | 80 | N | BA3-019 |  | 2021-05-26
DB Netz AG | BA3-012 | Bremerhaven - Bremen | > | Stubben | Stubben | 2023 | 2023 | 22 | 22 | 2023-05-31 | 8:00 | 2023-06-01 | 8:00 | 1d, 0h | Continuous | Track & Rail |  |  | S | [8 empty] | 80 | N | BA3-012 |  | 2021-05-26
DB Netz AG | BA3-009 | Bremerhaven - Bremen | <> | Brh-Wulsdorf | Lübberstedt | 2023 | 2023 | 22 | 22 | 2023-05-30 | 1:00 | 2023-05-30 | 2:30 | 0d, 1h | Continuous | Track & Rail | T | [10 empty] | 80 | N | BA3-009 |  | 2021-05-26
DB Netz AG | BA3-020 | Bremerhaven - Bremen | > | Lübberstedt | Stubben | 2023 | 2023 | 21 | 22 | 2023-05-22 | 0:00 | 2023-05-30 | 4:00 | 8d, 4h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | BA3-020 |  | 2021-05-26
DB Netz AG | BA3-010 | Bremerhaven - Bremen | > | Stubben | Stubben | 2023 | 2023 | 22 | 22 | 2023-05-30 | 4:00 | 2023-05-31 | 8:00 | 1d, 4h | Continuous | Track & Rail |  |  | S | [8 empty] | 80 | N | BA3-010 |  | 2021-07-14
DB Netz AG | C24-037 | Bremerhaven - Bremen | > | Stubben | Brh-Wulsdorf | 2023 | 2023 | 26 | 26 | 2023-06-28 | 0:00 | 2023-07-01 | 5:00 | 3d, 5h | Periodical | Track & Rail |  | LT | [9 empty] | 80 | N | C24-037 |  | 2021-05-25
DB Netz AG | C24-001 | Bremerhaven - Bremen | <> | Brh-Wulsdorf | Stubben | 2023 | 2023 | 25 | 25 | 2023-06-23 | 4:00 | 2023-06-24 | 8:00 | 1d, 4h | Continuous | Track & Rail |  |  | S | [8 empty] | 80 | N | C24-001 |  | 2021-07-09
DB Netz AG | C24-038 | Bremerhaven - Bremen | < | Stubben | Lübberstedt | 2023 | 2023 | 24 | 24 | 2023-06-16 | 0:00 | 2023-06-16 | 4:00 | 0d, 4h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | C24-038 |  | 2021-05-25
DB Netz AG | C24-002 | Bremerhaven - Bremen | < | Stubben | Lübberstedt | 2023 | 2023 | 24 | 24 | 2023-06-14 | 0:00 | 2023-06-14 | 5:00 | 0d, 5h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | C24-002 |  | 2021-05-25
DB Netz AG | C24-028 | Bremerhaven - Bremen | > | Stubben | Brh-Wulsdorf | 2023 | 2023 | 25 | 26 | 2023-06-24 | 0:00 | 2023-06-27 | 5:00 | 3d, 5h | Periodical | Track & Rail |  | LT | [9 empty] | 80 | N | C24-028 |  | 2021-05-25
DB Netz AG | C24-030 | Bremerhaven - Bremen | < | Brh-Wulsdorf | Stubben | 2023 | 2023 | 25 | 25 | 2023-06-24 | 8:00 | 2023-06-25 | 8:00 | 1d, 0h | Continuous | Track & Rail |  |  | S | [8 empty] | 80 | N | C24-030 |  | 2021-07-12
DB Netz AG | C24-054 | Bremerhaven - Bremen | <> | Brh-Wulsdorf | Stubben | 2023 | 2023 | 25 | 26 | 2023-06-24 | 0:00 | 2023-06-27 | 5:00 | 3d, 5h | Periodical | Track & Rail |  |  | S | [8 empty] | 80 | N | C24-054 |  | 2021-07-12
DB Netz AG | C24-022 | Bremerhaven - Bremen | <> | Stubben | Brh-Wulsdorf | 2023 | 2023 | 22 | 22 | 2023-05-30 | 23:00 | 2023-06-02 | 0:00 | 2d, 1h | Continuous | Track & Rail |  |  | S | [8 empty] | 80 | N | C24-022 |  | 2021-07-12
DB Netz AG | C24-047 | Bremerhaven - Bremen | < | Stubben | Lübberstedt | 2023 | 2023 | 24 | 25 | 2023-06-18 | 0:00 | 2023-06-20 | 4:00 | 2d, 4h | Periodical | Track & Rail |  | LT | [9 empty] | 80 | N | C24-047 |  | 2021-05-25
DB Netz AG | C24-032 | Bremerhaven - Bremen | > | Stubben | Brh-Wulsdorf | 2023 | 2023 | 21 | 22 | 2023-05-22 | 0:00 | 2023-05-30 | 5:00 | 8d, 5h | Periodical | Track & Rail |  | LT | [9 empty] | 80 | N | C24-032 |  | 2021-05-25
DB Netz AG | C24-013 | Bremerhaven - Bremen | <> | Brh-Wulsdorf | Stubben | 2023 | 2023 | 26 | 26 | 2023-06-28 | 0:00 | 2023-07-01 | 5:00 | 3d, 5h | Periodical | Track & Rail |  |  | S | [8 empty] | 80 | N | C24-013 |  | 2021-07-12
DB Netz AG | C24-033 | Bremerhaven - Bremen | <> | Brh-Wulsdorf | Stubben | 2023 | 2023 | 21 | 21 | 2023-05-22 | 0:00 | 2023-05-26 | 5:00 | 4d, 5h | Periodical | Track & Rail |  |  | S | [8 empty] | 80 | N | C24-033 |  | 2021-05-25
DB Netz AG | C24-061 | Bremerhaven - Bremen | < | Stubben | Lübberstedt | 2023 | 2023 | 22 | 22 | 2023-06-02 | 0:00 | 2023-06-02 | 4:00 | 0d, 4h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | C24-061 |  | 2021-07-12
DB Netz AG | C24-023 | Bremerhaven - Bremen | <> | Stubben | Brh-Wulsdorf | 2023 | 2023 | 27 | 27 | 2023-07-03 | 6:00 | 2023-07-07 | 18:00 | 4d, 12h | Periodical | Track & Rail |  |  | S | [8 empty] | 80 | N | C24-023 |  | 2021-07-12
DB Netz AG | C24-014 | Bremerhaven - Bremen | <> | Stubben | Brh-Wulsdorf | 2023 | 2023 | 20 | 20 | 2023-05-15 | 6:00 | 2023-05-19 | 18:00 | 4d, 12h | Periodical | Track & Rail |  |  | S | [8 empty] | 80 | N | C24-014 |  | 2021-07-12
DB Netz AG | C24-035 | Bremerhaven - Bremen | <> | Lunestedt | Loxstedt | 2023 | 2023 | 21 | 21 | 2023-05-22 | 6:00 | 2023-05-26 | 18:00 | 4d, 12h | Periodical | Track & Rail |  |  | S | [8 empty] | 80 | N | C24-035 |  | 2021-07-12
DB Netz AG | C24-049 | Bremerhaven - Bremen | <> | Brh-Wulsdorf | Brh-Wulsdorf | 2023 | 2023 | 22 | 25 | 2023-05-30 | 8:00 | 2023-06-23 | 18:00 | 24d, 10h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | C24-049 |  | 2021-07-12
DB Netz AG | C24-004 | Bremerhaven - Bremen | < | Stubben | Lübberstedt | 2023 | 2023 | 23 | 23 | 2023-06-09 | 0:00 | 2023-06-09 | 4:00 | 0d, 4h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | C24-004 |  | 2021-05-25
DB Netz AG | C24-056 | Bremerhaven - Bremen | < | Stubben | Lübberstedt | 2023 | 2023 | 22 | 22 | 2023-05-30 | 23:00 | 2023-05-31 | 3:00 | 0d, 4h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | C24-056 |  | 2021-05-25
DB Netz AG | C24-043 | Bremerhaven - Bremen | <> | Brh-Wulsdorf | Brh-Wulsdorf | 2023 | 2023 | 22 | 25 | 2023-05-30 | 8:00 | 2023-06-23 | 18:00 | 24d, 10h | Continuous | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | C24-043 |  | 2021-07-21
DB Netz AG | C24-008 | Bremerhaven - Bremen | <> | Stubben | Brh-Wulsdorf | 2023 | 2023 | 23 | 24 | 2023-06-11 | 0:00 | 2023-06-14 | 5:00 | 3d, 5h | Continuous | Track & Rail |  |  | S | [8 empty] | 80 | N | C24-008 |  | 2021-07-12
DB Netz AG | C24-017 | Bremerhaven - Bremen | <> | Stubben | Brh-Wulsdorf | 2023 | 2023 | 24 | 25 | 2023-06-14 | 5:00 | 2023-06-23 | 4:00 | 8d, 23h | Continuous | Track & Rail |  |  | S | [8 empty] | 80 | N | C24-017 |  | 2021-07-13
DB Netz AG | C24-064 | Bremerhaven - Bremen | < | Brh-Wulsdorf | Stubben | 2023 | 2023 | 22 | 25 | 2023-05-30 | 23:00 | 2023-06-23 | 4:00 | 23d, 5h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | C24-064 |  | 2021-05-25
DB Netz AG | C24-065 | Bremerhaven - Bremen | <> | Stubben | Brh-Wulsdorf | 2023 | 2023 | 22 | 23 | 2023-06-02 | 0:00 | 2023-06-09 | 20:00 | 7d, 20h | Continuous | Track & Rail |  |  | S | [8 empty] | 80 | N | C24-065 |  | 2021-07-13
DB Netz AG | C24-044 | Bremerhaven - Bremen | <> | Stubben | Brh-Wulsdorf | 2023 | 2023 | 23 | 23 | 2023-06-09 | 20:00 | 2023-06-11 | 0:00 | 1d, 4h | Continuous | Track & Rail |  |  | S | [8 empty] | 80 | N | C24-044 |  | 2021-07-13
DB Netz AG | C24-066 | Bremerhaven - Bremen | <> | Brh-Wulsdorf | Stubben | 2023 | 2023 | 21 | 22 | 2023-05-27 | 0:00 | 2023-05-30 | 5:00 | 3d, 5h | Periodical | Track & Rail |  |  | S | [8 empty] | 80 | N | C24-066 |  | 2021-07-13
DB Netz AG | C24-045 | Bremerhaven - Bremen | <> | Stubben | Brh-Wulsdorf | 2023 | 2023 | 26 | 26 | 2023-06-26 | 6:00 | 2023-06-30 | 18:00 | 4d, 12h | Periodical | Track & Rail |  |  | S | [8 empty] | 80 | N | C24-045 |  | 2021-07-13
DB Netz AG | C24-027 | Bremerhaven - Bremen | < | Stubben | Lübberstedt | 2023 | 2023 | 25 | 25 | 2023-06-23 | 0:00 | 2023-06-23 | 4:00 | 0d, 4h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | C24-027 |  | 2021-05-25
DB Netz AG | C2A-002 | Berlin - Dresden | <> | Grün Kreuz Süd | Grün Kreuz West | 2023 | 2023 | 21 | 22 | 2023-05-26 | 21:00 | 2023-05-29 | 5:00 | 2d, 8h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | C2A-002 |  | 2021-04-26
DB Netz AG | C55-002 | Hamburg - Magdeburg | <> | Salzwedel Gbf | Salzwedel | 2023 | 2023 | 20 | 20 | 2023-05-15 | 5:00 | 2023-05-21 | 18:00 | 6d, 13h | Continuous | Miscellaneous |  |  | S | [8 empty] | 80 | N | C55-002 |  | 2021-06-02
DB Netz AG | C55-001 | Hamburg - Magdeburg | <> | Salzwedel Gbf | Salzwedel Gbf | 2023 | 2023 | 20 | 20 | 2023-05-15 | 5:00 | 2023-05-21 | 18:00 | 6d, 13h | Continuous | Miscellaneous |  |  | S | [8 empty] | 80 | N | C55-001 |  | 2021-06-03
DB Netz AG | C5F-001 | Dresden - Děčín | <> | Bad Schandau | Bad Schandau | 2023 | 2023 | 27 | 30 | 2023-07-03 | 23:00 | 2023-07-25 | 5:00 | 21d, 6h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | C5F-001 |  | 2021-05-21
DB Netz AG | C5F-002 | Dresden - Děčín | <> | Königst (Sä) Üst | Bad Schandau Ost | 2023 | 2023 | 27 | 30 | 2023-07-03 | 23:00 | 2023-07-25 | 5:00 | 21d, 6h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | C5F-002 |  | 2021-05-21
DB Netz AG | C5F-003 | Dresden - Děčín | <> | Königst (Sä) Üst | Bad Schandau Gr | 2023 | 2023 | 27 | 30 | 2023-07-03 | 23:00 | 2023-07-25 | 5:00 | 21d, 6h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80,54 | N | C5F-003 |  | 2021-05-21
DB Netz AG | CA7-015 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 21 | 26 | 2023-05-22 | 5:30 | 2023-06-26 | 5:30 | 35d, 0h | Continuous | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | CA7-015 |  | 2021-05-26
DB Netz AG | CA7-022 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 21 | 26 | 2023-05-22 | 5:30 | 2023-06-26 | 5:30 | 35d, 0h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | CA7-022 |  | 2021-05-26
DB Netz AG | CA7-031 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 21 | 26 | 2023-05-22 | 5:30 | 2023-06-26 | 5:30 | 35d, 0h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | CA7-031 |  | 2021-05-26
DB Netz AG | CA7-032 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 21 | 25 | 2023-05-25 | 21:30 | 2023-06-24 | 5:30 | 29d, 8h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | CA7-032 |  | 2021-05-26
DB Netz AG | CA7-006 | Dresden - Děčín | <> | Dresden Hbf | Dresden Mitte | 2023 | 2023 | 21 | 25 | 2023-05-25 | 21:30 | 2023-06-24 | 5:30 | 29d, 8h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | CA7-006 |  | 2021-05-26
DB Netz AG | CA7-004 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 21 | 25 | 2023-05-25 | 21:30 | 2023-06-24 | 5:30 | 29d, 8h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | CA7-004 |  | 2021-05-26
DB Netz AG | CA7-008 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 26 | 26 | 2023-06-26 | 7:00 | 2023-06-30 | 20:00 | 4d, 13h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | CA7-008 |  | 2021-05-26
DB Netz AG | CA7-009 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 26 | 26 | 2023-06-26 | 7:00 | 2023-06-30 | 20:00 | 4d, 13h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | CA7-009 |  | 2021-05-26
DB Netz AG | CB3-001 | Dresden - Děčín | <> | Dresden Hbf | Dresden Mitte | 2023 | 2023 | 24 | 24 | 2023-06-16 | 22:00 | 2023-06-17 | 5:00 | 0d, 7h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | CB3-001 |  | 2021-06-10
DB Netz AG | CB3-005 | Dresden - Děčín | <> | Dresden Hbf | Dre Freibg Str | 2023 | 2023 | 24 | 24 | 2023-06-16 | 22:00 | 2023-06-17 | 5:00 | 0d, 7h | Continuous | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | CB3-005 |  | 2021-06-10
DB Netz AG | CB3-003 | Dresden - Děčín | < | Dresden Mitte | Dresden Hbf | 2023 | 2023 | 24 | 24 | 2023-06-16 | 22:00 | 2023-06-18 | 5:00 | 1d, 7h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | CB3-003 |  | 2021-06-10
DB Netz AG | CB3-008 | Dresden - Děčín | <> | Dresden Hbf | Dresden Mitte | 2023 | 2023 | 24 | 24 | 2023-06-12 | 22:00 | 2023-06-13 | 5:00 | 0d, 7h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | CB3-008 |  | 2021-06-10
DB Netz AG | CB3-002 | Dresden - Děčín | <> | Dre-Friedrichst | Dre Freibg Str | 2023 | 2023 | 24 | 24 | 2023-06-12 | 22:00 | 2023-06-13 | 5:00 | 0d, 7h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | CB3-002 |  | 2021-06-09
DB Netz AG | CB3-007 | Dresden - Děčín | <> | Dresden Hbf | Dre Freibg Str | 2023 | 2023 | 24 | 24 | 2023-06-12 | 22:00 | 2023-06-13 | 5:00 | 0d, 7h | Continuous | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | CB3-007 |  | 2021-06-09
DB Netz AG | CB3-004 | Dresden - Děčín | <> | Dresden Hbf | Dresden Mitte | 2023 | 2023 | 24 | 24 | 2023-06-12 | 22:00 | 2023-06-13 | 5:00 | 0d, 7h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | CB3-004 |  | 2021-06-09
DB Netz AG | CB3-009 | Dresden - Děčín | <> | Dresden-Altstadt | Dre Freibg Str | 2023 | 2023 | 24 | 24 | 2023-06-12 | 22:00 | 2023-06-13 | 5:00 | 0d, 7h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | CB3-009 |  | 2021-06-09
DB Netz AG | CB3-006 | Dresden - Děčín | <> | Dresden Hbf | Dresden Mitte | 2023 | 2023 | 24 | 24 | 2023-06-13 | 22:00 | 2023-06-16 | 5:00 | 2d, 7h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | CB3-006 |  | 2021-06-10
DB Netz AG | CB3-010 | Dresden - Děčín | <> | Dresden Hbf | Dre Freibg Str | 2023 | 2023 | 24 | 24 | 2023-06-13 | 22:00 | 2023-06-16 | 5:00 | 2d, 7h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | CB3-010 |  | 2021-06-10
DB Netz AG | CB9-003 | Dresden - Děčín | <> | Dresden-Altstadt | Dresden Hbf | 2023 | 2023 | 27 | 32 | 2023-07-09 | 6:00 | 2023-08-12 | 14:00 | 34d, 8h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | CB9-003 |  | 2021-06-08
DB Netz AG | CB9-001 | Dresden - Děčín | > | Dresden Hbf | Dresden Mitte | 2023 | 2023 | 27 | 32 | 2023-07-09 | 6:00 | 2023-08-12 | 14:00 | 34d, 8h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | CB9-001 |  | 2021-06-08
DB Netz AG | CB9-002 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 27 | 32 | 2023-07-09 | 6:00 | 2023-08-12 | 14:00 | 34d, 8h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | CB9-002 |  | 2021-06-08
DB Netz AG | 22 | Rostock - Berlin | <> | Schönfließ West | Birkenwerd b Bln | 2023 | 2023 | 25 | 25 | 2023-06-20 | 22:00 | 2023-06-23 | 4:00 | 2d, 6h | Periodical | Signal | T | [10 empty] | 80 | N | 22 |  | 2021-08-05
DB Netz AG | 2105-001 | Rostock - Berlin | <> | Bergfelde Ost | Hohen Neuend Sw | 2023 | 2023 | 25 | 26 | 2023-06-25 | 22:00 | 2023-06-30 | 4:00 | 4d, 6h | Periodical | Signal | T | [10 empty] | 80 | N | 2105-001 |  | 2021-08-24
DB Netz AG | 2105-002 | Rostock - Berlin | <> | Hohen Neuend W | Birkenwerd b Bln | 2023 | 2023 | 25 | 26 | 2023-06-25 | 22:00 | 2023-06-30 | 4:00 | 4d, 6h | Periodical | Signal | T | [10 empty] | 80 | N | 2105-002 |  | 2021-11-15
DB Netz AG | 2105-003 | Rostock - Berlin | <> | Schönfließ West | Hohen Neuend Sw | 2023 | 2023 | 25 | 26 | 2023-06-25 | 22:00 | 2023-06-30 | 4:00 | 4d, 6h | Periodical | Signal | T | [10 empty] | 80 | N | 2105-003 |  | 2021-08-24
DB Netz AG | 2105-004 | Rostock - Berlin | <> | Schönfließ West | Birkenwerd b Bln | 2023 | 2023 | 25 | 26 | 2023-06-25 | 22:00 | 2023-06-30 | 4:00 | 4d, 6h | Periodical | Signal | T | [10 empty] | 80 | N | 2105-004 |  | 2021-11-15
DB Netz AG | 2105-005 | Rostock - Berlin | <> | Birkenwerd b Bln | Oranienburg | 2023 | 2023 | 25 | 26 | 2023-06-25 | 22:00 | 2023-06-30 | 4:00 | 4d, 6h | Periodical | Signal | T | [10 empty] | 80 | N | 2105-005 |  | 2021-11-15
DB Netz AG | 2105-006 | Rostock - Berlin | <> | Bergfelde Ost | Hohen Neuend Sw | 2023 | 2023 | 23 | 24 | 2023-06-11 | 22:00 | 2023-06-16 | 4:00 | 4d, 6h | Periodical | Signal | T | [10 empty] | 80 | N | 2105-006 |  | 2021-08-18
DB Netz AG | 215D-015 | Rostock - Berlin | <> | Birkenwerd b Bln | Birkenwerder N | 2023 | 2023 | 27 | 27 | 2023-07-04 | 9:00 | 2023-07-05 | 15:00 | 1d, 6h | Periodical | Signal |  | ST | [9 empty] | 80 | N | 215D-015 |  | 2021-10-26
DB Netz AG | 215D-019 | Rostock - Berlin | <> | Birkenwerd b Bln | Birkenwerd b Bln | 2023 | 2023 | 27 | 27 | 2023-07-06 | 9:00 | 2023-07-06 | 15:00 | 0d, 6h | Continuous | Signal |  |  |  |  | X | [6 empty] | 80 | N | 215D-019 |  | 2021-10-26
DB Netz AG | 215D-020 | Rostock - Berlin | <> | Birkenwerd b Bln | Birkenwerd b Bln | 2023 | 2023 | 27 | 27 | 2023-07-06 | 9:00 | 2023-07-06 | 15:00 | 0d, 6h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 215D-020 |  | 2021-08-20
DB Netz AG | 215D-021 | Rostock - Berlin | <> | Birkenwerder N | Birkenwerd b Bln | 2023 | 2023 | 26 | 27 | 2023-06-30 | 9:00 | 2023-07-03 | 15:00 | 3d, 6h | Periodical | Signal |  | ST | [9 empty] | 80 | N | 215D-021 |  | 2021-10-26
DB Netz AG | 2105-007 | Rostock - Berlin | <> | Hohen Neuend Sw | Schönfließ West | 2023 | 2023 | 23 | 24 | 2023-06-11 | 22:00 | 2023-06-16 | 4:00 | 4d, 6h | Periodical | Signal | T | [10 empty] | 80 | N | 2105-007 |  | 2021-08-18
DB Netz AG | 2.2 | Rostock - Berlin | <> | Birkenwerd b Bln | Hohen Neuend W | 2023 | 2023 | 24 | 25 | 2023-06-18 | 22:00 | 2023-06-20 | 4:00 | 1d, 6h | Periodical | Signal | T | [10 empty] | 80 | N | 2.2 |  | 2021-10-26
DB Netz AG | D07-011 | Hannover - Magdeburg | > | Weddel Abzw | Schmiedekamp | 2023 | 2023 | 24 | 24 | 2023-06-16 | 21:55 | 2023-06-16 | 22:15 | 0d, 0h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | D07-011 |  | 2021-10-21
DB Netz AG | D07-004 | Hannover - Magdeburg | > | Weddel Abzw | Schmiedekamp | 2023 | 2023 | 24 | 34 | 2023-06-17 | 21:40 | 2023-08-23 | 22:00 | 67d, 0h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | D07-004 |  | 2021-10-21
DB Netz AG | D07-003 | Hannover - Magdeburg | <> | Weddel Abzw | Fallersleben | 2023 | 2023 | 24 | 34 | 2023-06-16 | 22:15 | 2023-08-24 | 22:05 | 68d, 23h | Continuous | Miscellaneous | T | [10 empty] | 80 | Y | D07-003 |  | 2021-10-21
DB Netz AG | D99-004 | Falkenberg - Dresden | <> | Coswig (bei Dre) | Radeb-Naundf Abz | 2023 | 2023 | 26 | 26 | 2023-06-28 | 6:00 | 2023-06-28 | 20:00 | 0d, 14h | Continuous | Bridge | T | [10 empty] | 80 | N | D99-004 |  | 2021-05-11
DB Netz AG | D9C-004 | Dresden - Děčín | <> | Bad Schandau | Bad Schandau Ost | 2023 | 2023 | 23 | 42 | 2023-06-05 | 16:30 | 2023-10-17 | 17:30 | 134d, 1h | Periodical | Miscellaneous | T | [10 empty] | 80 | Y | D9C-004 |  | 2021-05-29
DB Netz AG | D9C-001 | Dresden - Děčín | <> | Bad Schandau | Bad Schandau | 2023 | 2023 | 23 | 42 | 2023-06-05 | 16:30 | 2023-10-17 | 17:30 | 134d, 1h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | Y | D9C-001 |  | 2021-05-29
DB Netz AG | D9C-002 | Dresden - Děčín | <> | Bad Schandau | Bad Schandau Ost | 2023 | 2023 | 23 | 42 | 2023-06-05 | 6:30 | 2023-10-17 | 7:30 | 134d, 1h | Periodical | Miscellaneous | T | [10 empty] | 80 | Y | D9C-002 |  | 2021-06-30
DB Netz AG | D9C-005 | Dresden - Děčín | <> | Bad Schandau | Bad Schandau | 2023 | 2023 | 23 | 42 | 2023-06-05 | 6:30 | 2023-10-17 | 7:30 | 134d, 1h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | Y | D9C-005 |  | 2021-06-30
DB Netz AG | D9C-006 | Dresden - Děčín | <> | Bad Schandau Ost | Bad Schandau Ost | 2023 | 2023 | 22 | 43 | 2023-06-04 | 0:01 | 2023-10-26 | 23:59 | 144d, 23h | Continuous | Miscellaneous |  |  |  | P | [7 empty] | 80 | Y | D9C-006 |  | 2021-05-29
DB Netz AG | D9C-003 | Dresden - Děčín | <> | Bad Schandau Ost | Bad Schandau Ost | 2023 | 2023 | 22 | 43 | 2023-06-04 | 0:01 | 2023-10-26 | 23:59 | 144d, 23h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | Y | D9C-003 |  | 2021-05-29
DB Netz AG | E9F-024 | Berlin - Dresden | <> | Großenh Cott Bf | Brieske | 2023 | 2023 | 20 | 20 | 2023-05-20 | 16:00 | 2023-05-21 | 4:00 | 0d, 12h | Continuous | Signal | T | [10 empty] | 80 | N | E9F-024 |  | 2021-05-18
DB Netz AG | E9F-015 | Berlin - Dresden | <> | Großenh Cott Bf | Brieske | 2023 | 2023 | 20 | 21 | 2023-05-21 | 20:00 | 2023-05-22 | 4:00 | 0d, 8h | Continuous | Signal | T | [10 empty] | 80 | N | E9F-015 |  | 2021-05-18
DB Netz AG | ECA-009 | Bremen - Hannover | <> | Wunstorf | Wunstorf | 2023 | 2023 | 20 | 24 | 2023-05-15 | 7:00 | 2023-06-12 | 22:00 | 28d, 15h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | ECA-009 |  | 2021-06-03
DB Netz AG | ECA-001 | Bremen - Hannover | <> | Wunstorf | Wunstorf | 2023 | 2023 | 20 | 25 | 2023-05-17 | 22:00 | 2023-06-23 | 17:00 | 36d, 19h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | ECA-001 |  | 2021-06-03
DB Netz AG | F05-001 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 24 | 27 | 2023-06-12 | 4:00 | 2023-07-08 | 16:00 | 26d, 12h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | F05-001 |  | 2021-06-09
DB Netz AG | F05-002 | Dresden - Děčín | > | Dresden Hbf | Dresden Mitte | 2023 | 2023 | 24 | 27 | 2023-06-12 | 4:00 | 2023-07-08 | 16:00 | 26d, 12h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | F05-002 |  | 2021-06-09
DB Netz AG | F29-007 | Hamburg - Magdeburg | <> | Veddel | Hmb-Wlb Abzw | 2023 | 2023 | 19 | 19 | 2023-05-11 | 23:00 | 2023-05-12 | 2:00 | 0d, 3h | Continuous | Switch | T | [10 empty] | 80 | N | F29-007 |  | 2021-07-21
DB Netz AG | F29-010 | Hamburg - Magdeburg | > | Hmb-Wlb Abzw | Veddel | 2023 | 2023 | 19 | 19 | 2023-05-12 | 2:00 | 2023-05-12 | 5:00 | 0d, 3h | Continuous | Switch |  | LT | [9 empty] | 80 | N | F29-010 |  | 2021-05-23
DB Netz AG | F5A-006 | Hamburg - Magdeburg | < | Mg-Neustadt | Mg-Eichenw Üst | 2023 | 2023 | 21 | 25 | 2023-05-28 | 22:00 | 2023-06-19 | 4:00 | 21d, 6h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | F5A-006 |  | 2021-05-06
DB Netz AG | F5A-008 | Hamburg - Magdeburg | < | Mg-Rothensee | Mg-Rothensee Rmf | 2023 | 2023 | 21 | 25 | 2023-05-28 | 22:00 | 2023-06-19 | 4:00 | 21d, 6h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | F5A-008 |  | 2021-05-06
DB Netz AG | F5A-014 | Hamburg - Magdeburg | < | Mg-Rothensee Rmf | Mg-Neustadt | 2023 | 2023 | 21 | 25 | 2023-05-28 | 22:00 | 2023-06-19 | 4:00 | 21d, 6h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | F5A-014 |  | 2021-05-06
DB Netz AG | F5A-011 | Hamburg - Magdeburg | < | Mg-Eichenw Üst | Mg-Neustadt | 2023 | 2023 | 25 | 25 | 2023-06-23 | 6:30 | 2023-06-23 | 20:30 | 0d, 14h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | F5A-011 |  | 2021-05-06
DB Netz AG | F5A-001 | Hamburg - Magdeburg | > | Mg-Eichenw Üst | Mg-Neustadt | 2023 | 2023 | 19 | 21 | 2023-05-14 | 22:00 | 2023-05-22 | 4:00 | 7d, 6h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | F5A-001 |  | 2021-05-06
DB Netz AG | F5A-012 | Hamburg - Magdeburg | <> | Mg-Rothensee | Mg-Rothensee Rmf | 2023 | 2023 | 19 | 21 | 2023-05-14 | 22:00 | 2023-05-22 | 4:00 | 7d, 6h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | F5A-012 |  | 2021-05-06
DB Netz AG | F5A-004 | Hamburg - Magdeburg | < | Mg-Rothensee Rmf | Mg-Neustadt | 2023 | 2023 | 19 | 21 | 2023-05-14 | 22:00 | 2023-05-22 | 4:00 | 7d, 6h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | F5A-004 |  | 2021-05-06
DB Netz AG | F5A-003 | Hamburg - Magdeburg | > | Mg-Neustadt | Glindenberg | 2023 | 2023 | 21 | 25 | 2023-05-25 | 6:30 | 2023-06-22 | 20:30 | 28d, 14h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | F5A-003 |  | 2021-05-06
DB Netz AG | F80-008 | Dresden - Děčín | <> | Dre-Friedrichst | Dresden Mitte | 2023 | 2023 | 27 | 27 | 2023-07-08 | 16:00 | 2023-07-09 | 6:00 | 0d, 14h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | F80-008 |  | 2021-06-09
DB Netz AG | F80-011 | Dresden - Děčín | <> | Dresden-Reick | Dresden Mitte | 2023 | 2023 | 27 | 27 | 2023-07-08 | 16:00 | 2023-07-09 | 6:00 | 0d, 14h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | F80-011 |  | 2021-06-09
DB Netz AG | F80-006 | Dresden - Děčín | <> | Dresden-Altstadt | Dresden Hbf | 2023 | 2023 | 27 | 27 | 2023-07-08 | 16:00 | 2023-07-09 | 6:00 | 0d, 14h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | F80-006 |  | 2021-07-01
DB Netz AG | F80-003 | Dresden - Děčín | <> | Dre-Reick Abstbf | Dre-Neustadt | 2023 | 2023 | 27 | 27 | 2023-07-08 | 16:00 | 2023-07-09 | 6:00 | 0d, 14h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | F80-003 |  | 2021-06-09
DB Netz AG | F80-009 | Dresden - Děčín | <> | Dresden-Altstadt | Dre Freibg Str | 2023 | 2023 | 27 | 27 | 2023-07-08 | 16:00 | 2023-07-09 | 6:00 | 0d, 14h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | F80-009 |  | 2021-06-08
DB Netz AG | F80-010 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 27 | 27 | 2023-07-08 | 16:00 | 2023-07-09 | 6:00 | 0d, 14h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | F80-010 |  | 2021-06-08
DB Netz AG | F80-007 | Dresden - Děčín | <> | Dresden Hbf | Dre-Neustadt | 2023 | 2023 | 27 | 27 | 2023-07-08 | 16:00 | 2023-07-09 | 6:00 | 0d, 14h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | F80-007 |  | 2021-06-09
DB Netz AG | F80-004 | Dresden - Děčín | <> | Dre-Friedrichst | Dre Freibg Str | 2023 | 2023 | 27 | 27 | 2023-07-08 | 16:00 | 2023-07-09 | 6:00 | 0d, 14h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | F80-004 |  | 2021-06-09
DB Netz AG | F80-001 | Berlin - Dresden | <> | Dre-Neustadt | Dre-Neustadt Gbf | 2023 | 2023 | 27 | 27 | 2023-07-08 | 16:00 | 2023-07-09 | 6:00 | 0d, 14h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | F80-001 |  | 2021-07-01
DB Netz AG | F80-002 | Dresden - Děčín | <> | Dresden-Altstadt | Dresden Hbf | 2023 | 2023 | 27 | 27 | 2023-07-08 | 5:00 | 2023-07-08 | 16:00 | 0d, 11h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | F80-002 |  | 2021-06-08
DB Netz AG | F80-005 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 27 | 27 | 2023-07-08 | 5:00 | 2023-07-08 | 16:00 | 0d, 11h | Continuous | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | F80-005 |  | 2021-06-08
DB Netz AG | F9B-001 | Falkenberg - Dresden | <> | Coswig (bei Dre) | Radebeul Nord | 2023 | 2023 | 26 | 26 | 2023-06-26 | 6:00 | 2023-06-27 | 20:00 | 1d, 14h | Periodical | Bridge | T | [10 empty] | 80 | N | F9B-001 |  | 2021-05-12
DB Netz AG | F9B-003 | Falkenberg - Dresden | <> | Coswig (bei Dre) | Radebeul Nord | 2023 | 2023 | 26 | 26 | 2023-06-26 | 6:00 | 2023-06-27 | 20:00 | 1d, 14h | Periodical | Bridge | T | [10 empty] | 80 | N | F9B-003 |  | 2021-05-11
DB Netz AG | F9B-002 | Falkenberg - Dresden | <> | Coswig (bei Dre) | Coswig (bei Dre) | 2023 | 2023 | 26 | 26 | 2023-06-26 | 6:00 | 2023-06-27 | 20:00 | 1d, 14h | Periodical | Bridge |  | ST | [9 empty] | 80 | N | F9B-002 |  | 2021-05-11
DB Netz AG | F9B-004 | Falkenberg - Dresden | <> | Coswig (bei Dre) | Coswig (bei Dre) | 2023 | 2023 | 26 | 26 | 2023-06-26 | 6:00 | 2023-06-27 | 20:00 | 1d, 14h | Periodical | Bridge |  | ST | [9 empty] | 80 | N | F9B-004 |  | 2021-05-11
DB Netz AG | FA4-014 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 27 | 27 | 2023-07-06 | 3:30 | 2023-07-06 | 5:30 | 0d, 2h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | FA4-014 |  | 2021-05-26
DB Netz AG | FA4-041 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 27 | 27 | 2023-07-06 | 3:30 | 2023-07-06 | 5:30 | 0d, 2h | Continuous | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | FA4-041 |  | 2021-05-26
DB Netz AG | FA4-042 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 27 | 32 | 2023-07-06 | 21:30 | 2023-08-12 | 5:30 | 36d, 8h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | FA4-042 |  | 2021-05-27
DB Netz AG | FA4-043 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 27 | 32 | 2023-07-06 | 21:30 | 2023-08-12 | 5:30 | 36d, 8h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | FA4-043 |  | 2021-05-27
DB Netz AG | FA4-044 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 27 | 32 | 2023-07-06 | 21:30 | 2023-08-12 | 5:30 | 36d, 8h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | FA4-044 |  | 2021-05-27
DB Netz AG | FA4-030 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 27 | 32 | 2023-07-06 | 21:30 | 2023-08-12 | 5:30 | 36d, 8h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | FA4-030 |  | 2021-05-27
DB Netz AG | FA4-021 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 27 | 33 | 2023-07-06 | 5:30 | 2023-08-14 | 5:30 | 39d, 0h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | FA4-021 |  | 2021-05-27
DB Netz AG | FA4-016 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 27 | 33 | 2023-07-06 | 5:30 | 2023-08-14 | 5:30 | 39d, 0h | Continuous | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | FA4-016 |  | 2021-05-27
DB Netz AG | FA4-035 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 27 | 33 | 2023-07-06 | 5:30 | 2023-08-14 | 5:30 | 39d, 0h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | FA4-035 |  | 2021-05-27
DB Netz AG | FA4-012 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 26 | 27 | 2023-07-01 | 7:00 | 2023-07-05 | 20:00 | 4d, 13h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | FA4-012 |  | 2021-05-27
DB Netz AG | FC8-001 | Falkenberg - Dresden | <> | Weißig (b Groß) | Priestewitz | 2023 | 2023 | 24 | 24 | 2023-06-13 | 0:00 | 2023-06-13 | 3:00 | 0d, 3h | Continuous | Track & Rail | T | [10 empty] | 80 | N | FC8-001 |  | 2021-05-21
DB Netz AG | FC8-005 | Falkenberg - Dresden | <> | Kottewitz | Leckwitz | 2023 | 2023 | 24 | 24 | 2023-06-13 | 0:00 | 2023-06-13 | 3:00 | 0d, 3h | Continuous | Track & Rail | T | [10 empty] | 80 | N | FC8-005 |  | 2021-05-21
DB Netz AG | FC8-003 | Magdeburg - Falkenberg | <> | Zeithain Bogendr | Röderau | 2023 | 2023 | 24 | 24 | 2023-06-16 | 2:00 | 2023-06-16 | 5:00 | 0d, 3h | Continuous | Track & Rail | T | [10 empty] | 80 | N | FC8-003 |  | 2021-05-21
DB Netz AG | FC8-002 | Falkenberg - Dresden | <> | Rohrwerk | Zeithain Bogendr | 2023 | 2023 | 24 | 24 | 2023-06-16 | 2:00 | 2023-06-16 | 5:00 | 0d, 3h | Continuous | Track & Rail | T | [10 empty] | 80 | N | FC8-002 |  | 2021-05-21
DB Netz AG | FC8-007 | Falkenberg - Dresden | < | Zeithain Bogendr | Riesa | 2023 | 2023 | 24 | 24 | 2023-06-16 | 2:00 | 2023-06-16 | 5:00 | 0d, 3h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | FC8-007 |  | 2021-05-21
DB Netz AG | FC8-008 | Falkenberg - Dresden | < | Leckwitz | Zeithain Bogendr | 2023 | 2023 | 24 | 24 | 2023-06-12 | 21:00 | 2023-06-16 | 5:00 | 3d, 8h | Periodical | Track & Rail |  | LT | [9 empty] | 80 | N | FC8-008 |  | 2021-05-21
DB Netz AG | FC8-006 | Falkenberg - Dresden | > | Kottewitz | Weißig (b Groß) | 2023 | 2023 | 24 | 24 | 2023-06-12 | 21:00 | 2023-06-13 | 0:01 | 0d, 3h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | FC8-006 |  | 2021-05-21
DB Netz AG | 10CC-001 | Dresden - Děčín | <> | Dresden-Altstadt | Dresden Hbf | 2023 | 2023 | 23 | 24 | 2023-06-09 | 4:00 | 2023-06-12 | 4:00 | 3d, 0h | Continuous | Signal | T | [10 empty] | 80 | N | 10CC-001 |  | 2021-06-11
DB Netz AG | 10CC-004 | Berlin - Dresden | <> | Dre-Neustadt | Dre-Neustadt Gbf | 2023 | 2023 | 23 | 24 | 2023-06-09 | 4:00 | 2023-06-12 | 4:00 | 3d, 0h | Continuous | Signal | T | [10 empty] | 80 | N | 10CC-004 |  | 2021-06-11
DB Netz AG | 10CC-002 | Dresden - Děčín | <> | Dre-Friedrichst | Dre Freibg Str | 2023 | 2023 | 23 | 24 | 2023-06-09 | 4:00 | 2023-06-12 | 4:00 | 3d, 0h | Continuous | Signal | T | [10 empty] | 80 | N | 10CC-002 |  | 2021-06-11
DB Netz AG | 10CC-003 | Dresden - Děčín | <> | Dre-Reick Abstbf | Dre-Neustadt | 2023 | 2023 | 23 | 24 | 2023-06-09 | 4:00 | 2023-06-12 | 4:00 | 3d, 0h | Continuous | Signal | T | [10 empty] | 80 | N | 10CC-003 |  | 2021-06-11
DB Netz AG | 10CC-009 | Dresden - Děčín | <> | Dresden-Altstadt | Dresden Hbf | 2023 | 2023 | 23 | 24 | 2023-06-09 | 4:00 | 2023-06-12 | 4:00 | 3d, 0h | Continuous | Signal | T | [10 empty] | 80 | N | 10CC-009 |  | 2021-06-11
DB Netz AG | 10CC-008 | Dresden - Děčín | <> | Dresden-Reick | Dre-Neustadt | 2023 | 2023 | 23 | 24 | 2023-06-09 | 4:00 | 2023-06-12 | 4:00 | 3d, 0h | Continuous | Signal | T | [10 empty] | 80 | N | 10CC-008 |  | 2021-06-11
DB Netz AG | 10CC-006 | Dresden - Děčín | <> | Dre-Friedrichst | Dresden Mitte | 2023 | 2023 | 23 | 24 | 2023-06-09 | 4:00 | 2023-06-12 | 4:00 | 3d, 0h | Continuous | Signal | T | [10 empty] | 80 | N | 10CC-006 |  | 2021-06-11
DB Netz AG | 10CC-005 | Dresden - Děčín | <> | Dresden-Altstadt | Dre Freibg Str | 2023 | 2023 | 23 | 24 | 2023-06-09 | 4:00 | 2023-06-12 | 4:00 | 3d, 0h | Continuous | Signal | T | [10 empty] | 80 | N | 10CC-005 |  | 2021-06-11
DB Netz AG | 10CC-007 | Dresden - Děčín | <> | Dresden Hbf | Dre-Neustadt | 2023 | 2023 | 23 | 24 | 2023-06-09 | 4:00 | 2023-06-12 | 4:00 | 3d, 0h | Continuous | Signal | T | [10 empty] | 80 | N | 10CC-007 |  | 2021-06-11
DB Netz AG | 10CF-002 | Dresden - Děčín | <> | Schöna | Schöna | 2023 | 2023 | 22 | 22 | 2023-06-03 | 18:00 | 2023-06-04 | 8:00 | 0d, 14h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 10CF-002 |  | 2021-05-28
DB Netz AG | 10CF-003 | Dresden - Děčín | <> | Bad Schandau | Bad Schandau Gr | 2023 | 2023 | 22 | 22 | 2023-06-03 | 18:00 | 2023-06-04 | 8:00 | 0d, 14h | Continuous | Signal | T | [10 empty] | 80,54 | N | 10CF-003 |  | 2021-05-28
DB Netz AG | 10CF-001 | Dresden - Děčín | <> | Bad Schandau Ost | Bad Schandau Ost | 2023 | 2023 | 22 | 22 | 2023-06-03 | 18:00 | 2023-06-04 | 8:00 | 0d, 14h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 10CF-001 |  | 2021-05-28
DB Netz AG | 10ED-005 | Dresden - Děčín | <> | Dre-Neustadt | Dresden Hbf | 2023 | 2023 | 22 | 22 | 2023-06-03 | 20:00 | 2023-06-04 | 5:00 | 0d, 9h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 10ED-005 |  | 2021-06-11
DB Netz AG | 10ED-008 | Dresden - Děčín | <> | Dre Freibg Str | Dresden-Altstadt | 2023 | 2023 | 22 | 23 | 2023-06-03 | 5:00 | 2023-06-09 | 4:00 | 5d, 23h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | 10ED-008 |  | 2021-06-11
DB Netz AG | 10ED-009 | Dresden - Děčín | <> | Dresden Hbf | Dresden Mitte | 2023 | 2023 | 22 | 23 | 2023-06-03 | 5:00 | 2023-06-09 | 4:00 | 5d, 23h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | 10ED-009 |  | 2021-06-11
DB Netz AG | 10ED-010 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 22 | 23 | 2023-06-03 | 5:00 | 2023-06-09 | 4:00 | 5d, 23h | Continuous | Miscellaneous |  |  |  | P | [7 empty] | 80 | N | 10ED-010 |  | 2021-06-11
DB Netz AG | 10ED-001 | Dresden - Děčín | <> | Dre Freibg Str | Dre-Friedrichst | 2023 | 2023 | 22 | 23 | 2023-06-03 | 5:00 | 2023-06-09 | 4:00 | 5d, 23h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | 10ED-001 |  | 2021-06-11
DB Netz AG | 10ED-004 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 23 | 23 | 2023-06-08 | 22:00 | 2023-06-09 | 4:00 | 0d, 6h | Continuous | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 10ED-004 |  | 2021-06-11
DB Netz AG | 10ED-002 | Dresden - Děčín | < | Dresden-Altstadt | Dresden Hbf | 2023 | 2023 | 23 | 23 | 2023-06-08 | 22:00 | 2023-06-09 | 4:00 | 0d, 6h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 10ED-002 |  | 2021-06-11
DB Netz AG | 10ED-006 | Dresden - Děčín | <> | Dresden Hbf | Dresden Mitte | 2023 | 2023 | 23 | 23 | 2023-06-08 | 22:00 | 2023-06-09 | 4:00 | 0d, 6h | Continuous | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 10ED-006 |  | 2021-06-11
DB Netz AG | 10ED-007 | Dresden - Děčín | <> | Dresden Hbf | Dresden Mitte | 2023 | 2023 | 23 | 23 | 2023-06-08 | 22:00 | 2023-06-09 | 4:00 | 0d, 6h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | 10ED-007 |  | 2021-06-11
DB Netz AG | 1113-002 | Dresden - Děčín | < | Bad Schandau | Bad Schandau Ost | 2023 | 2023 | 19 | 19 | 2023-05-10 | 23:00 | 2023-05-13 | 5:00 | 2d, 6h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | 1113-002 |  | 2021-05-28
DB Netz AG | 1113-018 | Dresden - Děčín | < | Bad Schandau Ost | Bad Schandau Ost | 2023 | 2023 | 19 | 19 | 2023-05-10 | 23:00 | 2023-05-13 | 5:00 | 2d, 6h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1113-018 |  | 2021-05-28
DB Netz AG | 1113-013 | Dresden - Děčín | < | Bad Schandau | Bad Schandau Ost | 2023 | 2023 | 19 | 19 | 2023-05-10 | 23:00 | 2023-05-13 | 5:00 | 2d, 6h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 1113-013 |  | 2021-05-28
DB Netz AG | 1113-014 | Dresden - Děčín | <> | Bad Schandau | Bad Schandau Gr | 2023 | 2023 | 19 | 19 | 2023-05-10 | 23:00 | 2023-05-13 | 5:00 | 2d, 6h | Periodical | Miscellaneous |  |  |  | P | [7 empty] | 80,54 | N | 1113-014 |  | 2021-05-28
DB Netz AG | 1113-007 | Dresden - Děčín | < | Bad Schandau | Bad Schandau | 2023 | 2023 | 19 | 19 | 2023-05-10 | 23:00 | 2023-05-13 | 5:00 | 2d, 6h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1113-007 |  | 2021-05-28
DB Netz AG | 15DB-001 | Hamburg - Magdeburg | <> | Meckelfeld | Hmb-Harburg | 2023 | 2023 | 25 | 27 | 2023-06-24 | 22:00 | 2023-07-03 | 6:00 | 8d, 8h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | 15DB-001 |  | 2021-05-26
DB Netz AG | 15DB-002 | Hamburg - Magdeburg | <> | Meckelfeld | Hmb-Harburg | 2023 | 2023 | 22 | 24 | 2023-06-02 | 22:00 | 2023-06-12 | 4:00 | 9d, 6h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | 15DB-002 |  | 2021-05-25
DB Netz AG | 15DB-003 | Hamburg - Magdeburg | < | Hmb-Harburg | Meckelfeld | 2023 | 2023 | 25 | 27 | 2023-06-24 | 20:00 | 2023-07-03 | 6:00 | 8d, 10h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | 15DB-003 |  | 2021-07-27
DB Netz AG | 15DB-004 | Hamburg - Magdeburg | < | Hmb-Harburg | Meckelfeld | 2023 | 2023 | 24 | 25 | 2023-06-12 | 22:00 | 2023-06-19 | 4:00 | 6d, 6h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 15DB-004 |  | 2021-07-27
DB Netz AG | 15DB-005 | Hamburg - Magdeburg | > | Meckelfeld | Hmb-Harburg | 2023 | 2023 | 25 | 27 | 2023-06-24 | 22:00 | 2023-07-03 | 6:00 | 8d, 8h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | 15DB-005 |  | 2021-07-27
DB Netz AG | 15DB-006 | Hamburg - Magdeburg | > | Meckelfeld | Hmb-Harburg | 2023 | 2023 | 24 | 25 | 2023-06-12 | 22:00 | 2023-06-19 | 4:00 | 6d, 6h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 15DB-006 |  | 2021-07-27
DB Netz AG | 1286-003 | Magdeburg - Falkenberg | <> | Fak unt Bf W 15 | Fak unt Bf B 20 | 2023 | 2023 | 24 | 24 | 2023-06-12 | 9:00 | 2023-06-12 | 12:00 | 0d, 3h | Continuous | Bridge |  | ST | [9 empty] | 80 | N | 1286-003
DB Netz AG | 1286-001 | Magdeburg - Falkenberg | > | Wahrenbrück | Fak unt Bf B 20 | 2023 | 2023 | 24 | 24 | 2023-06-12 | 9:00 | 2023-06-12 | 12:00 | 0d, 3h | Continuous | Bridge |  | LT | [9 empty] | 80 | N | 1286-001
DB Netz AG | 1286-002 | Magdeburg - Falkenberg | <> | Falkenberg ob Bf | Fak unt Bf W 17 | 2023 | 2023 | 24 | 24 | 2023-06-12 | 9:00 | 2023-06-12 | 12:00 | 0d, 3h | Continuous | Bridge |  |  |  |  | X | [6 empty] | 80 | N | 1286-002
DB Netz AG | 1289-006 | Magdeburg - Falkenberg | < | Fermerswalde | Fermerswalde | 2023 | 2023 | 19 | 19 | 2023-05-13 | 22:00 | 2023-05-14 | 4:00 | 0d, 6h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1289-006 |  | 2021-04-06
DB Netz AG | 12B0-001 | Magdeburg - Falkenberg | <> | Lu Wittenberg | Lu Wittenberg | 2023 | 2023 | 27 | 27 | 2023-07-05 | 0:00 | 2023-07-05 | 4:00 | 0d, 4h | Continuous | Switch | T | [10 empty] | 80 | N | 12B0-001 |  | 2021-05-04
DB Netz AG | 12B0-005 | Magdeburg - Falkenberg | < | Lu Wb-Piesteritz | Lu Wittenberg | 2023 | 2023 | 27 | 27 | 2023-07-04 | 20:00 | 2023-07-05 | 4:00 | 0d, 8h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 12B0-005 |  | 2021-05-04
DB Netz AG | 12B0-007 | Magdeburg - Falkenberg | <> | Lu Wittenberg | Lu Wittenberg | 2023 | 2023 | 27 | 27 | 2023-07-04 | 16:00 | 2023-07-05 | 4:00 | 0d, 12h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 12B0-007 |  | 2021-05-04
DB Netz AG | 12B0-003 | Magdeburg - Falkenberg | < | Lu Wb-Pieste Wbf | Lu Wittenberg | 2023 | 2023 | 27 | 27 | 2023-07-04 | 20:00 | 2023-07-05 | 4:00 | 0d, 8h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 12B0-003 |  | 2021-05-04
DB Netz AG | D99-003 | Falkenberg - Dresden | <> | Coswig (bei Dre) | Radeb-Naundf Abz | 2023 | 2023 | 26 | 26 | 2023-06-28 | 6:00 | 2023-06-28 | 20:00 | 0d, 14h | Continuous | Bridge |  |  |  |  | X | [6 empty] | 80 | N | D99-003 |  | 2020-09-30
DB Netz AG | D99-005 | Falkenberg - Dresden | <> | Coswig (bei Dre) | Coswig (bei Dre) | 2023 | 2023 | 26 | 26 | 2023-06-28 | 6:00 | 2023-06-28 | 20:00 | 0d, 14h | Continuous | Bridge |  |  |  |  | X | [6 empty] | 80 | N | D99-005 |  | 2020-09-30
DB Netz AG | 12E5-004 | Berlin - Dresden | > | Zahna | Lu Wittenberg | 2023 | 2023 | 22 | 23 | 2023-06-01 | 21:00 | 2023-06-11 | 5:00 | 9d, 8h | Continuous | Signal |  |  | S | [8 empty] | 80 | N | 12E5-004 |  | 2021-05-13
DB Netz AG | 12E5-005 | Berlin - Dresden | < | Lu Wittenberg | Zahna | 2023 | 2023 | 24 | 25 | 2023-06-14 | 21:00 | 2023-06-22 | 5:00 | 7d, 8h | Continuous | Signal |  |  | S | [8 empty] | 80 | N | 12E5-005 |  | 2021-05-13
DB Netz AG | 130D-002 | Magdeburg - Falkenberg | < | Lu Wb-Pieste Wbf | Lu Wittenberg | 2023 | 2023 | 19 | 20 | 2023-05-10 | 23:00 | 2023-05-16 | 5:00 | 5d, 6h | Periodical | Signal |  | LT | [9 empty] | 80 | N | 130D-002 |  | 2021-05-17
DB Netz AG | 13 | Magdeburg - Falkenberg | <> | Lu Wittenberg | Lu Wittenberg | 2023 | 2023 | 20 | 20 | 2023-05-17 | 6:00 | 2023-05-19 | 22:00 | 2d, 16h | Periodical | Signal |  | ST | [9 empty] | 80 | N | 13 |  | 2021-05-21
DB Netz AG | FC8-004 | Falkenberg - Dresden | <> | Zeithain Bogendr | Riesa | 2023 | 2023 | 24 | 24 | 2023-06-16 | 2:00 | 2023-06-16 | 5:00 | 0d, 3h | Continuous | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | FC8-004 |  | 2021-05-21
DB Netz AG | C5F-004 | Dresden - Děčín | <> | Bad Schandau | Bad Schandau | 2023 | 2023 | 27 | 30 | 2023-07-03 | 23:00 | 2023-07-25 | 5:00 | 21d, 6h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | C5F-004 |  | 2021-05-21
DB Netz AG | A7D-004 | Hamburg - Magdeburg | <> | Salzwedel Gbf | Salzwedel | 2023 | 2023 | 19 | 20 | 2023-05-13 | 5:00 | 2023-05-15 | 5:00 | 2d, 0h | Continuous | Signal | T | [10 empty] | 80 | N | A7D-004 |  | 2020-09-30
DB Netz AG | A7D-002 | Hamburg - Magdeburg | <> | Salzwedel Gbf | Salzwedel | 2023 | 2023 | 19 | 20 | 2023-05-13 | 5:00 | 2023-05-15 | 5:00 | 2d, 0h | Continuous | Signal | T | [10 empty] | 80 | N | A7D-002 |  | 2020-09-30
DB Netz AG | 10CF-004 | Dresden - Děčín | <> | Dolni Zleb | Bad Schandau Gr | 2023 | 2023 | 22 | 22 | 2023-06-03 | 18:00 | 2023-06-04 | 8:00 | 0d, 14h | Continuous | Signal | T | [10 empty] | 80,54,80,54 | N | 10CF-004 |  | 2020-09-29
DB Netz AG | C03-003 | Hamburg - Magdeburg | <> | Stendal Hbf | Veerßen | 2023 | 2023 | 19 | 19 | 2023-05-12 | 21:00 | 2023-05-13 | 5:00 | 0d, 8h | Continuous | Signal | T | [10 empty] | 80 | N | C03-003 |  | 2021-06-02
DB Netz AG | C03-004 | Hamburg - Magdeburg | <> | Wieren | Bodenteich | 2023 | 2023 | 19 | 19 | 2023-05-12 | 21:00 | 2023-05-13 | 5:00 | 0d, 8h | Continuous | Signal | T | [10 empty] | 80 | N | C03-004 |  | 2020-09-30
DB Netz AG | C03-005 | Hamburg - Magdeburg | <> | Salzwedel Gbf | Ritze DB-Grenze | 2023 | 2023 | 19 | 19 | 2023-05-12 | 21:00 | 2023-05-13 | 5:00 | 0d, 8h | Continuous | Signal | T | [10 empty] | 80 | N | C03-005 |  | 2020-09-30
DB Netz AG | CB9-004 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 27 | 32 | 2023-07-09 | 6:00 | 2023-08-12 | 14:00 | 34d, 8h | Continuous | Miscellaneous |  |  |  | P | [7 empty] | 80 | Y | CB9-004 |  | 2021-06-08
DB Netz AG | CB9-005 | Dresden - Děčín | <> | Dresden Hbf | Dre Freibg Str | 2023 | 2023 | 27 | 32 | 2023-07-09 | 6:00 | 2023-08-12 | 14:00 | 34d, 8h | Continuous | Miscellaneous |  |  |  | P | [7 empty] | 80 | Y | CB9-005 |  | 2021-06-08
DB Netz AG | CB9-006 | Dresden - Děčín | <> | Dresden Hbf | Dresden Mitte | 2023 | 2023 | 27 | 32 | 2023-07-09 | 6:00 | 2023-08-12 | 14:00 | 34d, 8h | Continuous | Miscellaneous |  |  |  | P | [7 empty] | 80 | Y | CB9-006 |  | 2021-06-08
DB Netz AG | CB9-007 | Dresden - Děčín | <> | Dresden Hbf | Dre Freibg Str | 2023 | 2023 | 27 | 32 | 2023-07-09 | 6:00 | 2023-08-12 | 14:00 | 34d, 8h | Continuous | Miscellaneous |  |  |  | P | [7 empty] | 80 | Y | CB9-007 |  | 2021-06-08
DB Netz AG | F80-013 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 27 | 27 | 2023-07-08 | 5:00 | 2023-07-08 | 16:00 | 0d, 11h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | F80-013 |  | 2021-06-08
DB Netz AG | F05-003 | Dresden - Děčín | < | Dresden Hbf | Dresden Mitte | 2023 | 2023 | 24 | 27 | 2023-06-12 | 4:00 | 2023-07-08 | 16:00 | 26d, 12h | Continuous | Miscellaneous |  |  |  | P | [7 empty] | 80 | Y | F05-003 |  | 2021-06-09
DB Netz AG | F05-004 | Dresden - Děčín | <> | Dresden Hbf | Dresden Mitte | 2023 | 2023 | 24 | 27 | 2023-06-12 | 4:00 | 2023-07-08 | 16:00 | 26d, 12h | Continuous | Miscellaneous |  |  |  | P | [7 empty] | 80 | Y | F05-004 |  | 2021-06-09
DB Netz AG | F05-005 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 24 | 27 | 2023-06-12 | 4:00 | 2023-07-08 | 16:00 | 26d, 12h | Continuous | Miscellaneous |  |  |  | P | [7 empty] | 80 | Y | F05-005 |  | 2021-06-09
DB Netz AG | F05-006 | Dresden - Děčín | <> | Dresden Hbf | Dresden Mitte | 2023 | 2023 | 24 | 27 | 2023-06-12 | 4:00 | 2023-07-08 | 16:00 | 26d, 12h | Continuous | Miscellaneous |  |  |  | P | [7 empty] | 80 | Y | F05-006 |  | 2021-06-09
DB Netz AG | CB3-011 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 24 | 24 | 2023-06-13 | 0:00 | 2023-06-13 | 5:00 | 0d, 5h | Continuous | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | CB3-011 |  | 2021-06-10
DB Netz AG | CB3-012 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 24 | 24 | 2023-06-13 | 0:00 | 2023-06-13 | 5:00 | 0d, 5h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | CB3-012 |  | 2021-06-10
DB Netz AG | CB3-013 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 24 | 24 | 2023-06-13 | 0:00 | 2023-06-13 | 5:00 | 0d, 5h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | CB3-013 |  | 2021-06-10
DB Netz AG | CB3-014 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 24 | 24 | 2023-06-13 | 0:00 | 2023-06-13 | 5:00 | 0d, 5h | Continuous | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | CB3-014 |  | 2021-06-10
DB Netz AG | CB3-015 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 24 | 24 | 2023-06-17 | 4:15 | 2023-06-17 | 5:00 | 0d, 0h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | CB3-015 |  | 2021-06-10
DB Netz AG | CB3-016 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 24 | 24 | 2023-06-17 | 4:15 | 2023-06-17 | 5:00 | 0d, 0h | Continuous | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | CB3-016 |  | 2021-10-06
DB Netz AG | CB3-017 | Dresden - Děčín | < | Dresden Mitte | Dresden Hbf | 2023 | 2023 | 24 | 24 | 2023-06-16 | 22:00 | 2023-06-18 | 5:00 | 1d, 7h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | CB3-017 |  | 2020-09-30
DB Netz AG | 10ED-011 | Dresden - Děčín | <> | Dresden Mitte | Dresden Hbf | 2023 | 2023 | 22 | 23 | 2023-06-03 | 5:00 | 2023-06-09 | 4:00 | 5d, 23h | Continuous | Miscellaneous |  |  |  | P | [7 empty] | 80 | N | 10ED-011 |  | 2021-06-11
DB Netz AG | 10CC-012 | Dresden - Děčín | <> | Schöna | Dre-Neustadt | 2023 | 2023 | 24 | 24 | 2023-06-12 | 0:00 | 2023-06-12 | 4:00 | 0d, 4h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 10CC-012 |  | 2021-06-11
DB Netz AG | 10CC-014 | Falkenberg - Dresden | <> | Dre-Neustadt | Radebeul Nord | 2023 | 2023 | 24 | 24 | 2023-06-12 | 0:00 | 2023-06-12 | 4:00 | 0d, 4h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 10CC-014 |  | 2021-06-11
DB Netz AG | 10CC-015 | Berlin - Dresden | <> | Hohenleipisch | Az | 2023 | 2023 | 24 | 24 | 2023-06-12 | 0:00 | 2023-06-12 | 4:00 | 0d, 4h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 10CC-015 |  | 2021-06-11
DB Netz AG | 10CC-016 | Dresden - Děčín | <> | Heidenau | Dohna (Sachs) | 2023 | 2023 | 24 | 24 | 2023-06-12 | 0:00 | 2023-06-12 | 4:00 | 0d, 4h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 10CC-016 |  | 2021-06-11
DB Netz AG | 10CC-017 | Dresden - Děčín | <> | Sebnitz (Sachs) | Bad Schandau | 2023 | 2023 | 24 | 24 | 2023-06-12 | 0:00 | 2023-06-12 | 4:00 | 0d, 4h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 10CC-017 |  | 2021-06-11
DB Netz AG | 10CC-019 | Falkenberg - Dresden | <> | Dre-Neustadt | Radebeul Nord | 2023 | 2023 | 24 | 24 | 2023-06-12 | 0:00 | 2023-06-12 | 4:00 | 0d, 4h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 10CC-019 |  | 2021-06-11
DB Netz AG | 10CC-020 | Berlin - Dresden | <> | Az | Radebeul Nord | 2023 | 2023 | 24 | 24 | 2023-06-12 | 0:00 | 2023-06-12 | 4:00 | 0d, 4h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 10CC-020 |  | 2021-06-11
DB Netz AG | 10CC-021 | Dresden - Děčín | <> | Dre-Neustadt | Dresden Hbf | 2023 | 2023 | 24 | 24 | 2023-06-12 | 0:00 | 2023-06-12 | 4:00 | 0d, 4h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 10CC-021 |  | 2021-06-11
DB Netz AG | 10CC-022 | Dresden - Děčín | <> | Dre-Neustadt | Dre-Klotzsch Bbf | 2023 | 2023 | 24 | 24 | 2023-06-12 | 0:00 | 2023-06-12 | 4:00 | 0d, 4h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 10CC-022 |  | 2021-06-11
DB Netz AG | 10CC-023 | Berlin - Dresden | <> | Dre-Pieschen Abz | Dre-Neustadt | 2023 | 2023 | 24 | 24 | 2023-06-12 | 0:00 | 2023-06-12 | 4:00 | 0d, 4h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 10CC-023 |  | 2021-06-11
DB Netz AG | 10CC-024 | Falkenberg - Dresden | <> | Leckwitz | Kottewitz | 2023 | 2023 | 24 | 24 | 2023-06-12 | 0:00 | 2023-06-12 | 4:00 | 0d, 4h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 10CC-024 |  | 2021-06-11
DB Netz AG | 1437-002 | Magdeburg - Falkenberg | < | Fermerswalde | Fak unt Bf W 26 | 2023 | 2023 | 19 | 19 | 2023-05-12 | 10:00 | 2023-05-12 | 16:00 | 0d, 6h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 1437-002 |  | 2021-05-21
DB Netz AG | 1437-003 | Magdeburg - Falkenberg | < | Fermerswalde | Fermerswalde | 2023 | 2023 | 19 | 19 | 2023-05-13 | 10:00 | 2023-05-13 | 16:00 | 0d, 6h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 1437-003 |  | 2021-07-29
DB Netz AG | 1437-004 | Magdeburg - Falkenberg | < | Annaburg | Fermerswalde | 2023 | 2023 | 19 | 20 | 2023-05-14 | 10:00 | 2023-05-15 | 16:00 | 1d, 6h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | 1437-004 |  | 2021-06-30
DB Netz AG | 1437-005 | Magdeburg - Falkenberg | < | Jessen (Elster) | Annaburg | 2023 | 2023 | 20 | 20 | 2023-05-16 | 10:00 | 2023-05-17 | 16:00 | 1d, 6h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | 1437-005 |  | 2021-06-30
DB Netz AG | 1470-001 | Magdeburg - Falkenberg | < | Coswig (Anh) Gbf | Lu Wb-P Wbf West | 2023 | 2023 | 21 | 21 | 2023-05-24 | 22:00 | 2023-05-25 | 6:00 | 0d, 8h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 1470-001 |  | 2021-09-14
DB Netz AG | 146B-001 | Magdeburg - Falkenberg | > | Lu Wb-P Wbf West | Coswig (Anh) Gbf | 2023 | 2023 | 20 | 20 | 2023-05-20 | 22:00 | 2023-05-21 | 6:00 | 0d, 8h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 146B-001 |  | 2021-09-17
DB Netz AG | 1463-001 | Magdeburg - Falkenberg | > | Coswig (Anh) Gbf | Meinsdorf | 2023 | 2023 | 20 | 21 | 2023-05-21 | 22:00 | 2023-05-22 | 6:00 | 0d, 8h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 1463-001 |  | 2021-09-14
DB Netz AG | 1462-001 | Magdeburg - Falkenberg | < | Meinsdorf | Coswig (Anh) Gbf | 2023 | 2023 | 21 | 21 | 2023-05-23 | 22:00 | 2023-05-24 | 6:00 | 0d, 8h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 1462-001 |  | 2021-09-14
DB Netz AG | 1506-001 | Hannover - Magdeburg | <> | Hannover-Linden | Hannover-Linden | 2023 | 2023 | 20 | 24 | 2023-05-15 | 7:00 | 2023-06-12 | 22:00 | 28d, 15h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1506-001 |  | 2021-04-28
DB Netz AG | 1506-002 | Hannover - Magdeburg | <> | Hannover-Linden | Hannover-Linden | 2023 | 2023 | 20 | 24 | 2023-05-15 | 7:00 | 2023-06-12 | 22:00 | 28d, 15h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1506-002 |  | 2021-04-28
DB Netz AG | 1463-002 | Magdeburg - Falkenberg | <> | Roßlau(Elbe) Gbf | Roßlau(Elbe) Gbf | 2023 | 2023 | 21 | 21 | 2023-05-22 | 22:00 | 2023-05-23 | 6:00 | 0d, 8h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 1463-002 |  | 2021-09-14
DB Netz AG | 1640-013 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 20 | 20 | 2023-05-15 | 20:00 | 2023-05-18 | 5:00 | 2d, 9h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 1640-013
DB Netz AG | 1640-014 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 20 | 20 | 2023-05-15 | 20:00 | 2023-05-18 | 5:00 | 2d, 9h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 1640-014
DB Netz AG | 1640-015 | Dresden - Děčín | > | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 20 | 20 | 2023-05-15 | 20:00 | 2023-05-18 | 5:00 | 2d, 9h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 1640-015
DB Netz AG | 1640-016 | Dresden - Děčín | > | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 20 | 20 | 2023-05-15 | 20:00 | 2023-05-18 | 5:00 | 2d, 9h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 1640-016
DB Netz AG | 1642-001 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 26 | 26 | 2023-06-26 | 23:00 | 2023-06-29 | 5:00 | 2d, 6h | Periodical | Catenary | T | [10 empty] | 80 | N | 1642-001 |  | 2021-05-20
DB Netz AG | 1642-002 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 26 | 26 | 2023-06-26 | 23:00 | 2023-06-29 | 5:00 | 2d, 6h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 1642-002 |  | 2021-05-20
DB Netz AG | 1437-008 | Magdeburg - Falkenberg | < | Fermerswalde | Fak unt Bf B 20 | 2023 | 2023 | 19 | 19 | 2023-05-10 | 10:00 | 2023-05-11 | 16:00 | 1d, 6h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | 1437-008 |  | 2021-05-21
DB Netz AG | 1741-001 | Dresden - Děčín | <> | Pirna Gbf | Pirna Gbf | 2023 | 2023 | 22 | 24 | 2023-06-01 | 8:00 | 2023-06-17 | 16:00 | 16d, 8h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 1741-001 |  | 2021-04-06
DB Netz AG | 1741-002 | Dresden - Děčín | <> | Pirna Gbf | Pirna Gbf | 2023 | 2023 | 22 | 24 | 2023-06-01 | 8:00 | 2023-06-17 | 16:00 | 16d, 8h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 1741-002 |  | 2021-04-06
DB Netz AG | 1741-003 | Dresden - Děčín | <> | Pirna Gbf | Pirna | 2023 | 2023 | 23 | 23 | 2023-06-09 | 22:00 | 2023-06-11 | 16:00 | 1d, 18h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 1741-003 |  | 2021-04-06
DB Netz AG | 1741-004 | Dresden - Děčín | <> | Pirna | Pirna Gbf | 2023 | 2023 | 23 | 23 | 2023-06-09 | 22:00 | 2023-06-11 | 16:00 | 1d, 18h | Continuous | Switch |  |  |  |  | X | [6 empty] | 80 | N | 1741-004 |  | 2021-04-06
DB Netz AG | 1741-005 | Dresden - Děčín | <> | Pirna | Pirna Gbf | 2023 | 2023 | 23 | 23 | 2023-06-09 | 22:00 | 2023-06-11 | 16:00 | 1d, 18h | Continuous | Switch |  |  |  |  | X | [6 empty] | 80 | N | 1741-005 |  | 2021-04-06
DB Netz AG | 1741-006 | Dresden - Děčín | <> | Pirna Gbf | Pirna | 2023 | 2023 | 23 | 23 | 2023-06-10 | 22:00 | 2023-06-11 | 5:00 | 0d, 7h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 1741-006 |  | 2021-04-06
DB Netz AG | 1741-007 | Dresden - Děčín | < | Heidenau | Pirna | 2023 | 2023 | 23 | 23 | 2023-06-11 | 15:15 | 2023-06-11 | 16:00 | 0d, 0h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 1741-007 |  | 2021-04-06
DB Netz AG | 1741-008 | Dresden - Děčín | <> | Pirna Gbf | Pirna | 2023 | 2023 | 23 | 23 | 2023-06-11 | 15:15 | 2023-06-11 | 16:00 | 0d, 0h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 1741-008 |  | 2021-04-06
DB Netz AG | 1741-009 | Dresden - Děčín | <> | Pirna Gbf | Pirna | 2023 | 2023 | 23 | 23 | 2023-06-11 | 15:15 | 2023-06-11 | 16:00 | 0d, 0h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 1741-009 |  | 2021-04-06
DB Netz AG | 1741-010 | Dresden - Děčín | <> | Pirna Gbf | Pirna Gbf | 2023 | 2023 | 24 | 24 | 2023-06-12 | 22:00 | 2023-06-16 | 5:00 | 3d, 7h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 1741-010 |  | 2021-04-06
DB Netz AG | 1741-011 | Dresden - Děčín | <> | Pirna | Pirna Gbf | 2023 | 2023 | 24 | 24 | 2023-06-12 | 22:00 | 2023-06-16 | 5:00 | 3d, 7h | Continuous | Switch |  |  |  |  | X | [6 empty] | 80 | N | 1741-011 |  | 2021-04-06
DB Netz AG | 1741-012 | Dresden - Děčín | <> | Pirna | Pirna Gbf | 2023 | 2023 | 24 | 24 | 2023-06-12 | 22:00 | 2023-06-16 | 5:00 | 3d, 7h | Continuous | Switch |  |  |  |  | X | [6 empty] | 80 | N | 1741-012 |  | 2021-04-06
DB Netz AG | 1741-014 | Dresden - Děčín | <> | Pirna Gbf | Pirna Gbf | 2023 | 2023 | 24 | 24 | 2023-06-15 | 20:00 | 2023-06-16 | 4:00 | 0d, 8h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 1741-014 |  | 2021-04-06
DB Netz AG | 1741-015 | Dresden - Děčín | < | Heidenau | Pirna | 2023 | 2023 | 24 | 24 | 2023-06-16 | 4:00 | 2023-06-16 | 5:00 | 0d, 1h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 1741-015 |  | 2021-04-06
DB Netz AG | 1741-016 | Dresden - Děčín | <> | Pirna Gbf | Pirna | 2023 | 2023 | 24 | 24 | 2023-06-16 | 4:00 | 2023-06-16 | 5:00 | 0d, 1h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 1741-016 |  | 2021-04-06
DB Netz AG | 1741-017 | Dresden - Děčín | <> | Pirna Gbf | Pirna | 2023 | 2023 | 24 | 24 | 2023-06-16 | 4:00 | 2023-06-16 | 5:00 | 0d, 1h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 1741-017 |  | 2021-04-06
DB Netz AG | 1742-001 | Dresden - Děčín | <> | Pirna Gbf | Pirna Gbf | 2023 | 2023 | 24 | 27 | 2023-06-17 | 16:00 | 2023-07-09 | 16:00 | 22d, 0h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 1742-001 |  | 2021-04-06
DB Netz AG | 1742-002 | Dresden - Děčín | <> | Pirna Gbf | Pirna Gbf | 2023 | 2023 | 24 | 27 | 2023-06-17 | 16:00 | 2023-07-09 | 16:00 | 22d, 0h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 1742-002 |  | 2021-04-06
DB Netz AG | 1742-004 | Dresden - Děčín | <> | Pirna Gbf | Pirna | 2023 | 2023 | 26 | 27 | 2023-06-28 | 20:00 | 2023-07-06 | 5:00 | 7d, 9h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 1742-004 |  | 2021-04-06
DB Netz AG | 1742-005 | Dresden - Děčín | <> | Pirna Gbf | Pirna Gbf | 2023 | 2023 | 26 | 27 | 2023-06-28 | 20:00 | 2023-07-06 | 5:00 | 7d, 9h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 1742-005 |  | 2021-04-06
DB Netz AG | 1742-006 | Dresden - Děčín | <> | Pirna | Pirna Gbf | 2023 | 2023 | 26 | 27 | 2023-06-28 | 20:00 | 2023-07-06 | 5:00 | 7d, 9h | Continuous | Switch |  |  |  |  | X | [6 empty] | 80 | N | 1742-006 |  | 2021-04-06
DB Netz AG | 1742-007 | Dresden - Děčín | <> | Pirna | Pirna Gbf | 2023 | 2023 | 26 | 27 | 2023-06-28 | 20:00 | 2023-07-06 | 5:00 | 7d, 9h | Continuous | Switch |  |  |  |  | X | [6 empty] | 80 | N | 1742-007 |  | 2021-04-06
DB Netz AG | 1742-008 | Dresden - Děčín | <> | Pirna Gbf | Pirna Gbf | 2023 | 2023 | 26 | 27 | 2023-06-28 | 20:00 | 2023-07-06 | 5:00 | 7d, 9h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 1742-008 |  | 2021-04-06
DB Netz AG | 1742-009 | Dresden - Děčín | <> | Pirna Gbf | Pirna Gbf | 2023 | 2023 | 26 | 27 | 2023-06-28 | 20:00 | 2023-07-06 | 5:00 | 7d, 9h | Continuous | Switch |  |  |  | P | [7 empty] | 80 | N | 1742-009 |  | 2021-04-06
DB Netz AG | 1742-010 | Dresden - Děčín | <> | Pirna Gbf | Pirna Gbf | 2023 | 2023 | 26 | 27 | 2023-06-29 | 5:00 | 2023-07-06 | 5:00 | 7d, 0h | Continuous | Switch |  |  | S | [8 empty] | 80 | N | 1742-010 |  | 2021-04-06
DB Netz AG | 1742-011 | Dresden - Děčín | <> | Heidenau | Pirna | 2023 | 2023 | 26 | 27 | 2023-06-28 | 20:00 | 2023-07-06 | 4:00 | 7d, 8h | Periodical | Switch |  | LT | [9 empty] | 80 | N | 1742-011 |  | 2021-04-06
DB Netz AG | 1742-012 | Dresden - Děčín | < | Pirna Gbf | Pirna Gbf | 2023 | 2023 | 26 | 27 | 2023-06-28 | 20:00 | 2023-07-06 | 4:00 | 7d, 8h | Periodical | Switch |  |  |  |  | X | [6 empty] | 80 | N | 1742-012 |  | 2021-04-06
DB Netz AG | 1742-013 | Dresden - Děčín | <> | Pirna Gbf | Pirna Gbf | 2023 | 2023 | 26 | 27 | 2023-06-28 | 20:00 | 2023-07-06 | 4:00 | 7d, 8h | Periodical | Switch |  |  |  | P | [7 empty] | 80 | N | 1742-013 |  | 2021-04-06
DB Netz AG | 1742-014 | Dresden - Děčín | <> | Pirna Gbf | Pirna | 2023 | 2023 | 27 | 27 | 2023-07-06 | 4:00 | 2023-07-06 | 5:00 | 0d, 1h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 1742-014 |  | 2021-04-06
DB Netz AG | 1742-015 | Dresden - Děčín | <> | Pirna Gbf | Pirna | 2023 | 2023 | 27 | 27 | 2023-07-06 | 4:00 | 2023-07-06 | 5:00 | 0d, 1h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 1742-015 |  | 2021-04-06
DB Netz AG | 1742-016 | Dresden - Děčín | <> | Pirna Gbf | Pirna Gbf | 2023 | 2023 | 27 | 27 | 2023-07-06 | 5:00 | 2023-07-08 | 13:00 | 2d, 8h | Continuous | Switch |  |  | S | [8 empty] | 80 | N | 1742-016 |  | 2021-04-06
DB Netz AG | 1742-017 | Dresden - Děčín | <> | Pirna Gbf | Pirna Gbf | 2023 | 2023 | 27 | 27 | 2023-07-06 | 5:00 | 2023-07-08 | 13:00 | 2d, 8h | Continuous | Switch |  |  | S | [8 empty] | 80 | N | 1742-017 |  | 2021-04-06
DB Netz AG | 1779-010 | Rostock - Berlin | <> | Biesdf Kr Nord | Bln Nordost | 2023 | 2023 | 24 | 24 | 2023-06-17 | 8:00 | 2023-06-18 | 8:00 | 1d, 0h | Continuous | Bridge | T | [10 empty] | 80 | N | 1779-010
DB Netz AG | 1779-012 | Rostock - Berlin | <> | Biesdf Kr Nord | Bln Nordost | 2023 | 2023 | 25 | 25 | 2023-06-19 | 8:00 | 2023-06-19 | 14:00 | 0d, 6h | Continuous | Bridge | T | [10 empty] | 80 | N | 1779-012
DB Netz AG | 17B3-001 | Berlin - Dresden | <> | Großenh Cott Bf | Lampertswalde | 2023 | 2023 | 23 | 23 | 2023-06-06 | 9:00 | 2023-06-06 | 17:00 | 0d, 8h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | 17B3-001 |  | 2021-05-25
DB Netz AG | 17B3-002 | Berlin - Dresden | <> | Großenh Cott Bf | Ruhland | 2023 | 2023 | 23 | 23 | 2023-06-07 | 9:00 | 2023-06-07 | 15:00 | 0d, 6h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | 17B3-002 |  | 2021-05-25
DB Netz AG | 17C9-001 | Rostock - Berlin | <> | Waren (Müritz) | Waren (Müritz) | 2023 | 2023 | 23 | 24 | 2023-06-09 | 22:00 | 2023-06-16 | 22:00 | 7d, 0h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 17C9-001 |  | 2021-04-23
DB Netz AG | 17C9-002 | Rostock - Berlin | <> | Waren (Müritz) | Waren (Müritz) | 2023 | 2023 | 23 | 24 | 2023-06-09 | 22:00 | 2023-06-16 | 22:00 | 7d, 0h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 17C9-002 |  | 2021-04-23
DB Netz AG | 17C9-004 | Rostock - Berlin | <> | Waren (Müritz) | Waren (Müritz) | 2023 | 2023 | 23 | 24 | 2023-06-09 | 22:00 | 2023-06-16 | 22:00 | 7d, 0h | Continuous | Track & Rail |  |  |  | P | [7 empty] | 80 | N | 17C9-004 |  | 2021-04-23
DB Netz AG | 1849-010 | Falkenberg - Dresden | < | Niederau | Priestewitz | 2023 | 2023 | 19 | 19 | 2023-05-11 | 5:00 | 2023-05-13 | 11:00 | 2d, 6h | Continuous | Track & Rail |  |  | S | [8 empty] | 80 | N | 1849-010 |  | 2021-05-05
DB Netz AG | 1849-011 | Falkenberg - Dresden | <> | Priestewitz | Niederau | 2023 | 2023 | 19 | 19 | 2023-05-10 | 21:00 | 2023-05-12 | 5:00 | 1d, 8h | Periodical | Track & Rail | T | [10 empty] | 80 | N | 1849-011 |  | 2021-05-05
DB Netz AG | 1849-012 | Falkenberg - Dresden | <> | Priestewitz | Niederau | 2023 | 2023 | 19 | 19 | 2023-05-10 | 21:00 | 2023-05-12 | 5:00 | 1d, 8h | Periodical | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | 1849-012 |  | 2021-05-05
DB Netz AG | 1849-013 | Falkenberg - Dresden | <> | Priestewitz | Coswig Stw 1 | 2023 | 2023 | 19 | 19 | 2023-05-11 | 4:00 | 2023-05-11 | 5:00 | 0d, 1h | Continuous | Track & Rail | T | [10 empty] | 80 | N | 1849-013 |  | 2021-05-05
DB Netz AG | 1849-014 | Falkenberg - Dresden | <> | Priestewitz | Großenh Cott Bf | 2023 | 2023 | 19 | 19 | 2023-05-11 | 4:00 | 2023-05-11 | 5:00 | 0d, 1h | Continuous | Track & Rail | T | [10 empty] | 80 | N | 1849-014 |  | 2021-05-05
DB Netz AG | 1889-001 | Falkenberg - Dresden | < | Kottewitz | Leckwitz | 2023 | 2023 | 21 | 21 | 2023-05-22 | 21:00 | 2023-05-24 | 4:00 | 1d, 7h | Periodical | Track & Rail |  | LT | [9 empty] | 80 | N | 1889-001
DB Netz AG | 1889-002 | Falkenberg - Dresden | > | Weinböhla | Großenh Berl Bf | 2023 | 2023 | 21 | 21 | 2023-05-22 | 21:00 | 2023-05-22 | 23:00 | 0d, 2h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1889-002
DB Netz AG | 1889-003 | Falkenberg - Dresden | > | Weinböhla | Großenh Berl Bf | 2023 | 2023 | 21 | 21 | 2023-05-22 | 21:00 | 2023-05-23 | 21:30 | 1d, 0h | Periodical | Track & Rail |  | LT | [9 empty] | 80 | N | 1889-003
DB Netz AG | 1889-004 | Falkenberg - Dresden | > | Weinböhla | Großenh Berl Bf | 2023 | 2023 | 21 | 21 | 2023-05-23 | 4:00 | 2023-05-24 | 4:30 | 1d, 0h | Periodical | Track & Rail |  | LT | [9 empty] | 80 | N | 1889-004
DB Netz AG | 1889-005 | Falkenberg - Dresden | < | Kottewitz | Leckwitz | 2023 | 2023 | 21 | 21 | 2023-05-23 | 4:00 | 2023-05-24 | 4:30 | 1d, 0h | Periodical | Track & Rail |  | LT | [9 empty] | 80 | N | 1889-005
DB Netz AG | 18.8 | Falkenberg - Dresden | > | Niederau | Coswig (bei Dre) | 2023 | 2023 | 21 | 21 | 2023-05-24 | 21:00 | 2023-05-24 | 22:30 | 0d, 1h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 18.8 |  | 2021-04-07
DB Netz AG | 1.88 | Falkenberg - Dresden | > | Coswig Stw 1 | Coswig (bei Dre) | 2023 | 2023 | 21 | 21 | 2023-05-24 | 22:30 | 2023-05-25 | 1:30 | 0d, 3h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1.88 |  | 2021-04-07
DB Netz AG | 0.188 | Falkenberg - Dresden | > | Meißen | Coswig Stw 1 | 2023 | 2023 | 21 | 21 | 2023-05-24 | 22:30 | 2023-05-25 | 1:30 | 0d, 3h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 0.188 |  | 2021-04-07
DB Netz AG | 0.0188 | Falkenberg - Dresden | < | Coswig Stw 1 | Niederau | 2023 | 2023 | 21 | 21 | 2023-05-25 | 1:30 | 2023-05-25 | 3:00 | 0d, 1h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 0.0188 |  | 2021-04-07
DB Netz AG | 0.00188 | Falkenberg - Dresden | < | Coswig (bei Dre) | Coswig Stw 1 | 2023 | 2023 | 21 | 21 | 2023-05-25 | 3:00 | 2023-05-25 | 4:30 | 0d, 1h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 0.00188 |  | 2021-04-07
DB Netz AG | 0.000188 | Falkenberg - Dresden | <> | Coswig (bei Dre) | Coswig (bei Dre) | 2023 | 2023 | 21 | 21 | 2023-05-25 | 3:00 | 2023-05-25 | 4:30 | 0d, 1h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 0.000188 |  | 2021-04-07
DB Netz AG | 1891-001 | Falkenberg - Dresden | < | Dre-Neustadt | Dre-Pieschen Abz | 2023 | 2023 | 21 | 21 | 2023-05-25 | 21:00 | 2023-05-26 | 4:00 | 0d, 7h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1891-001 |  | 2021-04-26
DB Netz AG | 1891-002 | Falkenberg - Dresden | <> | Dre-Neustadt | Dre-Neustadt | 2023 | 2023 | 21 | 21 | 2023-05-25 | 21:00 | 2023-05-26 | 4:00 | 0d, 7h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1891-002 |  | 2021-04-26
DB Netz AG | 1891-003 | Falkenberg - Dresden | <> | Dre-Neustadt | Dre-Neustadt | 2023 | 2023 | 21 | 21 | 2023-05-26 | 1:00 | 2023-05-26 | 4:00 | 0d, 3h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1891-003 |  | 2021-04-26
DB Netz AG | 1944-001 | Dresden - Děčín | > | Dresden Hbf | Freital Ost | 2023 | 2023 | 22 | 22 | 2023-05-30 | 21:00 | 2023-05-30 | 23:00 | 0d, 2h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1944-001 |  | 2021-04-26
DB Netz AG | 1944-002 | Dresden - Děčín | > | Dresden Hbf | Freital Ost | 2023 | 2023 | 22 | 22 | 2023-05-30 | 23:00 | 2023-05-31 | 1:00 | 0d, 2h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1944-002 |  | 2021-04-26
DB Netz AG | 1944-011 | Dresden - Děčín | < | Dresden-Altstadt | Dresden Hbf | 2023 | 2023 | 22 | 22 | 2023-06-04 | 21:00 | 2023-06-04 | 23:00 | 0d, 2h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1944-011 |  | 2021-04-26
DB Netz AG | 1959-001 | Rostock - Berlin | > | Neustrelitz Hbf | Kratzeburg | 2023 | 2023 | 27 | 27 | 2023-07-05 | 21:00 | 2023-07-06 | 5:00 | 0d, 8h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1959-001
DB Netz AG | 195F-001 | Dresden - Děčín | > | Dre-Niedersedl | Dresden Hbf | 2023 | 2023 | 24 | 24 | 2023-06-13 | 20:00 | 2023-06-13 | 23:00 | 0d, 3h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 195F-001 |  | 2021-04-07
DB Netz AG | 195F-002 | Dresden - Děčín | < | Dresden Hbf | Dre-Niedersedl | 2023 | 2023 | 24 | 24 | 2023-06-13 | 23:00 | 2023-06-14 | 2:00 | 0d, 3h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 195F-002 |  | 2021-04-07
DB Netz AG | 195F-004 | Dresden - Děčín | <> | Dresden Hbf | Dre-Niedersedl | 2023 | 2023 | 24 | 24 | 2023-06-14 | 2:00 | 2023-06-14 | 4:00 | 0d, 2h | Continuous | Maintenance | T | [10 empty] | 80 | N | 195F-004 |  | 2021-04-07
DB Netz AG | 196B-001 | Dresden - Děčín | <> | Dre-Neustadt | Dre-Neustadt | 2023 | 2023 | 24 | 24 | 2023-06-14 | 21:00 | 2023-06-15 | 2:00 | 0d, 5h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 196B-001 |  | 2021-04-26
DB Netz AG | 196B-002 | Dresden - Děčín | <> | Dre-Neustadt | Dre-Neustadt | 2023 | 2023 | 24 | 24 | 2023-06-14 | 22:00 | 2023-06-14 | 23:30 | 0d, 1h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 196B-002 |  | 2021-04-26
DB Netz AG | 196B-003 | Falkenberg - Dresden | <> | Dre-Neustadt | Dre-Neustadt | 2023 | 2023 | 24 | 24 | 2023-06-14 | 23:30 | 2023-06-15 | 2:00 | 0d, 2h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 196B-003 |  | 2021-04-26
DB Netz AG | 196B-004 | Falkenberg - Dresden | <> | Dre-Neustadt | Dre-Neustadt | 2023 | 2023 | 24 | 24 | 2023-06-15 | 1:00 | 2023-06-15 | 2:00 | 0d, 1h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 196B-004 |  | 2021-04-26
DB Netz AG | 196B-005 | Falkenberg - Dresden | < | Dre-Neustadt | Radebeul Ost | 2023 | 2023 | 24 | 24 | 2023-06-15 | 1:00 | 2023-06-15 | 2:00 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 196B-005 |  | 2021-04-26
DB Netz AG | 196B-006 | Dresden - Děčín | <> | Dre-Neustadt | Dre-Neustadt | 2023 | 2023 | 24 | 24 | 2023-06-15 | 2:00 | 2023-06-15 | 4:30 | 0d, 2h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 196B-006 |  | 2021-04-26
DB Netz AG | 196B-007 | Dresden - Děčín | < | Dre-Neustadt | Dresden Mitte | 2023 | 2023 | 24 | 24 | 2023-06-15 | 2:00 | 2023-06-15 | 4:30 | 0d, 2h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 196B-007 |  | 2021-04-26
DB Netz AG | 196B-008 | Dresden - Děčín | <> | Dre-Neustadt | Dre-Neustadt | 2023 | 2023 | 24 | 24 | 2023-06-15 | 2:00 | 2023-06-15 | 4:30 | 0d, 2h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 196B-008 |  | 2021-04-26
DB Netz AG | 196B-009 | Dresden - Děčín | > | Dre-Neustadt | Dre-Neustadt | 2023 | 2023 | 24 | 24 | 2023-06-15 | 21:00 | 2023-06-16 | 2:00 | 0d, 5h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 196B-009 |  | 2021-04-26
DB Netz AG | 196B-010 | Dresden - Děčín | <> | Dre-Neustadt | Dre-Neustadt | 2023 | 2023 | 24 | 24 | 2023-06-15 | 21:00 | 2023-06-16 | 2:00 | 0d, 5h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 196B-010 |  | 2021-04-26
DB Netz AG | 196B-011 | Dresden - Děčín | <> | Dre-Neustadt | Dre-Klotzsche | 2023 | 2023 | 24 | 24 | 2023-06-16 | 0:30 | 2023-06-16 | 2:00 | 0d, 1h | Continuous | Maintenance | T | [10 empty] | 80 | N | 196B-011 |  | 2021-04-26
DB Netz AG | 196B-012 | Dresden - Děčín | < | Dre-Neustadt | Dre-Klotzsche | 2023 | 2023 | 24 | 24 | 2023-06-16 | 2:00 | 2023-06-16 | 4:00 | 0d, 2h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 196B-012 |  | 2021-04-26
DB Netz AG | 196F-001 | Falkenberg - Dresden | <> | Coswig (bei Dre) | Coswig (bei Dre) | 2023 | 2023 | 24 | 24 | 2023-06-16 | 21:00 | 2023-06-17 | 2:00 | 0d, 5h | Continuous | Maintenance | T | [10 empty] | 80 | N | 196F-001 |  | 2021-04-07
DB Netz AG | 196F-002 | Falkenberg - Dresden | <> | Coswig Stw 1 | Coswig (bei Dre) | 2023 | 2023 | 24 | 24 | 2023-06-16 | 21:00 | 2023-06-17 | 2:00 | 0d, 5h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 196F-002 |  | 2021-04-07
DB Netz AG | 196F-003 | Falkenberg - Dresden | <> | Coswig Stw 1 | Radebeul Nord | 2023 | 2023 | 24 | 24 | 2023-06-17 | 0:30 | 2023-06-17 | 2:00 | 0d, 1h | Continuous | Maintenance | T | [10 empty] | 80 | N | 196F-003 |  | 2021-04-07
DB Netz AG | 196F-004 | Falkenberg - Dresden | <> | Coswig Stw 1 | Coswig (bei Dre) | 2023 | 2023 | 24 | 24 | 2023-06-17 | 0:30 | 2023-06-17 | 4:30 | 0d, 4h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 196F-004 |  | 2021-04-07
DB Netz AG | 196F-005 | Falkenberg - Dresden | <> | Coswig Stw 1 | Coswig (bei Dre) | 2023 | 2023 | 24 | 24 | 2023-06-17 | 2:00 | 2023-06-17 | 4:30 | 0d, 2h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 196F-005 |  | 2021-04-07
DB Netz AG | 196F-006 | Falkenberg - Dresden | > | Meißen | Coswig Stw 1 | 2023 | 2023 | 24 | 24 | 2023-06-17 | 2:00 | 2023-06-17 | 4:30 | 0d, 2h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 196F-006 |  | 2021-04-07
DB Netz AG | 196A-001 | Rostock - Berlin | <> | Kavelstorf | Laage (Meckl) | 2023 | 2023 | 23 | 24 | 2023-06-09 | 21:00 | 2023-06-12 | 10:00 | 2d, 13h | Continuous | Miscellaneous |  |  | S | [8 empty] | 80 | N | 196A-001 |  | 2022-04-26
DB Netz AG | 196A-002 | Rostock - Berlin | <> | Kavelstorf | Laage (Meckl) | 2023 | 2023 | 24 | 24 | 2023-06-12 | 10:00 | 2023-06-14 | 10:00 | 2d, 0h | Continuous | Miscellaneous |  |  | S | [8 empty] | 80 | N | 196A-002 |  | 2022-04-26
DB Netz AG | 19D6-002 | Rostock - Berlin | < | Kavelstorf | Laage (Meckl) | 2023 | 2023 | 19 | 19 | 2023-05-10 | 22:00 | 2023-05-11 | 6:00 | 0d, 8h | Continuous | Catenary |  | LT | [9 empty] | 80 | N | 19D6-002 |  | 2021-10-27
DB Netz AG | 19D6-003 | Rostock - Berlin | < | Laage (Meckl) | Laage (Meckl) | 2023 | 2023 | 19 | 19 | 2023-05-10 | 22:00 | 2023-05-11 | 6:00 | 0d, 8h | Continuous | Catenary |  | ST | [9 empty] | 80 | N | 19D6-003 |  | 2021-10-27
DB Netz AG | 19D6-004 | Rostock - Berlin | < | Kavelstorf | Kavelstorf | 2023 | 2023 | 19 | 19 | 2023-05-10 | 22:00 | 2023-05-11 | 6:00 | 0d, 8h | Continuous | Catenary |  | ST | [9 empty] | 80 | N | 19D6-004 |  | 2021-10-27
DB Netz AG | 19D6-005 | Rostock - Berlin | <> | Kavelstorf | Dalwitzhof | 2023 | 2023 | 19 | 19 | 2023-05-10 | 22:00 | 2023-05-11 | 6:00 | 0d, 8h | Continuous | Catenary | T | [10 empty] | 80 | N | 19D6-005 |  | 2021-10-27
DB Netz AG | 19D6-006 | Rostock - Berlin | > | Kavelstorf | Kavelstorf | 2023 | 2023 | 19 | 19 | 2023-05-11 | 22:00 | 2023-05-12 | 6:00 | 0d, 8h | Continuous | Catenary |  | ST | [9 empty] | 80 | N | 19D6-006 |  | 2021-10-27
DB Netz AG | 19D6-007 | Rostock - Berlin | > | Laage (Meckl) | Kavelstorf | 2023 | 2023 | 19 | 19 | 2023-05-11 | 22:00 | 2023-05-12 | 6:00 | 0d, 8h | Continuous | Catenary |  | LT | [9 empty] | 80 | N | 19D6-007 |  | 2021-10-27
DB Netz AG | 19F2-001 | Magdeburg - Falkenberg | <> | Biederitz | Biederitz | 2023 | 2023 | 19 | 19 | 2023-05-10 | 19:45 | 2023-05-10 | 20:00 | 0d, 0h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 19F2-001 |  | 2021-05-20
DB Netz AG | 19F2-002 | Magdeburg - Falkenberg | > | Biederitz | Brücke | 2023 | 2023 | 19 | 19 | 2023-05-10 | 20:00 | 2023-05-10 | 22:00 | 0d, 2h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 19F2-002 |  | 2021-09-06
DB Netz AG | 19F2-003 | Magdeburg - Falkenberg | > | Biederitz | Biederitz | 2023 | 2023 | 19 | 19 | 2023-05-10 | 20:00 | 2023-05-10 | 22:00 | 0d, 2h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 19F2-003 |  | 2021-05-20
DB Netz AG | 19F2-004 | Magdeburg - Falkenberg | > | Gerwisch | Brücke | 2023 | 2023 | 19 | 19 | 2023-05-10 | 20:00 | 2023-05-10 | 22:00 | 0d, 2h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 19F2-004 |  | 2021-05-20
DB Netz AG | 19F2-005 | Magdeburg - Falkenberg | <> | Biederitz | Biederitz | 2023 | 2023 | 19 | 19 | 2023-05-10 | 20:00 | 2023-05-10 | 22:00 | 0d, 2h | Continuous | Switch |  |  |  | P | [7 empty] | 80 | N | 19F2-005 |  | 2021-05-20
DB Netz AG | 19F2-006 | Magdeburg - Falkenberg | <> | Biederitz | Biederitz | 2023 | 2023 | 19 | 19 | 2023-05-10 | 20:00 | 2023-05-10 | 22:00 | 0d, 2h | Continuous | Switch |  |  |  | P | [7 empty] | 80 | N | 19F2-006 |  | 2021-09-06
DB Netz AG | 19F2-007 | Magdeburg - Falkenberg | <> | Biederitz | Biederitz | 2023 | 2023 | 19 | 19 | 2023-05-10 | 20:00 | 2023-05-10 | 22:00 | 0d, 2h | Continuous | Switch |  |  |  | P | [7 empty] | 80 | N | 19F2-007 |  | 2021-05-20
DB Netz AG | 19F2-008 | Magdeburg - Falkenberg | > | Biederitz | Biederitz | 2023 | 2023 | 19 | 19 | 2023-05-10 | 20:00 | 2023-05-10 | 22:00 | 0d, 2h | Continuous | Switch |  |  |  |  | X | [6 empty] | 80 | N | 19F2-008 |  | 2021-05-20
DB Netz AG | 19F2-009 | Magdeburg - Falkenberg | <> | Biederitz | Biederitz | 2023 | 2023 | 19 | 19 | 2023-05-10 | 22:00 | 2023-05-11 | 2:00 | 0d, 4h | Continuous | Switch |  |  |  | P | [7 empty] | 80 | N | 19F2-009 |  | 2021-05-20
DB Netz AG | 19F2-010 | Magdeburg - Falkenberg | < | Brücke | Biederitz | 2023 | 2023 | 19 | 19 | 2023-05-10 | 22:00 | 2023-05-11 | 2:00 | 0d, 4h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 19F2-010 |  | 2021-12-20
DB Netz AG | 19F2-011 | Magdeburg - Falkenberg | <> | Biederitz | Biederitz | 2023 | 2023 | 19 | 19 | 2023-05-10 | 22:00 | 2023-05-11 | 2:00 | 0d, 4h | Continuous | Switch | T | [10 empty] | 80 | N | 19F2-011 |  | 2021-05-20
DB Netz AG | 19F2-012 | Magdeburg - Falkenberg | <> | Biederitz | Biederitz | 2023 | 2023 | 19 | 19 | 2023-05-10 | 22:00 | 2023-05-11 | 2:00 | 0d, 4h | Continuous | Switch | T | [10 empty] | 80 | N | 19F2-012 |  | 2021-12-20
DB Netz AG | 19F2-013 | Magdeburg - Falkenberg | <> | Biederitz | Biederitz | 2023 | 2023 | 19 | 19 | 2023-05-10 | 22:00 | 2023-05-11 | 2:00 | 0d, 4h | Continuous | Switch |  |  |  |  | X | [6 empty] | 80 | N | 19F2-013 |  | 2021-05-20
DB Netz AG | 19F2-014 | Magdeburg - Falkenberg | <> | Biederitz | Biederitz | 2023 | 2023 | 19 | 19 | 2023-05-10 | 22:00 | 2023-05-11 | 2:00 | 0d, 4h | Continuous | Switch |  |  |  |  | X | [6 empty] | 80 | N | 19F2-014 |  | 2021-05-20
DB Netz AG | 19F2-015 | Magdeburg - Falkenberg | <> | Biederitz | Biederitz | 2023 | 2023 | 19 | 19 | 2023-05-11 | 2:00 | 2023-05-11 | 4:00 | 0d, 2h | Continuous | Switch | T | [10 empty] | 80 | N | 19F2-015 |  | 2021-05-20
DB Netz AG | 19F2-016 | Magdeburg - Falkenberg | <> | Biederitz | Biederitz | 2023 | 2023 | 19 | 19 | 2023-05-11 | 2:00 | 2023-05-11 | 4:00 | 0d, 2h | Continuous | Switch | T | [10 empty] | 80 | N | 19F2-016 |  | 2021-05-20
DB Netz AG | 19F2-017 | Magdeburg - Falkenberg | <> | Biederitz | Biederitz | 2023 | 2023 | 19 | 19 | 2023-05-11 | 2:00 | 2023-05-11 | 4:00 | 0d, 2h | Continuous | Switch |  |  |  | P | [7 empty] | 80 | N | 19F2-017 |  | 2021-05-20
DB Netz AG | 19F2-018 | Magdeburg - Falkenberg | <> | Biederitz | Biederitz | 2023 | 2023 | 19 | 19 | 2023-05-11 | 2:00 | 2023-05-11 | 4:00 | 0d, 2h | Continuous | Switch |  |  |  |  | X | [6 empty] | 80 | N | 19F2-018 |  | 2021-05-20
DB Netz AG | 19F2-019 | Magdeburg - Falkenberg | <> | Biederitz | Biederitz | 2023 | 2023 | 19 | 19 | 2023-05-11 | 2:00 | 2023-05-11 | 4:00 | 0d, 2h | Continuous | Switch |  |  |  |  | X | [6 empty] | 80 | N | 19F2-019 |  | 2021-05-20
DB Netz AG | 19FD-001 | Magdeburg - Falkenberg | <> | Biederitz | Biederitz | 2023 | 2023 | 19 | 19 | 2023-05-11 | 18:45 | 2023-05-11 | 19:00 | 0d, 0h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 19FD-001 |  | 2021-05-21
DB Netz AG | 19FD-002 | Magdeburg - Falkenberg | > | Gerwisch | Biederitz | 2023 | 2023 | 19 | 19 | 2023-05-11 | 19:00 | 2023-05-11 | 20:00 | 0d, 1h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 19FD-002 |  | 2021-05-21
DB Netz AG | 19FD-003 | Magdeburg - Falkenberg | > | Gerwisch | Brücke | 2023 | 2023 | 19 | 19 | 2023-05-11 | 19:00 | 2023-05-11 | 20:00 | 0d, 1h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 19FD-003 |  | 2021-05-21
DB Netz AG | 19FD-004 | Magdeburg - Falkenberg | > | Biederitz | Biederitz | 2023 | 2023 | 19 | 19 | 2023-05-11 | 19:00 | 2023-05-11 | 20:00 | 0d, 1h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 19FD-004 |  | 2021-05-21
DB Netz AG | 19FD-005 | Magdeburg - Falkenberg | <> | Biederitz | Biederitz | 2023 | 2023 | 19 | 19 | 2023-05-11 | 19:00 | 2023-05-11 | 20:00 | 0d, 1h | Continuous | Switch |  |  |  | P | [7 empty] | 80 | N | 19FD-005 |  | 2021-05-21
DB Netz AG | 19FD-006 | Magdeburg - Falkenberg | > | Gerwisch | Brücke | 2023 | 2023 | 19 | 19 | 2023-05-11 | 20:00 | 2023-05-11 | 22:00 | 0d, 2h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 19FD-006 |  | 2021-09-07
DB Netz AG | 19FD-008 | Magdeburg - Falkenberg | > | Biederitz | Biederitz | 2023 | 2023 | 19 | 19 | 2023-05-11 | 20:00 | 2023-05-11 | 22:00 | 0d, 2h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 19FD-008 |  | 2021-05-21
DB Netz AG | 19FD-009 | Magdeburg - Falkenberg | <> | Biederitz | Biederitz | 2023 | 2023 | 19 | 19 | 2023-05-11 | 20:00 | 2023-05-11 | 22:00 | 0d, 2h | Continuous | Switch |  |  |  | P | [7 empty] | 80 | N | 19FD-009 |  | 2021-05-21
DB Netz AG | 19FD-010 | Magdeburg - Falkenberg | <> | Biederitz | Biederitz | 2023 | 2023 | 19 | 19 | 2023-05-11 | 20:00 | 2023-05-11 | 22:00 | 0d, 2h | Continuous | Switch |  |  |  |  | X | [6 empty] | 80 | N | 19FD-010 |  | 2021-05-21
DB Netz AG | 19FD-011 | Magdeburg - Falkenberg | < | Brücke | Gerwisch | 2023 | 2023 | 19 | 19 | 2023-05-11 | 22:00 | 2023-05-12 | 3:00 | 0d, 5h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 19FD-011 |  | 2021-05-21
DB Netz AG | 19FD-012 | Magdeburg - Falkenberg | < | Biederitz | Biederitz | 2023 | 2023 | 19 | 19 | 2023-05-11 | 22:00 | 2023-05-12 | 3:00 | 0d, 5h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 19FD-012 |  | 2021-05-21
DB Netz AG | 19FD-013 | Magdeburg - Falkenberg | <> | Biederitz | Biederitz | 2023 | 2023 | 19 | 19 | 2023-05-11 | 22:00 | 2023-05-12 | 3:00 | 0d, 5h | Continuous | Switch |  |  |  | P | [7 empty] | 80 | N | 19FD-013 |  | 2021-05-21
DB Netz AG | 19FD-014 | Magdeburg - Falkenberg | < | Biederitz | Biederitz | 2023 | 2023 | 19 | 19 | 2023-05-11 | 22:00 | 2023-05-12 | 3:00 | 0d, 5h | Continuous | Switch |  |  |  |  | X | [6 empty] | 80 | N | 19FD-014 |  | 2021-05-21
DB Netz AG | 19FD-015 | Magdeburg - Falkenberg | <> | Biederitz | Gerwisch | 2023 | 2023 | 19 | 19 | 2023-05-12 | 3:00 | 2023-05-12 | 4:30 | 0d, 1h | Continuous | Switch | T | [10 empty] | 80 | N | 19FD-015 |  | 2021-05-21
DB Netz AG | 19FD-016 | Magdeburg - Falkenberg | <> | Biederitz | Biederitz | 2023 | 2023 | 19 | 19 | 2023-05-12 | 3:00 | 2023-05-12 | 4:30 | 0d, 1h | Continuous | Switch |  |  |  |  | X | [6 empty] | 80 | N | 19FD-016 |  | 2021-05-21
DB Netz AG | 1A2E-008 | Rostock - Berlin | <> | Lalendorf Ost | Lalendorf Ost | 2023 | 2023 | 19 | 19 | 2023-05-10 | 21:30 | 2023-05-11 | 5:00 | 0d, 7h | Continuous | Track & Rail |  |  |  | P | [7 empty] | 80 | N | 1A2E-008 |  | 2021-05-21
DB Netz AG | 1A2E-009 | Rostock - Berlin | > | Langhagen | Plaaz Abzw | 2023 | 2023 | 19 | 19 | 2023-05-11 | 22:00 | 2023-05-12 | 5:00 | 0d, 7h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1A2E-009 |  | 2021-05-21
DB Netz AG | 1A2E-010 | Rostock - Berlin | <> | Langhagen | Lalendorf Ost | 2023 | 2023 | 19 | 19 | 2023-05-11 | 22:00 | 2023-05-12 | 5:00 | 0d, 7h | Continuous | Track & Rail |  |  |  | P | [7 empty] | 80 | N | 1A2E-010 |  | 2021-05-21
DB Netz AG | 1A2E-012 | Rostock - Berlin | > | Vollrathsruhe | Plaaz Abzw | 2023 | 2023 | 19 | 19 | 2023-05-13 | 2:30 | 2023-05-13 | 5:00 | 0d, 2h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1A2E-012 |  | 2021-05-21
DB Netz AG | 1A2E-013 | Rostock - Berlin | > | Langhagen | Langhagen | 2023 | 2023 | 19 | 19 | 2023-05-13 | 2:30 | 2023-05-13 | 5:00 | 0d, 2h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1A2E-013 |  | 2021-05-21
DB Netz AG | 1A2E-014 | Rostock - Berlin | > | Langhagen | Plaaz Abzw | 2023 | 2023 | 19 | 19 | 2023-05-12 | 22:00 | 2023-05-13 | 5:00 | 0d, 7h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1A2E-014 |  | 2021-05-21
DB Netz AG | 1A2E-015 | Rostock - Berlin | <> | Lalendorf Ost | Langhagen | 2023 | 2023 | 19 | 19 | 2023-05-12 | 22:00 | 2023-05-13 | 5:00 | 0d, 7h | Continuous | Track & Rail |  |  |  | P | [7 empty] | 80 | N | 1A2E-015 |  | 2021-05-21
DB Netz AG | 1A2E-016 | Rostock - Berlin | <> | Langhagen | Langhagen | 2023 | 2023 | 19 | 19 | 2023-05-13 | 2:30 | 2023-05-13 | 5:00 | 0d, 2h | Continuous | Track & Rail |  |  |  | P | [7 empty] | 80 | N | 1A2E-016 |  | 2021-05-21
DB Netz AG | 1A2E-017 | Rostock - Berlin | > | Vollrathsruhe | Plaaz Abzw | 2023 | 2023 | 19 | 19 | 2023-05-13 | 22:00 | 2023-05-14 | 5:00 | 0d, 7h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1A2E-017 |  | 2021-05-21
DB Netz AG | 1A2E-018 | Rostock - Berlin | > | Langhagen | Langhagen | 2023 | 2023 | 19 | 19 | 2023-05-13 | 22:00 | 2023-05-14 | 5:00 | 0d, 7h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1A2E-018 |  | 2021-05-21
DB Netz AG | 1A2E-019 | Rostock - Berlin | > | Vollrathsruhe | Vollrathsruhe | 2023 | 2023 | 19 | 19 | 2023-05-13 | 22:00 | 2023-05-14 | 5:00 | 0d, 7h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1A2E-019 |  | 2021-05-21
DB Netz AG | 1A2E-021 | Rostock - Berlin | <> | Langhagen | Langhagen | 2023 | 2023 | 19 | 19 | 2023-05-13 | 22:00 | 2023-05-14 | 5:00 | 0d, 7h | Continuous | Track & Rail |  |  |  | P | [7 empty] | 80 | N | 1A2E-021 |  | 2021-05-21
DB Netz AG | 1A9E-001 | Rostock - Berlin | > | Neustrelitz Hbf | Kargow | 2023 | 2023 | 27 | 27 | 2023-07-03 | 21:00 | 2023-07-05 | 2:00 | 1d, 5h | Periodical | Switch |  | LT | [9 empty] | 80 | N | 1A9E-001 |  | 2022-07-20
DB Netz AG | 1A9E-002 | Rostock - Berlin | > | Kratzeburg | Kratzeburg | 2023 | 2023 | 27 | 27 | 2023-07-03 | 21:00 | 2023-07-05 | 2:00 | 1d, 5h | Periodical | Switch |  | ST | [9 empty] | 80 | N | 1A9E-002 |  | 2022-07-20
DB Netz AG | 1A9E-004 | Rostock - Berlin | <> | Neustrelitz Hbf | Kargow | 2023 | 2023 | 27 | 27 | 2023-07-04 | 2:00 | 2023-07-05 | 5:00 | 1d, 3h | Periodical | Switch | T | [10 empty] | 80 | N | 1A9E-004 |  | 2022-07-20
DB Netz AG | 1A91-005 | Rostock - Berlin | <> | Ostendgestell | Eichgestell | 2023 | 2023 | 21 | 21 | 2023-05-26 | 22:00 | 2023-05-27 | 10:00 | 0d, 12h | Continuous | Signal | T | [10 empty] | 80 | N | 1A91-005 |  | 2021-04-30
DB Netz AG | 1AC5-006 | Bremen - Hannover | > | Seelze West | Ahlem | 2023 | 2023 | 20 | 21 | 2023-05-15 | 7:00 | 2023-05-22 | 13:00 | 7d, 6h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | 1AC5-006 |  | 2021-05-03
DB Netz AG | 1AC5-007 | Bremen - Hannover | <> | Seelze Ost | Seelze Ost | 2023 | 2023 | 20 | 20 | 2023-05-16 | 23:00 | 2023-05-18 | 5:00 | 1d, 6h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1AC5-007 |  | 2021-05-03
DB Netz AG | 1AC5-008 | Bremen - Hannover | <> | Seelze Ost | Seelze Ost | 2023 | 2023 | 20 | 20 | 2023-05-16 | 23:00 | 2023-05-18 | 5:00 | 1d, 6h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1AC5-008 |  | 2021-05-03
DB Netz AG | 1AC5-009 | Bremen - Hannover | <> | Seelze Ost | Letter Abzw | 2023 | 2023 | 21 | 21 | 2023-05-23 | 8:00 | 2023-05-25 | 16:00 | 2d, 8h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | 1AC5-009 |  | 2021-05-03
DB Netz AG | 1AC5-010 | Bremen - Hannover | <> | Seelze Ost | Seelze Ost | 2023 | 2023 | 23 | 23 | 2023-06-06 | 23:00 | 2023-06-10 | 5:00 | 3d, 6h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1AC5-010 |  | 2021-05-03
DB Netz AG | 1AC5-011 | Bremen - Hannover | <> | Seelze Ost | Seelze Ost | 2023 | 2023 | 23 | 24 | 2023-06-05 | 7:00 | 2023-06-12 | 13:00 | 7d, 6h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1AC5-011 |  | 2021-05-03
DB Netz AG | 1AC5-013 | Bremen - Hannover | <> | Seelze Ost | Seelze Ost | 2023 | 2023 | 24 | 24 | 2023-06-13 | 8:00 | 2023-06-15 | 16:00 | 2d, 8h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1AC5-013 |  | 2021-09-17
DB Netz AG | 1AC5-014 | Bremen - Hannover | <> | Seelze Ost | Seelze Ost | 2023 | 2023 | 25 | 26 | 2023-06-19 | 7:00 | 2023-06-26 | 13:00 | 7d, 6h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1AC5-014 |  | 2021-05-03
DB Netz AG | 1AC5-015 | Bremen - Hannover | <> | Seelze Ost | Seelze Ost | 2023 | 2023 | 26 | 26 | 2023-06-27 | 8:00 | 2023-06-29 | 16:00 | 2d, 8h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1AC5-015 |  | 2021-05-03
DB Netz AG | 1AC5-016 | Bremen - Hannover | <> | Seelze Ost | Seelze Ost | 2023 | 2023 | 26 | 26 | 2023-06-27 | 8:00 | 2023-06-29 | 16:00 | 2d, 8h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1AC5-016 |  | 2021-05-03
DB Netz AG | 1AC5-017 | Bremen - Hannover | <> | Seelze Ost | Seelze Ost | 2023 | 2023 | 27 | 28 | 2023-07-03 | 7:00 | 2023-07-10 | 13:00 | 7d, 6h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1AC5-017 |  | 2021-05-03
DB Netz AG | 1AC5-018 | Bremen - Hannover | <> | Seelze Ost | Seelze Ost | 2023 | 2023 | 27 | 27 | 2023-07-04 | 8:00 | 2023-07-06 | 16:00 | 2d, 8h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1AC5-018 |  | 2021-05-03
DB Netz AG | 1B24-001 | Rostock - Berlin | < | Lalendorf Ost | Vollrathsruhe | 2023 | 2023 | 24 | 25 | 2023-06-18 | 21:00 | 2023-06-23 | 5:00 | 4d, 8h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 1B24-001 |  | 2021-10-08
DB Netz AG | 1B24-002 | Rostock - Berlin | < | Langhagen | Langhagen | 2023 | 2023 | 24 | 25 | 2023-06-18 | 21:00 | 2023-06-23 | 5:00 | 4d, 8h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 1B24-002 |  | 2021-10-08
DB Netz AG | 1AC5-022 | Bremen - Hannover | <> | Seelze Ost | Seelze Ost | 2023 | 2023 | 27 | 27 | 2023-07-04 | 8:00 | 2023-07-06 | 16:00 | 2d, 8h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1AC5-022 |  | 2021-05-03
DB Netz AG | 1B24-003 | Rostock - Berlin | <> | Vollrathsruhe | Langhagen | 2023 | 2023 | 25 | 25 | 2023-06-19 | 0:00 | 2023-06-19 | 3:00 | 0d, 3h | Continuous | Catenary | T | [10 empty] | 80 | N | 1B24-003 |  | 2021-10-08
DB Netz AG | 1B24-004 | Rostock - Berlin | < | Langhagen | Langhagen | 2023 | 2023 | 25 | 25 | 2023-06-19 | 0:00 | 2023-06-19 | 3:00 | 0d, 3h | Continuous | Catenary |  | ST | [9 empty] | 80 | N | 1B24-004 |  | 2021-10-08
DB Netz AG | 1AC5-025 | Bremen - Hannover | <> | Seelze Ost | Seelze Ost | 2023 | 2023 | 26 | 27 | 2023-07-02 | 8:00 | 2023-07-04 | 16:00 | 2d, 8h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1AC5-025 |  | 2021-05-03
DB Netz AG | 1B24-005 | Rostock - Berlin | <> | Langhagen | Plaaz Abzw | 2023 | 2023 | 25 | 25 | 2023-06-23 | 0:00 | 2023-06-23 | 3:00 | 0d, 3h | Continuous | Catenary | T | [10 empty] | 80 | N | 1B24-005 |  | 2021-10-08
DB Netz AG | 1B24-006 | Rostock - Berlin | > | Langhagen | Langhagen | 2023 | 2023 | 25 | 25 | 2023-06-23 | 0:00 | 2023-06-23 | 3:00 | 0d, 3h | Continuous | Catenary |  | ST | [9 empty] | 80 | N | 1B24-006 |  | 2021-10-08
DB Netz AG | 1B39-001 | Hamburg - Magdeburg | <> | Uelzen Gbf | Uelzen | 2023 | 2023 | 20 | 20 | 2023-05-15 | 23:00 | 2023-05-19 | 5:00 | 3d, 6h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1B39-001 |  | 2022-05-03
DB Netz AG | 1B39-002 | Hamburg - Magdeburg | <> | Uelzen Gbf | Uelzen Gbf | 2023 | 2023 | 20 | 20 | 2023-05-15 | 23:00 | 2023-05-19 | 5:00 | 3d, 6h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 1B39-002 |  | 2021-11-19
DB Netz AG | 1B39-003 | Hamburg - Magdeburg | <> | Uelzen Gbf | Uelzen Gbf | 2023 | 2023 | 20 | 20 | 2023-05-15 | 23:00 | 2023-05-19 | 5:00 | 3d, 6h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1B39-003 |  | 2022-05-03
DB Netz AG | 1B3A-001 | Hamburg - Magdeburg | <> | Uelzen Gbf | Uelzen | 2023 | 2023 | 25 | 25 | 2023-06-19 | 23:00 | 2023-06-22 | 5:00 | 2d, 6h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1B3A-001 |  | 2022-05-03
DB Netz AG | 1B3A-002 | Hamburg - Magdeburg | <> | Uelzen Gbf | Uelzen Gbf | 2023 | 2023 | 25 | 25 | 2023-06-19 | 23:00 | 2023-06-22 | 5:00 | 2d, 6h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1B3A-002 |  | 2022-05-03
DB Netz AG | 1B3A-003 | Hamburg - Magdeburg | <> | Uelzen Gbf | Uelzen Gbf | 2023 | 2023 | 25 | 25 | 2023-06-19 | 23:00 | 2023-06-22 | 5:00 | 2d, 6h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 1B3A-003 |  | 2021-11-19
DB Netz AG | 1B40-001 | Hamburg - Magdeburg | <> | Uelzen Gbf | Uelzen | 2023 | 2023 | 26 | 27 | 2023-06-30 | 5:00 | 2023-07-03 | 5:00 | 3d, 0h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 1B40-001 |  | 2022-05-03
DB Netz AG | 1B40-002 | Hamburg - Magdeburg | <> | Uelzen Gbf | Uelzen Gbf | 2023 | 2023 | 26 | 27 | 2023-06-30 | 5:00 | 2023-07-03 | 5:00 | 3d, 0h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 1B40-002 |  | 2022-05-03
DB Netz AG | 1B40-003 | Hamburg - Magdeburg | <> | Uelzen Gbf | Uelzen Gbf | 2023 | 2023 | 26 | 27 | 2023-06-30 | 5:00 | 2023-07-03 | 5:00 | 3d, 0h | Continuous | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 1B40-003 |  | 2021-11-19
DB Netz AG | 1B40-004 | Hamburg - Magdeburg | <> | Fischerhof | Uelzen Gbf | 2023 | 2023 | 27 | 28 | 2023-07-08 | 21:00 | 2023-07-10 | 5:00 | 1d, 8h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | 1B40-004 |  | 2022-05-03
DB Netz AG | 1B40-005 | Hamburg - Magdeburg | <> | Uelzen Gbf | Uelzen Gbf | 2023 | 2023 | 27 | 28 | 2023-07-08 | 21:00 | 2023-07-10 | 5:00 | 1d, 8h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1B40-005 |  | 2022-05-03
DB Netz AG | 1B40-006 | Hamburg - Magdeburg | <> | Uelzen Gbf | Uelzen Gbf | 2023 | 2023 | 27 | 28 | 2023-07-08 | 21:00 | 2023-07-10 | 5:00 | 1d, 8h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 1B40-006 |  | 2021-11-19
DB Netz AG | 1959-006 | Rostock - Berlin | > | Neustrelitz Hbf | Kargow | 2023 | 2023 | 27 | 27 | 2023-07-06 | 21:00 | 2023-07-07 | 5:00 | 0d, 8h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1959-006
DB Netz AG | 1BF1-001 | Berlin - Dresden | > | Saarmund | Gensh Heide Mitt | 2023 | 2023 | 26 | 26 | 2023-06-29 | 22:00 | 2023-06-30 | 2:00 | 0d, 4h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1BF1-001 |  | 2021-08-27
DB Netz AG | 1BF1-003 | Berlin - Dresden | <> | Saarmund | Glasow Damm West | 2023 | 2023 | 26 | 26 | 2023-06-29 | 22:00 | 2023-06-30 | 6:00 | 0d, 8h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 1BF1-003 |  | 2021-08-27
DB Netz AG | 1BF1-005 | Berlin - Dresden | > | Genshagenr Heide | Glasow Damm West | 2023 | 2023 | 26 | 26 | 2023-06-30 | 2:00 | 2023-06-30 | 6:00 | 0d, 4h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1BF1-005 |  | 2021-08-27
DB Netz AG | 1C80-001 | Rostock - Berlin | > | Neustrelitz Hbf | Kargow | 2023 | 2023 | 27 | 27 | 2023-07-07 | 21:00 | 2023-07-08 | 1:00 | 0d, 4h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1C80-001
DB Netz AG | 1C80-003 | Rostock - Berlin | > | Kratzeburg | Waren (Müritz) | 2023 | 2023 | 27 | 27 | 2023-07-08 | 1:00 | 2023-07-08 | 5:00 | 0d, 4h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1C80-003
DB Netz AG | 1C80-004 | Rostock - Berlin | <> | Kargow | Kargow | 2023 | 2023 | 27 | 27 | 2023-07-08 | 1:00 | 2023-07-08 | 5:00 | 0d, 4h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1C80-004
DB Netz AG | 1D52-001 | Hannover - Magdeburg | > | Hannover Hbf | Waldhausen | 2023 | 2023 | 25 | 25 | 2023-06-19 | 21:40 | 2023-06-20 | 4:50 | 0d, 7h | Continuous | Catenary |  | LT | [9 empty] | 80 | N | 1D52-001 |  | 2022-07-19
DB Netz AG | 1DE0-001 | Bremen - Hannover | <> | Nienburg (Weser) | Nienburg (Weser) | 2023 | 2023 | 27 | 28 | 2023-07-09 | 23:00 | 2023-07-10 | 5:00 | 0d, 6h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 1DE0-001 |  | 2021-04-13
DB Netz AG | 1DE0-002 | Bremerhaven - Bremen | < | Rohrsen/Nienburg | Linsburg | 2023 | 2023 | 27 | 28 | 2023-07-09 | 23:00 | 2023-07-10 | 5:00 | 0d, 6h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 1DE0-002 |  | 2021-04-13
DB Netz AG | 1DE0-003 | Bremen - Hannover | <> | Nienburg (Weser) | Nienburg (Weser) | 2023 | 2023 | 27 | 28 | 2023-07-09 | 23:00 | 2023-07-10 | 5:00 | 0d, 6h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 1DE0-003 |  | 2021-04-13
DB Netz AG | 1DE0-004 | Bremerhaven - Bremen | < | Rohrsen/Nienburg | Linsburg | 2023 | 2023 | 27 | 28 | 2023-07-09 | 23:00 | 2023-07-10 | 5:00 | 0d, 6h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 1DE0-004 |  | 2021-04-13
DB Netz AG | 1F0E-001 | Hamburg - Magdeburg | < | Hmb-Hausbruch | Hmb Unterelbe | 2023 | 2023 | 20 | 21 | 2023-05-16 | 6:00 | 2023-05-23 | 6:00 | 7d, 0h | Continuous | Miscellaneous |  |  | S | [8 empty] | 80 | N | 1F0E-001 |  | 2021-06-16
DB Netz AG | 1F0E-002 | Hamburg - Magdeburg | > | Hmb Unterelbe | Hmb-Hausbruch | 2023 | 2023 | 20 | 21 | 2023-05-16 | 6:00 | 2023-05-23 | 6:00 | 7d, 0h | Continuous | Miscellaneous |  |  | S | [8 empty] | 80 | N | 1F0E-002 |  | 2021-06-16
DB Netz AG | 1F0E-003 | Hamburg - Magdeburg | > | Hmb-Harburg | Hmb-Hausbruch | 2023 | 2023 | 20 | 20 | 2023-05-19 | 22:00 | 2023-05-21 | 4:00 | 1d, 6h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 1F0E-003 |  | 2021-06-16
DB Netz AG | 1F0E-005 | Hamburg - Magdeburg | <> | Hmb Unterelbe | Hmb Unterelbe | 2023 | 2023 | 20 | 20 | 2023-05-20 | 4:00 | 2023-05-21 | 4:00 | 1d, 0h | Continuous | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 1F0E-005 |  | 2021-06-16
DB Netz AG | 1F0E-006 | Hamburg - Magdeburg | < | Hmb-Hausbruch | Hmb Unterelbe | 2023 | 2023 | 20 | 21 | 2023-05-21 | 1:00 | 2023-05-22 | 6:00 | 1d, 5h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 1F0E-006 |  | 2021-06-16
DB Netz AG | 1F0E-008 | Hamburg - Magdeburg | <> | Hmb Unterelbe | Hmb-Hausbruch | 2023 | 2023 | 20 | 20 | 2023-05-21 | 1:00 | 2023-05-21 | 4:00 | 0d, 3h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | 1F0E-008 |  | 2021-06-16
DB Netz AG | 1F20-001 | Hamburg - Magdeburg | <> | Hmb Unterelbe | Hmb-Hausbruch | 2023 | 2023 | 27 | 27 | 2023-07-09 | 0:00 | 2023-07-09 | 4:00 | 0d, 4h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | 1F20-001 |  | 2021-06-16
DB Netz AG | 1F52-001 | Bremerhaven - Bremen | > | Brm-Sebaldsbrück | Bremen Hbf | 2023 | 2023 | 23 | 23 | 2023-06-05 | 23:00 | 2023-06-09 | 5:00 | 3d, 6h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 1F52-001 |  | 2022-07-26
DB Netz AG | 1FE6-001 | Hamburg - Magdeburg | <> | Stendal Hbf | Stendal Hbf | 2023 | 2023 | 20 | 20 | 2023-05-19 | 8:00 | 2023-05-21 | 18:00 | 2d, 10h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 1FE6-001 |  | 2022-07-15
DB Netz AG | 2005-001 | Hannover - Magdeburg | <> | Marienborn | Marienborn | 2023 | 2023 | 23 | 23 | 2023-06-09 | 21:35 | 2023-06-09 | 21:50 | 0d, 0h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 2005-001 |  | 2021-10-13
DB Netz AG | 2005-002 | Hannover - Magdeburg | < | Harbke | Wefensleben | 2023 | 2023 | 23 | 23 | 2023-06-09 | 21:50 | 2023-06-09 | 23:50 | 0d, 2h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 2005-002 |  | 2021-10-13
DB Netz AG | 2005-003 | Hannover - Magdeburg | <> | Marienborn | Marienborn | 2023 | 2023 | 23 | 23 | 2023-06-09 | 21:50 | 2023-06-09 | 23:50 | 0d, 2h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 2005-003
DB Netz AG | 2005-005 | Hannover - Magdeburg | <> | Harbke | Marienborn | 2023 | 2023 | 23 | 23 | 2023-06-09 | 23:50 | 2023-06-10 | 0:40 | 0d, 0h | Continuous | Maintenance | T | [10 empty] | 80 | N | 2005-005
DB Netz AG | 2005-006 | Hannover - Magdeburg | > | Wefensleben | Marienborn | 2023 | 2023 | 23 | 23 | 2023-06-10 | 0:40 | 2023-06-10 | 2:30 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 2005-006
DB Netz AG | 2005-007 | Hannover - Magdeburg | <> | Marienborn | Marienborn | 2023 | 2023 | 23 | 23 | 2023-06-10 | 0:40 | 2023-06-10 | 2:30 | 0d, 1h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 2005-007
DB Netz AG | 2005-009 | Hannover - Magdeburg | <> | Marienborn | Wefensleben | 2023 | 2023 | 23 | 23 | 2023-06-10 | 2:30 | 2023-06-10 | 3:20 | 0d, 0h | Continuous | Maintenance | T | [10 empty] | 80 | N | 2005-009
DB Netz AG | 200C-002 | Hannover - Magdeburg | <> | Marienborn | Marienborn | 2023 | 2023 | 23 | 23 | 2023-06-08 | 20:45 | 2023-06-08 | 21:00 | 0d, 0h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 200C-002
DB Netz AG | 200C-003 | Hannover - Magdeburg | > | Wefensleben | Harbke | 2023 | 2023 | 23 | 23 | 2023-06-08 | 21:00 | 2023-06-09 | 5:00 | 0d, 8h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 200C-003 |  | 2021-10-13
DB Netz AG | 200C-004 | Hannover - Magdeburg | <> | Marienborn | Wefensleben | 2023 | 2023 | 23 | 23 | 2023-06-08 | 21:00 | 2023-06-09 | 5:00 | 0d, 8h | Continuous | Track & Rail |  |  |  | P | [7 empty] | 80 | N | 200C-004
DB Netz AG | 200C-005 | Hannover - Magdeburg | > | Wefensleben | Marienborn | 2023 | 2023 | 23 | 23 | 2023-06-08 | 21:00 | 2023-06-09 | 5:00 | 0d, 8h | Continuous | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | 200C-005
DB Netz AG | 2012-001 | Hannover - Magdeburg | <> | Marienborn | Marienborn | 2023 | 2023 | 23 | 23 | 2023-06-07 | 20:45 | 2023-06-07 | 21:00 | 0d, 0h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 2012-001
DB Netz AG | 2012-002 | Hannover - Magdeburg | <> | Harbke | Marienborn | 2023 | 2023 | 23 | 23 | 2023-06-07 | 21:00 | 2023-06-08 | 5:00 | 0d, 8h | Continuous | Track & Rail |  |  |  | P | [7 empty] | 80 | N | 2012-002
DB Netz AG | 2012-003 | Hannover - Magdeburg | > | Wefensleben | Harbke | 2023 | 2023 | 23 | 23 | 2023-06-07 | 21:00 | 2023-06-08 | 5:00 | 0d, 8h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 2012-003
DB Netz AG | 2012-004 | Hannover - Magdeburg | > | Marienborn | Harbke | 2023 | 2023 | 23 | 23 | 2023-06-07 | 21:00 | 2023-06-08 | 5:00 | 0d, 8h | Continuous | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | 2012-004
DB Netz AG | 208D-001 | Rostock - Berlin | <> | Rostock Seehafen | Rostock Seehafen | 2023 | 2023 | 26 | 35 | 2023-06-26 | 6:00 | 2023-09-02 | 6:00 | 68d, 0h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 208D-001
DB Netz AG | 2017-001 | Hannover - Magdeburg | <> | Marienborn | Marienborn | 2023 | 2023 | 23 | 23 | 2023-06-06 | 20:45 | 2023-06-06 | 21:00 | 0d, 0h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 2017-001
DB Netz AG | 1FE6-002 | Hannover - Magdeburg | <> | Stendal Hbf | Stendal Hbf | 2023 | 2023 | 20 | 20 | 2023-05-21 | 1:40 | 2023-05-21 | 4:10 | 0d, 2h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 1FE6-002 |  | 2022-07-15
DB Netz AG | 2017-002 | Hannover - Magdeburg | <> | Helmstedt | Marienborn | 2023 | 2023 | 23 | 23 | 2023-06-06 | 21:00 | 2023-06-07 | 5:00 | 0d, 8h | Continuous | Track & Rail |  |  |  | P | [7 empty] | 80 | N | 2017-002
DB Netz AG | 2017-003 | Hannover - Magdeburg | > | Marienborn | Helmstedt | 2023 | 2023 | 23 | 23 | 2023-06-06 | 21:00 | 2023-06-07 | 5:00 | 0d, 8h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 2017-003 |  | 2021-10-13
DB Netz AG | 2017-004 | Hannover - Magdeburg | > | Marienborn | Helmstedt | 2023 | 2023 | 23 | 23 | 2023-06-06 | 21:00 | 2023-06-07 | 5:00 | 0d, 8h | Continuous | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | 2017-004
DB Netz AG | 1FE6-003 | Hamburg - Magdeburg | <> | Stendal Hbf | Stendal Hbf | 2023 | 2023 | 20 | 20 | 2023-05-21 | 1:40 | 2023-05-21 | 4:10 | 0d, 2h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 1FE6-003 |  | 2022-07-15
DB Netz AG | 1FE6-008 | Hamburg - Magdeburg | <> | Stendal Hbf | Stendal Hbf | 2023 | 2023 | 20 | 20 | 2023-05-19 | 21:20 | 2023-05-19 | 23:30 | 0d, 2h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 1FE6-008 |  | 2022-07-15
DB Netz AG | 1FE6-009 | Hamburg - Magdeburg | <> | Stendal Hbf | Stendal Hbf | 2023 | 2023 | 20 | 20 | 2023-05-19 | 23:30 | 2023-05-20 | 3:40 | 0d, 4h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 1FE6-009 |  | 2022-07-15
DB Netz AG | 2047-003 | Wilhelmshaven - Bremen | > | Bookholzberg | Delmenhorst | 2023 | 2023 | 19 | 19 | 2023-05-10 | 22:10 | 2023-05-12 | 4:50 | 1d, 6h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 2047-003 |  | 2021-10-14
DB Netz AG | 2047-004 | Wilhelmshaven - Bremen | <> | Delmenhorst | Delmenhorst | 2023 | 2023 | 19 | 19 | 2023-05-10 | 22:00 | 2023-05-12 | 5:00 | 1d, 7h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 2047-004 |  | 2021-10-14
DB Netz AG | 2053-002 | Rostock - Berlin | <> | Biesdf Kr Nord | Biesdf Kr Nord | 2023 | 2023 | 19 | 20 | 2023-05-12 | 22:00 | 2023-05-15 | 4:00 | 2d, 6h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 2053-002 |  | 2021-05-20
DB Netz AG | 2053-003 | Rostock - Berlin | <> | Biesdf Kr Nord | Ahrensfelde | 2023 | 2023 | 26 | 27 | 2023-06-30 | 22:00 | 2023-07-03 | 4:00 | 2d, 6h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | 2053-003 |  | 2021-10-15
DB Netz AG | 2053-004 | Rostock - Berlin | <> | Biesdf Kr Nord | Biesdf Kr Nord | 2023 | 2023 | 26 | 27 | 2023-06-30 | 22:00 | 2023-07-03 | 4:00 | 2d, 6h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 2053-004 |  | 2021-10-15
DB Netz AG | 20.5 | Bremen - Hannover | <> | Brm-Sebaldsbrück | Brm-Sebaldsbrück | 2023 | 2023 | 27 | 27 | 2023-07-08 | 23:00 | 2023-07-09 | 5:00 | 0d, 6h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 20.5 |  | 2022-07-26
DB Netz AG | 2061-001 | Wilhelmshaven - Bremen | <> | Oldb (Oldb) Hbf | Oldb (Oldb) Hbf | 2023 | 2023 | 23 | 27 | 2023-06-05 | 7:00 | 2023-07-03 | 5:00 | 27d, 22h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 2061-001 |  | 2021-05-04
DB Netz AG | 2061-002 | Wilhelmshaven - Bremen | <> | Oldb (Oldb) Hbf | Oldb (Oldb) Hbf | 2023 | 2023 | 26 | 27 | 2023-07-02 | 23:00 | 2023-07-03 | 6:00 | 0d, 7h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 2061-002 |  | 2021-05-04
DB Netz AG | 2061-003 | Wilhelmshaven - Bremen | > | Oldb (Oldb) Hbf | Tweelbäke | 2023 | 2023 | 26 | 27 | 2023-07-02 | 23:00 | 2023-07-03 | 6:00 | 0d, 7h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 2061-003 |  | 2021-12-02
DB Netz AG | 1FE6-011 | Hamburg - Magdeburg | <> | Stendal Hbf | Stendal Hbf | 2023 | 2023 | 20 | 20 | 2023-05-19 | 23:30 | 2023-05-20 | 3:40 | 0d, 4h | Continuous | Maintenance | T | [10 empty] | 80 | N | 1FE6-011 |  | 2022-07-15
DB Netz AG | 201C-001 | Hamburg - Magdeburg | > | Meckelfeld | Hmb-Harburg | 2023 | 2023 | 22 | 23 | 2023-06-02 | 23:00 | 2023-06-05 | 5:00 | 2d, 6h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | 201C-001 |  | 2022-04-27
DB Netz AG | 201C-003 | Hamburg - Magdeburg | > | Meckelfeld | Hmb-Harburg | 2023 | 2023 | 24 | 24 | 2023-06-12 | 4:00 | 2023-06-14 | 6:00 | 2d, 2h | Continuous | Miscellaneous |  |  | S | [8 empty] | 80 | N | 201C-003 |  | 2022-04-27
DB Netz AG | 201C-004 | Hamburg - Magdeburg | > | Hmb-Harburg | Hmb-Harburg | 2023 | 2023 | 22 | 23 | 2023-06-02 | 23:00 | 2023-06-05 | 5:00 | 2d, 6h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 201C-004 |  | 2022-04-27
DB Netz AG | 1FE6-012 | Hamburg - Magdeburg | <> | Stendal Hbf | Stendal Hbf | 2023 | 2023 | 20 | 20 | 2023-05-19 | 21:20 | 2023-05-19 | 23:30 | 0d, 2h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 1FE6-012 |  | 2022-07-15
DB Netz AG | 201C-007 | Hamburg - Magdeburg | < | Hmb-Harburg | Meckelfeld | 2023 | 2023 | 25 | 25 | 2023-06-19 | 4:00 | 2023-06-21 | 6:00 | 2d, 2h | Continuous | Miscellaneous |  |  | S | [8 empty] | 80 | N | 201C-007 |  | 2022-04-27
DB Netz AG | 20A1-001 | Magdeburg - Falkenberg | <> | Biederitz | Biederitz | 2023 | 2023 | 19 | 19 | 2023-05-12 | 19:45 | 2023-05-12 | 20:00 | 0d, 0h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 20A1-001 |  | 2021-05-20
DB Netz AG | 20A1-002 | Magdeburg - Falkenberg | > | Brücke | Biederitz | 2023 | 2023 | 19 | 19 | 2023-05-12 | 20:00 | 2023-05-12 | 21:00 | 0d, 1h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 20A1-002 |  | 2021-05-20
DB Netz AG | 20A1-003 | Magdeburg - Falkenberg | < | Biederitz | Biederitz | 2023 | 2023 | 19 | 19 | 2023-05-12 | 20:00 | 2023-05-12 | 21:00 | 0d, 1h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 20A1-003 |  | 2021-05-20
DB Netz AG | 20A1-004 | Magdeburg - Falkenberg | > | Biederitz | Biederitz | 2023 | 2023 | 19 | 19 | 2023-05-12 | 20:00 | 2023-05-12 | 21:00 | 0d, 1h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 20A1-004 |  | 2021-05-20
DB Netz AG | 20A1-005 | Magdeburg - Falkenberg | > | Biederitz | Biederitz | 2023 | 2023 | 19 | 19 | 2023-05-12 | 20:00 | 2023-05-12 | 21:00 | 0d, 1h | Continuous | Switch |  |  |  |  | X | [6 empty] | 80 | N | 20A1-005 |  | 2021-05-20
DB Netz AG | 20A1-006 | Magdeburg - Falkenberg | > | Biederitz | Königsborn | 2023 | 2023 | 19 | 19 | 2023-05-12 | 20:00 | 2023-05-12 | 21:00 | 0d, 1h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 20A1-006 |  | 2021-05-20
DB Netz AG | 20A1-007 | Magdeburg - Falkenberg | <> | Biederitz | Biederitz | 2023 | 2023 | 19 | 19 | 2023-05-12 | 21:00 | 2023-05-13 | 4:00 | 0d, 7h | Continuous | Switch |  |  |  | P | [7 empty] | 80 | N | 20A1-007 |  | 2021-05-20
DB Netz AG | 20A1-008 | Magdeburg - Falkenberg | <> | Biederitz | Biederitz | 2023 | 2023 | 19 | 19 | 2023-05-12 | 21:00 | 2023-05-13 | 4:00 | 0d, 7h | Continuous | Switch | T | [10 empty] | 80 | N | 20A1-008 |  | 2021-05-20
DB Netz AG | 20A1-009 | Magdeburg - Falkenberg | <> | Biederitz | Biederitz | 2023 | 2023 | 19 | 19 | 2023-05-12 | 20:00 | 2023-05-12 | 21:00 | 0d, 1h | Continuous | Switch |  |  |  | P | [7 empty] | 80 | N | 20A1-009 |  | 2021-05-20
DB Netz AG | 20A1-010 | Magdeburg - Falkenberg | <> | Biederitz | Biederitz | 2023 | 2023 | 19 | 19 | 2023-05-12 | 20:00 | 2023-05-12 | 21:00 | 0d, 1h | Continuous | Switch |  |  |  | P | [7 empty] | 80 | N | 20A1-010 |  | 2021-10-14
DB Netz AG | 20A1-011 | Magdeburg - Falkenberg | <> | Biederitz | Biederitz | 2023 | 2023 | 19 | 19 | 2023-05-12 | 21:00 | 2023-05-13 | 4:00 | 0d, 7h | Continuous | Switch | T | [10 empty] | 80 | N | 20A1-011 |  | 2021-05-20
DB Netz AG | 20A1-012 | Magdeburg - Falkenberg | <> | Biederitz | Biederitz | 2023 | 2023 | 19 | 19 | 2023-05-12 | 21:00 | 2023-05-13 | 4:00 | 0d, 7h | Continuous | Switch |  |  |  |  | X | [6 empty] | 80 | N | 20A1-012 |  | 2021-05-20
DB Netz AG | 20A1-013 | Magdeburg - Falkenberg | < | Brücke | Biederitz | 2023 | 2023 | 19 | 19 | 2023-05-12 | 21:00 | 2023-05-13 | 4:00 | 0d, 7h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 20A1-013 |  | 2021-10-14
DB Netz AG | 2105-008 | Rostock - Berlin | <> | Birkenwerd b Bln | Hohen Neuend Sw | 2023 | 2023 | 23 | 24 | 2023-06-11 | 22:00 | 2023-06-16 | 4:00 | 4d, 6h | Periodical | Signal | T | [10 empty] | 80 | N | 2105-008 |  | 2022-05-16
DB Netz AG | 22.3 | Rostock - Berlin | <> | Waren (Müritz) | Waren (Müritz) | 2023 | 2023 | 25 | 26 | 2023-06-19 | 8:00 | 2023-06-29 | 18:00 | 10d, 10h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 22.3 |  | 2021-05-20
DB Netz AG | 2105-009 | Rostock - Berlin | <> | Birkenwerder N | Birkenwerd b Bln | 2023 | 2023 | 25 | 26 | 2023-06-25 | 22:00 | 2023-06-30 | 4:00 | 4d, 6h | Periodical | Signal | T | [10 empty] | 80 | N | 2105-009 |  | 2021-11-15
DB Netz AG | 2105-012 | Rostock - Berlin | <> | Birkenwerder N | Birkenwerder S-B | 2023 | 2023 | 25 | 26 | 2023-06-25 | 22:00 | 2023-06-30 | 4:00 | 4d, 6h | Periodical | Signal | T | [10 empty] | 80 | N | 2105-012 |  | 2022-05-16
DB Netz AG | 2105-013 | Rostock - Berlin | <> | Birkenwerder S-B | Birkenwerd b Bln | 2023 | 2023 | 25 | 26 | 2023-06-25 | 22:00 | 2023-06-30 | 4:00 | 4d, 6h | Periodical | Signal | T | [10 empty] | 80 | N | 2105-013 |  | 2021-11-15
DB Netz AG | 215D-035 | Rostock - Berlin | <> | Birkenwerder S-B | Birkenwerder N | 2023 | 2023 | 26 | 27 | 2023-06-30 | 9:00 | 2023-07-03 | 15:00 | 3d, 6h | Periodical | Signal | T | [10 empty] | 80 | N | 215D-035 |  | 2021-11-15
DB Netz AG | 272A-001 | Rostock - Berlin | <> | Kavelstorf | Dalwitzhof | 2023 | 2023 | 21 | 24 | 2023-05-26 | 4:00 | 2023-06-16 | 10:00 | 21d, 6h | Continuous | Bridge |  |  | S | [8 empty] | 80 | N | 272A-001 |  | 2021-08-18
DB Netz AG | 266C-006 | Rostock - Berlin | <> | Kavelstorf | Dalwitzhof | 2023 | 2023 | 20 | 20 | 2023-05-16 | 23:00 | 2023-05-19 | 5:00 | 2d, 6h | Periodical | Bridge | T | [10 empty] | 80 | N | 266C-006 |  | 2022-05-09
DB Netz AG | 266C-007 | Rostock - Berlin | <> | Kavelstorf | Dalwitzhof | 2023 | 2023 | 20 | 21 | 2023-05-19 | 23:00 | 2023-05-27 | 6:00 | 7d, 7h | Periodical | Bridge | T | [10 empty] | 80 | N | 266C-007 |  | 2022-05-09
DB Netz AG | 266C-008 | Rostock - Berlin | <> | Kavelstorf | Dalwitzhof | 2023 | 2023 | 20 | 21 | 2023-05-20 | 22:20 | 2023-05-28 | 6:00 | 7d, 7h | Periodical | Bridge | T | [10 empty] | 80 | N | 266C-008 |  | 2022-05-09
DB Netz AG | 266C-009 | Rostock - Berlin | <> | Kavelstorf | Dalwitzhof | 2023 | 2023 | 21 | 22 | 2023-05-22 | 23:00 | 2023-06-02 | 5:00 | 10d, 6h | Periodical | Bridge | T | [10 empty] | 80 | N | 266C-009 |  | 2022-05-09
DB Netz AG | 1889-006 | Falkenberg - Dresden | < | Kottewitz | Leckwitz | 2023 | 2023 | 21 | 21 | 2023-05-22 | 21:00 | 2023-05-22 | 23:00 | 0d, 2h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1889-006
DB Netz AG | 1889-007 | Falkenberg - Dresden | < | Kottewitz | Leckwitz | 2023 | 2023 | 21 | 21 | 2023-05-22 | 21:00 | 2023-05-23 | 21:30 | 1d, 0h | Periodical | Track & Rail |  | LT | [9 empty] | 80 | N | 1889-007
DB Netz AG | 1BDD-001 | Rostock - Berlin | <> | Laage (Meckl) | Kavelstorf | 2023 | 2023 | 20 | 20 | 2023-05-15 | 8:00 | 2023-05-16 | 16:00 | 1d, 8h | Periodical | Track & Rail | T | [10 empty] | 80 | N | 1BDD-001 |  | 2021-05-26
DB Netz AG | 1BDD-002 | Rostock - Berlin | <> | Laage (Meckl) | Kavelstorf | 2023 | 2023 | 21 | 21 | 2023-05-23 | 7:30 | 2023-05-25 | 16:00 | 2d, 8h | Periodical | Track & Rail | T | [10 empty] | 80 | N | 1BDD-002 |  | 2021-05-26
DB Netz AG | 1BDD-003 | Rostock - Berlin | <> | Laage (Meckl) | Laage (Meckl) | 2023 | 2023 | 21 | 21 | 2023-05-23 | 7:30 | 2023-05-25 | 16:00 | 2d, 8h | Periodical | Track & Rail |  | ST | [9 empty] | 80 | N | 1BDD-003 |  | 2021-05-26
DB Netz AG | 2FC1-001 | Rostock - Berlin | > | Lalendorf Ost | Laage (Meckl) | 2023 | 2023 | 22 | 22 | 2023-05-29 | 7:00 | 2023-05-31 | 15:45 | 2d, 8h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | 2FC1-001 |  | 2022-01-31
DB Netz AG | 2FC1-002 | Rostock - Berlin | > | Lalendorf Ost | Laage (Meckl) | 2023 | 2023 | 22 | 22 | 2023-06-01 | 7:00 | 2023-06-02 | 15:45 | 1d, 8h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | 2FC1-002 |  | 2022-01-31
DB Netz AG | 2FC1-003 | Rostock - Berlin | > | Langhagen | Plaaz Abzw | 2023 | 2023 | 22 | 22 | 2023-06-03 | 7:00 | 2023-06-03 | 15:45 | 0d, 8h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | 2FC1-003 |  | 2022-01-31
DB Netz AG | 2FC1-004 | Rostock - Berlin | < | Laage (Meckl) | Plaaz Abzw | 2023 | 2023 | 23 | 23 | 2023-06-05 | 7:00 | 2023-06-06 | 15:45 | 1d, 8h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | 2FC1-004 |  | 2022-01-31
DB Netz AG | 2FC1-005 | Rostock - Berlin | < | Laage (Meckl) | Langhagen | 2023 | 2023 | 23 | 23 | 2023-06-07 | 7:00 | 2023-06-08 | 15:45 | 1d, 8h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | 2FC1-005 |  | 2022-01-31
DB Netz AG | 2FC1-006 | Rostock - Berlin | <> | Priemerbg-NUP Gü | Plaaz Abzw | 2023 | 2023 | 23 | 23 | 2023-06-07 | 7:00 | 2023-06-08 | 15:45 | 1d, 8h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | 2FC1-006 |  | 2022-01-31
DB Netz AG | 2FC1-007 | Rostock - Berlin | < | Laage (Meckl) | Langhagen | 2023 | 2023 | 23 | 23 | 2023-06-09 | 7:00 | 2023-06-09 | 15:45 | 0d, 8h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 2FC1-007 |  | 2022-01-31
DB Netz AG | 2FC1-008 | Rostock - Berlin | <> | Lalendorf Ost | Lalendorf | 2023 | 2023 | 23 | 23 | 2023-06-09 | 7:00 | 2023-06-09 | 15:45 | 0d, 8h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | 2FC1-008 |  | 2022-01-31
DB Netz AG | A43-003 | Bremerhaven - Bremen | <> | Bremen Rbf Abzw | Bremen-Burg | 2023 | 2023 | 28 | 31 | 2023-07-13 | 23:00 | 2023-08-01 | 5:00 | 18d, 6h | Periodical | Miscellaneous |  |  | S | [8 empty] | 80 | N | A43-003 |  | 2021-06-08
DB Netz AG | A43-004 | Bremerhaven - Bremen | < | Bremen-Burg | Bremen Rbf Abzw | 2023 | 2023 | 28 | 31 | 2023-07-13 | 23:00 | 2023-08-01 | 5:00 | 18d, 6h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | A43-004 |  | 2021-05-11
DB Netz AG | A43-005 | Bremerhaven - Bremen | > | Bremen Hbf | Bremen-Burg | 2023 | 2023 | 35 | 35 | 2023-09-01 | 1:30 | 2023-09-01 | 4:30 | 0d, 3h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | A43-005 |  | 2021-05-11
DB Netz AG | A43-002 | Bremerhaven - Bremen | < | Bremen-Burg | Bremen Rbf Abzw | 2023 | 2023 | 35 | 35 | 2023-08-31 | 22:30 | 2023-09-01 | 1:30 | 0d, 3h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | A43-002 |  | 2021-05-11
DB Netz AG | A59-006 | Bremerhaven - Bremen | > | Bremen-Burg | Bremen-Burg | 2023 | 2023 | 31 | 31 | 2023-08-04 | 1:00 | 2023-08-04 | 4:30 | 0d, 3h | Continuous | Bridge |  | ST | [9 empty] | 80 | N | A59-006 |  | 2021-05-21
DB Netz AG | A59-001 | Bremerhaven - Bremen | <> | Bremen-Vegesack | Bremen-Burg | 2023 | 2023 | 31 | 33 | 2023-08-04 | 1:00 | 2023-08-14 | 4:30 | 10d, 3h | Continuous | Bridge | T | [10 empty] | 80 | N | A59-001 |  | 2021-07-22
DB Netz AG | A59-004 | Bremerhaven - Bremen | <> | Bremen-Vegesack | Bremen-Burg | 2023 | 2023 | 31 | 33 | 2023-08-04 | 1:00 | 2023-08-14 | 4:30 | 10d, 3h | Continuous | Bridge | T | [10 empty] | 80 | N | A59-004 |  | 2021-07-22
DB Netz AG | A59-002 | Bremerhaven - Bremen | > | Bremen-Burg | Bremen-Burg | 2023 | 2023 | 31 | 33 | 2023-08-05 | 0:00 | 2023-08-14 | 4:30 | 9d, 4h | Periodical | Bridge |  | ST | [9 empty] | 80 | N | A59-002 |  | 2021-07-22
DB Netz AG | A85-001 | Magdeburg - Falkenberg | <> | Mg-Sudenburg | Mg-Sudenburg | 2023 | 2023 | 34 | 35 | 2023-08-21 | 21:00 | 2023-08-29 | 5:00 | 7d, 8h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | A85-001 |  | 2021-05-31
DB Netz AG | A85-002 | Magdeburg - Falkenberg | <> | Mg-Sudenburg | Mg-Sudenburg | 2023 | 2023 | 32 | 33 | 2023-08-07 | 21:00 | 2023-08-19 | 5:00 | 11d, 8h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | A85-002 |  | 2021-05-31
DB Netz AG | AFD-016 | Hannover - Magdeburg | < | Magdeburg Hbf | Magdeburg-Buckau | 2023 | 2023 | 35 | 35 | 2023-08-29 | 8:00 | 2023-08-30 | 16:00 | 1d, 8h | Periodical | Signal |  | LT | [9 empty] | 80 | N | AFD-016 |  | 2021-05-26
DB Netz AG | AFD-027 | Hannover - Magdeburg | <> | Mg-Sudenburg | Magdeburg-Buckau | 2023 | 2023 | 36 | 37 | 2023-09-08 | 8:00 | 2023-09-11 | 16:00 | 3d, 8h | Periodical | Signal | T | [10 empty] | 80 | N | AFD-027 |  | 2021-05-10
DB Netz AG | AFD-001 | Hamburg - Magdeburg | < | Magdeburg Hbf | Magdeburg-Buckau | 2023 | 2023 | 36 | 37 | 2023-09-08 | 8:00 | 2023-09-11 | 16:00 | 3d, 8h | Periodical | Signal |  | LT | [9 empty] | 80 | N | AFD-001 |  | 2021-05-10
DB Netz AG | AFD-008 | Hannover - Magdeburg | <> | Mg-Sudenburg | Magdeburg-Buckau | 2023 | 2023 | 36 | 36 | 2023-09-06 | 8:00 | 2023-09-07 | 16:00 | 1d, 8h | Periodical | Signal | T | [10 empty] | 80 | N | AFD-008 |  | 2021-06-04
DB Netz AG | AFD-020 | Hamburg - Magdeburg | <> | Magdeburg Hbf | Magdeburg-Buckau | 2023 | 2023 | 36 | 36 | 2023-09-06 | 8:00 | 2023-09-07 | 16:00 | 1d, 8h | Periodical | Signal | T | [10 empty] | 80 | N | AFD-020 |  | 2021-05-18
DB Netz AG | AFD-002 | Hannover - Magdeburg | <> | Magdeburg Hbf | Mg Südseite | 2023 | 2023 | 33 | 33 | 2023-08-15 | 8:00 | 2023-08-18 | 16:00 | 3d, 8h | Periodical | Signal |  | ST | [9 empty] | 80 | N | AFD-002 |  | 2021-06-04
DB Netz AG | AFD-013 | Hannover - Magdeburg | <> | Magdeburg-Buckau | Magdeburg Hbf | 2023 | 2023 | 33 | 33 | 2023-08-15 | 8:00 | 2023-08-18 | 16:00 | 3d, 8h | Periodical | Signal | T | [10 empty] | 80 | N | AFD-013 |  | 2021-05-12
DB Netz AG | AFD-004 | Hannover - Magdeburg | <> | Magdeburg-Buckau | Magdeburg Hbf | 2023 | 2023 | 33 | 33 | 2023-08-15 | 8:00 | 2023-08-18 | 16:00 | 3d, 8h | Periodical | Signal |  |  |  |  | X | [6 empty] | 80 | N | AFD-004 |  | 2021-05-12
DB Netz AG | AFD-009 | Hannover - Magdeburg | > | Magdeburg Hbf | Magdeburg-Buckau | 2023 | 2023 | 32 | 32 | 2023-08-09 | 8:00 | 2023-08-10 | 16:00 | 1d, 8h | Periodical | Signal |  | LT | [9 empty] | 80 | N | AFD-009 |  | 2021-05-18
DB Netz AG | AFD-023 | Hannover - Magdeburg | <> | Magdeburg Hbf | Magdeburg Hbf | 2023 | 2023 | 32 | 32 | 2023-08-09 | 8:00 | 2023-08-10 | 16:00 | 1d, 8h | Periodical | Signal |  | ST | [9 empty] | 80 | N | AFD-023 |  | 2021-05-18
DB Netz AG | AFD-017 | Hannover - Magdeburg | > | Magdeburg Hbf | Magdeburg Hbf | 2023 | 2023 | 32 | 32 | 2023-08-07 | 8:00 | 2023-08-08 | 16:00 | 1d, 8h | Periodical | Signal |  | ST | [9 empty] | 80 | N | AFD-017 |  | 2021-06-04
DB Netz AG | AFD-021 | Hannover - Magdeburg | <> | Magdeburg Hbf | Mg Südseite | 2023 | 2023 | 32 | 33 | 2023-08-11 | 8:00 | 2023-08-14 | 16:00 | 3d, 8h | Periodical | Signal | T | [10 empty] | 80 | N | AFD-021 |  | 2021-05-18
DB Netz AG | AFD-010 | Hannover - Magdeburg | < | Magdeburg-Buckau | Magdeburg Hbf | 2023 | 2023 | 32 | 33 | 2023-08-11 | 8:00 | 2023-08-14 | 16:00 | 3d, 8h | Periodical | Signal |  | LT | [9 empty] | 80 | N | AFD-010 |  | 2021-05-18
DB Netz AG | AFD-005 | Hannover - Magdeburg | <> | Magdeburg Hbf | Mg Südseite | 2023 | 2023 | 32 | 33 | 2023-08-11 | 8:00 | 2023-08-14 | 16:00 | 3d, 8h | Periodical | Signal |  | ST | [9 empty] | 80 | N | AFD-005 |  | 2021-05-18
DB Netz AG | AFD-029 | Hannover - Magdeburg | <> | Mg-Fermersleben | Magdeburg Hbf | 2023 | 2023 | 34 | 35 | 2023-08-25 | 8:00 | 2023-08-28 | 16:00 | 3d, 8h | Periodical | Signal | T | [10 empty] | 80 | N | AFD-029 |  | 2021-06-04
DB Netz AG | AFD-006 | Hannover - Magdeburg | > | Magdeburg Hbf | Magdeburg-Buckau | 2023 | 2023 | 32 | 32 | 2023-08-07 | 8:00 | 2023-08-08 | 16:00 | 1d, 8h | Periodical | Signal |  | LT | [9 empty] | 80 | N | AFD-006 |  | 2021-05-17
DB Netz AG | AFD-026 | Hamburg - Magdeburg | > | Magdeburg-Buckau | Magdeburg Hbf | 2023 | 2023 | 36 | 36 | 2023-09-04 | 8:00 | 2023-09-05 | 16:00 | 1d, 8h | Periodical | Signal |  | LT | [9 empty] | 80 | N | AFD-026 |  | 2021-05-18
DB Netz AG | AFD-011 | Hannover - Magdeburg | <> | Magdeburg Hbf | Mg Südseite | 2023 | 2023 | 34 | 34 | 2023-08-21 | 8:00 | 2023-08-24 | 16:00 | 3d, 8h | Periodical | Signal |  | ST | [9 empty] | 80 | N | AFD-011 |  | 2021-05-18
DB Netz AG | AFD-012 | Hannover - Magdeburg | > | Magdeburg Hbf | Magdeburg-Buckau | 2023 | 2023 | 34 | 34 | 2023-08-21 | 8:00 | 2023-08-24 | 16:00 | 3d, 8h | Periodical | Signal |  | LT | [9 empty] | 80 | N | AFD-012 |  | 2021-06-04
DB Netz AG | AFD-018 | Hannover - Magdeburg | < | Magdeburg-Buckau | Magdeburg Hbf | 2023 | 2023 | 34 | 34 | 2023-08-21 | 8:00 | 2023-08-24 | 16:00 | 3d, 8h | Periodical | Signal |  | LT | [9 empty] | 80 | N | AFD-018 |  | 2021-05-18
DB Netz AG | B07-010 | Bremen - Hannover | > | Bremen Hbf | Bremen Hbf | 2023 | 2023 | 31 | 31 | 2023-08-03 | 7:00 | 2023-08-03 | 13:00 | 0d, 6h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | B07-010 |  | 2021-05-12
DB Netz AG | B07-020 | Bremen - Hannover | <> | Bremen Hbf | Bremen Hbf | 2023 | 2023 | 33 | 33 | 2023-08-14 | 14:00 | 2023-08-14 | 22:00 | 0d, 8h | Continuous | Track & Rail | T | [10 empty] | 80 | N | B07-020 |  | 2021-07-22
DB Netz AG | B07-011 | Bremen - Hannover | <> | Bremen Hbf | Bremen Rbf Ausf | 2023 | 2023 | 33 | 33 | 2023-08-14 | 14:00 | 2023-08-14 | 22:00 | 0d, 8h | Continuous | Track & Rail | T | [10 empty] | 80 | N | B07-011 |  | 2021-05-12
DB Netz AG | B07-018 | Bremen - Hannover | > | Bremen Hbf | Bremen Hbf | 2023 | 2023 | 33 | 33 | 2023-08-14 | 18:00 | 2023-08-14 | 21:30 | 0d, 3h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | B07-018 |  | 2021-05-12
DB Netz AG | B07-021 | Bremen - Hannover | > | Bremen Hbf | Bremen Hbf | 2023 | 2023 | 31 | 33 | 2023-08-03 | 7:00 | 2023-08-16 | 14:00 | 13d, 7h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | B07-021 |  | 2021-05-12
DB Netz AG | B07-015 | Bremen - Hannover | > | Bremen Hbf | Bremen Hbf | 2023 | 2023 | 31 | 31 | 2023-08-01 | 7:00 | 2023-08-01 | 12:00 | 0d, 5h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | B07-015 |  | 2021-07-22
DB Netz AG | B07-007 | Bremen - Hannover | <> | Bremen Hbf | Bremen Rbf Ausf | 2023 | 2023 | 31 | 31 | 2023-08-01 | 7:00 | 2023-08-01 | 12:00 | 0d, 5h | Continuous | Track & Rail | T | [10 empty] | 80 | N | B07-007 |  | 2021-07-22
DB Netz AG | B07-016 | Bremen - Hannover | > | Bremen Hbf | Bremen Hbf | 2023 | 2023 | 31 | 31 | 2023-08-03 | 0:00 | 2023-08-03 | 3:00 | 0d, 3h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | B07-016 |  | 2021-05-12
DB Netz AG | B07-004 | Bremen - Hannover | < | Bremen Rbf Ausf | Bremen Hbf | 2023 | 2023 | 32 | 33 | 2023-08-12 | 4:00 | 2023-08-15 | 5:00 | 3d, 1h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | B07-004 |  | 2021-05-12
DB Netz AG | B07-001 | Bremen - Hannover | > | Bremen Hbf | Bremen Hbf | 2023 | 2023 | 32 | 33 | 2023-08-12 | 4:00 | 2023-08-15 | 5:00 | 3d, 1h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | B07-001 |  | 2021-07-22
DB Netz AG | B07-022 | Bremen - Hannover | < | Bremen Hbf | Bremen Hbf | 2023 | 2023 | 31 | 32 | 2023-08-05 | 22:00 | 2023-08-11 | 4:00 | 5d, 6h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | B07-022 |  | 2021-05-12
DB Netz AG | B07-023 | Bremen - Hannover | < | Bremen Rbf Ausf | Bremen Hbf | 2023 | 2023 | 31 | 32 | 2023-08-05 | 22:00 | 2023-08-11 | 4:00 | 5d, 6h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | B07-023 |  | 2021-05-12
DB Netz AG | B07-008 | Bremen - Hannover | > | Bremen Hbf | Bremen Hbf | 2023 | 2023 | 33 | 33 | 2023-08-15 | 7:00 | 2023-08-15 | 12:00 | 0d, 5h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | B07-008 |  | 2021-07-22
DB Netz AG | B07-005 | Bremen - Hannover | <> | Bremen Hbf | Bremen Rbf Ausf | 2023 | 2023 | 33 | 33 | 2023-08-15 | 7:00 | 2023-08-15 | 12:00 | 0d, 5h | Continuous | Track & Rail | T | [10 empty] | 80 | N | B07-005 |  | 2021-07-26
DB Netz AG | B07-006 | Bremen - Hannover | <> | Bremen Hbf | Bremen Rbf Abzw | 2023 | 2023 | 32 | 32 | 2023-08-09 | 5:00 | 2023-08-09 | 8:00 | 0d, 3h | Continuous | Track & Rail | T | [10 empty] | 80 | N | B07-006 |  | 2021-07-22
DB Netz AG | B07-017 | Bremen - Hannover | < | Bremen Hbf | Bremen Hbf | 2023 | 2023 | 32 | 33 | 2023-08-11 | 4:00 | 2023-08-15 | 5:00 | 4d, 1h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | B07-017 |  | 2021-05-12
DB Netz AG | B07-012 | Bremen - Hannover | > | Bremen Hbf | Bremen Hbf | 2023 | 2023 | 31 | 32 | 2023-08-05 | 22:00 | 2023-08-11 | 4:00 | 5d, 6h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | B07-012 |  | 2021-05-12
DB Netz AG | B07-024 | Bremen - Hannover | <> | Bremen Hbf | Bremen Rbf Ausf | 2023 | 2023 | 31 | 31 | 2023-08-05 | 0:00 | 2023-08-05 | 3:00 | 0d, 3h | Continuous | Track & Rail | T | [10 empty] | 80 | N | B07-024 |  | 2021-05-12
DB Netz AG | B07-013 | Bremen - Hannover | > | Bremen Hbf | Bremen Hbf | 2023 | 2023 | 31 | 31 | 2023-08-05 | 22:00 | 2023-08-06 | 0:00 | 0d, 2h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | B07-013 |  | 2021-07-26
DB Netz AG | B07-025 | Bremen - Hannover | <> | Bremen Hbf | Bremen Rbf Ausf | 2023 | 2023 | 31 | 31 | 2023-08-06 | 2:00 | 2023-08-06 | 6:00 | 0d, 4h | Continuous | Track & Rail | T | [10 empty] | 80 | N | B07-025 |  | 2021-05-12
DB Netz AG | B07-002 | Bremen - Hannover | > | Bremen Hbf | Bremen Hbf | 2023 | 2023 | 31 | 31 | 2023-08-06 | 2:00 | 2023-08-06 | 6:00 | 0d, 4h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | B07-002 |  | 2021-05-12
DB Netz AG | B07-003 | Bremen - Hannover | > | Bremen Hbf | Bremen Hbf | 2023 | 2023 | 33 | 33 | 2023-08-16 | 14:00 | 2023-08-16 | 17:00 | 0d, 3h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | B07-003 |  | 2021-05-12
DB Netz AG | B07-014 | Bremen - Hannover | > | Bremen Hbf | Brm Hbf ehem Bwn | 2023 | 2023 | 31 | 31 | 2023-08-02 | 7:00 | 2023-08-02 | 13:00 | 0d, 6h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | B07-014 |  | 2021-05-12
DB Netz AG | B07-009 | Bremen - Hannover | < | Bremen Rbf Ausf | Bremen Hbf | 2023 | 2023 | 31 | 31 | 2023-08-02 | 7:00 | 2023-08-02 | 13:00 | 0d, 6h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | B07-009 |  | 2021-05-12
DB Netz AG | B07-019 | Bremen - Hannover | > | Bremen Hbf | Bremen Hbf | 2023 | 2023 | 32 | 32 | 2023-08-08 | 9:30 | 2023-08-08 | 13:00 | 0d, 3h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | B07-019 |  | 2021-05-12
DB Netz AG | B07-026 | Bremen - Hannover | <> | Bremen Hbf | Bremen Rbf Ausf | 2023 | 2023 | 32 | 32 | 2023-08-08 | 9:30 | 2023-08-08 | 13:00 | 0d, 3h | Continuous | Track & Rail | T | [10 empty] | 80 | N | B07-026 |  | 2021-05-12
DB Netz AG | B10-004 | Hannover - Magdeburg | <> | Groß Gleidingen | Groß Gleidingen | 2023 | 2023 | 28 | 29 | 2023-07-14 | 16:05 | 2023-07-17 | 15:55 | 2d, 23h | Continuous | Switch |  |  | S | [8 empty] | 80 | N | B10-004 |  | 2021-05-04
DB Netz AG | B10-002 | Hannover - Magdeburg | <> | Groß Gleidingen | Groß Gleidingen | 2023 | 2023 | 29 | 29 | 2023-07-17 | 15:55 | 2023-07-19 | 16:00 | 2d, 0h | Continuous | Switch |  |  | S | [8 empty] | 80 | N | B10-002 |  | 2021-05-04
DB Netz AG | B10-001 | Hannover - Magdeburg | <> | Groß Gleidingen | Groß Gleidingen | 2023 | 2023 | 28 | 29 | 2023-07-12 | 17:00 | 2023-07-19 | 17:00 | 7d, 0h | Continuous | Switch |  | ST | [9 empty] | 80 | N | B10-001 |  | 2021-05-04
DB Netz AG | B10-003 | Hannover - Magdeburg | > | Groß Gleidingen | Groß Gleidingen | 2023 | 2023 | 28 | 29 | 2023-07-14 | 16:05 | 2023-07-17 | 15:55 | 2d, 23h | Continuous | Switch |  | ST | [9 empty] | 80 | N | B10-003 |  | 2021-05-04
DB Netz AG | B10-009 | Hannover - Magdeburg | <> | Groß Gleidingen | Bedding Nordkopf | 2023 | 2023 | 28 | 29 | 2023-07-14 | 16:05 | 2023-07-17 | 15:55 | 2d, 23h | Continuous | Switch | T | [10 empty] | 80 | N | B10-009 |  | 2021-05-04
DB Netz AG | B10-005 | Hannover - Magdeburg | <> | Groß Gleidingen | Groß Gleidingen | 2023 | 2023 | 28 | 28 | 2023-07-12 | 22:20 | 2023-07-13 | 5:15 | 0d, 6h | Continuous | Switch |  | ST | [9 empty] | 80 | N | B10-005 |  | 2021-05-04
DB Netz AG | B10-008 | Hannover - Magdeburg | <> | Groß Gleidingen | Gabelung (Brg) | 2023 | 2023 | 28 | 28 | 2023-07-12 | 22:20 | 2023-07-13 | 5:15 | 0d, 6h | Continuous | Switch | T | [10 empty] | 80 | N | B10-008 |  | 2021-05-04
DB Netz AG | B10-010 | Hannover - Magdeburg | <> | Groß Gleidingen | Bedding Nordkopf | 2023 | 2023 | 28 | 28 | 2023-07-12 | 22:20 | 2023-07-13 | 5:15 | 0d, 6h | Continuous | Switch | T | [10 empty] | 80 | N | B10-010 |  | 2021-05-04
DB Netz AG | B10-006 | Hannover - Magdeburg | <> | Groß Gleidingen | Gabelung (Brg) | 2023 | 2023 | 28 | 29 | 2023-07-14 | 23:20 | 2023-07-17 | 5:15 | 2d, 5h | Periodical | Switch | T | [10 empty] | 80 | N | B10-006 |  | 2021-05-04
DB Netz AG | B10-007 | Hannover - Magdeburg | <> | Groß Gleidingen | Groß Gleidingen | 2023 | 2023 | 28 | 29 | 2023-07-14 | 23:20 | 2023-07-17 | 5:15 | 2d, 5h | Periodical | Switch |  | ST | [9 empty] | 80 | N | B10-007 |  | 2021-05-04
DB Netz AG | B2F-010 | Rostock - Berlin | <> | Ostendgestell | Eichgestell | 2023 | 2023 | 31 | 31 | 2023-08-05 | 20:00 | 2023-08-06 | 4:00 | 0d, 8h | Continuous |  | T | [10 empty] | 80 | N | B2F-010 |  | 2021-05-12
DB Netz AG | B2F-006 | Rostock - Berlin | <> | Stadtforst | Eichgestell | 2023 | 2023 | 31 | 31 | 2023-08-05 | 20:00 | 2023-08-06 | 4:00 | 0d, 8h | Continuous |  | T | [10 empty] | 80 | N | B2F-006 |  | 2021-05-12
DB Netz AG | B2F-014 | Berlin - Dresden | <> | Eichgestell | Bln Wendenh | 2023 | 2023 | 31 | 31 | 2023-08-05 | 20:00 | 2023-08-06 | 4:00 | 0d, 8h | Continuous |  | T | [10 empty] | 80 | N | B2F-014 |  | 2021-06-01
DB Netz AG | B85-011 | Hamburg - Magdeburg | < | Hmb-Neugraben | Hmb-Hausbruch | 2023 | 2023 | 28 | 28 | 2023-07-10 | 23:00 | 2023-07-14 | 6:00 | 3d, 7h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | B85-011 |  | 2021-05-05
DB Netz AG | B85-020 | Hamburg - Magdeburg | > | Hmb-Hausbruch | Hmb-Neugraben | 2023 | 2023 | 34 | 34 | 2023-08-21 | 23:00 | 2023-08-25 | 6:00 | 3d, 7h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | B85-020 |  | 2021-05-05
DB Netz AG | B85-001 | Hamburg - Magdeburg | < | Hmb-Neugraben | Hmb-Hausbruch | 2023 | 2023 | 33 | 33 | 2023-08-14 | 23:00 | 2023-08-18 | 6:00 | 3d, 7h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | B85-001 |  | 2021-05-05
DB Netz AG | B85-004 | Hamburg - Magdeburg | > | Hmb-Hausbruch | Hmb-Neugraben | 2023 | 2023 | 33 | 34 | 2023-08-18 | 22:00 | 2023-08-21 | 4:00 | 2d, 6h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | B85-004 |  | 2021-05-04
DB Netz AG | B85-002 | Hamburg - Magdeburg | < | Hmb-Neugraben | Hmb-Hausbruch | 2023 | 2023 | 28 | 29 | 2023-07-15 | 9:00 | 2023-07-17 | 4:00 | 1d, 19h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | B85-002 |  | 2021-05-05
DB Netz AG | B85-013 | Hamburg - Magdeburg | < | Hmb-Neugraben | Hmb-Hausbruch | 2023 | 2023 | 32 | 33 | 2023-08-11 | 22:00 | 2023-08-14 | 4:00 | 2d, 6h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | B85-013 |  | 2021-05-05
DB Netz AG | BA3-005 | Bremerhaven - Bremen | <> | Stubben | Stubben | 2023 | 2023 | 28 | 28 | 2023-07-15 | 23:00 | 2023-07-16 | 6:30 | 0d, 7h | Continuous | Track & Rail |  |  | S | [8 empty] | 80 | N | BA3-005 |  | 2021-05-26
DB Netz AG | BA3-015 | Bremerhaven - Bremen | > | Lübberstedt | Stubben | 2023 | 2023 | 28 | 29 | 2023-07-16 | 23:00 | 2023-07-17 | 5:00 | 0d, 6h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | BA3-015 |  | 2021-05-26
DB Netz AG | BA3-021 | Bremerhaven - Bremen | <> | Stubben | Stubben | 2023 | 2023 | 28 | 29 | 2023-07-16 | 23:00 | 2023-07-17 | 5:00 | 0d, 6h | Continuous | Track & Rail |  |  | S | [8 empty] | 80 | N | BA3-021 |  | 2021-05-26
DB Netz AG | BA3-008 | Bremerhaven - Bremen | <> | Stubben | Stubben | 2023 | 2023 | 28 | 28 | 2023-07-10 | 6:00 | 2023-07-12 | 18:00 | 2d, 12h | Periodical | Track & Rail |  |  | S | [8 empty] | 80 | N | BA3-008 |  | 2021-07-14
DB Netz AG | BA3-014 | Bremerhaven - Bremen | > | Lübberstedt | Stubben | 2023 | 2023 | 28 | 28 | 2023-07-15 | 23:00 | 2023-07-16 | 6:30 | 0d, 7h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | BA3-014 |  | 2021-05-26
DB Netz AG | BAD-003 | Hamburg - Magdeburg | > | Lüneburg Gbf | Lüneburg Nordk | 2023 | 2023 | 32 | 32 | 2023-08-08 | 23:00 | 2023-08-08 | 23:59 | 0d, 0h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | BAD-003 |  | 2021-04-15
DB Netz AG | BAD-014 | Hamburg - Magdeburg | > | Lüneburg | Lüneburg Nordk | 2023 | 2023 | 31 | 32 | 2023-08-01 | 4:00 | 2023-08-08 | 5:00 | 7d, 1h | Continuous | Miscellaneous |  |  | S | [8 empty] | 80 | N | BAD-014 |  | 2021-04-20
DB Netz AG | BAD-007 | Hamburg - Magdeburg | > | Lüneburg Gbf | Lüneburg Nordk | 2023 | 2023 | 31 | 31 | 2023-07-31 | 23:00 | 2023-08-01 | 4:00 | 0d, 5h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | BAD-007 |  | 2021-04-20
DB Netz AG | BAD-008 | Hamburg - Magdeburg | <> | Lüneburg | Lüneburg | 2023 | 2023 | 31 | 31 | 2023-07-31 | 22:00 | 2023-08-04 | 6:00 | 3d, 8h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | BAD-008 |  | 2021-04-23
DB Netz AG | BAD-012 | Hamburg - Magdeburg | < | Lüneburg Nordk | Lüneburg | 2023 | 2023 | 31 | 32 | 2023-08-05 | 1:00 | 2023-08-08 | 5:00 | 3d, 4h | Continuous | Miscellaneous |  |  | S | [8 empty] | 80 | N | BAD-012 |  | 2021-04-20
DB Netz AG | BAD-004 | Hamburg - Magdeburg | <> | Lüneburg | Lüneburg | 2023 | 2023 | 31 | 32 | 2023-07-31 | 7:00 | 2023-08-09 | 7:00 | 9d, 0h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | BAD-004 |  | 2021-04-22
DB Netz AG | BAD-005 | Hamburg - Magdeburg | <> | Lüneburg | Adendorf | 2023 | 2023 | 31 | 32 | 2023-08-04 | 23:00 | 2023-08-07 | 4:00 | 2d, 5h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | BAD-005 |  | 2021-04-20
DB Netz AG | BAD-015 | Hamburg - Magdeburg | <> | Lüneburg Gbf | Lüneburg Nordk | 2023 | 2023 | 31 | 32 | 2023-08-05 | 0:00 | 2023-08-08 | 5:00 | 3d, 5h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | BAD-015 |  | 2021-04-20
DB Netz AG | BAD-013 | Hamburg - Magdeburg | < | Lüneburg Nordk | Lüneburg Gbf | 2023 | 2023 | 32 | 32 | 2023-08-08 | 23:00 | 2023-08-09 | 4:00 | 0d, 5h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | BAD-013 |  | 2021-04-20
DB Netz AG | BAD-010 | Hamburg - Magdeburg | <> | Lüneburg | Lüneburg | 2023 | 2023 | 31 | 31 | 2023-07-31 | 22:00 | 2023-08-04 | 6:00 | 3d, 8h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | BAD-010 |  | 2021-04-20
DB Netz AG | BAD-001 | Hamburg - Magdeburg | <> | Lüneburg | Lüneburg | 2023 | 2023 | 32 | 32 | 2023-08-08 | 22:00 | 2023-08-09 | 6:00 | 0d, 8h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | BAD-001 |  | 2021-04-20
DB Netz AG | BAD-006 | Hamburg - Magdeburg | < | Lüneburg Nordk | Lüneburg Gbf | 2023 | 2023 | 31 | 31 | 2023-08-04 | 20:00 | 2023-08-05 | 1:00 | 0d, 5h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | BAD-006 |  | 2021-04-20
DB Netz AG | BAD-002 | Hamburg - Magdeburg | <> | Lüneburg | Lüneburg | 2023 | 2023 | 31 | 32 | 2023-08-04 | 18:00 | 2023-08-08 | 6:00 | 3d, 12h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | BAD-002 |  | 2021-04-20
DB Netz AG | BAD-009 | Hamburg - Magdeburg | <> | Lüneburg | Lüneburg | 2023 | 2023 | 31 | 32 | 2023-08-04 | 18:00 | 2023-08-08 | 6:00 | 3d, 12h | Continuous | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | BAD-009 |  | 2021-04-23
DB Netz AG | BAD-011 | Hamburg - Magdeburg | <> | Lüneburg | Lüneburg | 2023 | 2023 | 32 | 32 | 2023-08-08 | 22:00 | 2023-08-09 | 6:00 | 0d, 8h | Continuous | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | BAD-011 |  | 2021-04-23
DB Netz AG | BD0-017 | Bremerhaven - Bremen | <> | Osterholz-Scharm | Bremen-Burg | 2023 | 2023 | 35 | 36 | 2023-09-01 | 23:00 | 2023-09-09 | 5:00 | 7d, 6h | Periodical | Signal |  |  | S | [8 empty] | 80 | N | BD0-017 |  | 2021-07-21
DB Netz AG | BD0-012 | Bremerhaven - Bremen | < | Osterholz-Scharm | Bremen-Burg | 2023 | 2023 | 36 | 37 | 2023-09-09 | 23:00 | 2023-09-14 | 5:00 | 4d, 6h | Periodical | Signal |  | LT | [9 empty] | 80 | N | BD0-012 |  | 2021-05-26
DB Netz AG | BD0-024 | Bremerhaven - Bremen | <> | Bremen-Burg | Osterholz-Scharm | 2023 | 2023 | 36 | 37 | 2023-09-09 | 23:00 | 2023-09-14 | 5:00 | 4d, 6h | Periodical | Signal |  |  | S | [8 empty] | 80 | N | BD0-024 |  | 2021-07-21
DB Netz AG | BD0-006 | Bremerhaven - Bremen | > | Bremen-Burg | Osterholz-Scharm | 2023 | 2023 | 35 | 36 | 2023-09-01 | 23:00 | 2023-09-09 | 5:00 | 7d, 6h | Periodical | Signal |  | LT | [9 empty] | 80 | N | BD0-006 |  | 2021-05-26
DB Netz AG | BF7-001 | Hamburg - Magdeburg | <> | Magdeburg Hbf | Magdeburg Hbf | 2023 | 2023 | 31 | 49 | 2023-08-04 | 0:00 | 2023-12-09 | 23:59 | 128d, 0h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | BF7-001 |  | 2021-05-11
DB Netz AG | C12-003 | Hamburg - Magdeburg | <> | Salzwedel Gbf | Salzwedel Gbf | 2023 | 2023 | 36 | 36 | 2023-09-09 | 0:00 | 2023-09-09 | 6:00 | 0d, 6h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | C12-003 |  | 2021-06-03
DB Netz AG | C12-001 | Hamburg - Magdeburg | <> | Salzwedel Gbf | Salzwedel Gbf | 2023 | 2023 | 36 | 36 | 2023-09-08 | 20:00 | 2023-09-09 | 6:00 | 0d, 10h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | C12-001 |  | 2021-06-04
DB Netz AG | C12-002 | Hamburg - Magdeburg | <> | Salzwedel Gbf | Salzwedel | 2023 | 2023 | 36 | 36 | 2023-09-09 | 0:00 | 2023-09-09 | 3:00 | 0d, 3h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | C12-002 |  | 2021-06-03
DB Netz AG | C24-060 | Bremerhaven - Bremen | <> | Brh-Wulsdorf | Brh-Wulsdorf | 2023 | 2023 | 33 | 35 | 2023-08-18 | 10:00 | 2023-08-28 | 18:00 | 10d, 8h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | C24-060 |  | 2021-07-09
DB Netz AG | C24-039 | Bremerhaven - Bremen | <> | Stubben | Brh-Wulsdorf | 2023 | 2023 | 35 | 35 | 2023-09-02 | 22:00 | 2023-09-03 | 6:00 | 0d, 8h | Continuous | Track & Rail |  |  | S | [8 empty] | 80 | N | C24-039 |  | 2021-07-12
DB Netz AG | C24-031 | Bremerhaven - Bremen | < | Brh-Wulsdorf | Stubben | 2023 | 2023 | 36 | 36 | 2023-09-09 | 22:00 | 2023-09-10 | 6:00 | 0d, 8h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | C24-031 |  | 2021-05-25
DB Netz AG | C24-036 | Bremerhaven - Bremen | <> | Stubben | Brh-Wulsdorf | 2023 | 2023 | 35 | 36 | 2023-09-03 | 22:00 | 2023-09-04 | 4:00 | 0d, 6h | Continuous | Track & Rail |  |  | S | [8 empty] | 80 | N | C24-036 |  | 2021-07-12
DB Netz AG | C24-025 | Bremerhaven - Bremen | <> | Stubben | Brh-Wulsdorf | 2023 | 2023 | 33 | 33 | 2023-08-14 | 6:00 | 2023-08-18 | 18:00 | 4d, 12h | Periodical | Track & Rail |  |  | S | [8 empty] | 80 | N | C24-025 |  | 2021-07-12
DB Netz AG | C24-005 | Bremerhaven - Bremen | < | Brh-Wulsdorf | Stubben | 2023 | 2023 | 35 | 35 | 2023-09-02 | 22:00 | 2023-09-03 | 6:00 | 0d, 8h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | C24-005 |  | 2021-05-25
DB Netz AG | C24-063 | Bremerhaven - Bremen | < | Brh-Wulsdorf | Stubben | 2023 | 2023 | 35 | 36 | 2023-09-03 | 22:00 | 2023-09-04 | 4:00 | 0d, 6h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | C24-063 |  | 2021-05-25
DB Netz AG | C24-057 | Bremerhaven - Bremen | <> | Stubben | Brh-Wulsdorf | 2023 | 2023 | 36 | 36 | 2023-09-09 | 22:00 | 2023-09-10 | 6:00 | 0d, 8h | Continuous | Track & Rail |  |  | S | [8 empty] | 80 | N | C24-057 |  | 2021-07-13
DB Netz AG | C24-010 | Bremerhaven - Bremen | <> | Stubben | Brh-Wulsdorf | 2023 | 2023 | 32 | 32 | 2023-08-07 | 6:00 | 2023-08-11 | 18:00 | 4d, 12h | Periodical | Track & Rail |  |  | S | [8 empty] | 80 | N | C24-010 |  | 2021-07-13
DB Netz AG | C59-003 | Dresden - Děčín | <> | Dre-Reick Abstbf | Dre-Neustadt | 2023 | 2023 | 36 | 36 | 2023-09-09 | 16:00 | 2023-09-10 | 6:00 | 0d, 14h | Continuous | Signal | T | [10 empty] | 80 | N | C59-003 |  | 2021-06-04
DB Netz AG | C59-006 | Dresden - Děčín | <> | Dresden-Altstadt | Dresden Hbf | 2023 | 2023 | 36 | 36 | 2023-09-09 | 16:00 | 2023-09-10 | 6:00 | 0d, 14h | Continuous | Signal | T | [10 empty] | 80 | N | C59-006 |  | 2021-06-04
DB Netz AG | C59-004 | Dresden - Děčín | <> | Dresden-Reick | Dre-Neustadt | 2023 | 2023 | 36 | 36 | 2023-09-09 | 16:00 | 2023-09-10 | 6:00 | 0d, 14h | Continuous | Signal | T | [10 empty] | 80 | N | C59-004 |  | 2021-06-04
DB Netz AG | C59-002 | Berlin - Dresden | <> | Dre-Neustadt | Dre-Neustadt Gbf | 2023 | 2023 | 36 | 36 | 2023-09-09 | 16:00 | 2023-09-10 | 6:00 | 0d, 14h | Continuous | Signal | T | [10 empty] | 80 | N | C59-002 |  | 2021-06-04
DB Netz AG | C59-009 | Dresden - Děčín | <> | Dresden-Altstadt | Dre Freibg Str | 2023 | 2023 | 36 | 36 | 2023-09-09 | 16:00 | 2023-09-10 | 6:00 | 0d, 14h | Continuous | Signal | T | [10 empty] | 80 | N | C59-009 |  | 2021-06-04
DB Netz AG | C59-007 | Dresden - Děčín | <> | Dre-Friedrichst | Dre Freibg Str | 2023 | 2023 | 36 | 36 | 2023-09-09 | 16:00 | 2023-09-10 | 6:00 | 0d, 14h | Continuous | Signal | T | [10 empty] | 80 | N | C59-007 |  | 2021-06-04
DB Netz AG | C59-008 | Dresden - Děčín | <> | Dresden Hbf | Dre-Neustadt | 2023 | 2023 | 36 | 36 | 2023-09-09 | 16:00 | 2023-09-10 | 6:00 | 0d, 14h | Continuous | Signal | T | [10 empty] | 80 | N | C59-008 |  | 2021-06-04
DB Netz AG | C59-005 | Dresden - Děčín | <> | Dresden-Altstadt | Dresden Hbf | 2023 | 2023 | 36 | 36 | 2023-09-09 | 16:00 | 2023-09-10 | 6:00 | 0d, 14h | Continuous | Signal | T | [10 empty] | 80 | N | C59-005 |  | 2021-07-01
DB Netz AG | C59-010 | Dresden - Děčín | <> | Dre-Friedrichst | Dresden Mitte | 2023 | 2023 | 36 | 36 | 2023-09-09 | 16:00 | 2023-09-10 | 6:00 | 0d, 14h | Continuous | Signal | T | [10 empty] | 80 | N | C59-010 |  | 2021-06-04
DB Netz AG | C74-001 | Dresden - Děčín | <> | Obervogelgesang | Königst (Sä) Üst | 2023 | 2023 | 31 | 31 | 2023-07-31 | 23:00 | 2023-08-02 | 5:00 | 1d, 6h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | C74-001 |  | 2021-05-25
DB Netz AG | C74-004 | Dresden - Děčín | > | Königst (Sä) Üst | Kurort Rathen | 2023 | 2023 | 31 | 38 | 2023-08-02 | 8:00 | 2023-09-20 | 16:00 | 49d, 8h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | C74-004 |  | 2021-05-25
DB Netz AG | C74-003 | Dresden - Děčín | <> | Obervogelgesang | Königst (Sä) Üst | 2023 | 2023 | 31 | 38 | 2023-08-01 | 5:00 | 2023-09-21 | 23:00 | 51d, 18h | Continuous | Miscellaneous |  |  |  | P | [7 empty] | 80 | N | C74-003 |  | 2021-10-06
DB Netz AG | C74-006 | Dresden - Děčín | > | Kurort Rathen | Kurort Rathen | 2023 | 2023 | 31 | 38 | 2023-08-02 | 8:00 | 2023-09-20 | 16:00 | 49d, 8h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | C74-006 |  | 2021-05-25
DB Netz AG | C74-005 | Dresden - Děčín | > | Kurort Rathen | Kurort Rathen | 2023 | 2023 | 31 | 38 | 2023-07-31 | 20:00 | 2023-09-22 | 8:00 | 52d, 12h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | C74-005 |  | 2021-05-25
DB Netz AG | C86-007 | Dresden - Děčín | <> | Dre Freibg Str | Dre-Friedrichst | 2023 | 2023 | 35 | 36 | 2023-09-01 | 21:00 | 2023-09-04 | 5:00 | 2d, 8h | Continuous | Catenary | T | [10 empty] | 80 | N | C86-007 |  | 2021-06-04
DB Netz AG | C86-009 | Dresden - Děčín | <> | Dresden-Altstadt | Dresden Hbf | 2023 | 2023 | 35 | 36 | 2023-09-01 | 21:00 | 2023-09-04 | 5:00 | 2d, 8h | Continuous | Catenary | T | [10 empty] | 80 | N | C86-009 |  | 2021-06-04
DB Netz AG | C86-010 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 35 | 36 | 2023-09-01 | 21:00 | 2023-09-04 | 5:00 | 2d, 8h | Continuous | Catenary |  | ST | [9 empty] | 80 | N | C86-010 |  | 2021-06-04
DB Netz AG | C86-011 | Dresden - Děčín | <> | Dresden-Altstadt | Dre Freibg Str | 2023 | 2023 | 35 | 36 | 2023-09-01 | 21:00 | 2023-09-04 | 5:00 | 2d, 8h | Continuous | Catenary | T | [10 empty] | 80 | N | C86-011 |  | 2021-06-04
DB Netz AG | C86-008 | Dresden - Děčín | <> | Dresden Hbf | Dresden Mitte | 2023 | 2023 | 35 | 36 | 2023-09-01 | 21:00 | 2023-09-04 | 5:00 | 2d, 8h | Continuous | Catenary | T | [10 empty] | 80 | N | C86-008 |  | 2021-06-04
DB Netz AG | C86-003 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 34 | 35 | 2023-08-25 | 21:00 | 2023-08-28 | 5:00 | 2d, 8h | Continuous | Catenary |  | ST | [9 empty] | 80 | N | C86-003 |  | 2021-06-04
DB Netz AG | C86-004 | Dresden - Děčín | <> | Dresden-Altstadt | Dresden Hbf | 2023 | 2023 | 34 | 35 | 2023-08-25 | 21:00 | 2023-08-28 | 5:00 | 2d, 8h | Continuous | Catenary | T | [10 empty] | 80 | N | C86-004 |  | 2021-06-04
DB Netz AG | C86-002 | Dresden - Děčín | <> | Dresden Hbf | Dresden Mitte | 2023 | 2023 | 34 | 35 | 2023-08-25 | 21:00 | 2023-08-28 | 5:00 | 2d, 8h | Continuous | Catenary | T | [10 empty] | 80 | N | C86-002 |  | 2021-06-04
DB Netz AG | C86-005 | Dresden - Děčín | <> | Dre-Friedrichst | Dre Freibg Str | 2023 | 2023 | 34 | 35 | 2023-08-25 | 21:00 | 2023-08-28 | 5:00 | 2d, 8h | Continuous | Catenary | T | [10 empty] | 80 | N | C86-005 |  | 2021-06-04
DB Netz AG | C86-006 | Dresden - Děčín | <> | Dresden-Altstadt | Dre Freibg Str | 2023 | 2023 | 34 | 35 | 2023-08-25 | 21:00 | 2023-08-28 | 5:00 | 2d, 8h | Continuous | Catenary | T | [10 empty] | 80 | N | C86-006 |  | 2021-06-04
DB Netz AG | C86-012 | Dresden - Děčín | < | Dresden Mitte | Dresden Hbf | 2023 | 2023 | 35 | 36 | 2023-09-01 | 21:00 | 2023-09-04 | 5:00 | 2d, 8h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | C86-012 |  | 2021-07-01
DB Netz AG | C86-001 | Dresden - Děčín | < | Dresden Mitte | Dresden Hbf | 2023 | 2023 | 34 | 35 | 2023-08-25 | 21:00 | 2023-08-28 | 5:00 | 2d, 8h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | C86-001 |  | 2021-07-01
DB Netz AG | 215D-001 | Rostock - Berlin | < | Oranienburg | Birkenwerd b Bln | 2023 | 2023 | 30 | 30 | 2023-07-25 | 22:00 | 2023-07-26 | 4:00 | 0d, 6h | Continuous | Signal |  | LT | [9 empty] | 80 | N | 215D-001 |  | 2021-10-26
DB Netz AG | 215D-002 | Rostock - Berlin | <> | Birkenwerd b Bln | Birkenwerd b Bln | 2023 | 2023 | 28 | 28 | 2023-07-12 | 22:00 | 2023-07-13 | 4:00 | 0d, 6h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 215D-002 |  | 2021-05-05
DB Netz AG | 215D-003 | Rostock - Berlin | <> | Schönfließ West | Hohen Neuend Sw | 2023 | 2023 | 28 | 28 | 2023-07-12 | 22:00 | 2023-07-13 | 4:00 | 0d, 6h | Continuous | Signal | T | [10 empty] | 80 | N | 215D-003 |  | 2021-08-18
DB Netz AG | 215D-004 | Rostock - Berlin | <> | Bergfelde Ost | Hohen Neuend Sw | 2023 | 2023 | 28 | 28 | 2023-07-12 | 22:00 | 2023-07-13 | 4:00 | 0d, 6h | Continuous | Signal | T | [10 empty] | 80 | N | 215D-004 |  | 2021-08-18
DB Netz AG | 215D-005 | Rostock - Berlin | <> | Birkenwerd b Bln | Oranienburg | 2023 | 2023 | 28 | 28 | 2023-07-12 | 22:00 | 2023-07-13 | 4:00 | 0d, 6h | Continuous | Signal | T | [10 empty] | 80 | N | 215D-005 |  | 2021-08-18
DB Netz AG | 215D-006 | Rostock - Berlin | <> | Hohen Neuend W | Birkenwerd b Bln | 2023 | 2023 | 28 | 28 | 2023-07-12 | 22:00 | 2023-07-13 | 4:00 | 0d, 6h | Continuous | Signal | T | [10 empty] | 80 | N | 215D-006 |  | 2021-11-15
DB Netz AG | 215D-007 | Rostock - Berlin | <> | Schönfließ West | Birkenwerd b Bln | 2023 | 2023 | 28 | 28 | 2023-07-12 | 22:00 | 2023-07-13 | 4:00 | 0d, 6h | Continuous | Signal | T | [10 empty] | 80 | N | 215D-007 |  | 2021-11-15
DB Netz AG | 215D-008 | Rostock - Berlin | <> | Birkenwerd b Bln | Hohen Neuend W | 2023 | 2023 | 30 | 30 | 2023-07-25 | 22:00 | 2023-07-26 | 4:00 | 0d, 6h | Continuous | Signal | T | [10 empty] | 80 | N | 215D-008 |  | 2021-10-26
DB Netz AG | 215D-009 | Rostock - Berlin | <> | Birkenwerd b Bln | Birkenwerd b Bln | 2023 | 2023 | 30 | 30 | 2023-07-25 | 22:00 | 2023-07-26 | 4:00 | 0d, 6h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 215D-009 |  | 2021-05-05
DB Netz AG | 215D-011 | Rostock - Berlin | < | Oranienburg | Birkenwerd b Bln | 2023 | 2023 | 29 | 29 | 2023-07-18 | 22:00 | 2023-07-19 | 4:00 | 0d, 6h | Continuous | Signal |  | LT | [9 empty] | 80 | N | 215D-011 |  | 2021-05-05
DB Netz AG | 215D-012 | Rostock - Berlin | <> | Hohen Neuend Sw | Schönfließ West | 2023 | 2023 | 29 | 29 | 2023-07-18 | 22:00 | 2023-07-19 | 4:00 | 0d, 6h | Continuous | Signal | T | [10 empty] | 80 | N | 215D-012 |  | 2021-08-18
DB Netz AG | 215D-013 | Rostock - Berlin | <> | Birkenwerd b Bln | Birkenwerd b Bln | 2023 | 2023 | 29 | 29 | 2023-07-18 | 22:00 | 2023-07-19 | 4:00 | 0d, 6h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 215D-013 |  | 2021-08-18
DB Netz AG | 215D-016 | Rostock - Berlin | <> | Oranienburg | Oranienburg | 2023 | 2023 | 30 | 30 | 2023-07-26 | 8:00 | 2023-07-27 | 18:00 | 1d, 10h | Periodical | Signal |  | ST | [9 empty] | 80 | N | 215D-016 |  | 2021-09-07
DB Netz AG | 215D-017 | Rostock - Berlin | < | Oranienburg | Birkenwerder N | 2023 | 2023 | 29 | 30 | 2023-07-23 | 22:00 | 2023-07-24 | 4:00 | 0d, 6h | Continuous | Signal |  | LT | [9 empty] | 80 | N | 215D-017 |  | 2021-05-06
DB Netz AG | 215D-018 | Rostock - Berlin | <> | Oranienburg | Oranienburg | 2023 | 2023 | 29 | 30 | 2023-07-23 | 22:00 | 2023-07-24 | 4:00 | 0d, 6h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 215D-018 |  | 2021-05-06
DB Netz AG | 215D-022 | Rostock - Berlin | < | Oranienburg | Birkenwerder N | 2023 | 2023 | 28 | 29 | 2023-07-16 | 22:00 | 2023-07-17 | 4:00 | 0d, 6h | Continuous | Signal |  | LT | [9 empty] | 80 | N | 215D-022 |  | 2021-05-07
DB Netz AG | 215D-023 | Rostock - Berlin | <> | Oranienburg | Oranienburg | 2023 | 2023 | 28 | 29 | 2023-07-16 | 22:00 | 2023-07-17 | 4:00 | 0d, 6h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 215D-023 |  | 2021-05-07
DB Netz AG | 1309-004 | Rostock - Berlin | <> | Schönfließ West | Hohen Neuend Sw | 2023 | 2023 | 36 | 39 | 2023-09-08 | 21:00 | 2023-09-29 | 21:00 | 21d, 0h | Continuous | Signal | T | [10 empty] | 80 | N | 1309-004 |  | 2021-08-12
DB Netz AG | 1309-002 | Rostock - Berlin | <> | Birkenwerd b Bln | Birkenwerd b Bln | 2023 | 2023 | 36 | 39 | 2023-09-08 | 21:00 | 2023-09-29 | 21:00 | 21d, 0h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 1309-002 |  | 2021-05-07
DB Netz AG | 1309-005 | Rostock - Berlin | <> | Bergfelde Ost | Hohen Neuend Sw | 2023 | 2023 | 36 | 39 | 2023-09-08 | 21:00 | 2023-09-29 | 21:00 | 21d, 0h | Continuous | Signal | T | [10 empty] | 80 | N | 1309-005 |  | 2021-08-12
DB Netz AG | 1309-003 | Rostock - Berlin | <> | Schönfließ West | Birkenwerd b Bln | 2023 | 2023 | 36 | 39 | 2023-09-08 | 21:00 | 2023-09-29 | 21:00 | 21d, 0h | Continuous | Signal | T | [10 empty] | 80 | N | 1309-003 |  | 2021-11-15
DB Netz AG | 1309-001 | Rostock - Berlin | <> | Birkenwerd b Bln | Oranienburg | 2023 | 2023 | 36 | 39 | 2023-09-08 | 21:00 | 2023-09-29 | 21:00 | 21d, 0h | Continuous | Signal | T | [10 empty] | 80 | N | 1309-001 |  | 2021-09-15
DB Netz AG | 1309-006 | Rostock - Berlin | <> | Hohen Neuend W | Birkenwerd b Bln | 2023 | 2023 | 36 | 39 | 2023-09-08 | 21:00 | 2023-09-29 | 21:00 | 21d, 0h | Continuous | Signal | T | [10 empty] | 80 | N | 1309-006 |  | 2021-11-15
DB Netz AG | 215D-024 | Rostock - Berlin | <> | Hohen Neuend Sw | Schönfließ West | 2023 | 2023 | 30 | 30 | 2023-07-24 | 22:00 | 2023-07-25 | 4:00 | 0d, 6h | Continuous | Signal | T | [10 empty] | 80 | N | 215D-024 |  | 2021-10-25
DB Netz AG | 215D-025 | Rostock - Berlin | <> | Hohen Neuend Sw | Schönfließ West | 2023 | 2023 | 29 | 29 | 2023-07-17 | 22:00 | 2023-07-18 | 4:00 | 0d, 6h | Continuous | Signal | T | [10 empty] | 80 | N | 215D-025 |  | 2021-10-25
DB Netz AG | 215D-026 | Rostock - Berlin | <> | Birkenwerder N | Hohen Neuend W | 2023 | 2023 | 29 | 29 | 2023-07-18 | 22:00 | 2023-07-19 | 4:00 | 0d, 6h | Continuous | Signal | T | [10 empty] | 80 | N | 215D-026 |  | 2021-05-07
DB Netz AG | 215D-027 | Rostock - Berlin | <> | Oranienburg | Oranienburg | 2023 | 2023 | 30 | 30 | 2023-07-24 | 8:00 | 2023-07-25 | 18:00 | 1d, 10h | Periodical | Signal |  | ST | [9 empty] | 80 | N | 215D-027 |  | 2021-10-26
DB Netz AG | 215D-028 | Rostock - Berlin | < | Oranienburg | Birkenwerd b Bln | 2023 | 2023 | 30 | 30 | 2023-07-24 | 8:00 | 2023-07-25 | 18:00 | 1d, 10h | Periodical | Signal |  | LT | [9 empty] | 80 | N | 215D-028 |  | 2021-05-07
DB Netz AG | 0.185 | Rostock - Berlin | <> | Birkenwerd b Bln | Birkenwerder N | 2023 | 2023 | 28 | 36 | 2023-07-12 | 22:00 | 2023-09-07 | 18:00 | 56d, 20h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 0.185 |  | 2021-05-07
DB Netz AG | 215D-029 | Rostock - Berlin | <> | Schönfließ West | Hohen Neuend Sw | 2023 | 2023 | 30 | 30 | 2023-07-25 | 22:00 | 2023-07-26 | 4:00 | 0d, 6h | Continuous | Signal | T | [10 empty] | 80 | N | 215D-029 |  | 2021-11-15
DB Netz AG | D07-010 | Rostock - Berlin | <> | Weddel Abzw | Fallersleben | 2023 | 2023 | 29 | 29 | 2023-07-22 | 23:35 | 2023-07-23 | 7:30 | 0d, 7h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | D07-010 |  | 2021-05-10
DB Netz AG | D4D-015 | Rostock - Berlin | <> | Oranienburg | Oranienburg | 2023 | 2023 | 36 | 39 | 2023-09-04 | 6:00 | 2023-09-29 | 16:00 | 25d, 10h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | D4D-015 |  | 2021-05-07
DB Netz AG | DBE-001 | Dresden - Děčín | <> | Dresden-Altstadt | Dresden Hbf | 2023 | 2023 | 32 | 32 | 2023-08-12 | 14:00 | 2023-08-13 | 6:00 | 0d, 16h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | DBE-001 |  | 2021-07-01
DB Netz AG | DBE-002 | Dresden - Děčín | <> | Dresden-Altstadt | Dre Freibg Str | 2023 | 2023 | 32 | 32 | 2023-08-12 | 14:00 | 2023-08-13 | 6:00 | 0d, 16h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | DBE-002 |  | 2021-06-04
DB Netz AG | DBE-007 | Berlin - Dresden | <> | Dre-Neustadt | Dre-Neustadt Gbf | 2023 | 2023 | 32 | 32 | 2023-08-12 | 14:00 | 2023-08-13 | 6:00 | 0d, 16h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | DBE-007 |  | 2021-06-04
DB Netz AG | DBE-014 | Dresden - Děčín | <> | Dre-Reick Abstbf | Dre-Neustadt | 2023 | 2023 | 32 | 32 | 2023-08-12 | 14:00 | 2023-08-13 | 6:00 | 0d, 16h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | DBE-014 |  | 2021-06-04
DB Netz AG | DBE-008 | Dresden - Děčín | <> | Dresden Hbf | Dre-Neustadt | 2023 | 2023 | 32 | 32 | 2023-08-12 | 14:00 | 2023-08-13 | 6:00 | 0d, 16h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | DBE-008 |  | 2021-06-04
DB Netz AG | DBE-010 | Dresden - Děčín | <> | Dre-Friedrichst | Dre Freibg Str | 2023 | 2023 | 32 | 32 | 2023-08-12 | 14:00 | 2023-08-13 | 6:00 | 0d, 16h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | DBE-010 |  | 2021-06-04
DB Netz AG | DBE-004 | Dresden - Děčín | <> | Dre-Friedrichst | Dresden Mitte | 2023 | 2023 | 32 | 32 | 2023-08-12 | 14:00 | 2023-08-13 | 6:00 | 0d, 16h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | DBE-004 |  | 2021-06-04
DB Netz AG | DBE-003 | Dresden - Děčín | <> | Dresden-Altstadt | Dresden Hbf | 2023 | 2023 | 32 | 32 | 2023-08-12 | 14:00 | 2023-08-13 | 6:00 | 0d, 16h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | DBE-003 |  | 2021-06-04
DB Netz AG | DBE-005 | Dresden - Děčín | <> | Dresden-Reick | Dre-Neustadt | 2023 | 2023 | 32 | 32 | 2023-08-12 | 14:00 | 2023-08-13 | 6:00 | 0d, 16h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | DBE-005 |  | 2021-06-04
DB Netz AG | DBE-009 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 32 | 32 | 2023-08-12 | 2:00 | 2023-08-12 | 14:00 | 0d, 12h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | DBE-009 |  | 2021-07-01
DB Netz AG | DBE-012 | Dresden - Děčín | <> | Dresden Hbf | Dre-Neustadt | 2023 | 2023 | 32 | 32 | 2023-08-12 | 10:00 | 2023-08-12 | 14:00 | 0d, 4h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | DBE-012 |  | 2021-06-04
DB Netz AG | DBE-015 | Dresden - Děčín | < | Dre Freibg Str | Dre-Friedrichst | 2023 | 2023 | 32 | 32 | 2023-08-12 | 10:00 | 2023-08-12 | 14:00 | 0d, 4h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | DBE-015 |  | 2021-06-04
DB Netz AG | DBE-013 | Dresden - Děčín | <> | Dresden-Altstadt | Dre Freibg Str | 2023 | 2023 | 32 | 32 | 2023-08-12 | 10:00 | 2023-08-12 | 14:00 | 0d, 4h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | DBE-013 |  | 2021-06-04
DB Netz AG | DBE-006 | Dresden - Děčín | <> | Dresden Hbf | Dresden Mitte | 2023 | 2023 | 32 | 32 | 2023-08-12 | 10:00 | 2023-08-12 | 14:00 | 0d, 4h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | DBE-006 |  | 2021-06-04
DB Netz AG | E0F-001 | Dresden - Děčín | <> | Dresden-Altstadt | Dre Freibg Str | 2023 | 2023 | 32 | 33 | 2023-08-13 | 22:30 | 2023-08-17 | 4:30 | 3d, 6h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | E0F-001 |  | 2021-06-04
DB Netz AG | E0F-002 | Dresden - Děčín | <> | Dresden Hbf | Dresden Mitte | 2023 | 2023 | 32 | 33 | 2023-08-13 | 22:30 | 2023-08-17 | 4:30 | 3d, 6h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | E0F-002 |  | 2021-06-04
DB Netz AG | E0F-003 | Dresden - Děčín | <> | Dre-Friedrichst | Dre Freibg Str | 2023 | 2023 | 32 | 33 | 2023-08-13 | 22:30 | 2023-08-17 | 4:30 | 3d, 6h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | E0F-003 |  | 2021-06-04
DB Netz AG | EFF-001 | Rostock - Berlin | > | Oranienburg | Neustrelitz Hbf | 2023 | 2023 | 36 | 39 | 2023-09-08 | 21:00 | 2023-09-29 | 5:00 | 20d, 8h | Periodical | Maintenance |  | LT | [9 empty] | 80 | N | EFF-001 |  | 2021-06-08
DB Netz AG | EFF-002 | Rostock - Berlin | > | Birkenwerd b Bln | Oranienburg | 2023 | 2023 | 36 | 39 | 2023-09-08 | 21:00 | 2023-09-29 | 5:00 | 20d, 8h | Periodical | Maintenance |  | LT | [9 empty] | 80 | N | EFF-002 |  | 2021-06-08
DB Netz AG | F54-003 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 32 | 36 | 2023-08-13 | 6:00 | 2023-09-09 | 16:00 | 27d, 10h | Continuous | Switch |  | ST | [9 empty] | 80 | N | F54-003 |  | 2021-06-03
DB Netz AG | F54-004 | Dresden - Děčín | <> | Dresden Hbf | Dre-Neustadt | 2023 | 2023 | 32 | 36 | 2023-08-13 | 6:00 | 2023-09-09 | 16:00 | 27d, 10h | Continuous | Switch | T | [10 empty] | 80 | N | F54-004 |  | 2021-06-03
DB Netz AG | F54-002 | Dresden - Děčín | <> | Dresden Hbf | Dre-Neustadt | 2023 | 2023 | 32 | 36 | 2023-08-13 | 6:00 | 2023-09-09 | 16:00 | 27d, 10h | Continuous | Switch |  | ST | [9 empty] | 80 | N | F54-002 |  | 2021-06-03
DB Netz AG | F54-001 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 32 | 36 | 2023-08-13 | 6:00 | 2023-09-09 | 16:00 | 27d, 10h | Continuous | Switch |  | ST | [9 empty] | 80 | Y | F54-001 |  | 2021-06-03
DB Netz AG | F8F-004 | Dresden - Děčín | <> | Dre-Friedrichst | Dre Freibg Str | 2023 | 2023 | 34 | 35 | 2023-08-22 | 22:00 | 2023-09-01 | 5:00 | 9d, 7h | Periodical | Catenary | T | [10 empty] | 80 | N | F8F-004 |  | 2021-06-04
DB Netz AG | F8F-002 | Dresden - Děčín | <> | Dresden-Altstadt | Dre Freibg Str | 2023 | 2023 | 34 | 35 | 2023-08-22 | 22:00 | 2023-09-01 | 5:00 | 9d, 7h | Periodical | Catenary | T | [10 empty] | 80 | N | F8F-002 |  | 2021-06-04
DB Netz AG | F8F-005 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 34 | 35 | 2023-08-22 | 22:00 | 2023-09-01 | 5:00 | 9d, 7h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | F8F-005 |  | 2021-06-04
DB Netz AG | F8F-003 | Dresden - Děčín | <> | Dresden Hbf | Dresden Mitte | 2023 | 2023 | 34 | 35 | 2023-08-22 | 22:00 | 2023-09-01 | 5:00 | 9d, 7h | Periodical | Catenary | T | [10 empty] | 80 | N | F8F-003 |  | 2021-06-04
DB Netz AG | F8F-001 | Dresden - Děčín | <> | Dresden-Altstadt | Dresden Hbf | 2023 | 2023 | 34 | 35 | 2023-08-22 | 22:00 | 2023-09-01 | 5:00 | 9d, 7h | Periodical | Catenary | T | [10 empty] | 80 | N | F8F-001 |  | 2021-06-04
DB Netz AG | FA4-002 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 33 | 35 | 2023-08-17 | 21:30 | 2023-09-02 | 5:30 | 15d, 8h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | FA4-002 |  | 2021-05-27
DB Netz AG | FA4-033 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 33 | 35 | 2023-08-17 | 21:30 | 2023-09-02 | 5:30 | 15d, 8h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | FA4-033 |  | 2021-05-27
DB Netz AG | FA4-034 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 33 | 35 | 2023-08-17 | 21:30 | 2023-09-02 | 5:30 | 15d, 8h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | FA4-034 |  | 2021-05-27
DB Netz AG | FA4-010 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 33 | 35 | 2023-08-17 | 21:30 | 2023-09-02 | 5:30 | 15d, 8h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | FA4-010 |  | 2021-05-27
DB Netz AG | FA4-037 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 33 | 35 | 2023-08-17 | 21:30 | 2023-09-02 | 5:30 | 15d, 8h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | FA4-037 |  | 2021-05-27
DB Netz AG | FA4-046 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 33 | 35 | 2023-08-17 | 21:30 | 2023-09-02 | 5:30 | 15d, 8h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | FA4-046 |  | 2021-05-27
DB Netz AG | FA4-015 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 33 | 36 | 2023-08-14 | 5:30 | 2023-09-04 | 5:30 | 21d, 0h | Continuous | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | FA4-015 |  | 2021-05-27
DB Netz AG | FA4-038 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 33 | 36 | 2023-08-14 | 5:30 | 2023-09-04 | 5:30 | 21d, 0h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | FA4-038 |  | 2021-05-27
DB Netz AG | FA4-040 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 33 | 33 | 2023-08-14 | 3:30 | 2023-08-14 | 5:30 | 0d, 2h | Continuous | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | FA4-040 |  | 2021-05-27
DB Netz AG | FA4-005 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 33 | 33 | 2023-08-14 | 3:30 | 2023-08-14 | 5:30 | 0d, 2h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | FA4-005 |  | 2021-05-27
DB Netz AG | FA4-028 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 35 | 36 | 2023-09-02 | 7:00 | 2023-09-06 | 20:00 | 4d, 13h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | FA4-028 |  | 2021-05-27
DB Netz AG | 12B0-006 | Magdeburg - Falkenberg | <> | Lu Wittenberg | Lu Wittenberg | 2023 | 2023 | 28 | 28 | 2023-07-11 | 16:00 | 2023-07-12 | 4:00 | 0d, 12h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 12B0-006 |  | 2021-05-04
DB Netz AG | 12B0-008 | Magdeburg - Falkenberg | < | Lu Wb-Piesteritz | Lu Wittenberg | 2023 | 2023 | 28 | 28 | 2023-07-11 | 20:00 | 2023-07-12 | 4:00 | 0d, 8h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 12B0-008 |  | 2021-05-04
DB Netz AG | 12B0-004 | Magdeburg - Falkenberg | < | Lu Wb-Pieste Wbf | Lu Wittenberg | 2023 | 2023 | 28 | 28 | 2023-07-11 | 20:00 | 2023-07-12 | 4:00 | 0d, 8h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 12B0-004 |  | 2021-05-04
DB Netz AG | 12B0-009 | Magdeburg - Falkenberg | <> | Lu Wittenberg | Lu Wittenberg | 2023 | 2023 | 28 | 28 | 2023-07-12 | 0:00 | 2023-07-12 | 4:00 | 0d, 4h | Continuous | Switch | T | [10 empty] | 80 | N | 12B0-009 |  | 2021-05-04
DB Netz AG | F54-005 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 32 | 36 | 2023-08-13 | 6:00 | 2023-09-09 | 16:00 | 27d, 10h | Continuous | Switch |  |  |  | P | [7 empty] | 80 | Y | F54-005 |  | 2021-06-03
DB Netz AG | F54-006 | Dresden - Děčín | <> | Dresden Hbf | Dresden Mitte | 2023 | 2023 | 32 | 36 | 2023-08-13 | 6:00 | 2023-09-09 | 16:00 | 27d, 10h | Continuous | Switch |  |  |  | P | [7 empty] | 80 | Y | F54-006 |  | 2021-06-03
DB Netz AG | F54-007 | Dresden - Děčín | <> | Dresden Hbf | Dre Freibg Str | 2023 | 2023 | 32 | 36 | 2023-08-13 | 6:00 | 2023-09-09 | 16:00 | 27d, 10h | Continuous | Switch |  |  |  | P | [7 empty] | 80 | Y | F54-007 |  | 2021-06-03
DB Netz AG | AFD-032 | Hannover - Magdeburg | <> | Magdeburg Hbf | Mg Südseite | 2023 | 2023 | 32 | 32 | 2023-08-09 | 8:00 | 2023-08-10 | 16:00 | 1d, 8h | Periodical | Signal |  |  |  |  | X | [6 empty] | 80 | N | AFD-032 |  | 2021-06-04
DB Netz AG | C12-004 | Hamburg - Magdeburg | <> | Salzwedel Gbf | Salzwedel Gbf | 2023 | 2023 | 36 | 36 | 2023-09-08 | 20:00 | 2023-09-09 | 6:00 | 0d, 10h | Continuous | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | C12-004 |  | 2020-09-30
DB Netz AG | C12-005 | Hamburg - Magdeburg | <> | Salzwedel Gbf | Salzwedel | 2023 | 2023 | 36 | 36 | 2023-09-09 | 0:00 | 2023-09-09 | 6:00 | 0d, 6h | Continuous | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | C12-005 |  | 2020-09-30
DB Netz AG | C12-006 | Hamburg - Magdeburg | <> | Salzwedel Gbf | Salzwedel | 2023 | 2023 | 36 | 36 | 2023-09-09 | 0:00 | 2023-09-09 | 3:00 | 0d, 3h | Continuous | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | C12-006 |  | 2020-09-30
DB Netz AG | AFD-033 | Magdeburg - Falkenberg | <> | Magdeburg Hbf | Magdeburg Hbf | 2023 | 2023 | 32 | 32 | 2023-08-09 | 8:00 | 2023-08-10 | 16:00 | 1d, 8h | Periodical | Signal |  |  |  |  | X | [6 empty] | 80 | N | AFD-033 |  | 2021-06-04
DB Netz AG | B07-027 | Bremen - Hannover | <> | Bremen Hbf | Bremen Hbf | 2023 | 2023 | 33 | 33 | 2023-08-14 | 14:00 | 2023-08-14 | 22:00 | 0d, 8h | Continuous | Track & Rail | T | [10 empty] | 80 | N | B07-027
DB Netz AG | 1586-001 | Hannover - Magdeburg | <> | Groß Gleidingen | Bedding Nordkopf | 2023 | 2023 | 36 | 36 | 2023-09-07 | 22:35 | 2023-09-08 | 5:30 | 0d, 6h | Continuous | Switch | T | [10 empty] | 80 | N | 1586-001 |  | 2021-07-23
DB Netz AG | 1586-002 | Hannover - Magdeburg | <> | Groß Gleidingen | Gabelung (Brg) | 2023 | 2023 | 36 | 36 | 2023-09-08 | 1:35 | 2023-09-08 | 5:30 | 0d, 3h | Continuous | Switch | T | [10 empty] | 80 | N | 1586-002 |  | 2021-07-23
DB Netz AG | B07-028 | Bremen - Hannover | > | Bremen Hbf | Bremen Hbf | 2023 | 2023 | 31 | 31 | 2023-08-05 | 22:00 | 2023-08-06 | 0:00 | 0d, 2h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | B07-028
DB Netz AG | 1656-001 | Dresden - Děčín | <> | Dresden Hbf | Dre-Neustadt | 2023 | 2023 | 31 | 31 | 2023-07-31 | 22:00 | 2023-08-01 | 5:00 | 0d, 7h | Continuous | Catenary | T | [10 empty] | 80 | N | 1656-001 |  | 2021-05-20
DB Netz AG | 1656-002 | Dresden - Děčín | <> | Dresden Hbf | Dre-Neustadt | 2023 | 2023 | 31 | 31 | 2023-07-31 | 22:00 | 2023-08-01 | 5:00 | 0d, 7h | Continuous | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 1656-002 |  | 2021-05-20
DB Netz AG | 1658-001 | Dresden - Děčín | < | Dresden Mitte | Dresden Hbf | 2023 | 2023 | 31 | 31 | 2023-08-01 | 22:00 | 2023-08-02 | 1:00 | 0d, 3h | Continuous | Catenary |  | ST | [9 empty] | 80 | N | 1658-001 |  | 2021-05-20
DB Netz AG | 1658-002 | Dresden - Děčín | <> | Dresden Hbf | Dresden Mitte | 2023 | 2023 | 31 | 31 | 2023-08-01 | 22:00 | 2023-08-02 | 1:00 | 0d, 3h | Continuous | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 1658-002 |  | 2021-05-20
DB Netz AG | 1658-003 | Dresden - Děčín | <> | Dre-Neustadt | Dresden Hbf | 2023 | 2023 | 31 | 31 | 2023-08-02 | 1:00 | 2023-08-02 | 5:00 | 0d, 4h | Continuous | Catenary | T | [10 empty] | 80 | N | 1658-003 |  | 2021-07-30
DB Netz AG | 1658-004 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 31 | 31 | 2023-08-02 | 1:00 | 2023-08-02 | 5:00 | 0d, 4h | Continuous | Catenary |  | ST | [9 empty] | 80 | N | 1658-004 |  | 2021-05-20
DB Netz AG | 165A-001 | Dresden - Děčín | <> | Dre-Neustadt | Dresden Hbf | 2023 | 2023 | 31 | 31 | 2023-08-02 | 18:00 | 2023-08-03 | 5:00 | 0d, 11h | Continuous | Catenary | T | [10 empty] | 80 | N | 165A-001 |  | 2021-05-20
DB Netz AG | 165A-002 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 31 | 31 | 2023-08-02 | 18:00 | 2023-08-03 | 5:00 | 0d, 11h | Continuous | Catenary |  | ST | [9 empty] | 80 | N | 165A-002 |  | 2021-05-20
DB Netz AG | 165A-003 | Dresden - Děčín | <> | Dresden Mitte | Dresden Hbf | 2023 | 2023 | 31 | 31 | 2023-08-02 | 18:00 | 2023-08-03 | 5:00 | 0d, 11h | Continuous | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 165A-003 |  | 2021-05-20
DB Netz AG | 165A-004 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 31 | 31 | 2023-08-02 | 18:00 | 2023-08-03 | 5:00 | 0d, 11h | Continuous | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 165A-004 |  | 2021-05-20
DB Netz AG | 165B-001 | Dresden - Děčín | <> | Dresden Hbf | Dre-Neustadt | 2023 | 2023 | 31 | 31 | 2023-08-04 | 18:00 | 2023-08-04 | 23:59 | 0d, 5h | Continuous | Catenary | T | [10 empty] | 80 | N | 165B-001 |  | 2021-05-20
DB Netz AG | 165B-002 | Dresden - Děčín | > | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 31 | 31 | 2023-08-04 | 18:00 | 2023-08-04 | 23:59 | 0d, 5h | Continuous | Catenary |  |  | S | [8 empty] | 80 | N | 165B-002 |  | 2021-05-20
DB Netz AG | 165B-003 | Dresden - Děčín | <> | Dresden Hbf | Dre-Neustadt | 2023 | 2023 | 31 | 31 | 2023-08-04 | 18:00 | 2023-08-04 | 23:59 | 0d, 5h | Continuous | Catenary | T | [10 empty] | 80 | N | 165B-003 |  | 2021-05-20
DB Netz AG | 165B-004 | Dresden - Děčín | <> | Dre Freibg Str | Dre-Neustadt | 2023 | 2023 | 31 | 31 | 2023-08-04 | 18:00 | 2023-08-04 | 23:59 | 0d, 5h | Continuous | Catenary | T | [10 empty] | 80 | N | 165B-004 |  | 2021-05-20
DB Netz AG | 165B-005 | Dresden - Děčín | <> | Dre-Friedrichst | Dresden Mitte | 2023 | 2023 | 31 | 31 | 2023-08-04 | 18:00 | 2023-08-04 | 23:59 | 0d, 5h | Continuous | Catenary | T | [10 empty] | 80 | N | 165B-005 |  | 2021-05-20
DB Netz AG | 165B-006 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 31 | 31 | 2023-08-04 | 18:00 | 2023-08-04 | 23:59 | 0d, 5h | Continuous | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 165B-006 |  | 2021-05-20
DB Netz AG | 165B-007 | Dresden - Děčín | <> | Dre-Neustadt | Dresden Hbf | 2023 | 2023 | 31 | 31 | 2023-08-04 | 18:00 | 2023-08-04 | 23:59 | 0d, 5h | Continuous | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 165B-007 |  | 2021-05-20
DB Netz AG | 165B-008 | Dresden - Děčín | <> | Dre Freibg Str | Dresden Hbf | 2023 | 2023 | 31 | 31 | 2023-08-04 | 18:00 | 2023-08-04 | 23:59 | 0d, 5h | Continuous | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 165B-008 |  | 2021-05-20
DB Netz AG | 165B-009 | Dresden - Děčín | <> | Dre-Friedrichst | Dresden Mitte | 2023 | 2023 | 31 | 31 | 2023-08-04 | 18:00 | 2023-08-04 | 23:59 | 0d, 5h | Continuous | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 165B-009 |  | 2021-05-20
DB Netz AG | 165B-010 | Dresden - Děčín | <> | Dresden Hbf | Dre-Neustadt | 2023 | 2023 | 31 | 31 | 2023-08-05 | 0:00 | 2023-08-05 | 5:00 | 0d, 5h | Continuous | Catenary | T | [10 empty] | 80 | N | 165B-010 |  | 2021-05-20
DB Netz AG | 165B-011 | Dresden - Děčín | <> | Dresden Hbf | Dre-Neustadt | 2023 | 2023 | 31 | 31 | 2023-08-05 | 0:00 | 2023-08-05 | 5:00 | 0d, 5h | Continuous | Catenary | T | [10 empty] | 80 | N | 165B-011 |  | 2021-05-20
DB Netz AG | 165B-012 | Dresden - Děčín | <> | Dresden Hbf | Dre Freibg Str | 2023 | 2023 | 31 | 31 | 2023-08-05 | 0:00 | 2023-08-05 | 5:00 | 0d, 5h | Continuous | Catenary | T | [10 empty] | 80 | N | 165B-012 |  | 2021-05-20
DB Netz AG | 165B-013 | Dresden - Děčín | <> | Dre-Friedrichst | Dresden Mitte | 2023 | 2023 | 31 | 31 | 2023-08-05 | 0:00 | 2023-08-05 | 5:00 | 0d, 5h | Continuous | Catenary | T | [10 empty] | 80 | N | 165B-013 |  | 2021-05-20
DB Netz AG | 165B-014 | Dresden - Děčín | <> | Dresden Hbf | Dre-Neustadt | 2023 | 2023 | 31 | 31 | 2023-08-05 | 0:00 | 2023-08-05 | 5:00 | 0d, 5h | Continuous | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 165B-014 |  | 2021-05-20
DB Netz AG | 165B-015 | Dresden - Děčín | <> | Dresden Hbf | Dre-Neustadt | 2023 | 2023 | 31 | 31 | 2023-08-05 | 0:00 | 2023-08-05 | 5:00 | 0d, 5h | Continuous | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 165B-015 |  | 2021-05-20
DB Netz AG | 165B-016 | Dresden - Děčín | <> | Dre Freibg Str | Dre-Neustadt | 2023 | 2023 | 31 | 31 | 2023-08-05 | 0:00 | 2023-08-05 | 5:00 | 0d, 5h | Continuous | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 165B-016 |  | 2021-05-20
DB Netz AG | 165B-017 | Dresden - Děčín | <> | Dre-Friedrichst | Dresden Mitte | 2023 | 2023 | 31 | 31 | 2023-08-05 | 0:00 | 2023-08-05 | 5:00 | 0d, 5h | Continuous | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 165B-017 |  | 2021-05-20
DB Netz AG | 1667-001 | Dresden - Děčín | <> | Dresden Hbf | Dre-Neustadt | 2023 | 2023 | 31 | 31 | 2023-08-05 | 18:00 | 2023-08-06 | 23:59 | 1d, 5h | Periodical | Catenary | T | [10 empty] | 80 | N | 1667-001 |  | 2021-05-20
DB Netz AG | 1667-002 | Dresden - Děčín | <> | Dresden Hbf | Dre-Neustadt | 2023 | 2023 | 31 | 31 | 2023-08-05 | 18:00 | 2023-08-06 | 23:59 | 1d, 5h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 1667-002 |  | 2021-05-20
DB Netz AG | 1667-003 | Dresden - Děčín | <> | Dresden Hbf | Dre-Neustadt | 2023 | 2023 | 31 | 32 | 2023-08-06 | 0:00 | 2023-08-07 | 5:00 | 1d, 5h | Periodical | Catenary | T | [10 empty] | 80 | N | 1667-003 |  | 2021-05-20
DB Netz AG | 1667-004 | Dresden - Děčín | <> | Dresden Hbf | Dre-Neustadt | 2023 | 2023 | 31 | 32 | 2023-08-06 | 0:00 | 2023-08-07 | 5:00 | 1d, 5h | Periodical | Catenary | T | [10 empty] | 80 | N | 1667-004 |  | 2021-05-20
DB Netz AG | 1667-005 | Dresden - Děčín | <> | Dre Freibg Str | Dre-Neustadt | 2023 | 2023 | 31 | 32 | 2023-08-06 | 0:00 | 2023-08-07 | 5:00 | 1d, 5h | Periodical | Catenary | T | [10 empty] | 80 | N | 1667-005 |  | 2021-05-20
DB Netz AG | 1667-006 | Dresden - Děčín | <> | Dre-Friedrichst | Dresden Mitte | 2023 | 2023 | 31 | 32 | 2023-08-06 | 0:00 | 2023-08-07 | 5:00 | 1d, 5h | Periodical | Catenary | T | [10 empty] | 80 | N | 1667-006 |  | 2021-05-20
DB Netz AG | 1667-007 | Dresden - Děčín | <> | Dresden Hbf | Dre-Neustadt | 2023 | 2023 | 31 | 32 | 2023-08-06 | 0:00 | 2023-08-07 | 5:00 | 1d, 5h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 1667-007 |  | 2021-05-20
DB Netz AG | 1667-008 | Dresden - Děčín | <> | Dresden Hbf | Dre-Neustadt | 2023 | 2023 | 31 | 32 | 2023-08-06 | 0:00 | 2023-08-07 | 5:00 | 1d, 5h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 1667-008 |  | 2021-05-20
DB Netz AG | 1667-009 | Dresden - Děčín | <> | Dre Freibg Str | Dre-Neustadt | 2023 | 2023 | 31 | 32 | 2023-08-06 | 0:00 | 2023-08-07 | 5:00 | 1d, 5h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 1667-009 |  | 2021-05-20
DB Netz AG | 1667-010 | Dresden - Děčín | <> | Dre-Friedrichst | Dresden Mitte | 2023 | 2023 | 31 | 32 | 2023-08-06 | 0:00 | 2023-08-07 | 5:00 | 1d, 5h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 1667-010 |  | 2021-05-20
DB Netz AG | 166B-001 | Dresden - Děčín | <> | Dresden Hbf | Dre-Neustadt | 2023 | 2023 | 32 | 32 | 2023-08-07 | 18:00 | 2023-08-08 | 5:00 | 0d, 11h | Continuous | Catenary | T | [10 empty] | 80 | N | 166B-001 |  | 2021-05-20
DB Netz AG | 166C-001 | Dresden - Děčín | <> | Dresden Hbf | Dre-Neustadt | 2023 | 2023 | 32 | 32 | 2023-08-08 | 18:00 | 2023-08-10 | 5:00 | 1d, 11h | Periodical | Catenary | T | [10 empty] | 80 | N | 166C-001 |  | 2021-05-20
DB Netz AG | 166C-002 | Dresden - Děčín | <> | Dresden Hbf | Dre-Neustadt | 2023 | 2023 | 32 | 32 | 2023-08-08 | 18:00 | 2023-08-10 | 5:00 | 1d, 11h | Periodical | Catenary | T | [10 empty] | 80 | N | 166C-002 |  | 2021-05-20
DB Netz AG | 166C-003 | Dresden - Děčín | <> | Dre Freibg Str | Dre-Neustadt | 2023 | 2023 | 32 | 32 | 2023-08-08 | 18:00 | 2023-08-10 | 5:00 | 1d, 11h | Periodical | Catenary | T | [10 empty] | 80 | N | 166C-003 |  | 2021-05-20
DB Netz AG | 166C-004 | Dresden - Děčín | <> | Dre-Friedrichst | Dresden Mitte | 2023 | 2023 | 32 | 32 | 2023-08-08 | 18:00 | 2023-08-10 | 5:00 | 1d, 11h | Periodical | Catenary | T | [10 empty] | 80 | N | 166C-004 |  | 2021-05-20
DB Netz AG | 1674-001 | Dresden - Děčín | <> | Dresden Hbf | Dre Freibg Str | 2023 | 2023 | 34 | 34 | 2023-08-25 | 21:00 | 2023-08-26 | 1:00 | 0d, 4h | Continuous | Catenary | T | [10 empty] | 80 | N | 1674-001 |  | 2021-05-20
DB Netz AG | 1674-002 | Dresden - Děčín | <> | Dresden Hbf | Dre Freibg Str | 2023 | 2023 | 34 | 34 | 2023-08-26 | 1:00 | 2023-08-26 | 5:00 | 0d, 4h | Continuous | Catenary | T | [10 empty] | 80 | N | 1674-002 |  | 2021-05-20
DB Netz AG | 1674-003 | Dresden - Děčín | <> | Dresden Hbf | Dre Freibg Str | 2023 | 2023 | 34 | 34 | 2023-08-26 | 1:00 | 2023-08-26 | 5:00 | 0d, 4h | Continuous | Catenary | T | [10 empty] | 80 | N | 1674-003 |  | 2021-05-20
DB Netz AG | 1674-004 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 34 | 34 | 2023-08-26 | 1:00 | 2023-08-26 | 5:00 | 0d, 4h | Continuous | Catenary | T | [10 empty] | 80 | N | 1674-004 |  | 2021-05-20
DB Netz AG | 1679-001 | Dresden - Děčín | <> | Dresden Hbf | Dre Freibg Str | 2023 | 2023 | 34 | 34 | 2023-08-26 | 17:00 | 2023-08-26 | 23:59 | 0d, 6h | Continuous | Catenary | T | [10 empty] | 80 | N | 1679-001 |  | 2021-05-20
DB Netz AG | 1679-002 | Dresden - Děčín | < | Dresden Mitte | Dresden Hbf | 2023 | 2023 | 34 | 34 | 2023-08-26 | 17:00 | 2023-08-26 | 23:59 | 0d, 6h | Continuous | Catenary |  | ST | [9 empty] | 80 | N | 1679-002 |  | 2021-05-20
DB Netz AG | 1679-003 | Dresden - Děčín | <> | Dresden Hbf | Dre-Neustadt | 2023 | 2023 | 34 | 34 | 2023-08-27 | 0:00 | 2023-08-27 | 5:00 | 0d, 5h | Continuous | Catenary | T | [10 empty] | 80 | N | 1679-003 |  | 2021-05-20
DB Netz AG | 1679-004 | Dresden - Děčín | <> | Dre-Reick Abstbf | Dre-Neustadt | 2023 | 2023 | 34 | 34 | 2023-08-27 | 0:00 | 2023-08-27 | 5:00 | 0d, 5h | Continuous | Catenary | T | [10 empty] | 80 | N | 1679-004 |  | 2021-05-20
DB Netz AG | 1679-005 | Dresden - Děčín | <> | Dresden-Reick | Dresden Hbf | 2023 | 2023 | 34 | 34 | 2023-08-27 | 0:00 | 2023-08-27 | 5:00 | 0d, 5h | Continuous | Catenary | T | [10 empty] | 80 | N | 1679-005 |  | 2021-05-20
DB Netz AG | 1679-006 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 34 | 34 | 2023-08-27 | 0:00 | 2023-08-27 | 5:00 | 0d, 5h | Continuous | Catenary | T | [10 empty] | 80 | N | 1679-006 |  | 2021-05-20
DB Netz AG | 1679-007 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 34 | 34 | 2023-08-27 | 0:00 | 2023-08-27 | 5:00 | 0d, 5h | Continuous | Catenary | T | [10 empty] | 80 | N | 1679-007 |  | 2021-05-20
DB Netz AG | 1679-008 | Dresden - Děčín | <> | Dre Freibg Str | Dresden-Altstadt | 2023 | 2023 | 34 | 34 | 2023-08-27 | 0:00 | 2023-08-27 | 5:00 | 0d, 5h | Continuous | Catenary | T | [10 empty] | 80 | N | 1679-008 |  | 2021-05-20
DB Netz AG | 1679-009 | Dresden - Děčín | <> | Dre-Friedrichst | Dre Freibg Str | 2023 | 2023 | 34 | 34 | 2023-08-27 | 0:00 | 2023-08-27 | 5:00 | 0d, 5h | Continuous | Catenary | T | [10 empty] | 80 | N | 1679-009 |  | 2021-05-20
DB Netz AG | 1679-010 | Dresden - Děčín | <> | Dre-Friedrichst | Dresden Mitte | 2023 | 2023 | 34 | 34 | 2023-08-27 | 0:00 | 2023-08-27 | 5:00 | 0d, 5h | Continuous | Catenary | T | [10 empty] | 80 | N | 1679-010 |  | 2021-05-20
DB Netz AG | 1679-011 | Dresden - Děčín | <> | Dre-Neustadt | Dre-Neustadt Gbf | 2023 | 2023 | 34 | 34 | 2023-08-27 | 0:00 | 2023-08-27 | 5:00 | 0d, 5h | Continuous | Catenary | T | [10 empty] | 80 | N | 1679-011 |  | 2021-05-20
DB Netz AG | 167D-001 | Dresden - Děčín | <> | Dresden Hbf | Dre Freibg Str | 2023 | 2023 | 34 | 35 | 2023-08-27 | 17:00 | 2023-08-28 | 1:00 | 0d, 8h | Continuous | Catenary | T | [10 empty] | 80 | N | 167D-001 |  | 2021-05-20
DB Netz AG | 167D-002 | Dresden - Děčín | > | Dresden Hbf | Dresden Mitte | 2023 | 2023 | 34 | 35 | 2023-08-27 | 17:00 | 2023-08-28 | 1:00 | 0d, 8h | Continuous | Catenary |  | ST | [9 empty] | 80 | N | 167D-002 |  | 2021-05-20
DB Netz AG | 167D-003 | Dresden - Děčín | <> | Dresden Hbf | Dre-Neustadt | 2023 | 2023 | 35 | 35 | 2023-08-28 | 1:00 | 2023-08-28 | 5:00 | 0d, 4h | Continuous | Catenary | T | [10 empty] | 80 | N | 167D-003 |  | 2021-05-20
DB Netz AG | 167D-004 | Dresden - Děčín | <> | Dre-Reick Abstbf | Dre-Neustadt | 2023 | 2023 | 35 | 35 | 2023-08-28 | 1:00 | 2023-08-28 | 5:00 | 0d, 4h | Continuous | Catenary | T | [10 empty] | 80 | N | 167D-004 |  | 2021-05-20
DB Netz AG | 167D-005 | Dresden - Děčín | <> | Dresden-Reick | Dre-Neustadt | 2023 | 2023 | 35 | 35 | 2023-08-28 | 1:00 | 2023-08-28 | 5:00 | 0d, 4h | Continuous | Catenary | T | [10 empty] | 80 | N | 167D-005 |  | 2021-05-20
DB Netz AG | 167D-006 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 35 | 35 | 2023-08-28 | 1:00 | 2023-08-28 | 5:00 | 0d, 4h | Continuous | Catenary | T | [10 empty] | 80 | N | 167D-006 |  | 2021-05-20
DB Netz AG | 167D-007 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 35 | 35 | 2023-08-28 | 1:00 | 2023-08-28 | 5:00 | 0d, 4h | Continuous | Catenary | T | [10 empty] | 80 | N | 167D-007 |  | 2021-05-20
DB Netz AG | 167D-008 | Dresden - Děčín | <> | Dre Freibg Str | Dresden-Altstadt | 2023 | 2023 | 35 | 35 | 2023-08-28 | 1:00 | 2023-08-28 | 5:00 | 0d, 4h | Continuous | Catenary | T | [10 empty] | 80 | N | 167D-008 |  | 2021-05-20
DB Netz AG | 167D-009 | Dresden - Děčín | <> | Dre-Friedrichst | Dre Freibg Str | 2023 | 2023 | 35 | 35 | 2023-08-28 | 1:00 | 2023-08-28 | 5:00 | 0d, 4h | Continuous | Catenary | T | [10 empty] | 80 | N | 167D-009 |  | 2021-05-20
DB Netz AG | 167D-010 | Dresden - Děčín | <> | Dre-Friedrichst | Dresden Mitte | 2023 | 2023 | 35 | 35 | 2023-08-28 | 1:00 | 2023-08-28 | 5:00 | 0d, 4h | Continuous | Catenary | T | [10 empty] | 80 | N | 167D-010 |  | 2021-05-20
DB Netz AG | 167D-011 | Dresden - Děčín | <> | Dre-Neustadt | Dre-Neustadt Gbf | 2023 | 2023 | 35 | 35 | 2023-08-28 | 1:00 | 2023-08-28 | 5:00 | 0d, 4h | Continuous | Catenary | T | [10 empty] | 80 | N | 167D-011 |  | 2021-05-20
DB Netz AG | 1692-001 | Dresden - Děčín | <> | Dresden Hbf | Dre Freibg Str | 2023 | 2023 | 35 | 35 | 2023-09-02 | 17:00 | 2023-09-02 | 23:00 | 0d, 6h | Continuous | Catenary | T | [10 empty] | 80 | N | 1692-001 |  | 2021-05-20
DB Netz AG | 1692-002 | Dresden - Děčín | <> | Dresden Hbf | Dresden Mitte | 2023 | 2023 | 35 | 35 | 2023-09-02 | 17:00 | 2023-09-02 | 23:00 | 0d, 6h | Continuous | Catenary | T | [10 empty] | 80 | N | 1692-002 |  | 2021-05-20
DB Netz AG | 1692-003 | Dresden - Děčín | <> | Dre Freibg Str | Dresden-Altstadt | 2023 | 2023 | 35 | 35 | 2023-09-02 | 17:00 | 2023-09-02 | 23:00 | 0d, 6h | Continuous | Catenary | T | [10 empty] | 80 | N | 1692-003 |  | 2021-05-20
DB Netz AG | 1692-004 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 35 | 35 | 2023-09-02 | 17:00 | 2023-09-02 | 23:00 | 0d, 6h | Continuous | Catenary | T | [10 empty] | 80 | N | 1692-004 |  | 2021-05-20
DB Netz AG | 1692-005 | Dresden - Děčín | <> | Dre-Friedrichst | Dre Freibg Str | 2023 | 2023 | 35 | 35 | 2023-09-02 | 17:00 | 2023-09-02 | 23:00 | 0d, 6h | Continuous | Catenary | T | [10 empty] | 80 | N | 1692-005 |  | 2021-05-20
DB Netz AG | 1692-006 | Dresden - Děčín | <> | Dresden Hbf | Dre-Neustadt | 2023 | 2023 | 35 | 35 | 2023-09-02 | 23:00 | 2023-09-03 | 5:00 | 0d, 6h | Continuous | Catenary | T | [10 empty] | 80 | N | 1692-006 |  | 2021-05-20
DB Netz AG | 1692-007 | Dresden - Děčín | <> | Dre-Reick Abstbf | Dre-Neustadt | 2023 | 2023 | 35 | 35 | 2023-09-02 | 23:00 | 2023-09-03 | 5:00 | 0d, 6h | Continuous | Catenary | T | [10 empty] | 80 | N | 1692-007 |  | 2021-05-20
DB Netz AG | 1692-008 | Dresden - Děčín | <> | Dresden-Reick | Dre-Neustadt | 2023 | 2023 | 35 | 35 | 2023-09-02 | 23:00 | 2023-09-03 | 5:00 | 0d, 6h | Continuous | Catenary | T | [10 empty] | 80 | N | 1692-008 |  | 2021-05-20
DB Netz AG | 1692-009 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 35 | 35 | 2023-09-02 | 23:00 | 2023-09-03 | 5:00 | 0d, 6h | Continuous | Catenary | T | [10 empty] | 80 | N | 1692-009 |  | 2021-05-20
DB Netz AG | 1692-010 | Dresden - Děčín | <> | Dre Freibg Str | Dresden-Altstadt | 2023 | 2023 | 35 | 35 | 2023-09-02 | 23:00 | 2023-09-03 | 5:00 | 0d, 6h | Continuous | Catenary | T | [10 empty] | 80 | N | 1692-010 |  | 2021-05-20
DB Netz AG | 1692-011 | Dresden - Děčín | <> | Dre-Friedrichst | Dre Freibg Str | 2023 | 2023 | 35 | 35 | 2023-09-02 | 23:00 | 2023-09-03 | 5:00 | 0d, 6h | Continuous | Catenary | T | [10 empty] | 80 | N | 1692-011 |  | 2021-05-20
DB Netz AG | 1692-012 | Dresden - Děčín | <> | Dre-Friedrichst | Dresden Mitte | 2023 | 2023 | 35 | 35 | 2023-09-02 | 23:00 | 2023-09-03 | 5:00 | 0d, 6h | Continuous | Catenary | T | [10 empty] | 80 | N | 1692-012 |  | 2021-05-20
DB Netz AG | 1692-013 | Dresden - Děčín | <> | Dre-Neustadt | Dre-Neustadt Gbf | 2023 | 2023 | 35 | 35 | 2023-09-02 | 23:00 | 2023-09-03 | 5:00 | 0d, 6h | Continuous | Catenary | T | [10 empty] | 80 | N | 1692-013 |  | 2021-05-20
DB Netz AG | 1697-001 | Dresden - Děčín | <> | Dresden Hbf | Dre Freibg Str | 2023 | 2023 | 35 | 35 | 2023-09-03 | 17:00 | 2023-09-03 | 23:59 | 0d, 6h | Continuous | Catenary | T | [10 empty] | 80 | N | 1697-001 |  | 2021-05-20
DB Netz AG | 1697-002 | Dresden - Děčín | <> | Dre Freibg Str | Dresden-Altstadt | 2023 | 2023 | 35 | 35 | 2023-09-03 | 17:00 | 2023-09-03 | 23:59 | 0d, 6h | Continuous | Catenary | T | [10 empty] | 80 | N | 1697-002 |  | 2021-05-20
DB Netz AG | 1697-003 | Dresden - Děčín | <> | Dre-Friedrichst | Dre Freibg Str | 2023 | 2023 | 35 | 35 | 2023-09-03 | 17:00 | 2023-09-03 | 23:59 | 0d, 6h | Continuous | Catenary | T | [10 empty] | 80 | N | 1697-003 |  | 2021-05-20
DB Netz AG | 1697-004 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 35 | 35 | 2023-09-03 | 17:00 | 2023-09-03 | 23:59 | 0d, 6h | Continuous | Catenary | T | [10 empty] | 80 | N | 1697-004 |  | 2021-05-20
DB Netz AG | 1697-005 | Dresden - Děčín | <> | Dresden Hbf | Dre Freibg Str | 2023 | 2023 | 36 | 36 | 2023-09-04 | 0:00 | 2023-09-04 | 5:00 | 0d, 5h | Continuous | Catenary | T | [10 empty] | 80 | N | 1697-005 |  | 2021-05-20
DB Netz AG | 1697-006 | Dresden - Děčín | <> | Dre Freibg Str | Dresden-Altstadt | 2023 | 2023 | 36 | 36 | 2023-09-04 | 0:00 | 2023-09-04 | 5:00 | 0d, 5h | Continuous | Catenary | T | [10 empty] | 80 | N | 1697-006 |  | 2021-05-20
DB Netz AG | 1697-007 | Dresden - Děčín | <> | Dre-Friedrichst | Dre Freibg Str | 2023 | 2023 | 36 | 36 | 2023-09-04 | 0:00 | 2023-09-04 | 5:00 | 0d, 5h | Continuous | Catenary | T | [10 empty] | 80 | N | 1697-007 |  | 2021-05-20
DB Netz AG | 1697-008 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 36 | 36 | 2023-09-04 | 0:00 | 2023-09-04 | 5:00 | 0d, 5h | Continuous | Catenary | T | [10 empty] | 80 | N | 1697-008 |  | 2021-05-20
DB Netz AG | 1697-009 | Dresden - Děčín | <> | Dresden Hbf | Dre Freibg Str | 2023 | 2023 | 36 | 36 | 2023-09-04 | 0:00 | 2023-09-04 | 5:00 | 0d, 5h | Continuous | Catenary | T | [10 empty] | 80 | N | 1697-009 |  | 2021-05-20
DB Netz AG | 169D-001 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 36 | 36 | 2023-09-04 | 17:00 | 2023-09-05 | 5:00 | 0d, 12h | Continuous | Catenary | T | [10 empty] | 80 | N | 169D-001 |  | 2021-05-20
DB Netz AG | 169D-002 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 36 | 36 | 2023-09-04 | 17:00 | 2023-09-05 | 5:00 | 0d, 12h | Continuous | Catenary |  | ST | [9 empty] | 80 | N | 169D-002 |  | 2021-05-20
DB Netz AG | 169D-003 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 36 | 36 | 2023-09-04 | 17:00 | 2023-09-05 | 5:00 | 0d, 12h | Continuous | Catenary | T | [10 empty] | 80 | N | 169D-003 |  | 2021-05-20
DB Netz AG | 169D-004 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 36 | 36 | 2023-09-04 | 17:00 | 2023-09-05 | 5:00 | 0d, 12h | Continuous | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 169D-004 |  | 2021-05-20
DB Netz AG | 169D-005 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 36 | 36 | 2023-09-04 | 17:00 | 2023-09-05 | 5:00 | 0d, 12h | Continuous | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 169D-005 |  | 2021-05-20
DB Netz AG | 169D-007 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 36 | 36 | 2023-09-04 | 17:00 | 2023-09-05 | 5:00 | 0d, 12h | Continuous | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 169D-007 |  | 2021-05-20
DB Netz AG | 16A6-001 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 36 | 36 | 2023-09-05 | 19:00 | 2023-09-05 | 23:59 | 0d, 4h | Continuous | Catenary |  | ST | [9 empty] | 80 | N | 16A6-001 |  | 2021-05-20
DB Netz AG | 16A6-002 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 36 | 36 | 2023-09-06 | 0:00 | 2023-09-06 | 5:00 | 0d, 5h | Continuous | Catenary | T | [10 empty] | 80 | N | 16A6-002 |  | 2021-05-20
DB Netz AG | 16A6-003 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 36 | 36 | 2023-09-06 | 0:00 | 2023-09-06 | 5:00 | 0d, 5h | Continuous | Catenary |  | ST | [9 empty] | 80 | N | 16A6-003 |  | 2021-05-20
DB Netz AG | 16A6-004 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 36 | 36 | 2023-09-06 | 0:00 | 2023-09-06 | 5:00 | 0d, 5h | Continuous | Catenary | T | [10 empty] | 80 | N | 16A6-004 |  | 2021-05-20
DB Netz AG | 16A8-001 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 36 | 36 | 2023-09-06 | 19:00 | 2023-09-09 | 5:00 | 2d, 10h | Periodical | Catenary | T | [10 empty] | 80 | N | 16A8-001 |  | 2021-05-20
DB Netz AG | 16A8-002 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 36 | 36 | 2023-09-06 | 19:00 | 2023-09-09 | 5:00 | 2d, 10h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 16A8-002 |  | 2021-05-20
DB Netz AG | 16A8-003 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 36 | 36 | 2023-09-06 | 19:00 | 2023-09-09 | 5:00 | 2d, 10h | Periodical | Catenary | T | [10 empty] | 80 | N | 16A8-003 |  | 2021-05-20
DB Netz AG | 16D2-001 | Dresden - Děčín | <> | Bad Schandau | Königst (Sä) Üst | 2023 | 2023 | 36 | 36 | 2023-09-04 | 23:00 | 2023-09-10 | 5:00 | 5d, 6h | Periodical | Catenary | T | [10 empty] | 80 | N | 16D2-001 |  | 2021-04-27
DB Netz AG | 16D2-002 | Dresden - Děčín | <> | Bad Schandau | Bad Schandau | 2023 | 2023 | 36 | 36 | 2023-09-04 | 23:00 | 2023-09-10 | 5:00 | 5d, 6h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 16D2-002 |  | 2021-04-27
DB Netz AG | 16D2-004 | Dresden - Děčín | <> | Königst (Sä) Üst | Bad Schandau Gr | 2023 | 2023 | 36 | 36 | 2023-09-04 | 23:00 | 2023-09-10 | 5:00 | 5d, 6h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80,54 | N | 16D2-004 |  | 2021-04-27
DB Netz AG | 16D2-005 | Dresden - Děčín | <> | Bad Schandau Gr | Bad Schandau Gr | 2023 | 2023 | 36 | 36 | 2023-09-04 | 23:00 | 2023-09-10 | 5:00 | 5d, 6h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80,54 | N | 16D2-005 |  | 2021-04-27
DB Netz AG | 16D2-006 | Dresden - Děčín | <> | Bad Schandau | Bad Schandau | 2023 | 2023 | 36 | 36 | 2023-09-04 | 23:00 | 2023-09-10 | 5:00 | 5d, 6h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 16D2-006 |  | 2021-04-27
DB Netz AG | 16D2-008 | Dresden - Děčín | <> | Kurort Rathen | Bad Schandau | 2023 | 2023 | 36 | 36 | 2023-09-04 | 23:00 | 2023-09-10 | 5:00 | 5d, 6h | Continuous | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 16D2-008 |  | 2021-04-27
DB Netz AG | 1703-001 | Magdeburg - Falkenberg | > | Mg-Sudenburg | Niederndodeleben | 2023 | 2023 | 34 | 34 | 2023-08-25 | 21:25 | 2023-08-26 | 21:55 | 1d, 0h | Periodical | Maintenance |  | LT | [9 empty] | 80 | N | 1703-001 |  | 2022-05-19
DB Netz AG | 1703-002 | Magdeburg - Falkenberg | > | Mg-Sudenburg | Wellen | 2023 | 2023 | 34 | 34 | 2023-08-25 | 21:55 | 2023-08-26 | 22:55 | 1d, 1h | Periodical | Maintenance |  | LT | [9 empty] | 80 | N | 1703-002 |  | 2022-05-19
DB Netz AG | 1703-003 | Magdeburg - Falkenberg | > | Niederndodeleben | Dreileben-Drack | 2023 | 2023 | 34 | 34 | 2023-08-25 | 22:55 | 2023-08-26 | 23:10 | 1d, 0h | Periodical | Maintenance |  | LT | [9 empty] | 80 | N | 1703-003 |  | 2022-05-19
DB Netz AG | 1703-004 | Magdeburg - Falkenberg | > | Wellen | Eilsleb(b Mg)Gbf | 2023 | 2023 | 34 | 34 | 2023-08-25 | 23:10 | 2023-08-27 | 0:55 | 1d, 1h | Periodical | Maintenance |  | LT | [9 empty] | 80 | N | 1703-004 |  | 2022-05-19
DB Netz AG | 1703-005 | Magdeburg - Falkenberg | <> | Mg-Sudenburg | Eilsleb(b Mg)Gbf | 2023 | 2023 | 34 | 34 | 2023-08-25 | 21:25 | 2023-08-27 | 0:55 | 1d, 3h | Periodical | Maintenance |  |  |  | P | [7 empty] | 80 | N | 1703-005 |  | 2022-05-19
DB Netz AG | 1703-006 | Magdeburg - Falkenberg | > | Dreileben-Drack | Wefensleben | 2023 | 2023 | 34 | 34 | 2023-08-26 | 0:55 | 2023-08-27 | 1:15 | 1d, 0h | Periodical | Maintenance |  | LT | [9 empty] | 80 | N | 1703-006 |  | 2022-05-19
DB Netz AG | 1703-007 | Magdeburg - Falkenberg | > | Eilsleb(b Mg)Gbf | Wefensleben | 2023 | 2023 | 34 | 34 | 2023-08-26 | 1:15 | 2023-08-27 | 2:05 | 1d, 0h | Periodical | Maintenance |  | LT | [9 empty] | 80 | N | 1703-007 |  | 2022-05-19
DB Netz AG | 1703-008 | Hannover - Magdeburg | > | Wefensleben | Harbke | 2023 | 2023 | 34 | 34 | 2023-08-26 | 2:05 | 2023-08-27 | 3:15 | 1d, 1h | Periodical | Maintenance |  | LT | [9 empty] | 80 | N | 1703-008 |  | 2022-05-19
DB Netz AG | 1703-009 | Hannover - Magdeburg | > | Marienborn | Helmstedt | 2023 | 2023 | 34 | 34 | 2023-08-26 | 3:15 | 2023-08-27 | 4:10 | 1d, 0h | Periodical | Maintenance |  | LT | [9 empty] | 80 | N | 1703-009 |  | 2022-05-19
DB Netz AG | 1703-010 | Magdeburg - Falkenberg | <> | Eilsleb(b Mg)Gbf | Helmstedt | 2023 | 2023 | 34 | 34 | 2023-08-26 | 0:55 | 2023-08-27 | 4:10 | 1d, 3h | Periodical | Maintenance |  |  |  | P | [7 empty] | 80 | N | 1703-010 |  | 2022-05-19
DB Netz AG | 1705-001 | Dresden - Děčín | > | Pirna | Heidenau | 2023 | 2023 | 34 | 35 | 2023-08-27 | 21:00 | 2023-08-28 | 1:00 | 0d, 4h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1705-001 |  | 2021-04-07
DB Netz AG | 1705-002 | Dresden - Děčín | > | Pirna | Heidenau | 2023 | 2023 | 34 | 35 | 2023-08-27 | 21:00 | 2023-08-28 | 1:00 | 0d, 4h | Continuous | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | 1705-002 |  | 2021-04-07
DB Netz AG | 1705-003 | Dresden - Děčín | < | Heidenau | Pirna | 2023 | 2023 | 35 | 35 | 2023-08-28 | 1:00 | 2023-08-28 | 5:00 | 0d, 4h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1705-003 |  | 2021-04-07
DB Netz AG | 1705-004 | Dresden - Děčín | < | Heidenau | Pirna | 2023 | 2023 | 35 | 35 | 2023-08-28 | 1:00 | 2023-08-28 | 5:00 | 0d, 4h | Continuous | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | 1705-004 |  | 2021-04-07
DB Netz AG | 1705-005 | Dresden - Děčín | < | Pirna Gbf | Pirna | 2023 | 2023 | 35 | 35 | 2023-08-28 | 1:00 | 2023-08-28 | 3:00 | 0d, 2h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1705-005 |  | 2021-04-07
DB Netz AG | 1705-006 | Dresden - Děčín | < | Heidenau | Pirna | 2023 | 2023 | 35 | 35 | 2023-08-28 | 1:00 | 2023-08-28 | 3:00 | 0d, 2h | Continuous | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | 1705-006 |  | 2021-04-07
DB Netz AG | 1730-001 | Hamburg - Magdeburg | > | Winsen (Luhe) | Winsen (Luhe) | 2023 | 2023 | 31 | 32 | 2023-08-05 | 23:00 | 2023-08-13 | 5:00 | 7d, 6h | Continuous | Track & Rail |  |  | S | [8 empty] | 80 | N | 1730-001 |  | 2021-04-28
DB Netz AG | 1730-002 | Hamburg - Magdeburg | > | Winsen (Luhe) | Winsen (Luhe) | 2023 | 2023 | 31 | 32 | 2023-08-05 | 23:00 | 2023-08-07 | 5:00 | 1d, 6h | Periodical | Track & Rail |  | ST | [9 empty] | 80 | N | 1730-002 |  | 2021-04-28
DB Netz AG | 1730-003 | Hamburg - Magdeburg | < | Winsen (Luhe) | Winsen (Luhe) | 2023 | 2023 | 31 | 32 | 2023-08-05 | 23:00 | 2023-08-07 | 5:00 | 1d, 6h | Periodical | Track & Rail |  |  | S | [8 empty] | 80 | N | 1730-003 |  | 2021-04-28
DB Netz AG | 1730-004 | Hamburg - Magdeburg | > | Winsen (Luhe) | Winsen (Luhe) | 2023 | 2023 | 32 | 32 | 2023-08-07 | 8:00 | 2023-08-11 | 16:00 | 4d, 8h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1730-004 |  | 2021-04-28
DB Netz AG | 1779-016 | Rostock - Berlin | <> | Biesdf Kr Nord | Bln Nordost | 2023 | 2023 | 28 | 28 | 2023-07-11 | 8:00 | 2023-07-11 | 16:00 | 0d, 8h | Continuous | Bridge | T | [10 empty] | 80 | N | 1779-016
DB Netz AG | 1779-018 | Rostock - Berlin | <> | Biesdf Kr Nord | Bln Nordost | 2023 | 2023 | 29 | 29 | 2023-07-22 | 8:00 | 2023-07-23 | 20:00 | 1d, 12h | Periodical | Bridge | T | [10 empty] | 80 | N | 1779-018
DB Netz AG | 17B2-007 | Bremen - Hannover | > | Letter Abzw | Wunstorf | 2023 | 2023 | 36 | 36 | 2023-09-06 | 22:35 | 2023-09-08 | 4:45 | 1d, 6h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 17B2-007
DB Netz AG | 17B2-009 | Bremen - Hannover | <> | Seelze | Seelze West | 2023 | 2023 | 36 | 36 | 2023-09-06 | 22:35 | 2023-09-08 | 4:45 | 1d, 6h | Periodical | Catenary |  |  |  | P | [7 empty] | 80 | N | 17B2-009
DB Netz AG | 17B2-011 | Bremen - Hannover | <> | Seelze West | Seelze | 2023 | 2023 | 36 | 36 | 2023-09-06 | 22:35 | 2023-09-08 | 4:45 | 1d, 6h | Periodical | Catenary |  |  | S | [8 empty] | 80 | N | 17B2-011
DB Netz AG | 1730-005 | Hamburg - Magdeburg | > | Winsen (Luhe) | Winsen (Luhe) | 2023 | 2023 | 32 | 32 | 2023-08-07 | 8:00 | 2023-08-11 | 16:00 | 4d, 8h | Continuous | Track & Rail |  |  | S | [8 empty] | 80 | N | 1730-005 |  | 2021-04-28
DB Netz AG | 1730-006 | Hamburg - Magdeburg | > | Winsen (Luhe) | Winsen (Luhe) | 2023 | 2023 | 32 | 32 | 2023-08-11 | 23:00 | 2023-08-13 | 5:00 | 1d, 6h | Periodical | Track & Rail |  | ST | [9 empty] | 80 | N | 1730-006 |  | 2021-04-28
DB Netz AG | 1730-007 | Hamburg - Magdeburg | < | Winsen (Luhe) | Winsen (Luhe) | 2023 | 2023 | 32 | 32 | 2023-08-11 | 23:00 | 2023-08-13 | 5:00 | 1d, 6h | Periodical | Track & Rail |  |  | S | [8 empty] | 80 | N | 1730-007 |  | 2021-04-28
DB Netz AG | 18A2-001 | Bremerhaven - Bremen | <> | Bremen-Burg | Bremen-Burg | 2023 | 2023 | 35 | 35 | 2023-08-31 | 23:00 | 2023-09-01 | 5:00 | 0d, 6h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 18A2-001 |  | 2021-05-18
DB Netz AG | 1969-001 | Rostock - Berlin | <> | Laage (Meckl) | Kavelstorf | 2023 | 2023 | 30 | 31 | 2023-07-30 | 0:00 | 2023-07-31 | 5:00 | 1d, 5h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | 1969-001 |  | 2022-04-26
DB Netz AG | 1985-001 | Berlin - Dresden | > | Dre-Neustadt | Radebeul Ost | 2023 | 2023 | 35 | 35 | 2023-08-28 | 20:30 | 2023-08-29 | 4:30 | 0d, 8h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1985-001 |  | 2021-04-07
DB Netz AG | 1985-002 | Dresden - Děčín | > | Dre-Neustadt | Dre-Neustadt | 2023 | 2023 | 35 | 35 | 2023-08-28 | 20:30 | 2023-08-29 | 4:30 | 0d, 8h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1985-002 |  | 2021-04-07
DB Netz AG | 1985-003 | Berlin - Dresden | > | Dre-Neustadt | Radebeul Ost | 2023 | 2023 | 35 | 35 | 2023-08-28 | 20:30 | 2023-08-29 | 4:30 | 0d, 8h | Continuous | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | 1985-003 |  | 2021-04-07
DB Netz AG | 1985-004 | Berlin - Dresden | < | Radebeul Ost | Dre-Neustadt | 2023 | 2023 | 35 | 35 | 2023-08-29 | 20:30 | 2023-08-30 | 4:30 | 0d, 8h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1985-004 |  | 2021-04-07
DB Netz AG | 1985-005 | Dresden - Děčín | < | Dre-Neustadt | Dre-Neustadt | 2023 | 2023 | 35 | 35 | 2023-08-29 | 20:30 | 2023-08-30 | 4:30 | 0d, 8h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1985-005 |  | 2021-04-07
DB Netz AG | 1985-006 | Dresden - Děčín | < | Radebeul Ost | Dre-Neustadt | 2023 | 2023 | 35 | 35 | 2023-08-29 | 20:30 | 2023-08-30 | 4:30 | 0d, 8h | Continuous | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | 1985-006 |  | 2021-04-07
DB Netz AG | 1989-001 | Berlin - Dresden | > | Radebeul Ost | Radebeul Nord | 2023 | 2023 | 35 | 35 | 2023-08-30 | 21:00 | 2023-09-01 | 4:00 | 1d, 7h | Periodical | Track & Rail |  | LT | [9 empty] | 80 | N | 1989-001 |  | 2021-04-07
DB Netz AG | 1989-002 | Berlin - Dresden | > | Radebeul Ost | Radebeul Nord | 2023 | 2023 | 35 | 35 | 2023-08-30 | 21:00 | 2023-09-01 | 4:00 | 1d, 7h | Periodical | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | 1989-002 |  | 2021-04-07
DB Netz AG | 1989-003 | Falkenberg - Dresden | <> | Radebeul Ost | Coswig (bei Dre) | 2023 | 2023 | 35 | 35 | 2023-08-30 | 21:00 | 2023-09-01 | 4:00 | 1d, 7h | Periodical | Track & Rail |  |  |  | P | [7 empty] | 80 | N | 1989-003 |  | 2021-04-07
DB Netz AG | 1989-004 | Falkenberg - Dresden | > | Radebeul Nord | Coswig (bei Dre) | 2023 | 2023 | 35 | 35 | 2023-08-31 | 22:00 | 2023-09-01 | 4:00 | 0d, 6h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1989-004 |  | 2021-04-07
DB Netz AG | 1989-005 | Falkenberg - Dresden | > | Radebeul Nord | Coswig (bei Dre) | 2023 | 2023 | 35 | 35 | 2023-08-31 | 22:00 | 2023-09-01 | 4:00 | 0d, 6h | Continuous | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | 1989-005 |  | 2021-04-07
DB Netz AG | 1989-006 | Falkenberg - Dresden | < | Coswig (bei Dre) | Radebeul Ost | 2023 | 2023 | 35 | 36 | 2023-09-02 | 21:00 | 2023-09-04 | 4:00 | 1d, 7h | Periodical | Track & Rail |  | LT | [9 empty] | 80 | N | 1989-006 |  | 2021-04-07
DB Netz AG | 1989-007 | Falkenberg - Dresden | < | Coswig (bei Dre) | Radebeul Ost | 2023 | 2023 | 35 | 36 | 2023-09-02 | 21:00 | 2023-09-04 | 4:00 | 1d, 7h | Periodical | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | 1989-007 |  | 2021-04-07
DB Netz AG | 1989-008 | Falkenberg - Dresden | <> | Radebeul Ost | Coswig (bei Dre) | 2023 | 2023 | 35 | 36 | 2023-09-02 | 21:00 | 2023-09-04 | 4:00 | 1d, 7h | Periodical | Track & Rail |  |  |  | P | [7 empty] | 80 | N | 1989-008 |  | 2021-04-07
DB Netz AG | 1989-009 | Berlin - Dresden | < | Radebeul Ost | Dre-Neustadt | 2023 | 2023 | 35 | 35 | 2023-09-02 | 21:00 | 2023-09-02 | 23:00 | 0d, 2h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1989-009 |  | 2021-04-07
DB Netz AG | 1989-010 | Berlin - Dresden | < | Radebeul Ost | Dre-Neustadt | 2023 | 2023 | 35 | 35 | 2023-09-02 | 21:00 | 2023-09-02 | 23:00 | 0d, 2h | Continuous | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | 1989-010 |  | 2021-04-07
DB Netz AG | 1989-011 | Falkenberg - Dresden | < | Coswig (bei Dre) | Radebeul Nord | 2023 | 2023 | 35 | 36 | 2023-09-03 | 21:00 | 2023-09-04 | 4:00 | 0d, 7h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1989-011 |  | 2021-04-07
DB Netz AG | 1989-012 | Falkenberg - Dresden | < | Coswig (bei Dre) | Radebeul Nord | 2023 | 2023 | 35 | 36 | 2023-09-03 | 21:00 | 2023-09-04 | 4:00 | 0d, 7h | Continuous | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | 1989-012 |  | 2021-04-07
DB Netz AG | 1989-013 | Falkenberg - Dresden | < | Coswig (bei Dre) | Coswig (bei Dre) | 2023 | 2023 | 36 | 36 | 2023-09-04 | 2:00 | 2023-09-04 | 4:00 | 0d, 2h | Continuous | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | 1989-013 |  | 2021-04-07
DB Netz AG | 19.9 | Falkenberg - Dresden | <> | Coswig Stw 1 | Radebeul Nord | 2023 | 2023 | 35 | 35 | 2023-09-01 | 21:00 | 2023-09-01 | 23:00 | 0d, 2h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 19.9 |  | 2021-04-07
DB Netz AG | 1.99 | Falkenberg - Dresden | <> | Coswig Stw 1 | Coswig (bei Dre) | 2023 | 2023 | 35 | 35 | 2023-09-01 | 21:00 | 2023-09-01 | 23:00 | 0d, 2h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1.99 |  | 2021-04-07
DB Netz AG | 0.199 | Falkenberg - Dresden | <> | Coswig Stw 1 | Radebeul Nord | 2023 | 2023 | 35 | 35 | 2023-09-01 | 21:00 | 2023-09-01 | 23:00 | 0d, 2h | Continuous | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | 0.199 |  | 2021-04-07
DB Netz AG | 0.0199 | Falkenberg - Dresden | <> | Coswig (bei Dre) | Radebeul Nord | 2023 | 2023 | 35 | 35 | 2023-09-01 | 23:00 | 2023-09-02 | 1:30 | 0d, 2h | Continuous | Track & Rail | T | [10 empty] | 80 | N | 0.0199 |  | 2021-04-07
DB Netz AG | 0.00199 | Falkenberg - Dresden | <> | Coswig (bei Dre) | Radebeul Nord | 2023 | 2023 | 35 | 35 | 2023-09-01 | 23:00 | 2023-09-02 | 1:30 | 0d, 2h | Continuous | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | 0.00199 |  | 2021-04-07
DB Netz AG | 0.000199 | Falkenberg - Dresden | > | Radebeul Nord | Radebeul Ost | 2023 | 2023 | 35 | 35 | 2023-09-02 | 0:15 | 2023-09-02 | 1:30 | 0d, 1h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 0.000199 |  | 2021-04-07
DB Netz AG | 1.99e-05 | Berlin - Dresden | > | Az | Radebeul Nord | 2023 | 2023 | 35 | 35 | 2023-09-02 | 0:15 | 2023-09-02 | 1:30 | 0d, 1h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1.99e-05 |  | 2021-04-07
DB Netz AG | 1.99e-06 | Falkenberg - Dresden | < | Weinböhla | Az | 2023 | 2023 | 35 | 35 | 2023-09-02 | 0:15 | 2023-09-02 | 1:30 | 0d, 1h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1.99e-06 |  | 2021-04-07
DB Netz AG | 1.99e-07 | Falkenberg - Dresden | > | Coswig (bei Dre) | Radebeul Nord | 2023 | 2023 | 35 | 35 | 2023-09-02 | 0:15 | 2023-09-02 | 1:30 | 0d, 1h | Continuous | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | 1.99e-07 |  | 2021-04-07
DB Netz AG | 19A0-001 | Falkenberg - Dresden | < | Coswig (bei Dre) | Radeb-Naundf Abz | 2023 | 2023 | 35 | 35 | 2023-09-02 | 2:00 | 2023-09-02 | 4:00 | 0d, 2h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 19A0-001 |  | 2021-04-07
DB Netz AG | 19A0-002 | Falkenberg - Dresden | <> | Coswig (bei Dre) | Radeb-Naundf Abz | 2023 | 2023 | 35 | 35 | 2023-09-02 | 2:00 | 2023-09-02 | 4:00 | 0d, 2h | Continuous | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | 19A0-002 |  | 2021-04-07
DB Netz AG | 19A0-003 | Falkenberg - Dresden | < | Az | Cossebaude | 2023 | 2023 | 35 | 35 | 2023-09-02 | 2:00 | 2023-09-02 | 4:00 | 0d, 2h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 19A0-003 |  | 2021-04-07
DB Netz AG | 19A0-004 | Falkenberg - Dresden | < | Az | Cossebaude | 2023 | 2023 | 35 | 35 | 2023-09-02 | 2:00 | 2023-09-02 | 4:00 | 0d, 2h | Continuous | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | 19A0-004 |  | 2021-04-07
DB Netz AG | 19EE-001 | Hamburg - Magdeburg | <> | Lüneburg Gbf | Lüneburg Gbf | 2023 | 2023 | 36 | 36 | 2023-09-05 | 1:00 | 2023-09-08 | 5:00 | 3d, 4h | Periodical | Signal |  | ST | [9 empty] | 80 | N | 19EE-001 |  | 2021-05-14
DB Netz AG | 1A59-001 | Magdeburg - Falkenberg | < | Niederndodeleben | Mg-Sudenburg | 2023 | 2023 | 36 | 36 | 2023-09-04 | 23:50 | 2023-09-05 | 3:05 | 0d, 3h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1A59-001 |  | 2022-05-19
DB Netz AG | 1A59-002 | Hannover - Magdeburg | <> | Mg-Sudenburg | Mg-Sudenburg | 2023 | 2023 | 36 | 36 | 2023-09-04 | 23:50 | 2023-09-05 | 3:05 | 0d, 3h | Continuous | Maintenance | T | [10 empty] | 80 | N | 1A59-002 |  | 2022-05-19
DB Netz AG | 1A59-003 | Magdeburg - Falkenberg | <> | Mg-Sudenburg | Mg-Sudenburg | 2023 | 2023 | 36 | 36 | 2023-09-04 | 23:50 | 2023-09-05 | 3:05 | 0d, 3h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 1A59-003 |  | 2022-05-19
DB Netz AG | 1A59-004 | Magdeburg - Falkenberg | <> | Niederndodeleben | Mg-Sudenburg | 2023 | 2023 | 36 | 36 | 2023-09-05 | 3:05 | 2023-09-05 | 4:05 | 0d, 1h | Continuous | Maintenance | T | [10 empty] | 80 | N | 1A59-004 |  | 2022-05-19
DB Netz AG | 1A59-005 | Hannover - Magdeburg | <> | Mg-Sudenburg | Mg-Sudenburg | 2023 | 2023 | 36 | 36 | 2023-09-05 | 3:05 | 2023-09-05 | 4:05 | 0d, 1h | Continuous | Maintenance | T | [10 empty] | 80 | N | 1A59-005 |  | 2022-05-19
DB Netz AG | 1A59-006 | Magdeburg - Falkenberg | > | Mg-Sudenburg | Niederndodeleben | 2023 | 2023 | 36 | 36 | 2023-09-05 | 4:05 | 2023-09-05 | 5:30 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1A59-006 |  | 2022-05-19
DB Netz AG | 1A59-007 | Magdeburg - Falkenberg | <> | Mg-Sudenburg | Mg-Sudenburg | 2023 | 2023 | 36 | 36 | 2023-09-05 | 4:05 | 2023-09-05 | 5:30 | 0d, 1h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 1A59-007 |  | 2022-05-19
DB Netz AG | 1A60-001 | Hamburg - Magdeburg | < | Magdeburg Hbf | Magdeburg-Buckau | 2023 | 2023 | 36 | 36 | 2023-09-05 | 5:30 | 2023-09-05 | 8:30 | 0d, 3h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1A60-001 |  | 2022-05-19
DB Netz AG | 1A60-002 | Hannover - Magdeburg | <> | Magdeburg-Buckau | Mg-Sudenburg | 2023 | 2023 | 36 | 36 | 2023-09-05 | 5:30 | 2023-09-05 | 8:30 | 0d, 3h | Continuous | Maintenance | T | [10 empty] | 80 | N | 1A60-002 |  | 2022-05-19
DB Netz AG | 1A60-003 | Hamburg - Magdeburg | <> | Magdeburg-Buckau | Magdeburg Hbf | 2023 | 2023 | 36 | 36 | 2023-09-05 | 5:30 | 2023-09-05 | 8:30 | 0d, 3h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 1A60-003 |  | 2022-05-19
DB Netz AG | 1A94-001 | Magdeburg - Falkenberg | <> | Mg-Sudenburg | Eilsleben (b Mg) | 2023 | 2023 | 35 | 35 | 2023-08-28 | 0:40 | 2023-08-29 | 4:45 | 1d, 4h | Periodical | Maintenance |  |  |  | P | [7 empty] | 80 | N | 1A94-001 |  | 2022-05-19
DB Netz AG | 1A94-002 | Hannover - Magdeburg | < | Marienborn | Eilsleben (b Mg) | 2023 | 2023 | 34 | 35 | 2023-08-27 | 23:35 | 2023-08-29 | 0:40 | 1d, 1h | Periodical | Maintenance |  | LT | [9 empty] | 80 | N | 1A94-002 |  | 2022-05-19
DB Netz AG | 1A94-003 | Magdeburg - Falkenberg | < | Niederndodeleben | Mg-Sudenburg | 2023 | 2023 | 35 | 35 | 2023-08-28 | 4:30 | 2023-08-29 | 4:45 | 1d, 0h | Periodical | Maintenance |  | LT | [9 empty] | 80 | N | 1A94-003 |  | 2022-05-19
DB Netz AG | 1A94-004 | Hannover - Magdeburg | < | Helmstedt | Marienborn | 2023 | 2023 | 34 | 35 | 2023-08-27 | 21:55 | 2023-08-28 | 23:35 | 1d, 1h | Periodical | Maintenance |  | LT | [9 empty] | 80 | N | 1A94-004 |  | 2022-05-19
DB Netz AG | 1A94-005 | Magdeburg - Falkenberg | < | Dreileben-Drack | Niederndodeleben | 2023 | 2023 | 35 | 35 | 2023-08-28 | 2:50 | 2023-08-29 | 3:00 | 1d, 0h | Periodical | Maintenance |  | LT | [9 empty] | 80 | N | 1A94-005 |  | 2022-05-19
DB Netz AG | 1A94-006 | Magdeburg - Falkenberg | < | Eilsleb(b Mg)Gbf | Wellen | 2023 | 2023 | 35 | 35 | 2023-08-28 | 2:00 | 2023-08-29 | 2:50 | 1d, 0h | Periodical | Maintenance |  | LT | [9 empty] | 80 | N | 1A94-006 |  | 2022-05-19
DB Netz AG | 1A94-007 | Hannover - Magdeburg | < | Eilsleben (b Mg) | Dreileben-Drack | 2023 | 2023 | 35 | 35 | 2023-08-28 | 0:40 | 2023-08-29 | 2:00 | 1d, 1h | Periodical | Maintenance |  | LT | [9 empty] | 80 | N | 1A94-007 |  | 2022-05-19
DB Netz AG | 1A94-008 | Magdeburg - Falkenberg | < | Eilsleben (b Mg) | Eilsleben (b Mg) | 2023 | 2023 | 35 | 35 | 2023-08-28 | 0:40 | 2023-08-29 | 2:00 | 1d, 1h | Periodical | Maintenance |  | ST | [9 empty] | 80 | N | 1A94-008 |  | 2022-05-19
DB Netz AG | 1A94-009 | Magdeburg - Falkenberg | < | Wellen | Mg-Sudenburg | 2023 | 2023 | 35 | 35 | 2023-08-28 | 3:00 | 2023-08-29 | 4:30 | 1d, 1h | Periodical | Maintenance |  | LT | [9 empty] | 80 | N | 1A94-009 |  | 2022-05-19
DB Netz AG | 1A94-010 | Hannover - Magdeburg | < | Wefensleben | Wefensleben | 2023 | 2023 | 34 | 35 | 2023-08-27 | 23:35 | 2023-08-29 | 0:40 | 1d, 1h | Periodical | Maintenance |  | ST | [9 empty] | 80 | N | 1A94-010 |  | 2022-05-19
DB Netz AG | 1A94-011 | Hannover - Magdeburg | < | Eilsleben (b Mg) | Eilsleben (b Mg) | 2023 | 2023 | 34 | 35 | 2023-08-27 | 23:35 | 2023-08-29 | 0:40 | 1d, 1h | Periodical | Maintenance |  | ST | [9 empty] | 80 | N | 1A94-011 |  | 2022-05-19
DB Netz AG | 1A94-012 | Hannover - Magdeburg | < | Marienborn | Marienborn | 2023 | 2023 | 34 | 35 | 2023-08-27 | 23:35 | 2023-08-29 | 0:40 | 1d, 1h | Periodical | Maintenance |  | ST | [9 empty] | 80 | N | 1A94-012 |  | 2022-05-19
DB Netz AG | 1A94-013 | Magdeburg - Falkenberg | <> | Eilsleb(b Mg)Gbf | Helmstedt | 2023 | 2023 | 34 | 35 | 2023-08-27 | 21:55 | 2023-08-29 | 0:40 | 1d, 2h | Periodical | Maintenance |  |  |  | P | [7 empty] | 80 | N | 1A94-013 |  | 2022-05-19
DB Netz AG | 1AC5-019 | Bremen - Hannover | <> | Seelze Ost | Seelze Ost | 2023 | 2023 | 28 | 28 | 2023-07-11 | 8:00 | 2023-07-13 | 16:00 | 2d, 8h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1AC5-019 |  | 2021-05-03
DB Netz AG | 1AC5-020 | Bremen - Hannover | <> | Seelze Ost | Seelze Ost | 2023 | 2023 | 29 | 31 | 2023-07-17 | 7:00 | 2023-08-01 | 13:00 | 15d, 6h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1AC5-020 |  | 2021-05-03
DB Netz AG | 1AC5-021 | Bremen - Hannover | <> | Seelze Ost | Seelze Ost | 2023 | 2023 | 29 | 31 | 2023-07-17 | 7:00 | 2023-08-01 | 13:00 | 15d, 6h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1AC5-021 |  | 2021-05-03
DB Netz AG | 1AC5-023 | Bremen - Hannover | <> | Seelze Ost | Seelze Ost | 2023 | 2023 | 29 | 29 | 2023-07-18 | 7:00 | 2023-07-20 | 15:00 | 2d, 8h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1AC5-023 |  | 2021-05-03
DB Netz AG | 1AC5-024 | Bremen - Hannover | <> | Seelze West | Seelze Ost | 2023 | 2023 | 30 | 30 | 2023-07-25 | 8:00 | 2023-07-27 | 16:00 | 2d, 8h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1AC5-024 |  | 2021-05-03
DB Netz AG | 1AC5-026 | Bremen - Hannover | > | Kurve | Seelze Ost | 2023 | 2023 | 32 | 33 | 2023-08-07 | 7:00 | 2023-08-14 | 13:00 | 7d, 6h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | 1AC5-026 |  | 2021-05-03
DB Netz AG | 1AC5-027 | Bremen - Hannover | <> | Seelze Ost | Seelze Ost | 2023 | 2023 | 32 | 33 | 2023-08-07 | 7:00 | 2023-08-14 | 13:00 | 7d, 6h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1AC5-027 |  | 2021-05-03
DB Netz AG | 1AC5-028 | Bremen - Hannover | <> | Seelze Ost | Seelze Ost | 2023 | 2023 | 32 | 32 | 2023-08-08 | 8:00 | 2023-08-10 | 16:00 | 2d, 8h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1AC5-028 |  | 2021-05-03
DB Netz AG | 1AC5-029 | Bremen - Hannover | < | Han-Linden Hafen | Seelze West | 2023 | 2023 | 34 | 34 | 2023-08-21 | 7:00 | 2023-08-21 | 9:00 | 0d, 2h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 1AC5-029 |  | 2021-05-03
DB Netz AG | 1AC5-030 | Bremen - Hannover | <> | Seelze Ost | Seelze Ost | 2023 | 2023 | 35 | 35 | 2023-08-28 | 7:00 | 2023-08-28 | 13:00 | 0d, 6h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 1AC5-030 |  | 2021-05-03
DB Netz AG | 1AC5-031 | Bremen - Hannover | <> | Seelze Ost | Seelze Ost | 2023 | 2023 | 36 | 40 | 2023-09-04 | 7:00 | 2023-10-02 | 15:00 | 28d, 8h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1AC5-031 |  | 2021-05-03
DB Netz AG | 1B36-001 | Magdeburg - Falkenberg | <> | Dreileben-Drack | Dreileben-Drack | 2023 | 2023 | 36 | 36 | 2023-09-07 | 20:35 | 2023-09-07 | 20:50 | 0d, 0h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 1B36-001 |  | 2022-05-19
DB Netz AG | 1B36-002 | Magdeburg - Falkenberg | < | Eilsleb(b Mg)Gbf | Wellen | 2023 | 2023 | 36 | 36 | 2023-09-07 | 20:50 | 2023-09-07 | 23:50 | 0d, 3h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1B36-002 |  | 2022-05-19
DB Netz AG | 1B36-003 | Magdeburg - Falkenberg | <> | Dreileben-Drack | Dreileben-Drack | 2023 | 2023 | 36 | 36 | 2023-09-07 | 20:50 | 2023-09-07 | 23:50 | 0d, 3h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 1B36-003 |  | 2022-05-19
DB Netz AG | 1B36-005 | Magdeburg - Falkenberg | <> | Dreileben-Drack | Dreileben-Drack | 2023 | 2023 | 36 | 36 | 2023-09-07 | 23:50 | 2023-09-08 | 0:50 | 0d, 1h | Continuous | Maintenance | T | [10 empty] | 80 | N | 1B36-005 |  | 2022-05-19
DB Netz AG | 1B36-006 | Magdeburg - Falkenberg | <> | Dreileben-Drack | Eilsleb(b Mg)Gbf | 2023 | 2023 | 36 | 36 | 2023-09-08 | 2:20 | 2023-09-08 | 3:55 | 0d, 1h | Continuous | Maintenance | T | [10 empty] | 80 | N | 1B36-006 |  | 2022-05-19
DB Netz AG | 1B36-007 | Magdeburg - Falkenberg | > | Dreileben-Drack | Eilsleb(b Mg)Gbf | 2023 | 2023 | 36 | 36 | 2023-09-08 | 0:50 | 2023-09-08 | 2:20 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1B36-007 |  | 2022-05-19
DB Netz AG | 1B36-008 | Magdeburg - Falkenberg | <> | Dreileben-Drack | Dreileben-Drack | 2023 | 2023 | 36 | 36 | 2023-09-08 | 0:50 | 2023-09-08 | 2:20 | 0d, 1h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 1B36-008 |  | 2022-05-19
DB Netz AG | 1B41-001 | Hamburg - Magdeburg | <> | Uelzen Gbf | Uelzen Gbf | 2023 | 2023 | 31 | 32 | 2023-08-06 | 6:00 | 2023-08-08 | 5:00 | 1d, 23h | Continuous | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 1B41-001 |  | 2021-11-19
DB Netz AG | 1B41-002 | Hamburg - Magdeburg | <> | Uelzen Gbf | Uelzen | 2023 | 2023 | 31 | 32 | 2023-08-06 | 6:00 | 2023-08-08 | 5:00 | 1d, 23h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 1B41-002 |  | 2022-05-03
DB Netz AG | 1B41-003 | Hamburg - Magdeburg | <> | Uelzen Gbf | Uelzen Gbf | 2023 | 2023 | 31 | 32 | 2023-08-06 | 6:00 | 2023-08-08 | 5:00 | 1d, 23h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 1B41-003 |  | 2022-05-03
DB Netz AG | 1B7F-001 | Magdeburg - Falkenberg | <> | Eilsleb(b Mg)Gbf | Eilsleb(b Mg)Gbf | 2023 | 2023 | 35 | 35 | 2023-09-03 | 19:50 | 2023-09-03 | 20:05 | 0d, 0h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 1B7F-001 |  | 2022-05-19
DB Netz AG | 1B7F-002 | Magdeburg - Falkenberg | > | Dreileben-Drack | Eilsleben (b Mg) | 2023 | 2023 | 35 | 35 | 2023-09-03 | 20:05 | 2023-09-03 | 22:00 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1B7F-002 |  | 2022-05-19
DB Netz AG | 1B7F-003 | Magdeburg - Falkenberg | <> | Eilsleb(b Mg)Gbf | Eilsleb(b Mg)Gbf | 2023 | 2023 | 35 | 35 | 2023-09-03 | 20:05 | 2023-09-03 | 22:00 | 0d, 1h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 1B7F-003 |  | 2022-05-19
DB Netz AG | 1B7F-005 | Magdeburg - Falkenberg | <> | Dreileben-Drack | Eilsleb(b Mg)Gbf | 2023 | 2023 | 35 | 35 | 2023-09-03 | 22:00 | 2023-09-03 | 23:30 | 0d, 1h | Continuous | Maintenance | T | [10 empty] | 80 | N | 1B7F-005 |  | 2022-05-19
DB Netz AG | 1B7F-006 | Magdeburg - Falkenberg | < | Eilsleb(b Mg)Gbf | Dreileben-Drack | 2023 | 2023 | 35 | 36 | 2023-09-03 | 23:30 | 2023-09-04 | 1:00 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1B7F-006 |  | 2022-05-19
DB Netz AG | 1B7F-007 | Magdeburg - Falkenberg | < | Eilsleben (b Mg) | Eilsleb(b Mg)Gbf | 2023 | 2023 | 35 | 36 | 2023-09-03 | 23:30 | 2023-09-04 | 1:00 | 0d, 1h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 1B7F-007 |  | 2022-05-19
DB Netz AG | 1B7F-008 | Magdeburg - Falkenberg | <> | Eilsleb(b Mg)Gbf | Eilsleb(b Mg)Gbf | 2023 | 2023 | 35 | 36 | 2023-09-03 | 23:30 | 2023-09-04 | 1:00 | 0d, 1h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 1B7F-008 |  | 2022-05-19
DB Netz AG | 1B7F-010 | Hannover - Magdeburg | < | Wefensleben | Eilsleben (b Mg) | 2023 | 2023 | 36 | 36 | 2023-09-04 | 1:00 | 2023-09-04 | 3:30 | 0d, 2h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1B7F-010 |  | 2022-05-19
DB Netz AG | 1B7F-011 | Magdeburg - Falkenberg | < | Eilsleben (b Mg) | Eilsleben (b Mg) | 2023 | 2023 | 36 | 36 | 2023-09-04 | 1:00 | 2023-09-04 | 3:30 | 0d, 2h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 1B7F-011 |  | 2022-05-19
DB Netz AG | 1B7F-012 | Hannover - Magdeburg | <> | Eilsleben (b Mg) | Eilsleben (b Mg) | 2023 | 2023 | 36 | 36 | 2023-09-04 | 1:00 | 2023-09-04 | 3:30 | 0d, 2h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 1B7F-012 |  | 2022-05-19
DB Netz AG | 1B8C-001 | Magdeburg - Falkenberg | <> | Eilsleb(b Mg)Gbf | Eilsleb(b Mg)Gbf | 2023 | 2023 | 35 | 35 | 2023-09-02 | 19:50 | 2023-09-02 | 20:05 | 0d, 0h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 1B8C-001 |  | 2022-05-19
DB Netz AG | 1B8C-002 | Magdeburg - Falkenberg | > | Eilsleb(b Mg)Gbf | Wefensleben | 2023 | 2023 | 35 | 35 | 2023-09-02 | 20:05 | 2023-09-02 | 23:15 | 0d, 3h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1B8C-002 |  | 2022-05-19
DB Netz AG | 1B8C-003 | Magdeburg - Falkenberg | > | Eilsleb(b Mg)Gbf | Eilsleben (b Mg) | 2023 | 2023 | 35 | 35 | 2023-09-02 | 20:05 | 2023-09-02 | 23:15 | 0d, 3h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 1B8C-003 |  | 2022-05-19
DB Netz AG | 1B8C-004 | Magdeburg - Falkenberg | <> | Eilsleben (b Mg) | Eilsleben (b Mg) | 2023 | 2023 | 35 | 35 | 2023-09-02 | 20:05 | 2023-09-02 | 23:15 | 0d, 3h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 1B8C-004 |  | 2022-05-19
DB Netz AG | 1B8C-005 | Magdeburg - Falkenberg | <> | Eilsleben (b Mg) | Eilsleben (b Mg) | 2023 | 2023 | 35 | 35 | 2023-09-03 | 0:45 | 2023-09-03 | 3:00 | 0d, 2h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 1B8C-005 |  | 2022-05-19
DB Netz AG | 1B8C-007 | Hannover - Magdeburg | <> | Eilsleben (b Mg) | Wefensleben | 2023 | 2023 | 35 | 35 | 2023-09-02 | 23:15 | 2023-09-03 | 0:45 | 0d, 1h | Continuous | Maintenance | T | [10 empty] | 80 | N | 1B8C-007 |  | 2022-05-19
DB Netz AG | 1B8C-008 | Hannover - Magdeburg | < | Wefensleben | Eilsleben (b Mg) | 2023 | 2023 | 35 | 35 | 2023-09-03 | 0:45 | 2023-09-03 | 3:00 | 0d, 2h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1B8C-008 |  | 2022-05-19
DB Netz AG | 1B8C-009 | Magdeburg - Falkenberg | < | Eilsleben (b Mg) | Eilsleben (b Mg) | 2023 | 2023 | 35 | 35 | 2023-09-03 | 0:45 | 2023-09-03 | 3:00 | 0d, 2h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 1B8C-009 |  | 2022-05-19
DB Netz AG | 1D8C-001 | Bremen - Hannover | > | Wunstorf | Seelze West | 2023 | 2023 | 33 | 36 | 2023-08-20 | 7:00 | 2023-09-10 | 15:00 | 21d, 8h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 1D8C-001 |  | 2022-07-19
DB Netz AG | 1D8C-002 | Bremen - Hannover | > | Seelze West | Ahlem | 2023 | 2023 | 33 | 36 | 2023-08-20 | 7:00 | 2023-09-10 | 15:00 | 21d, 8h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 1D8C-002 |  | 2022-07-19
DB Netz AG | 1D8C-003 | Bremen - Hannover | > | Wunstorf | Gümmerwald | 2023 | 2023 | 33 | 36 | 2023-08-20 | 7:00 | 2023-09-10 | 15:00 | 21d, 8h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 1D8C-003 |  | 2022-07-19
DB Netz AG | 1D8C-004 | Bremen - Hannover | <> | Seelze West | Seelze West | 2023 | 2023 | 33 | 36 | 2023-08-20 | 7:00 | 2023-09-10 | 15:00 | 21d, 8h | Periodical | Catenary |  |  |  | P | [7 empty] | 80 | N | 1D8C-004 |  | 2022-07-19
DB Netz AG | 1DD4-001 | Bremerhaven - Bremen | < | Brh-Lehe Pbf | Bremerhaven Hbf | 2023 | 2023 | 28 | 28 | 2023-07-10 | 22:30 | 2023-07-13 | 4:30 | 2d, 6h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 1DD4-001 |  | 2021-04-27
DB Netz AG | 1DF3-001 | Bremerhaven - Bremen | <> | Bremen-Burg | Bremen-Vegesack | 2023 | 2023 | 31 | 33 | 2023-08-04 | 1:00 | 2023-08-14 | 1:00 | 10d, 0h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | 1DF3-001 |  | 2021-05-18
DB Netz AG | 1E21-001 | Hannover - Magdeburg | <> | Braunschweig Hbf | Brg-Gliesmarode | 2023 | 2023 | 32 | 32 | 2023-08-09 | 21:10 | 2023-08-10 | 5:00 | 0d, 7h | Continuous | Track & Rail | T | [10 empty] | 80 | N | 1E21-001 |  | 2021-05-21
DB Netz AG | 1E21-002 | Hannover - Magdeburg | <> | Braunschweig Hbf | Braunschweig Hbf | 2023 | 2023 | 32 | 32 | 2023-08-09 | 21:10 | 2023-08-09 | 23:10 | 0d, 2h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1E21-002 |  | 2021-05-21
DB Netz AG | 1E2A-001 | Bremerhaven - Bremen | < | Bremen-Vegesack | Bremen-Burg | 2023 | 2023 | 31 | 33 | 2023-08-04 | 1:00 | 2023-08-14 | 1:00 | 10d, 0h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 1E2A-001 |  | 2021-11-29
DB Netz AG | 1E2A-002 | Bremerhaven - Bremen | <> | Bremen-Vegesack | Bremen-Burg | 2023 | 2023 | 31 | 33 | 2023-08-05 | 0:00 | 2023-08-14 | 4:30 | 9d, 4h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | 1E2A-002 |  | 2021-05-18
DB Netz AG | 1EA0-001 | Hamburg - Magdeburg | < | Hmb-Harburg | Meckelfeld | 2023 | 2023 | 36 | 36 | 2023-09-04 | 22:00 | 2023-09-06 | 2:00 | 1d, 4h | Periodical | Track & Rail |  | LT | [9 empty] | 80 | N | 1EA0-001 |  | 2021-10-06
DB Netz AG | 1EA0-002 | Hamburg - Magdeburg | < | Hmb-Harb Bbf Süd | Meckelfeld | 2023 | 2023 | 36 | 36 | 2023-09-05 | 2:00 | 2023-09-06 | 6:00 | 1d, 4h | Periodical | Track & Rail |  | LT | [9 empty] | 80 | N | 1EA0-002 |  | 2021-10-06
DB Netz AG | 1F20-002 | Hamburg - Magdeburg | > | Hmb-Harburg | Hmb-Hausbruch | 2023 | 2023 | 28 | 28 | 2023-07-15 | 22:00 | 2023-07-16 | 5:00 | 0d, 7h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 1F20-002 |  | 2021-06-16
DB Netz AG | 1F20-003 | Hamburg - Magdeburg | < | Hmb-Hausbruch | Hmb Unterelbe | 2023 | 2023 | 28 | 29 | 2023-07-16 | 22:00 | 2023-07-17 | 5:00 | 0d, 7h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 1F20-003 |  | 2021-06-16
DB Netz AG | 1F3D-001 | Bremerhaven - Bremen | > | Dörverden | Verden (Aller) | 2023 | 2023 | 35 | 35 | 2023-08-28 | 23:00 | 2023-08-30 | 5:00 | 1d, 6h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 1F3D-001 |  | 2021-04-06
DB Netz AG | 1F98-005 | Hamburg - Magdeburg | < | Hmb-Roth Ro | Hmb-Wlb Abzw | 2023 | 2023 | 36 | 36 | 2023-09-09 | 23:00 | 2023-09-10 | 5:00 | 0d, 6h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 1F98-005 |  | 2021-04-28
DB Netz AG | 1F98-007 | Hamburg - Magdeburg | > | Hmb-Wlb Abzw | Hamburg Hbf | 2023 | 2023 | 36 | 36 | 2023-09-09 | 23:00 | 2023-09-10 | 5:00 | 0d, 6h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 1F98-007 |  | 2021-10-11
DB Netz AG | 2007-001 | Hannover - Magdeburg | <> | Braunschweig Rbf | Braunschweig Hbf | 2023 | 2023 | 29 | 29 | 2023-07-23 | 7:00 | 2023-07-23 | 14:00 | 0d, 7h | Continuous | Switch | T | [10 empty] | 80 | N | 2007-001
DB Netz AG | 2007-002 | Hannover - Magdeburg | <> | Braunschweig Rbf | Braunschweig Hbf | 2023 | 2023 | 30 | 30 | 2023-07-28 | 16:00 | 2023-07-30 | 8:00 | 1d, 16h | Continuous | Switch | T | [10 empty] | 80 | N | 2007-002
DB Netz AG | 2007-003 | Hannover - Magdeburg | <> | Braunschweig Rbf | Schmiedekamp | 2023 | 2023 | 30 | 30 | 2023-07-29 | 16:00 | 2023-07-30 | 8:00 | 0d, 16h | Continuous | Switch | T | [10 empty] | 80 | N | 2007-003
DB Netz AG | 208D-002 | Rostock - Berlin | <> | Ro Seehf Süd | Ro Seehf Süd | 2023 | 2023 | 34 | 37 | 2023-08-26 | 6:00 | 2023-09-13 | 6:00 | 18d, 0h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 208D-002
DB Netz AG | 208D-003 | Rostock - Berlin | <> | Ro Seehf Süd | Ro Seehf Süd | 2023 | 2023 | 35 | 35 | 2023-08-30 | 8:00 | 2023-08-30 | 12:00 | 0d, 4h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 208D-003
DB Netz AG | 208D-004 | Rostock - Berlin | <> | Rostock Seehafen | Ro Seehf Süd | 2023 | 2023 | 35 | 35 | 2023-08-30 | 8:00 | 2023-08-30 | 12:00 | 0d, 4h | Continuous | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 208D-004
DB Netz AG | 208D-005 | Rostock - Berlin | <> | Rostock Seehafen | Ro Seehf Süd | 2023 | 2023 | 35 | 35 | 2023-08-30 | 12:00 | 2023-08-30 | 16:00 | 0d, 4h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 208D-005
DB Netz AG | 208D-006 | Rostock - Berlin | <> | Rostock Seehafen | Ro Seehf Süd | 2023 | 2023 | 35 | 35 | 2023-08-30 | 12:00 | 2023-08-30 | 16:00 | 0d, 4h | Continuous | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 208D-006
DB Netz AG | 208D-007 | Rostock - Berlin | <> | Rostock Seehafen | Ro Seehf Süd | 2023 | 2023 | 35 | 35 | 2023-08-30 | 12:00 | 2023-08-30 | 16:00 | 0d, 4h | Continuous | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 208D-007
DB Netz AG | 208D-008 | Rostock - Berlin | <> | Ro Seehf Süd | Riekdahl | 2023 | 2023 | 35 | 36 | 2023-08-31 | 8:00 | 2023-09-06 | 18:00 | 6d, 10h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | 208D-008
DB Netz AG | 208D-009 | Rostock - Berlin | <> | Ro Seehf Süd | Ro Seehf Süd | 2023 | 2023 | 35 | 36 | 2023-08-31 | 8:00 | 2023-09-06 | 18:00 | 6d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 208D-009
DB Netz AG | 208D-010 | Rostock - Berlin | <> | Rostock Seehafen | Ro Seehf Süd | 2023 | 2023 | 35 | 35 | 2023-08-30 | 8:00 | 2023-08-30 | 12:00 | 0d, 4h | Continuous | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 208D-010
DB Netz AG | 208D-011 | Rostock - Berlin | <> | Ro Seehf Süd | Ro Seehf Süd | 2023 | 2023 | 36 | 36 | 2023-09-07 | 8:00 | 2023-09-09 | 18:00 | 2d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 208D-011
DB Netz AG | 208D-012 | Rostock - Berlin | <> | Ro Seehf Süd | Ro Seehf Süd | 2023 | 2023 | 36 | 36 | 2023-09-07 | 8:00 | 2023-09-09 | 18:00 | 2d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 208D-012
DB Netz AG | 208D-013 | Rostock - Berlin | <> | Riekdahl | Ro Seehf Süd | 2023 | 2023 | 36 | 36 | 2023-09-07 | 8:01 | 2023-09-09 | 18:00 | 2d, 9h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | 208D-013
DB Netz AG | 2095-001 | Bremerhaven - Bremen | <> | Brm-Sebaldsbrück | Brm-Sebaldsbrück | 2023 | 2023 | 32 | 32 | 2023-08-08 | 8:00 | 2023-08-09 | 15:00 | 1d, 7h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 2095-001 |  | 2021-04-13
DB Netz AG | 2097-001 | Bremen - Hannover | <> | Bremen Hbf | Bremen Hbf | 2023 | 2023 | 33 | 33 | 2023-08-14 | 8:00 | 2023-08-14 | 15:00 | 0d, 7h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 2097-001 |  | 2021-04-06
DB Netz AG | 2097-002 | Bremen - Hannover | <> | Bremen Hbf | Bremen Hbf | 2023 | 2023 | 33 | 33 | 2023-08-14 | 8:00 | 2023-08-14 | 15:00 | 0d, 7h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 2097-002 |  | 2021-04-06
DB Netz AG | 215D-031 | Rostock - Berlin | <> | Birkenwerd b Bln | Hohen Neuend W | 2023 | 2023 | 29 | 29 | 2023-07-18 | 22:00 | 2023-07-19 | 4:00 | 0d, 6h | Continuous | Signal |  |  |  |  | X | [6 empty] | 80 | N | 215D-031 |  | 2021-10-25
DB Netz AG | 2205-001 | Berlin - Dresden | <> | Glasow Damm Süd | Wünsdorf-Waldst | 2023 | 2023 | 36 | 36 | 2023-09-04 | 22:00 | 2023-09-05 | 4:00 | 0d, 6h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 2205-001 |  | 2022-03-23
DB Netz AG | 2205-002 | Berlin - Dresden | > | Glasow Damm Süd | Rangsdorf | 2023 | 2023 | 36 | 36 | 2023-09-04 | 22:00 | 2023-09-04 | 23:00 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 2205-002 |  | 2021-06-04
DB Netz AG | 2205-003 | Berlin - Dresden | > | Glasow Damm Ost | Glasow Damm Süd | 2023 | 2023 | 36 | 36 | 2023-09-04 | 22:00 | 2023-09-04 | 23:00 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 2205-003 |  | 2021-06-04
DB Netz AG | 2205-004 | Berlin - Dresden | <> | Glasow Damm Süd | Glasow Damm West | 2023 | 2023 | 36 | 36 | 2023-09-04 | 22:00 | 2023-09-04 | 23:00 | 0d, 1h | Continuous | Maintenance | T | [10 empty] | 80 | N | 2205-004 |  | 2021-06-04
DB Netz AG | 2205-005 | Berlin - Dresden | > | Rangsdorf | Rangsdorf | 2023 | 2023 | 36 | 36 | 2023-09-04 | 22:00 | 2023-09-04 | 23:00 | 0d, 1h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 2205-005 |  | 2021-06-04
DB Netz AG | 2205-006 | Berlin - Dresden | > | Glasow Damm Süd | Zossen | 2023 | 2023 | 36 | 36 | 2023-09-04 | 23:00 | 2023-09-05 | 2:00 | 0d, 3h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 2205-006 |  | 2021-06-04
DB Netz AG | 2205-007 | Berlin - Dresden | > | Rangsdorf | Zossen | 2023 | 2023 | 36 | 36 | 2023-09-04 | 23:00 | 2023-09-05 | 2:00 | 0d, 3h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 2205-007 |  | 2021-06-04
DB Netz AG | 2205-008 | Berlin - Dresden | > | Zossen | Wünsdorf-Waldst | 2023 | 2023 | 36 | 36 | 2023-09-05 | 2:00 | 2023-09-05 | 4:00 | 0d, 2h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 2205-008 |  | 2022-03-23
DB Netz AG | 215D-033 | Rostock - Berlin | <> | Hohen Neuend Sw | Birkenwerd b Bln | 2023 | 2023 | 29 | 29 | 2023-07-17 | 22:00 | 2023-07-18 | 4:00 | 0d, 6h | Continuous | Signal |  |  |  |  | X | [6 empty] | 80 | N | 215D-033 |  | 2021-10-26
DB Netz AG | 220D-001 | Berlin - Dresden | > | Zossen | Baruth (Mark) | 2023 | 2023 | 36 | 36 | 2023-09-05 | 22:00 | 2023-09-06 | 2:30 | 0d, 4h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 220D-001 |  | 2022-03-23
DB Netz AG | 220D-002 | Berlin - Dresden | <> | Wünsdorf-Waldst | Golßen NL | 2023 | 2023 | 36 | 36 | 2023-09-05 | 22:00 | 2023-09-06 | 4:30 | 0d, 6h | Continuous | Maintenance |  |  | S | [8 empty] | 80 | N | 220D-002 |  | 2021-06-04
DB Netz AG | 220D-003 | Berlin - Dresden | <> | Wünsdorf-Waldst | Golßen NL | 2023 | 2023 | 36 | 36 | 2023-09-05 | 22:00 | 2023-09-06 | 4:30 | 0d, 6h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 220D-003 |  | 2022-03-23
DB Netz AG | 220D-004 | Berlin - Dresden | > | Baruth (Mark) | Golßen NL | 2023 | 2023 | 36 | 36 | 2023-09-06 | 2:30 | 2023-09-06 | 4:30 | 0d, 2h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 220D-004 |  | 2021-06-04
DB Netz AG | 2212-001 | Berlin - Dresden | > | Baruth (Mark) | Golßen NL | 2023 | 2023 | 36 | 36 | 2023-09-06 | 22:00 | 2023-09-06 | 23:59 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 2212-001 |  | 2021-06-04
DB Netz AG | 2212-002 | Berlin - Dresden | <> | Baruth (Mark) | Luckau-Uckro | 2023 | 2023 | 36 | 36 | 2023-09-06 | 22:00 | 2023-09-07 | 4:00 | 0d, 6h | Continuous | Maintenance |  |  | S | [8 empty] | 80 | N | 2212-002 |  | 2021-06-04
DB Netz AG | 2212-003 | Berlin - Dresden | <> | Baruth (Mark) | Luckau-Uckro | 2023 | 2023 | 36 | 36 | 2023-09-06 | 22:00 | 2023-09-07 | 4:00 | 0d, 6h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 2212-003 |  | 2021-06-04
DB Netz AG | 2212-004 | Berlin - Dresden | > | Golßen NL | Luckau-Uckro | 2023 | 2023 | 36 | 36 | 2023-09-06 | 23:59 | 2023-09-07 | 4:00 | 0d, 4h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 2212-004 |  | 2021-06-04
DB Netz AG | 215D-034 | Rostock - Berlin | <> | Hohen Neuend Sw | Birkenwerd b Bln | 2023 | 2023 | 30 | 30 | 2023-07-24 | 22:00 | 2023-07-25 | 4:00 | 0d, 6h | Continuous | Signal |  |  |  |  | X | [6 empty] | 80 | N | 215D-034 |  | 2022-05-16
DB Netz AG | 2213-001 | Berlin - Dresden | > | Walddrehna | Doberlug-K ob Bf | 2023 | 2023 | 36 | 36 | 2023-09-07 | 22:00 | 2023-09-07 | 23:59 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 2213-001 |  | 2021-07-12
DB Netz AG | 2213-002 | Berlin - Dresden | <> | Doberlug-K ob Bf | Doberlug-K untBf | 2023 | 2023 | 36 | 36 | 2023-09-07 | 22:00 | 2023-09-07 | 23:59 | 0d, 1h | Continuous | Maintenance | T | [10 empty] | 80 | N | 2213-002 |  | 2021-07-12
DB Netz AG | 2213-003 | Berlin - Dresden | <> | Walddrehna | Hohenleipisch | 2023 | 2023 | 36 | 36 | 2023-09-07 | 22:00 | 2023-09-08 | 4:00 | 0d, 6h | Continuous | Maintenance |  |  | S | [8 empty] | 80 | N | 2213-003 |  | 2021-07-12
DB Netz AG | 2213-004 | Berlin - Dresden | <> | Walddrehna | Hohenleipisch | 2023 | 2023 | 36 | 36 | 2023-09-07 | 22:00 | 2023-09-08 | 4:00 | 0d, 6h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 2213-004 |  | 2021-07-12
DB Netz AG | 2213-005 | Berlin - Dresden | > | Doberlug-K ob Bf | Hohenleipisch | 2023 | 2023 | 36 | 36 | 2023-09-07 | 23:59 | 2023-09-08 | 4:00 | 0d, 4h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 2213-005 |  | 2021-07-12
DB Netz AG | 2219-001 | Berlin - Dresden | <> | Golßen NL | Brenitz-Sonnew | 2023 | 2023 | 36 | 36 | 2023-09-08 | 22:00 | 2023-09-09 | 5:00 | 0d, 7h | Continuous | Maintenance |  |  | S | [8 empty] | 80 | N | 2219-001 |  | 2021-07-12
DB Netz AG | 2219-002 | Berlin - Dresden | <> | Golßen NL | Brenitz-Sonnew | 2023 | 2023 | 36 | 36 | 2023-09-08 | 22:00 | 2023-09-09 | 5:00 | 0d, 7h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 2219-002 |  | 2021-07-12
DB Netz AG | 2219-003 | Berlin - Dresden | > | Golßen NL | Luckau-Uckro | 2023 | 2023 | 36 | 36 | 2023-09-08 | 22:00 | 2023-09-08 | 23:30 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 2219-003 |  | 2021-07-12
DB Netz AG | 2219-004 | Berlin - Dresden | > | Luckau-Uckro | Walddrehna | 2023 | 2023 | 36 | 36 | 2023-09-08 | 23:30 | 2023-09-09 | 4:00 | 0d, 4h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 2219-004 |  | 2021-07-12
DB Netz AG | 2219-005 | Berlin - Dresden | > | Walddrehna | Brenitz-Sonnew | 2023 | 2023 | 36 | 36 | 2023-09-09 | 3:00 | 2023-09-09 | 5:00 | 0d, 2h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 2219-005 |  | 2021-07-12
DB Netz AG | 1309-009 | Rostock - Berlin | <> | Birkenwerder N | Birkenwerd b Bln | 2023 | 2023 | 36 | 39 | 2023-09-08 | 21:00 | 2023-09-29 | 21:00 | 21d, 0h | Continuous | Signal | T | [10 empty] | 80 | N | 1309-009 |  | 2021-11-15
DB Netz AG | 215D-036 | Rostock - Berlin | <> | Birkenwerder N | Birkenwerd b Bln | 2023 | 2023 | 28 | 28 | 2023-07-12 | 22:00 | 2023-07-13 | 4:00 | 0d, 6h | Continuous | Signal | T | [10 empty] | 80 | N | 215D-036 |  | 2021-11-15
DB Netz AG | 215D-037 | Rostock - Berlin | <> | Birkenwerder N | Birkenwerd b Bln | 2023 | 2023 | 29 | 29 | 2023-07-18 | 22:00 | 2023-07-19 | 4:00 | 0d, 6h | Continuous | Signal | T | [10 empty] | 80 | N | 215D-037 |  | 2021-11-15
DB Netz AG | 215D-038 | Rostock - Berlin | <> | Schönfließ West | Hohen Neuend Sw | 2023 | 2023 | 30 | 30 | 2023-07-25 | 22:00 | 2023-07-26 | 4:00 | 0d, 6h | Continuous | Signal |  | LT | [9 empty] | 80 | N | 215D-038 |  | 2021-11-15
DB Netz AG | A4C-009 | Hannover - Magdeburg | <> | Magdeburg-Buckau | Mg-Sudenburg | 2023 | 2023 | 41 | 41 | 2023-10-10 | 8:00 | 2023-10-11 | 16:00 | 1d, 8h | Periodical | Catenary | T | [10 empty] | 80 | N | A4C-009 |  | 2021-06-01
DB Netz AG | A4C-002 | Hamburg - Magdeburg | < | Magdeburg Hbf | Magdeburg-Buckau | 2023 | 2023 | 41 | 41 | 2023-10-10 | 8:00 | 2023-10-11 | 16:00 | 1d, 8h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | A4C-002 |  | 2021-05-18
DB Netz AG | B30-006 | Wilhelmshaven - Bremen | <> | Weißer Floh | Wilhhv Ölweiche | 2023 | 2023 | 41 | 41 | 2023-10-15 | 1:00 | 2023-10-15 | 5:00 | 0d, 4h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | B30-006 |  | 2021-07-22
DB Netz AG | B30-001 | Wilhelmshaven - Bremen | <> | Weißer Floh | Heidmühle (Oldb) | 2023 | 2023 | 41 | 41 | 2023-10-15 | 1:00 | 2023-10-15 | 5:00 | 0d, 4h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | B30-001 |  | 2021-07-22
DB Netz AG | B30-005 | Wilhelmshaven - Bremen | <> | Oldb (Oldb) Hbf | Wilhelmshaven | 2023 | 2023 | 41 | 41 | 2023-10-15 | 1:00 | 2023-10-15 | 5:00 | 0d, 4h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | B30-005 |  | 2021-07-22
DB Netz AG | B9B-013 | Magdeburg - Falkenberg | <> | Mg-Sudenburg | Helmstedt | 2023 | 2023 | 40 | 40 | 2023-10-08 | 0:00 | 2023-10-08 | 4:00 | 0d, 4h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | B9B-013 |  | 2021-06-08
DB Netz AG | B9B-010 | Magdeburg - Falkenberg | <> | Magdeburg Hbf | Mg Südseite | 2023 | 2023 | 40 | 40 | 2023-10-07 | 10:00 | 2023-10-08 | 4:00 | 0d, 18h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | B9B-010 |  | 2021-06-03
DB Netz AG | B9B-014 | Magdeburg - Falkenberg | <> | Mg-Neustadt | Niederndodeleben | 2023 | 2023 | 40 | 40 | 2023-10-07 | 10:00 | 2023-10-08 | 4:00 | 0d, 18h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | B9B-014 |  | 2021-06-08
DB Netz AG | B9B-006 | Hamburg - Magdeburg | <> | Magdeburg Hbf | Mg-Neustadt | 2023 | 2023 | 40 | 40 | 2023-10-07 | 10:00 | 2023-10-08 | 4:00 | 0d, 18h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | B9B-006 |  | 2021-06-04
DB Netz AG | B9B-003 | Hannover - Magdeburg | <> | Magdeburg Hbf | Calbe (S) Ost | 2023 | 2023 | 40 | 40 | 2023-10-07 | 10:00 | 2023-10-08 | 4:00 | 0d, 18h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | B9B-003 |  | 2021-06-08
DB Netz AG | B9B-007 | Hamburg - Magdeburg | <> | Mg-Neustadt | Schönebeck(Elbe) | 2023 | 2023 | 40 | 40 | 2023-10-07 | 10:00 | 2023-10-08 | 4:00 | 0d, 18h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | B9B-007 |  | 2021-06-03
DB Netz AG | B9B-015 | Hannover - Magdeburg | <> | Magdeburg Hbf | Dodendorf | 2023 | 2023 | 40 | 40 | 2023-10-07 | 10:00 | 2023-10-08 | 4:00 | 0d, 18h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | B9B-015 |  | 2021-06-08
DB Netz AG | B9E-001 | Hamburg - Magdeburg | > | Magdeburg-Buckau | Magdeburg Hbf | 2023 | 2023 | 39 | 39 | 2023-09-27 | 8:00 | 2023-09-29 | 16:00 | 2d, 8h | Periodical | Miscellaneous |  | LT | [9 empty] | 80 | N | B9E-001 |  | 2021-05-17
DB Netz AG | BA8-004 | Hannover - Magdeburg | < | Mg Südseite | Magdeburg Hbf | 2023 | 2023 | 37 | 37 | 2023-09-12 | 8:00 | 2023-09-12 | 16:00 | 0d, 8h | Continuous | Signal |  | ST | [9 empty] | 80 | N | BA8-004 |  | 2021-05-26
DB Netz AG | BA8-001 | Hannover - Magdeburg | < | Magdeburg-Buckau | Magdeburg Hbf | 2023 | 2023 | 37 | 37 | 2023-09-14 | 8:00 | 2023-09-14 | 16:00 | 0d, 8h | Continuous | Signal |  | LT | [9 empty] | 80 | N | BA8-001 |  | 2021-05-26
DB Netz AG | BA8-017 | Hannover - Magdeburg | > | Magdeburg Hbf | Mg Südseite | 2023 | 2023 | 37 | 37 | 2023-09-14 | 8:00 | 2023-09-14 | 16:00 | 0d, 8h | Continuous | Signal |  | ST | [9 empty] | 80 | N | BA8-017 |  | 2021-05-12
DB Netz AG | BA8-010 | Hannover - Magdeburg | <> | Magdeburg Hbf | Mg Südseite | 2023 | 2023 | 37 | 37 | 2023-09-14 | 8:00 | 2023-09-14 | 16:00 | 0d, 8h | Continuous | Signal |  |  |  |  | X | [6 empty] | 80 | N | BA8-010 |  | 2021-05-26
DB Netz AG | BA8-013 | Hannover - Magdeburg | <> | Magdeburg Hbf | Mg Südseite | 2023 | 2023 | 37 | 37 | 2023-09-13 | 8:00 | 2023-09-13 | 16:00 | 0d, 8h | Continuous | Signal |  | ST | [9 empty] | 80 | N | BA8-013 |  | 2021-05-17
DB Netz AG | BA8-009 | Hamburg - Magdeburg | <> | Magdeburg-Buckau | Mg-Sudenburg | 2023 | 2023 | 38 | 38 | 2023-09-22 | 8:00 | 2023-09-22 | 16:00 | 0d, 8h | Continuous | Signal | T | [10 empty] | 80 | N | BA8-009 |  | 2021-05-17
DB Netz AG | BA8-003 | Hamburg - Magdeburg | < | Magdeburg Hbf | Magdeburg-Buckau | 2023 | 2023 | 38 | 38 | 2023-09-22 | 8:00 | 2023-09-22 | 16:00 | 0d, 8h | Continuous | Signal |  | LT | [9 empty] | 80 | N | BA8-003 |  | 2021-05-17
DB Netz AG | BA8-022 | Hamburg - Magdeburg | > | Magdeburg-Buckau | Magdeburg Hbf | 2023 | 2023 | 38 | 38 | 2023-09-21 | 8:00 | 2023-09-21 | 16:00 | 0d, 8h | Continuous | Signal |  | LT | [9 empty] | 80 | N | BA8-022 |  | 2021-05-17
DB Netz AG | BC2-001 | Hannover - Magdeburg | <> | Magdeburg-Buckau | Mg-Sudenburg | 2023 | 2023 | 41 | 41 | 2023-10-12 | 8:00 | 2023-10-12 | 16:00 | 0d, 8h | Continuous | Catenary | T | [10 empty] | 80 | N | BC2-001 |  | 2021-06-02
DB Netz AG | BC2-002 | Hamburg - Magdeburg | < | Magdeburg Hbf | Magdeburg-Buckau | 2023 | 2023 | 41 | 41 | 2023-10-12 | 8:00 | 2023-10-12 | 16:00 | 0d, 8h | Continuous | Catenary |  | LT | [9 empty] | 80 | N | BC2-002 |  | 2021-05-18
DB Netz AG | BD0-021 | Bremerhaven - Bremen | <> | Osterholz-Scharm | Osterholz-Scharm | 2023 | 2023 | 41 | 42 | 2023-10-12 | 23:00 | 2023-10-16 | 5:00 | 3d, 6h | Periodical | Signal |  |  | S | [8 empty] | 80 | N | BD0-021 |  | 2021-05-26
DB Netz AG | BD0-018 | Bremerhaven - Bremen | <> | Oldenbüttel | Bremen-Burg | 2023 | 2023 | 37 | 37 | 2023-09-15 | 23:40 | 2023-09-17 | 5:40 | 1d, 6h | Periodical | Signal | T | [10 empty] | 80 | N | BD0-018 |  | 2021-07-21
DB Netz AG | BD0-014 | Bremerhaven - Bremen | > | Bremen-Burg | Oldenbüttel | 2023 | 2023 | 40 | 41 | 2023-10-02 | 23:00 | 2023-10-12 | 5:00 | 9d, 6h | Periodical | Signal |  | LT | [9 empty] | 80 | N | BD0-014 |  | 2021-05-26
DB Netz AG | BD0-015 | Bremerhaven - Bremen | <> | Osterholz-Scharm | Osterholz-Scharm | 2023 | 2023 | 41 | 42 | 2023-10-12 | 23:00 | 2023-10-16 | 5:00 | 3d, 6h | Periodical | Signal |  | ST | [9 empty] | 80 | N | BD0-015 |  | 2021-05-26
DB Netz AG | BD0-002 | Bremerhaven - Bremen | <> | Osterholz-Scharm | Osterholz-Scharm | 2023 | 2023 | 37 | 40 | 2023-09-14 | 23:00 | 2023-10-02 | 5:00 | 17d, 6h | Periodical | Signal |  |  | S | [8 empty] | 80 | N | BD0-002 |  | 2021-07-21
DB Netz AG | BD0-019 | Bremerhaven - Bremen | < | Oldenbüttel | Bremen-Burg | 2023 | 2023 | 37 | 40 | 2023-09-14 | 23:00 | 2023-10-02 | 5:00 | 17d, 6h | Periodical | Signal |  | LT | [9 empty] | 80 | N | BD0-019 |  | 2021-07-21
DB Netz AG | BD0-022 | Bremerhaven - Bremen | <> | Oldenbüttel | Bremen-Burg | 2023 | 2023 | 38 | 38 | 2023-09-22 | 23:40 | 2023-09-24 | 5:40 | 1d, 6h | Periodical | Signal | T | [10 empty] | 80 | N | BD0-022 |  | 2021-07-21
DB Netz AG | BD0-007 | Bremerhaven - Bremen | <> | Osterholz-Scharm | Osterholz-Scharm | 2023 | 2023 | 40 | 41 | 2023-10-02 | 23:00 | 2023-10-12 | 5:00 | 9d, 6h | Periodical | Signal |  |  | S | [8 empty] | 80 | N | BD0-007 |  | 2021-07-21
DB Netz AG | C24-019 | Bremerhaven - Bremen | < | Brh-Wulsdorf | Stubben | 2023 | 2023 | 38 | 38 | 2023-09-22 | 22:00 | 2023-09-23 | 4:00 | 0d, 6h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | C24-019 |  | 2021-05-25
DB Netz AG | C24-020 | Bremerhaven - Bremen | < | Brh-Wulsdorf | Stubben | 2023 | 2023 | 36 | 37 | 2023-09-10 | 22:00 | 2023-09-11 | 4:00 | 0d, 6h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | C24-020 |  | 2021-05-25
DB Netz AG | C24-021 | Bremerhaven - Bremen | <> | Stubben | Brh-Wulsdorf | 2023 | 2023 | 37 | 37 | 2023-09-16 | 23:00 | 2023-09-17 | 7:00 | 0d, 8h | Continuous | Track & Rail |  |  | S | [8 empty] | 80 | N | C24-021 |  | 2021-07-12
DB Netz AG | C24-040 | Bremerhaven - Bremen | <> | Stubben | Brh-Wulsdorf | 2023 | 2023 | 37 | 37 | 2023-09-15 | 22:00 | 2023-09-16 | 4:00 | 0d, 6h | Continuous | Track & Rail |  |  | S | [8 empty] | 80 | N | C24-040 |  | 2021-07-12
DB Netz AG | C24-055 | Bremerhaven - Bremen | < | Brh-Wulsdorf | Stubben | 2023 | 2023 | 37 | 37 | 2023-09-15 | 22:00 | 2023-09-16 | 4:00 | 0d, 6h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | C24-055 |  | 2021-05-25
DB Netz AG | C24-048 | Bremerhaven - Bremen | <> | Stubben | Brh-Wulsdorf | 2023 | 2023 | 38 | 38 | 2023-09-22 | 22:00 | 2023-09-23 | 4:00 | 0d, 6h | Continuous | Track & Rail |  |  | S | [8 empty] | 80 | N | C24-048 |  | 2021-07-12
DB Netz AG | C24-041 | Bremerhaven - Bremen | <> | Stubben | Brh-Wulsdorf | 2023 | 2023 | 36 | 37 | 2023-09-10 | 22:00 | 2023-09-11 | 4:00 | 0d, 6h | Continuous | Track & Rail |  |  | S | [8 empty] | 80 | N | C24-041 |  | 2021-07-12
DB Netz AG | C24-050 | Bremerhaven - Bremen | <> | Stubben | Brh-Wulsdorf | 2023 | 2023 | 38 | 38 | 2023-09-23 | 22:00 | 2023-09-24 | 6:00 | 0d, 8h | Continuous | Track & Rail |  |  | S | [8 empty] | 80 | N | C24-050 |  | 2021-07-13
DB Netz AG | C24-058 | Bremerhaven - Bremen | < | Brh-Wulsdorf | Stubben | 2023 | 2023 | 37 | 37 | 2023-09-16 | 23:00 | 2023-09-17 | 7:00 | 0d, 8h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | C24-058 |  | 2021-05-25
DB Netz AG | C24-052 | Bremerhaven - Bremen | < | Brh-Wulsdorf | Stubben | 2023 | 2023 | 38 | 38 | 2023-09-23 | 22:00 | 2023-09-24 | 6:00 | 0d, 8h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | C24-052 |  | 2021-05-25
DB Netz AG | C4E-002 | Hamburg - Magdeburg | > | Magdeburg-Buckau | Magdeburg Hbf | 2023 | 2023 | 41 | 41 | 2023-10-09 | 8:00 | 2023-10-09 | 16:00 | 0d, 8h | Continuous | Catenary |  | LT | [9 empty] | 80 | N | C4E-002 |  | 2021-05-18
DB Netz AG | C6F-003 | Dresden - Děčín | <> | Dresden Hbf | Dresden Mitte | 2023 | 2023 | 37 | 37 | 2023-09-15 | 23:00 | 2023-09-17 | 4:00 | 1d, 5h | Periodical | Catenary | T | [10 empty] | 80 | N | C6F-003 |  | 2021-06-03
DB Netz AG | C6F-002 | Dresden - Děčín | <> | Dresden Hbf | Dresden Mitte | 2023 | 2023 | 37 | 37 | 2023-09-15 | 23:00 | 2023-09-17 | 4:00 | 1d, 5h | Periodical | Catenary | T | [10 empty] | 80 | N | C6F-002 |  | 2021-06-03
DB Netz AG | C6F-001 | Dresden - Děčín | <> | Dresden Hbf | Dresden Mitte | 2023 | 2023 | 37 | 37 | 2023-09-15 | 23:00 | 2023-09-17 | 4:00 | 1d, 5h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80 | N | C6F-001 |  | 2021-06-03
DB Netz AG | C6F-005 | Dresden - Děčín | <> | Dre-Friedrichst | Dre Freibg Str | 2023 | 2023 | 37 | 37 | 2023-09-15 | 23:00 | 2023-09-17 | 4:00 | 1d, 5h | Periodical | Catenary | T | [10 empty] | 80 | N | C6F-005 |  | 2021-06-03
DB Netz AG | C6F-006 | Dresden - Děčín | <> | Dre Freibg Str | Dresden-Altstadt | 2023 | 2023 | 37 | 37 | 2023-09-15 | 23:00 | 2023-09-17 | 4:00 | 1d, 5h | Periodical | Catenary | T | [10 empty] | 80 | N | C6F-006 |  | 2021-06-03
DB Netz AG | C6F-004 | Dresden - Děčín | < | Dresden Mitte | Dresden Hbf | 2023 | 2023 | 37 | 37 | 2023-09-15 | 23:00 | 2023-09-17 | 4:00 | 1d, 5h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | C6F-004 |  | 2021-06-03
DB Netz AG | C74-002 | Dresden - Děčín | <> | Königst (Sä) Üst | Obervogelgesang | 2023 | 2023 | 38 | 38 | 2023-09-20 | 23:00 | 2023-09-22 | 5:00 | 1d, 6h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | C74-002 |  | 2021-05-25
DB Netz AG | CB1-002 | Dresden - Děčín | <> | Dresden Hbf | Dresden Mitte | 2023 | 2023 | 37 | 37 | 2023-09-12 | 20:00 | 2023-09-13 | 4:00 | 0d, 8h | Continuous | Catenary | T | [10 empty] | 80 | N | CB1-002 |  | 2021-06-03
DB Netz AG | CB1-001 | Dresden - Děčín | <> | Dre Freibg Str | Dresden-Altstadt | 2023 | 2023 | 37 | 37 | 2023-09-12 | 20:00 | 2023-09-13 | 4:00 | 0d, 8h | Continuous | Catenary | T | [10 empty] | 80 | N | CB1-001 |  | 2021-06-03
DB Netz AG | CB1-003 | Dresden - Děčín | <> | Dre-Friedrichst | Dre Freibg Str | 2023 | 2023 | 37 | 37 | 2023-09-12 | 20:00 | 2023-09-13 | 4:00 | 0d, 8h | Continuous | Catenary | T | [10 empty] | 80 | N | CB1-003 |  | 2021-06-03
DB Netz AG | CB1-004 | Dresden - Děčín | <> | Dresden-Altstadt | Dresden Hbf | 2023 | 2023 | 37 | 37 | 2023-09-12 | 20:00 | 2023-09-13 | 4:00 | 0d, 8h | Continuous | Catenary | T | [10 empty] | 80 | N | CB1-004 |  | 2021-06-03
DB Netz AG | CCC-008 | Hannover - Magdeburg | <> | Braunschweig Rbf | Braunschweig Hbf | 2023 | 2023 | 39 | 39 | 2023-09-25 | 5:00 | 2023-09-25 | 7:00 | 0d, 2h | Continuous | Switch | T | [10 empty] | 80 | N | CCC-008 |  | 2021-06-08
DB Netz AG | CCC-007 | Hannover - Magdeburg | > | Groß Gleidingen | Braunschweig Hbf | 2023 | 2023 | 41 | 41 | 2023-10-09 | 1:45 | 2023-10-09 | 3:45 | 0d, 2h | Continuous | Switch |  | LT | [9 empty] | 80 | N | CCC-007 |  | 2021-06-08
DB Netz AG | CCC-011 | Hannover - Magdeburg | <> | Okerbrücke | Braunschweig Hbf | 2023 | 2023 | 40 | 41 | 2023-10-06 | 22:00 | 2023-10-09 | 5:45 | 2d, 7h | Continuous | Switch | T | [10 empty] | 80 | N | CCC-011 |  | 2021-05-17
DB Netz AG | CCC-013 | Hannover - Magdeburg | <> | Braunschweig Hbf | Braunschweig Hbf | 2023 | 2023 | 41 | 41 | 2023-10-11 | 14:00 | 2023-10-14 | 17:00 | 3d, 3h | Continuous | Switch |  | ST | [9 empty] | 80 | N | CCC-013 |  | 2021-05-17
DB Netz AG | CCC-012 | Hannover - Magdeburg | <> | Braunschweig Hbf | Braunschweig Hbf | 2023 | 2023 | 41 | 41 | 2023-10-11 | 14:00 | 2023-10-14 | 17:00 | 3d, 3h | Continuous | Switch |  | ST | [9 empty] | 80 | N | CCC-012 |  | 2021-06-08
DB Netz AG | CCC-002 | Hannover - Magdeburg | <> | Braunschweig Hbf | Braunschweig Hbf | 2023 | 2023 | 39 | 41 | 2023-09-25 | 7:00 | 2023-10-11 | 17:00 | 16d, 10h | Continuous | Switch |  | ST | [9 empty] | 80 | N | CCC-002 |  | 2021-05-17
DB Netz AG | CCC-005 | Hannover - Magdeburg | < | Buchhorst Abzw | Braunschweig Hbf | 2023 | 2023 | 41 | 41 | 2023-10-11 | 14:00 | 2023-10-13 | 22:00 | 2d, 8h | Continuous | Switch |  | LT | [9 empty] | 80 | N | CCC-005 |  | 2021-06-08
DB Netz AG | CCC-003 | Hannover - Magdeburg | < | Braunschweig Hbf | Gabelung (Brg) | 2023 | 2023 | 41 | 41 | 2023-10-09 | 5:45 | 2023-10-11 | 13:45 | 2d, 8h | Continuous | Switch |  | LT | [9 empty] | 80 | N | CCC-003 |  | 2021-06-08
DB Netz AG | CCC-004 | Hannover - Magdeburg | > | Groß Gleidingen | Braunschweig Hbf | 2023 | 2023 | 40 | 40 | 2023-10-06 | 23:45 | 2023-10-07 | 1:45 | 0d, 2h | Continuous | Switch |  | LT | [9 empty] | 80 | N | CCC-004 |  | 2021-06-08
DB Netz AG | CCC-006 | Hannover - Magdeburg | <> | Braunschweig Rbf | Braunschweig Hbf | 2023 | 2023 | 41 | 41 | 2023-10-09 | 5:45 | 2023-10-09 | 7:45 | 0d, 2h | Continuous | Switch | T | [10 empty] | 80 | N | CCC-006 |  | 2021-06-08
DB Netz AG | CCC-009 | Hannover - Magdeburg | > | Groß Gleidingen | Braunschweig Hbf | 2023 | 2023 | 40 | 41 | 2023-10-07 | 1:45 | 2023-10-09 | 1:45 | 2d, 0h | Continuous | Switch |  | LT | [9 empty] | 80 | N | CCC-009 |  | 2021-05-17
DB Netz AG | CCC-010 | Hannover - Magdeburg | <> | Okerbrücke | Braunschweig Hbf | 2023 | 2023 | 39 | 39 | 2023-09-25 | 3:00 | 2023-09-25 | 5:00 | 0d, 2h | Continuous | Switch | T | [10 empty] | 80 | N | CCC-010 |  | 2021-05-17
DB Netz AG | CCC-001 | Hannover - Magdeburg | <> | Braunschweig Hbf | Braunschweig Hbf | 2023 | 2023 | 39 | 41 | 2023-09-25 | 7:00 | 2023-10-09 | 7:45 | 14d, 0h | Continuous | Switch |  | ST | [9 empty] | 80 | N | CCC-001 |  | 2021-05-17
DB Netz AG | CCE-003 | Dresden - Děčín | <> | Heidenau | Dohna (Sachs) | 2023 | 2023 | 40 | 41 | 2023-10-07 | 19:00 | 2023-10-15 | 4:00 | 7d, 9h | Periodical | Signal | T | [10 empty] | 80 | N | CCE-003 |  | 2021-05-29
DB Netz AG | CCE-009 | Dresden - Děčín | <> | Dresden Hbf | Bad Schandau Ost | 2023 | 2023 | 40 | 41 | 2023-10-07 | 19:00 | 2023-10-15 | 4:00 | 7d, 9h | Periodical | Signal | T | [10 empty] | 80 | N | CCE-009 |  | 2021-05-29
DB Netz AG | CCE-004 | Dresden - Děčín | <> | Bad Schandau Ost | Bad Schandau Ost | 2023 | 2023 | 40 | 41 | 2023-10-07 | 19:00 | 2023-10-15 | 4:00 | 7d, 9h | Periodical | Signal |  | ST | [9 empty] | 80 | N | CCE-004 |  | 2021-05-29
DB Netz AG | CCE-008 | Dresden - Děčín | <> | Schöna | Schöna | 2023 | 2023 | 40 | 41 | 2023-10-07 | 19:00 | 2023-10-15 | 4:00 | 7d, 9h | Periodical | Signal |  | ST | [9 empty] | 80 | N | CCE-008 |  | 2021-05-29
DB Netz AG | CCE-001 | Dresden - Děčín | <> | Pirna | Dürrröhrsdorf | 2023 | 2023 | 40 | 41 | 2023-10-07 | 19:00 | 2023-10-15 | 4:00 | 7d, 9h | Periodical | Signal | T | [10 empty] | 80 | N | CCE-001 |  | 2021-05-29
DB Netz AG | CCE-006 | Dresden - Děčín | <> | Bad Schandau Gr | Bad Schandau | 2023 | 2023 | 40 | 41 | 2023-10-07 | 19:00 | 2023-10-15 | 4:00 | 7d, 9h | Periodical | Signal | T | [10 empty] | 80,54 | N | CCE-006 |  | 2021-06-03
DB Netz AG | CCE-010 | Dresden - Děčín | <> | Bad Schandau | Sebnitz (Sachs) | 2023 | 2023 | 40 | 41 | 2023-10-07 | 19:00 | 2023-10-15 | 4:00 | 7d, 9h | Periodical | Signal | T | [10 empty] | 80 | N | CCE-010 |  | 2021-05-29
DB Netz AG | CCE-002 | Dresden - Děčín | <> | Bad Schandau | Bad Schandau | 2023 | 2023 | 40 | 41 | 2023-10-07 | 19:00 | 2023-10-15 | 4:00 | 7d, 9h | Periodical | Signal |  | ST | [9 empty] | 80 | N | CCE-002 |  | 2021-05-29
DB Netz AG | CCE-007 | Dresden - Děčín | <> | Dresden Hbf | Pirna | 2023 | 2023 | 40 | 41 | 2023-10-07 | 19:00 | 2023-10-15 | 4:00 | 7d, 9h | Periodical | Signal | T | [10 empty] | 80 | N | CCE-007 |  | 2021-05-29
DB Netz AG | CEA-002 | Dresden - Děčín | <> | Dre Freibg Str | Dresden Mitte | 2023 | 2023 | 38 | 38 | 2023-09-23 | 9:00 | 2023-09-23 | 14:00 | 0d, 5h | Continuous | Catenary |  |  |  |  | X | [6 empty] | 80 | N | CEA-002 |  | 2021-06-03
DB Netz AG | CEA-001 | Dresden - Děčín | <> | Dresden Hbf | Dresden Mitte | 2023 | 2023 | 38 | 38 | 2023-09-23 | 1:00 | 2023-09-23 | 14:00 | 0d, 13h | Continuous | Catenary | T | [10 empty] | 80 | N | CEA-001 |  | 2021-06-03
DB Netz AG | CEB-002 | Dresden - Děčín | < | Dresden-Altstadt | Dresden Hbf | 2023 | 2023 | 41 | 41 | 2023-10-09 | 8:45 | 2023-10-11 | 14:15 | 2d, 5h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | CEB-002 |  | 2021-06-01
DB Netz AG | CEB-009 | Dresden - Děčín | < | Freital Ost | Dresden Hbf | 2023 | 2023 | 39 | 39 | 2023-09-25 | 7:00 | 2023-09-30 | 7:45 | 5d, 0h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | CEB-009 |  | 2021-06-01
DB Netz AG | CEB-008 | Dresden - Děčín | > | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 41 | 41 | 2023-10-12 | 8:45 | 2023-10-13 | 14:15 | 1d, 5h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | CEB-008 |  | 2021-06-01
DB Netz AG | CEB-010 | Dresden - Děčín | > | Dresden Hbf | Freital Ost | 2023 | 2023 | 40 | 40 | 2023-10-04 | 18:15 | 2023-10-07 | 19:00 | 3d, 0h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | CEB-010 |  | 2021-06-01
DB Netz AG | CEB-006 | Dresden - Děčín | < | Freital Ost | Dresden Hbf | 2023 | 2023 | 41 | 41 | 2023-10-09 | 14:15 | 2023-10-11 | 15:00 | 2d, 0h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | CEB-006 |  | 2021-06-01
DB Netz AG | CEB-003 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 40 | 40 | 2023-10-04 | 7:45 | 2023-10-07 | 18:15 | 3d, 10h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | CEB-003 |  | 2021-06-01
DB Netz AG | CEB-004 | Dresden - Děčín | < | Freital Ost | Dresden Hbf | 2023 | 2023 | 41 | 41 | 2023-10-09 | 8:00 | 2023-10-11 | 8:45 | 2d, 0h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | CEB-004 |  | 2021-06-01
DB Netz AG | CEB-007 | Dresden - Děčín | < | Dresden-Altstadt | Dresden Hbf | 2023 | 2023 | 39 | 39 | 2023-09-25 | 7:45 | 2023-09-30 | 18:15 | 5d, 10h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | CEB-007 |  | 2021-06-01
DB Netz AG | CEB-011 | Dresden - Děčín | < | Freital Ost | Dresden Hbf | 2023 | 2023 | 39 | 39 | 2023-09-25 | 18:15 | 2023-09-30 | 19:00 | 5d, 0h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | CEB-011 |  | 2021-06-01
DB Netz AG | CEB-005 | Dresden - Děčín | < | Dresden Hbf | Freital Ost | 2023 | 2023 | 41 | 41 | 2023-10-12 | 14:15 | 2023-10-13 | 15:00 | 1d, 0h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | CEB-005 |  | 2021-06-01
DB Netz AG | CEB-001 | Dresden - Děčín | > | Dresden Hbf | Freital Ost | 2023 | 2023 | 40 | 40 | 2023-10-04 | 7:00 | 2023-10-07 | 7:45 | 3d, 0h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | CEB-001 |  | 2021-06-14
DB Netz AG | CEB-012 | Dresden - Děčín | > | Dresden Hbf | Freital Ost | 2023 | 2023 | 41 | 41 | 2023-10-12 | 8:00 | 2023-10-13 | 8:45 | 1d, 0h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | CEB-012 |  | 2021-06-01
DB Netz AG | CEF-003 | Dresden - Děčín | <> | Helmstedt | Frellstedt | 2023 | 2023 | 40 | 41 | 2023-10-06 | 22:00 | 2023-10-09 | 5:00 | 2d, 7h | Continuous | Bridge | T | [10 empty] | 80 | N | CEF-003 |  | 2021-05-26
DB Netz AG | D18-003 | Dresden - Děčín | <> | Dresden Hbf | Dre-Neustadt | 2023 | 2023 | 38 | 38 | 2023-09-23 | 14:00 | 2023-09-24 | 6:00 | 0d, 16h | Continuous | Signal | T | [10 empty] | 80 | N | D18-003 |  | 2021-06-03
DB Netz AG | D18-004 | Dresden - Děčín | <> | Dre-Neustadt | Dre-Neustadt Gbf | 2023 | 2023 | 38 | 38 | 2023-09-23 | 14:00 | 2023-09-24 | 6:00 | 0d, 16h | Continuous | Signal | T | [10 empty] | 80 | N | D18-004 |  | 2021-06-03
DB Netz AG | D18-009 | Dresden - Děčín | <> | Dre-Friedrichst | Dre Freibg Str | 2023 | 2023 | 38 | 38 | 2023-09-23 | 14:00 | 2023-09-24 | 6:00 | 0d, 16h | Continuous | Signal | T | [10 empty] | 80 | N | D18-009 |  | 2021-06-03
DB Netz AG | D18-005 | Dresden - Děčín | <> | Dre-Reick Abstbf | Dre-Neustadt | 2023 | 2023 | 38 | 38 | 2023-09-23 | 14:00 | 2023-09-24 | 6:00 | 0d, 16h | Continuous | Signal | T | [10 empty] | 80 | N | D18-005 |  | 2021-06-03
DB Netz AG | D18-006 | Dresden - Děčín | <> | Dre-Friedrichst | Dresden Mitte | 2023 | 2023 | 38 | 38 | 2023-09-23 | 14:00 | 2023-09-24 | 6:00 | 0d, 16h | Continuous | Signal | T | [10 empty] | 80 | N | D18-006 |  | 2021-06-03
DB Netz AG | D18-001 | Dresden - Děčín | <> | Dresden-Altstadt | Dresden Hbf | 2023 | 2023 | 38 | 38 | 2023-09-23 | 14:00 | 2023-09-24 | 6:00 | 0d, 16h | Continuous | Signal | T | [10 empty] | 80 | N | D18-001 |  | 2021-06-03
DB Netz AG | D18-002 | Dresden - Děčín | <> | Dresden-Altstadt | Dresden Hbf | 2023 | 2023 | 38 | 38 | 2023-09-23 | 14:00 | 2023-09-24 | 6:00 | 0d, 16h | Continuous | Signal | T | [10 empty] | 80 | N | D18-002 |  | 2021-07-01
DB Netz AG | D18-007 | Dresden - Děčín | <> | Dresden-Altstadt | Dre Freibg Str | 2023 | 2023 | 38 | 38 | 2023-09-23 | 14:00 | 2023-09-24 | 6:00 | 0d, 16h | Continuous | Signal | T | [10 empty] | 80 | N | D18-007 |  | 2021-06-03
DB Netz AG | D18-008 | Dresden - Děčín | <> | Dresden-Reick | Dre-Neustadt | 2023 | 2023 | 38 | 38 | 2023-09-23 | 14:00 | 2023-09-24 | 6:00 | 0d, 16h | Continuous | Signal | T | [10 empty] | 80 | N | D18-008 |  | 2021-06-03
DB Netz AG | D1F-004 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 38 | 42 | 2023-09-24 | 6:00 | 2023-10-21 | 14:00 | 27d, 8h | Continuous | Switch | T | [10 empty] | 80 | N | D1F-004 |  | 2021-05-31
DB Netz AG | D1F-005 | Dresden - Děčín | <> | Dresden Hbf | Dre Freibg Str | 2023 | 2023 | 38 | 42 | 2023-09-24 | 6:00 | 2023-10-21 | 14:00 | 27d, 8h | Continuous | Switch |  | ST | [9 empty] | 80 | N | D1F-005 |  | 2021-05-31
DB Netz AG | D1F-002 | Dresden - Děčín | <> | Dresden-Altstadt | Dresden Hbf | 2023 | 2023 | 38 | 42 | 2023-09-24 | 6:00 | 2023-10-21 | 14:00 | 27d, 8h | Continuous | Switch |  |  |  |  | X | [6 empty] | 80 | N | D1F-002 |  | 2021-05-31
DB Netz AG | D1F-006 | Dresden - Děčín | <> | Dresden Hbf | Dre Freibg Str | 2023 | 2023 | 38 | 42 | 2023-09-24 | 6:00 | 2023-10-21 | 14:00 | 27d, 8h | Continuous | Switch |  |  |  |  | X | [6 empty] | 80 | N | D1F-006 |  | 2021-05-31
DB Netz AG | D1F-001 | Dresden - Děčín | <> | Dresden Hbf | Dre Freibg Str | 2023 | 2023 | 38 | 42 | 2023-09-24 | 6:00 | 2023-10-21 | 14:00 | 27d, 8h | Continuous | Switch | T | [10 empty] | 80 | N | D1F-001 |  | 2021-05-31
DB Netz AG | D1F-003 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 38 | 42 | 2023-09-24 | 6:00 | 2023-10-21 | 14:00 | 27d, 8h | Continuous | Switch |  | ST | [9 empty] | 80 | Y | D1F-003 |  | 2021-05-31
DB Netz AG | D26-001 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 39 | 39 | 2023-09-25 | 20:00 | 2023-09-30 | 4:00 | 4d, 8h | Periodical | Catenary | T | [10 empty] | 80 | N | D26-001 |  | 2021-06-01
DB Netz AG | D4D-009 | Rostock - Berlin | <> | Oranienburg | Oranienburg | 2023 | 2023 | 36 | 37 | 2023-09-10 | 22:00 | 2023-09-11 | 1:00 | 0d, 3h | Continuous | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | D4D-009 |  | 2021-05-07
DB Netz AG | D4D-001 | Rostock - Berlin | > | Oranienburg | Nassenheide | 2023 | 2023 | 36 | 37 | 2023-09-10 | 22:00 | 2023-09-11 | 1:00 | 0d, 3h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | D4D-001 |  | 2021-05-07
DB Netz AG | D4D-006 | Rostock - Berlin | <> | Oranienburg | Oranienburg | 2023 | 2023 | 36 | 37 | 2023-09-10 | 22:00 | 2023-09-11 | 1:00 | 0d, 3h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | D4D-006 |  | 2021-05-07
DB Netz AG | D4D-002 | Rostock - Berlin | <> | Oranienburg | Oranienburg | 2023 | 2023 | 38 | 39 | 2023-09-22 | 21:00 | 2023-09-25 | 4:00 | 2d, 7h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | D4D-002 |  | 2021-05-07
DB Netz AG | D4D-013 | Rostock - Berlin | > | Oranienburg | Nassenheide | 2023 | 2023 | 38 | 39 | 2023-09-22 | 21:00 | 2023-09-25 | 4:00 | 2d, 7h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | D4D-013 |  | 2021-05-07
DB Netz AG | D4D-008 | Rostock - Berlin | <> | Oranienburg | Oranienburg | 2023 | 2023 | 38 | 39 | 2023-09-22 | 21:00 | 2023-09-25 | 4:00 | 2d, 7h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | D4D-008 |  | 2021-05-07
DB Netz AG | D4D-003 | Rostock - Berlin | > | Oranienburg | Nassenheide | 2023 | 2023 | 38 | 39 | 2023-09-24 | 14:00 | 2023-09-25 | 4:00 | 0d, 14h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | D4D-003 |  | 2021-05-07
DB Netz AG | D4D-014 | Rostock - Berlin | <> | Oranienburg | Oranienburg | 2023 | 2023 | 38 | 39 | 2023-09-24 | 14:00 | 2023-09-25 | 4:00 | 0d, 14h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | D4D-014 |  | 2021-05-07
DB Netz AG | D4D-004 | Rostock - Berlin | <> | Oranienburg | Oranienburg | 2023 | 2023 | 38 | 39 | 2023-09-24 | 14:00 | 2023-09-25 | 4:00 | 0d, 14h | Continuous | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | D4D-004 |  | 2021-05-07
DB Netz AG | D4D-016 | Rostock - Berlin | <> | Oranienburg | Oranienburg | 2023 | 2023 | 37 | 39 | 2023-09-11 | 6:00 | 2023-09-25 | 4:00 | 13d, 22h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | D4D-016 |  | 2021-05-07
DB Netz AG | D4D-005 | Rostock - Berlin | > | Oranienburg | Nassenheide | 2023 | 2023 | 37 | 37 | 2023-09-11 | 1:00 | 2023-09-11 | 6:00 | 0d, 5h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | D4D-005 |  | 2021-05-07
DB Netz AG | D4D-010 | Rostock - Berlin | <> | Oranienburg | Oranienburg | 2023 | 2023 | 37 | 37 | 2023-09-11 | 1:00 | 2023-09-11 | 6:00 | 0d, 5h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | D4D-010 |  | 2021-05-07
DB Netz AG | D4D-011 | Rostock - Berlin | > | Birkenwerd b Bln | Oranienburg | 2023 | 2023 | 37 | 37 | 2023-09-11 | 1:00 | 2023-09-11 | 6:00 | 0d, 5h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | D4D-011 |  | 2021-05-07
DB Netz AG | D4D-012 | Rostock - Berlin | <> | Oranienburg | Oranienburg | 2023 | 2023 | 37 | 38 | 2023-09-11 | 6:00 | 2023-09-22 | 21:00 | 11d, 15h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | D4D-012 |  | 2021-05-07
DB Netz AG | D9F-004 | Dresden - Děčín | <> | Dresden-Altstadt | Dre Freibg Str | 2023 | 2023 | 37 | 37 | 2023-09-13 | 20:00 | 2023-09-15 | 4:00 | 1d, 8h | Periodical | Catenary | T | [10 empty] | 80 | N | D9F-004 |  | 2021-06-03
DB Netz AG | D9F-002 | Dresden - Děčín | <> | Dresden Hbf | Dresden Mitte | 2023 | 2023 | 37 | 37 | 2023-09-13 | 20:00 | 2023-09-15 | 4:00 | 1d, 8h | Periodical | Catenary | T | [10 empty] | 80 | N | D9F-002 |  | 2021-06-03
DB Netz AG | D9F-003 | Dresden - Děčín | <> | Dresden Hbf | Dresden Mitte | 2023 | 2023 | 37 | 37 | 2023-09-13 | 20:00 | 2023-09-15 | 4:00 | 1d, 8h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80 | N | D9F-003 |  | 2021-06-03
DB Netz AG | D9F-001 | Dresden - Děčín | <> | Dre Freibg Str | Dre-Friedrichst | 2023 | 2023 | 37 | 37 | 2023-09-13 | 20:00 | 2023-09-15 | 4:00 | 1d, 8h | Periodical | Catenary | T | [10 empty] | 80 | N | D9F-001 |  | 2021-06-03
DB Netz AG | DA1-003 | Bremen - Hannover | <> | Neustadt a Rbg | Wunstorf | 2023 | 2023 | 39 | 40 | 2023-10-01 | 23:05 | 2023-10-02 | 5:05 | 0d, 6h | Continuous | Signal | T | [10 empty] | 80 | N | DA1-003 |  | 2021-05-31
DB Netz AG | DA1-004 | Bremen - Hannover | <> | Neustadt a Rbg | Wunstorf | 2023 | 2023 | 39 | 39 | 2023-09-30 | 2:10 | 2023-09-30 | 5:10 | 0d, 3h | Continuous | Signal | T | [10 empty] | 80 | N | DA1-004 |  | 2021-05-31
DB Netz AG | DA1-002 | Bremen - Hannover | <> | Wunstorf | Neustadt a Rbg | 2023 | 2023 | 40 | 41 | 2023-10-06 | 23:05 | 2023-10-09 | 4:25 | 2d, 5h | Continuous | Signal | T | [10 empty] | 80 | N | DA1-002 |  | 2021-05-31
DB Netz AG | DA1-001 | Bremen - Hannover | <> | Neustadt a Rbg | Wunstorf | 2023 | 2023 | 39 | 39 | 2023-09-30 | 23:50 | 2023-10-01 | 6:50 | 0d, 7h | Continuous | Signal | T | [10 empty] | 80 | N | DA1-001 |  | 2021-05-31
DB Netz AG | DAE-004 | Dresden - Děčín | <> | Dresden Hbf | Dre-Neustadt | 2023 | 2023 | 38 | 38 | 2023-09-21 | 1:00 | 2023-09-21 | 5:00 | 0d, 4h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | DAE-004 |  | 2021-06-04
DB Netz AG | DAE-011 | Dresden - Děčín | <> | Dre-Reick Abstbf | Dre-Neustadt | 2023 | 2023 | 38 | 38 | 2023-09-21 | 1:00 | 2023-09-21 | 5:00 | 0d, 4h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | DAE-011 |  | 2021-06-04
DB Netz AG | DAE-014 | Dresden - Děčín | <> | Dre-Friedrichst | Dre Freibg Str | 2023 | 2023 | 38 | 38 | 2023-09-21 | 1:00 | 2023-09-21 | 5:00 | 0d, 4h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | DAE-014 |  | 2021-06-04
DB Netz AG | DAE-015 | Dresden - Děčín | <> | Dresden-Altstadt | Dre Freibg Str | 2023 | 2023 | 38 | 38 | 2023-09-21 | 1:00 | 2023-09-21 | 5:00 | 0d, 4h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | DAE-015 |  | 2021-06-04
DB Netz AG | DAE-001 | Dresden - Děčín | <> | Dresden-Reick | Dre-Neustadt | 2023 | 2023 | 38 | 38 | 2023-09-21 | 1:00 | 2023-09-21 | 5:00 | 0d, 4h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | DAE-001 |  | 2021-06-04
DB Netz AG | DAE-016 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 38 | 38 | 2023-09-21 | 1:00 | 2023-09-21 | 5:00 | 0d, 4h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | DAE-016 |  | 2021-06-04
DB Netz AG | DAE-007 | Dresden - Děčín | <> | Dre-Friedrichst | Dresden Mitte | 2023 | 2023 | 38 | 38 | 2023-09-21 | 1:00 | 2023-09-21 | 5:00 | 0d, 4h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | DAE-007 |  | 2021-06-04
DB Netz AG | DAE-017 | Dresden - Děčín | <> | Dresden-Altstadt | Dresden Hbf | 2023 | 2023 | 38 | 38 | 2023-09-21 | 1:00 | 2023-09-21 | 5:00 | 0d, 4h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | DAE-017 |  | 2021-07-01
DB Netz AG | DAE-002 | Dresden - Děčín | <> | Dre-Neustadt | Dre-Neustadt Gbf | 2023 | 2023 | 38 | 38 | 2023-09-21 | 1:00 | 2023-09-21 | 5:00 | 0d, 4h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | DAE-002 |  | 2021-06-04
DB Netz AG | DAE-008 | Dresden - Děčín | <> | Dre-Neustadt | Dre-Neustadt Gbf | 2023 | 2023 | 38 | 38 | 2023-09-20 | 19:00 | 2023-09-21 | 1:00 | 0d, 6h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | DAE-008 |  | 2021-06-04
DB Netz AG | DAE-005 | Dresden - Děčín | <> | Dresden Hbf | Dre-Neustadt | 2023 | 2023 | 38 | 38 | 2023-09-20 | 19:00 | 2023-09-21 | 1:00 | 0d, 6h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | DAE-005 |  | 2021-06-04
DB Netz AG | DAE-013 | Dresden - Děčín | <> | Dresden-Altstadt | Dresden Hbf | 2023 | 2023 | 38 | 38 | 2023-09-20 | 19:00 | 2023-09-21 | 1:00 | 0d, 6h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | DAE-013 |  | 2021-06-04
DB Netz AG | DAE-012 | Dresden - Děčín | <> | Dresden-Altstadt | Dresden Hbf | 2023 | 2023 | 38 | 38 | 2023-09-20 | 19:00 | 2023-09-21 | 1:00 | 0d, 6h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | DAE-012 |  | 2021-06-04
DB Netz AG | DAE-003 | Dresden - Děčín | <> | Dre-Friedrichst | Dresden Mitte | 2023 | 2023 | 38 | 38 | 2023-09-20 | 19:00 | 2023-09-21 | 1:00 | 0d, 6h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | DAE-003 |  | 2021-06-04
DB Netz AG | DAE-018 | Dresden - Děčín | <> | Dresden Hbf | Dre-Neustadt | 2023 | 2023 | 38 | 38 | 2023-09-20 | 19:00 | 2023-09-21 | 1:00 | 0d, 6h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | DAE-018 |  | 2021-06-04
DB Netz AG | DAE-009 | Dresden - Děčín | <> | Dre-Friedrichst | Dre Freibg Str | 2023 | 2023 | 38 | 38 | 2023-09-20 | 19:00 | 2023-09-21 | 1:00 | 0d, 6h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | DAE-009 |  | 2021-06-04
DB Netz AG | DAE-010 | Dresden - Děčín | <> | Dresden-Altstadt | Dre Freibg Str | 2023 | 2023 | 38 | 38 | 2023-09-20 | 19:00 | 2023-09-21 | 1:00 | 0d, 6h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | DAE-010 |  | 2021-06-04
DB Netz AG | E1B-001 | Dresden - Děčín | <> | Dresden Hbf | Dresden Mitte | 2023 | 2023 | 36 | 37 | 2023-09-10 | 20:00 | 2023-09-12 | 4:00 | 1d, 8h | Periodical | Catenary | T | [10 empty] | 80 | N | E1B-001 |  | 2021-06-02
DB Netz AG | E1B-002 | Dresden - Děčín | <> | Dresden Hbf | Dresden Mitte | 2023 | 2023 | 36 | 37 | 2023-09-10 | 20:00 | 2023-09-12 | 4:00 | 1d, 8h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80 | N | E1B-002 |  | 2021-06-02
DB Netz AG | EAE-004 | Wilhelmshaven - Bremen | <> | Veddel | Hmb-Wlb Abzw | 2023 | 2023 | 41 | 43 | 2023-10-13 | 22:00 | 2023-10-23 | 4:00 | 9d, 6h | Continuous | Signal | T | [10 empty] | 80 | N | EAE-004 |  | 2021-05-23
DB Netz AG | FA4-029 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 37 | 42 | 2023-09-12 | 21:30 | 2023-10-21 | 5:30 | 38d, 8h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | FA4-029 |  | 2021-05-27
DB Netz AG | FA4-006 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 37 | 42 | 2023-09-12 | 21:30 | 2023-10-21 | 5:30 | 38d, 8h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | FA4-006 |  | 2021-05-27
DB Netz AG | FA4-007 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 37 | 42 | 2023-09-12 | 21:30 | 2023-10-21 | 5:30 | 38d, 8h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | FA4-007 |  | 2021-05-27
DB Netz AG | FA4-013 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 37 | 42 | 2023-09-12 | 21:30 | 2023-10-21 | 5:30 | 38d, 8h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | FA4-013 |  | 2021-05-27
DB Netz AG | FA4-008 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 37 | 44 | 2023-09-11 | 5:30 | 2023-10-30 | 5:30 | 49d, 1h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | FA4-008 |  | 2021-05-27
DB Netz AG | FA4-019 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 37 | 44 | 2023-09-11 | 5:30 | 2023-10-30 | 5:30 | 49d, 1h | Continuous | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | FA4-019 |  | 2021-05-27
DB Netz AG | FA4-031 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 37 | 44 | 2023-09-11 | 5:30 | 2023-10-30 | 5:30 | 49d, 1h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | FA4-031 |  | 2021-05-27
DB Netz AG | FA4-036 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 37 | 37 | 2023-09-11 | 3:30 | 2023-09-11 | 5:30 | 0d, 2h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | FA4-036 |  | 2021-05-27
DB Netz AG | FA4-017 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 37 | 37 | 2023-09-11 | 3:30 | 2023-09-11 | 5:30 | 0d, 2h | Continuous | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | FA4-017 |  | 2021-05-27
DB Netz AG | 1031-002 | Dresden - Děčín | <> | Dre-Friedrichst | Dre Freibg Str | 2023 | 2023 | 37 | 38 | 2023-09-17 | 20:00 | 2023-09-20 | 4:00 | 2d, 8h | Periodical | Catenary | T | [10 empty] | 80 | N | 1031-002 |  | 2021-06-03
DB Netz AG | 1031-001 | Dresden - Děčín | <> | Dresden Hbf | Dresden Mitte | 2023 | 2023 | 37 | 38 | 2023-09-17 | 20:00 | 2023-09-20 | 4:00 | 2d, 8h | Periodical | Catenary | T | [10 empty] | 80 | N | 1031-001 |  | 2021-06-03
DB Netz AG | 1031-003 | Dresden - Děčín | <> | Dresden Hbf | Dresden Mitte | 2023 | 2023 | 37 | 38 | 2023-09-17 | 20:00 | 2023-09-20 | 4:00 | 2d, 8h | Periodical | Catenary | T | [10 empty] | 80 | N | 1031-003 |  | 2021-06-03
DB Netz AG | 1031-005 | Dresden - Děčín | <> | Dre Freibg Str | Dresden-Altstadt | 2023 | 2023 | 37 | 38 | 2023-09-17 | 20:00 | 2023-09-20 | 4:00 | 2d, 8h | Periodical | Catenary | T | [10 empty] | 80 | N | 1031-005 |  | 2021-06-03
DB Netz AG | 1031-006 | Dresden - Děčín | <> | Dresden Hbf | Dresden Mitte | 2023 | 2023 | 37 | 38 | 2023-09-17 | 20:00 | 2023-09-20 | 4:00 | 2d, 8h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 1031-006 |  | 2021-06-03
DB Netz AG | 1031-004 | Dresden - Děčín | <> | Dre Freibg Str | Dre-Friedrichst | 2023 | 2023 | 37 | 38 | 2023-09-17 | 20:00 | 2023-09-18 | 4:00 | 0d, 8h | Continuous | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 1031-004 |  | 2021-06-03
DB Netz AG | 1039-001 | Dresden - Děčín | <> | Dre-Friedrichst | Dre Freibg Str | 2023 | 2023 | 39 | 39 | 2023-09-30 | 22:00 | 2023-10-01 | 5:00 | 0d, 7h | Continuous | Catenary | T | [10 empty] | 80 | N | 1039-001 |  | 2021-06-01
DB Netz AG | 1039-003 | Dresden - Děčín | <> | Dresden-Altstadt | Dre Freibg Str | 2023 | 2023 | 39 | 39 | 2023-09-30 | 22:00 | 2023-10-01 | 5:00 | 0d, 7h | Continuous | Catenary | T | [10 empty] | 80 | N | 1039-003 |  | 2021-06-01
DB Netz AG | 1039-002 | Dresden - Děčín | <> | Dre Freibg Str | Dresden Mitte | 2023 | 2023 | 39 | 39 | 2023-09-30 | 22:00 | 2023-10-01 | 5:00 | 0d, 7h | Continuous | Catenary | T | [10 empty] | 80 | N | 1039-002 |  | 2021-06-01
DB Netz AG | 0.104 | Dresden - Děčín | <> | Dresden-Altstadt | Dre Freibg Str | 2023 | 2023 | 38 | 39 | 2023-09-24 | 22:00 | 2023-09-26 | 5:00 | 1d, 7h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | 0.104 |  | 2021-06-01
DB Netz AG | 0.0104 | Dresden - Děčín | <> | Dre Freibg Str | Dre-Friedrichst | 2023 | 2023 | 38 | 39 | 2023-09-24 | 22:00 | 2023-09-26 | 5:00 | 1d, 7h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | 0.0104 |  | 2021-06-01
DB Netz AG | 10.4 | Dresden - Děčín | <> | Dre Freibg Str | Dresden Mitte | 2023 | 2023 | 38 | 39 | 2023-09-24 | 22:00 | 2023-09-26 | 5:00 | 1d, 7h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | 10.4 |  | 2021-06-01
DB Netz AG | 1.04 | Dresden - Děčín | <> | Dresden Hbf | Dresden Mitte | 2023 | 2023 | 39 | 39 | 2023-09-25 | 22:00 | 2023-09-26 | 5:00 | 0d, 7h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 1.04 |  | 2021-06-01
DB Netz AG | 1086-007 | Dresden - Děčín | < | Bad Schandau | Bad Schandau | 2023 | 2023 | 41 | 41 | 2023-10-10 | 23:00 | 2023-10-11 | 5:00 | 0d, 6h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 1086-007 |  | 2021-05-29
DB Netz AG | 1086-004 | Dresden - Děčín | < | Bad Schandau | Bad Schandau | 2023 | 2023 | 40 | 41 | 2023-10-08 | 23:00 | 2023-10-09 | 5:00 | 0d, 6h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 1086-004 |  | 2021-05-29
DB Netz AG | 1086-009 | Dresden - Děčín | <> | Bad Schandau | Bad Schandau | 2023 | 2023 | 41 | 41 | 2023-10-11 | 23:00 | 2023-10-12 | 5:00 | 0d, 6h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 1086-009 |  | 2021-05-29
DB Netz AG | 1086-005 | Dresden - Děčín | <> | Bad Schandau | Bad Schandau | 2023 | 2023 | 41 | 41 | 2023-10-11 | 23:00 | 2023-10-12 | 5:00 | 0d, 6h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 1086-005 |  | 2021-05-29
DB Netz AG | 1086-002 | Dresden - Děčín | <> | Bad Schandau | Bad Schandau | 2023 | 2023 | 41 | 41 | 2023-10-12 | 23:00 | 2023-10-13 | 5:00 | 0d, 6h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 1086-002 |  | 2021-05-29
DB Netz AG | 1086-001 | Dresden - Děčín | <> | Bad Schandau | Bad Schandau | 2023 | 2023 | 41 | 41 | 2023-10-12 | 23:00 | 2023-10-13 | 5:00 | 0d, 6h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 1086-001 |  | 2021-05-29
DB Netz AG | 1086-003 | Dresden - Děčín | < | Bad Schandau | Bad Schandau | 2023 | 2023 | 41 | 41 | 2023-10-09 | 23:00 | 2023-10-10 | 5:00 | 0d, 6h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 1086-003 |  | 2021-05-29
DB Netz AG | 1086-006 | Dresden - Děčín | <> | Schöna | Bad Schandau | 2023 | 2023 | 38 | 42 | 2023-09-24 | 23:00 | 2023-10-17 | 5:00 | 22d, 6h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | 1086-006 |  | 2021-05-29
DB Netz AG | 1086-008 | Dresden - Děčín | <> | Bad Schandau Gr | Bad Schandau | 2023 | 2023 | 38 | 42 | 2023-09-24 | 23:00 | 2023-10-17 | 5:00 | 22d, 6h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80,54 | N | 1086-008 |  | 2021-05-29
DB Netz AG | 1086-010 | Dresden - Děčín | <> | Schöna | Schöna | 2023 | 2023 | 38 | 42 | 2023-09-24 | 23:00 | 2023-10-17 | 5:00 | 22d, 6h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1086-010 |  | 2021-05-29
DB Netz AG | 1116-005 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 36 | 38 | 2023-09-10 | 6:00 | 2023-09-23 | 14:00 | 13d, 8h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 1116-005 |  | 2021-06-02
DB Netz AG | 1116-002 | Dresden - Děčín | <> | Dresden Mitte | Dresden Hbf | 2023 | 2023 | 36 | 38 | 2023-09-10 | 6:00 | 2023-09-23 | 14:00 | 13d, 8h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 1116-002 |  | 2021-06-02
DB Netz AG | 1116-003 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 36 | 38 | 2023-09-10 | 6:00 | 2023-09-23 | 14:00 | 13d, 8h | Continuous | Switch |  |  |  |  | X | [6 empty] | 80 | N | 1116-003 |  | 2021-06-02
DB Netz AG | 1116-004 | Dresden - Děčín | <> | Dresden Hbf | Dresden Mitte | 2023 | 2023 | 36 | 38 | 2023-09-10 | 6:00 | 2023-09-23 | 14:00 | 13d, 8h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 1116-004 |  | 2021-06-02
DB Netz AG | 1116-001 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 36 | 38 | 2023-09-10 | 6:00 | 2023-09-23 | 14:00 | 13d, 8h | Continuous | Switch |  | ST | [9 empty] | 80 | Y | 1116-001 |  | 2021-06-02
DB Netz AG | 118B-002 | Hannover - Magdeburg | > | Braunschweig Hbf | Helmstedt | 2023 | 2023 | 38 | 41 | 2023-09-24 | 23:00 | 2023-10-13 | 5:00 | 18d, 6h | Periodical | Maintenance |  | LT | [9 empty] | 80 | N | 118B-002 |  | 2022-06-07
DB Netz AG | 11B8-001 | Hannover - Magdeburg | > | Lehrte | Groß Gleidingen | 2023 | 2023 | 39 | 41 | 2023-09-29 | 23:00 | 2023-10-13 | 5:00 | 13d, 6h | Periodical | Maintenance |  | LT | [9 empty] | 80 | N | 11B8-001 |  | 2021-01-12
DB Netz AG | 11D9-001 | Magdeburg - Falkenberg | > | Magdeburg Hbf | Helmstedt | 2023 | 2023 | 38 | 40 | 2023-09-23 | 21:00 | 2023-10-07 | 5:00 | 13d, 8h | Periodical | Maintenance |  | LT | [9 empty] | 80 | N | 11D9-001 |  | 2022-06-29
DB Netz AG | 11F0-001 | Bremerhaven - Bremen | > | Wunstorf | Bremen Hbf | 2023 | 2023 | 37 | 38 | 2023-09-14 | 23:00 | 2023-09-21 | 5:00 | 6d, 6h | Periodical | Maintenance |  | LT | [9 empty] | 80 | N | 11F0-001 |  | 2021-01-12
DB Netz AG | 1253-001 | Wilhelmshaven - Bremen | < | Bremen Hbf | Oldb (Oldb) Hbf | 2023 | 2023 | 39 | 41 | 2023-09-25 | 23:00 | 2023-10-09 | 5:00 | 13d, 6h | Periodical | Maintenance |  | LT | [9 empty] | 80 | N | 1253-001 |  | 2021-01-12
DB Netz AG | 12C1-002 | Magdeburg - Falkenberg | <> | Fermerswalde | Fermerswalde | 2023 | 2023 | 38 | 38 | 2023-09-19 | 21:00 | 2023-09-20 | 6:00 | 0d, 9h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 12C1-002 |  | 2021-05-09
DB Netz AG | 12C1-001 | Magdeburg - Falkenberg | <> | Fermerswalde | Fermerswalde | 2023 | 2023 | 39 | 39 | 2023-09-26 | 21:00 | 2023-09-27 | 6:00 | 0d, 9h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 12C1-001 |  | 2021-05-09
DB Netz AG | B9B-008 | Hannover - Magdeburg | <> | Magdeburg-Buckau | Mg-Sudenburg | 2023 | 2023 | 40 | 40 | 2023-10-07 | 10:00 | 2023-10-08 | 4:00 | 0d, 18h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | B9B-008 |  | 2021-06-08
DB Netz AG | CCE-011 | Dresden - Děčín | <> | Dolni Zleb | Bad Schandau Gr | 2023 | 2023 | 40 | 41 | 2023-10-07 | 19:00 | 2023-10-15 | 4:00 | 7d, 9h | Periodical | Signal |  |  |  |  | X | [6 empty] | 80,54,80,54 | N | CCE-011 |  | 2021-06-03
DB Netz AG | D1F-008 | Dresden - Děčín | <> | Dresden Hbf | Dre Freibg Str | 2023 | 2023 | 38 | 42 | 2023-09-24 | 6:00 | 2023-10-21 | 14:00 | 27d, 8h | Continuous | Switch |  |  |  | P | [7 empty] | 80 | Y | D1F-008 |  | 2021-05-31
DB Netz AG | D1F-009 | Dresden - Děčín | <> | Dresden Hbf | Dre Freibg Str | 2023 | 2023 | 38 | 42 | 2023-09-24 | 6:00 | 2023-10-21 | 14:00 | 27d, 8h | Continuous | Switch |  |  |  | P | [7 empty] | 80 | Y | D1F-009 |  | 2021-05-31
DB Netz AG | D1F-010 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 38 | 42 | 2023-09-24 | 6:00 | 2023-10-21 | 14:00 | 27d, 8h | Continuous | Switch |  | ST | [9 empty] | 80 | N | D1F-010 |  | 2021-05-31
DB Netz AG | 0.00104 | Dresden - Děčín | <> | Dre Freibg Str | Dre Freibg Str | 2023 | 2023 | 38 | 39 | 2023-09-24 | 22:00 | 2023-09-26 | 5:00 | 1d, 7h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 0.00104 |  | 2021-06-01
DB Netz AG | D26-002 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 39 | 39 | 2023-09-25 | 20:00 | 2023-09-30 | 4:00 | 4d, 8h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | D26-002 |  | 2021-06-01
DB Netz AG | B9E-002 | Magdeburg - Falkenberg | > | Magdeburg Hbf | Magdeburg Hbf | 2023 | 2023 | 39 | 39 | 2023-09-27 | 8:00 | 2023-09-29 | 16:00 | 2d, 8h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | B9E-002 |  | 2021-06-01
DB Netz AG | 1116-006 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 36 | 38 | 2023-09-10 | 6:00 | 2023-09-23 | 14:00 | 13d, 8h | Continuous | Switch |  |  |  | P | [7 empty] | 80 | Y | 1116-006 |  | 2021-06-02
DB Netz AG | 1116-007 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 36 | 38 | 2023-09-10 | 6:00 | 2023-09-23 | 14:00 | 13d, 8h | Continuous | Switch |  |  |  | P | [7 empty] | 80 | Y | 1116-007 |  | 2021-06-02
DB Netz AG | 1116-008 | Dresden - Děčín | <> | Dresden Hbf | Dresden Mitte | 2023 | 2023 | 36 | 38 | 2023-09-10 | 6:00 | 2023-09-23 | 14:00 | 13d, 8h | Continuous | Switch |  |  |  | P | [7 empty] | 80 | Y | 1116-008 |  | 2021-06-02
DB Netz AG | CCE-012 | Dresden - Děčín | <> | Bad Schandau Gr | Dolni Zleb | 2023 | 2023 | 40 | 41 | 2023-10-07 | 19:00 | 2023-10-15 | 4:00 | 7d, 9h | Periodical | Signal | T | [10 empty] | 80,54,80,54 | N | CCE-012 |  | 2021-06-03
DB Netz AG | 1031-007 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 37 | 38 | 2023-09-17 | 20:00 | 2023-09-18 | 4:00 | 0d, 8h | Continuous | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 1031-007 |  | 2021-06-03
DB Netz AG | DAE-019 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 38 | 38 | 2023-09-20 | 19:00 | 2023-09-21 | 1:00 | 0d, 6h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | DAE-019 |  | 2021-06-04
DB Netz AG | CCC-014 | Hannover - Magdeburg | <> | Braunschweig Hbf | Braunschweig Hbf | 2023 | 2023 | 41 | 41 | 2023-10-09 | 1:45 | 2023-10-09 | 3:45 | 0d, 2h | Continuous | Switch |  | ST | [9 empty] | 80 | N | CCC-014
DB Netz AG | CCC-015 | Hannover - Magdeburg | <> | Braunschweig Hbf | Braunschweig Hbf | 2023 | 2023 | 41 | 41 | 2023-10-11 | 14:00 | 2023-10-14 | 17:00 | 3d, 3h | Continuous | Switch |  | ST | [9 empty] | 80 | N | CCC-015
DB Netz AG | CCC-016 | Hannover - Magdeburg | <> | Braunschweig Hbf | Braunschweig Hbf | 2023 | 2023 | 41 | 41 | 2023-10-11 | 14:00 | 2023-10-13 | 22:00 | 2d, 8h | Continuous | Switch |  | ST | [9 empty] | 80 | N | CCC-016
DB Netz AG | CCC-017 | Hannover - Magdeburg | <> | Braunschweig Hbf | Braunschweig Hbf | 2023 | 2023 | 41 | 41 | 2023-10-09 | 5:45 | 2023-10-11 | 13:45 | 2d, 8h | Continuous | Switch |  | ST | [9 empty] | 80 | N | CCC-017
DB Netz AG | CCC-018 | Hannover - Magdeburg | <> | Braunschweig Hbf | Braunschweig Hbf | 2023 | 2023 | 40 | 40 | 2023-10-06 | 23:45 | 2023-10-07 | 1:45 | 0d, 2h | Continuous | Switch |  | ST | [9 empty] | 80 | N | CCC-018
DB Netz AG | 150B-001 | Hannover - Magdeburg | <> | Braunschweig Hbf | Braunschweig Hbf | 2023 | 2023 | 39 | 41 | 2023-09-25 | 7:00 | 2023-10-14 | 22:00 | 19d, 15h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 150B-001 |  | 2021-06-16
DB Netz AG | 16AC-001 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 38 | 38 | 2023-09-21 | 19:00 | 2023-09-22 | 5:00 | 0d, 10h | Continuous | Catenary | T | [10 empty] | 80 | N | 16AC-001 |  | 2021-05-21
DB Netz AG | 16AC-002 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 38 | 38 | 2023-09-21 | 19:00 | 2023-09-22 | 5:00 | 0d, 10h | Continuous | Catenary |  | ST | [9 empty] | 80 | N | 16AC-002 |  | 2021-05-21
DB Netz AG | 16AC-003 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 38 | 38 | 2023-09-21 | 19:00 | 2023-09-22 | 5:00 | 0d, 10h | Continuous | Catenary | T | [10 empty] | 80 | N | 16AC-003 |  | 2021-05-21
DB Netz AG | 16AC-004 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 38 | 38 | 2023-09-21 | 23:00 | 2023-09-22 | 5:00 | 0d, 6h | Continuous | Catenary |  | ST | [9 empty] | 80 | N | 16AC-004 |  | 2021-05-21
DB Netz AG | 16AC-005 | Dresden - Děčín | <> | Dresden Hbf | Dresden Mitte | 2023 | 2023 | 38 | 38 | 2023-09-21 | 23:00 | 2023-09-22 | 5:00 | 0d, 6h | Continuous | Catenary | T | [10 empty] | 80 | N | 16AC-005 |  | 2021-05-21
DB Netz AG | 16BA-001 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 38 | 38 | 2023-09-22 | 1:00 | 2023-09-22 | 4:00 | 0d, 3h | Continuous | Catenary | T | [10 empty] | 80 | N | 16BA-001 |  | 2021-05-21
DB Netz AG | 16BA-002 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 38 | 38 | 2023-09-22 | 1:00 | 2023-09-22 | 4:00 | 0d, 3h | Continuous | Catenary |  | ST | [9 empty] | 80 | N | 16BA-002 |  | 2021-05-21
DB Netz AG | 16BA-003 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 38 | 38 | 2023-09-22 | 1:00 | 2023-09-22 | 4:00 | 0d, 3h | Continuous | Catenary | T | [10 empty] | 80 | N | 16BA-003 |  | 2021-05-21
DB Netz AG | 16E2-001 | Dresden - Děčín | <> | Bad Schandau | Bad Schandau | 2023 | 2023 | 40 | 41 | 2023-10-08 | 23:00 | 2023-10-11 | 5:00 | 2d, 6h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 16E2-001 |  | 2021-04-27
DB Netz AG | 16E2-003 | Dresden - Děčín | < | Bad Schandau | Bad Schandau | 2023 | 2023 | 40 | 41 | 2023-10-08 | 23:00 | 2023-10-11 | 5:00 | 2d, 6h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 16E2-003 |  | 2021-04-27
DB Netz AG | 17B2-012 | Bremen - Hannover | < | Wunstorf | Letter Abzw | 2023 | 2023 | 37 | 37 | 2023-09-11 | 22:35 | 2023-09-13 | 5:05 | 1d, 6h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 17B2-012
DB Netz AG | 17B2-013 | Bremen - Hannover | <> | Seelze | Seelze West | 2023 | 2023 | 37 | 37 | 2023-09-11 | 22:35 | 2023-09-13 | 5:05 | 1d, 6h | Periodical | Catenary |  |  |  | P | [7 empty] | 80 | N | 17B2-013
DB Netz AG | 17B2-014 | Bremen - Hannover | <> | Seelze West | Seelze Mitte | 2023 | 2023 | 37 | 37 | 2023-09-11 | 22:35 | 2023-09-13 | 5:05 | 1d, 6h | Periodical | Catenary |  |  |  | P | [7 empty] | 80 | N | 17B2-014
DB Netz AG | 17B2-015 | Bremen - Hannover | <> | Seelze | Seelze West | 2023 | 2023 | 37 | 37 | 2023-09-11 | 22:35 | 2023-09-13 | 5:05 | 1d, 6h | Periodical | Catenary |  |  | S | [8 empty] | 80 | N | 17B2-015
DB Netz AG | 1849-017 | Falkenberg - Dresden | <> | Priestewitz | Coswig Stw 1 | 2023 | 2023 | 40 | 40 | 2023-10-05 | 4:00 | 2023-10-05 | 5:00 | 0d, 1h | Continuous | Track & Rail | T | [10 empty] | 80 | N | 1849-017 |  | 2021-05-05
DB Netz AG | 1849-018 | Falkenberg - Dresden | <> | Priestewitz | Großenh Cott Bf | 2023 | 2023 | 40 | 40 | 2023-10-05 | 4:00 | 2023-10-05 | 5:00 | 0d, 1h | Continuous | Track & Rail | T | [10 empty] | 80 | N | 1849-018 |  | 2021-05-05
DB Netz AG | 1849-020 | Falkenberg - Dresden | < | Niederau | Priestewitz | 2023 | 2023 | 40 | 40 | 2023-10-04 | 21:00 | 2023-10-06 | 5:00 | 1d, 8h | Periodical | Track & Rail |  | LT | [9 empty] | 80 | N | 1849-020 |  | 2021-05-05
DB Netz AG | 1849-021 | Falkenberg - Dresden | < | Niederau | Priestewitz | 2023 | 2023 | 40 | 40 | 2023-10-04 | 21:00 | 2023-10-06 | 5:00 | 1d, 8h | Periodical | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | 1849-021 |  | 2021-05-05
DB Netz AG | 1849-022 | Falkenberg - Dresden | <> | Priestewitz | Niederau | 2023 | 2023 | 40 | 40 | 2023-10-04 | 21:00 | 2023-10-06 | 5:00 | 1d, 8h | Periodical | Track & Rail |  |  |  | P | [7 empty] | 80 | N | 1849-022 |  | 2021-05-05
DB Netz AG | 190A-001 | Rostock - Berlin | < | Langhagen | Grabowhöfe | 2023 | 2023 | 41 | 42 | 2023-10-14 | 22:00 | 2023-10-19 | 6:00 | 4d, 8h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 190A-001 |  | 2021-10-27
DB Netz AG | 1978-020 | Falkenberg - Dresden | <> | Coswig (bei Dre) | Coswig (bei Dre) | 2023 | 2023 | 39 | 39 | 2023-09-25 | 20:00 | 2023-09-25 | 22:30 | 0d, 2h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1978-020 |  | 2021-04-20
DB Netz AG | 1978-022 | Falkenberg - Dresden | <> | Coswig Stw 1 | Coswig (bei Dre) | 2023 | 2023 | 39 | 39 | 2023-09-25 | 22:00 | 2023-09-26 | 5:00 | 0d, 7h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1978-022 |  | 2021-04-20
DB Netz AG | 1978-024 | Falkenberg - Dresden | < | Coswig Stw 1 | Radeb-Naundf Abz | 2023 | 2023 | 39 | 39 | 2023-09-25 | 22:00 | 2023-09-26 | 5:00 | 0d, 7h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1978-024 |  | 2021-04-20
DB Netz AG | 1978-025 | Falkenberg - Dresden | < | Radebeul-Naundf | Radebeul-Naundf | 2023 | 2023 | 39 | 39 | 2023-09-25 | 22:00 | 2023-09-26 | 5:00 | 0d, 7h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1978-025 |  | 2021-04-20
DB Netz AG | 1978-026 | Falkenberg - Dresden | <> | Coswig Stw 1 | Coswig (bei Dre) | 2023 | 2023 | 39 | 39 | 2023-09-25 | 22:00 | 2023-09-26 | 5:00 | 0d, 7h | Continuous | Track & Rail |  |  |  |  | X | [6 empty] | 80 | N | 1978-026 |  | 2021-04-20
DB Netz AG | 1978-027 | Falkenberg - Dresden | <> | Coswig (bei Dre) | Coswig (bei Dre) | 2023 | 2023 | 39 | 39 | 2023-09-26 | 22:00 | 2023-09-27 | 5:00 | 0d, 7h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1978-027 |  | 2021-04-20
DB Netz AG | 19F7-001 | Hamburg - Magdeburg | <> | Lüneburg Gbf | Lüneburg Gbf | 2023 | 2023 | 41 | 41 | 2023-10-09 | 23:00 | 2023-10-10 | 5:00 | 0d, 6h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 19F7-001 |  | 2021-05-14
DB Netz AG | 19F7-002 | Hamburg - Magdeburg | <> | Lüneburg Gbf | Lüneburg Gbf | 2023 | 2023 | 41 | 41 | 2023-10-09 | 23:00 | 2023-10-10 | 5:00 | 0d, 6h | Continuous | Signal |  |  |  |  | X | [6 empty] | 80 | N | 19F7-002 |  | 2021-05-14
DB Netz AG | 1AB4-001 | Bremen - Hannover | > | Neustadt a Rbg | Linsburg | 2023 | 2023 | 39 | 39 | 2023-09-30 | 2:10 | 2023-09-30 | 5:10 | 0d, 3h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 1AB4-001 |  | 2021-09-09
DB Netz AG | 1AB4-002 | Bremen - Hannover | > | Neustadt a Rbg | Linsburg | 2023 | 2023 | 39 | 39 | 2023-09-30 | 23:50 | 2023-10-01 | 5:10 | 0d, 5h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 1AB4-002 |  | 2021-09-09
DB Netz AG | 1AB4-003 | Bremen - Hannover | <> | Neustadt a Rbg | Linsburg | 2023 | 2023 | 39 | 40 | 2023-10-01 | 23:10 | 2023-10-02 | 5:05 | 0d, 5h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | 1AB4-003 |  | 2021-09-09
DB Netz AG | 1AB4-004 | Bremen - Hannover | < | Linsburg | Neustadt a Rbg | 2023 | 2023 | 40 | 41 | 2023-10-06 | 23:15 | 2023-10-09 | 4:10 | 2d, 4h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 1AB4-004 |  | 2021-09-09
DB Netz AG | 1AB4-005 | Bremen - Hannover | <> | Hagen (Han) | Hagen (Han) | 2023 | 2023 | 40 | 40 | 2023-10-02 | 7:00 | 2023-10-05 | 17:00 | 3d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1AB4-005 |  | 2021-09-09
DB Netz AG | 1AB4-006 | Bremen - Hannover | <> | Hagen (Han) | Hagen (Han) | 2023 | 2023 | 41 | 41 | 2023-10-09 | 7:00 | 2023-10-10 | 17:00 | 1d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1AB4-006 |  | 2021-09-09
DB Netz AG | 1B2E-001 | Magdeburg - Falkenberg | < | Niederndodeleben | Niederndodeleben | 2023 | 2023 | 38 | 38 | 2023-09-23 | 22:25 | 2023-09-23 | 23:10 | 0d, 0h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 1B2E-001 |  | 2022-07-13
DB Netz AG | 1B2E-002 | Magdeburg - Falkenberg | < | Wellen | Mg-Sudenburg | 2023 | 2023 | 38 | 38 | 2023-09-23 | 22:25 | 2023-09-23 | 23:10 | 0d, 0h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1B2E-002 |  | 2022-07-13
DB Netz AG | 1B2E-003 | Magdeburg - Falkenberg | < | Wellen | Mg-Sudenburg | 2023 | 2023 | 38 | 38 | 2023-09-23 | 23:10 | 2023-09-24 | 2:50 | 0d, 3h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1B2E-003 |  | 2022-07-13
DB Netz AG | 1B2E-004 | Magdeburg - Falkenberg | <> | Niederndodeleben | Niederndodeleben | 2023 | 2023 | 38 | 38 | 2023-09-23 | 23:10 | 2023-09-24 | 2:50 | 0d, 3h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 1B2E-004 |  | 2022-07-13
DB Netz AG | 1B2E-006 | Magdeburg - Falkenberg | <> | Niederndodeleben | Mg-Sudenburg | 2023 | 2023 | 38 | 38 | 2023-09-24 | 2:50 | 2023-09-24 | 3:45 | 0d, 0h | Continuous | Maintenance | T | [10 empty] | 80 | N | 1B2E-006 |  | 2022-07-13
DB Netz AG | 1B2E-007 | Magdeburg - Falkenberg | < | Wellen | Mg-Sudenburg | 2023 | 2023 | 38 | 38 | 2023-09-24 | 3:45 | 2023-09-24 | 5:35 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1B2E-007 |  | 2022-07-13
DB Netz AG | 1B2E-008 | Magdeburg - Falkenberg | <> | Niederndodeleben | Niederndodeleben | 2023 | 2023 | 38 | 38 | 2023-09-24 | 3:45 | 2023-09-24 | 5:35 | 0d, 1h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 1B2E-008 |  | 2022-07-13
DB Netz AG | 1AC5-032 | Bremen - Hannover | <> | Seelze Ost | Seelze Ost | 2023 | 2023 | 40 | 42 | 2023-10-08 | 20:00 | 2023-10-16 | 6:00 | 7d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1AC5-032 |  | 2021-05-03
DB Netz AG | 1AC5-033 | Bremen - Hannover | <> | Seelze Ost | Seelze Ost | 2023 | 2023 | 40 | 42 | 2023-10-08 | 20:00 | 2023-10-16 | 6:00 | 7d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1AC5-033 |  | 2021-05-03
DB Netz AG | 1B35-001 | Magdeburg - Falkenberg | < | Niederndodeleben | Niederndodeleben | 2023 | 2023 | 38 | 38 | 2023-09-24 | 22:20 | 2023-09-24 | 22:30 | 0d, 0h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 1B35-001 |  | 2022-07-13
DB Netz AG | 1B35-002 | Magdeburg - Falkenberg | < | Wellen | Mg-Sudenburg | 2023 | 2023 | 38 | 39 | 2023-09-24 | 22:30 | 2023-09-25 | 2:50 | 0d, 4h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1B35-002 |  | 2022-07-13
DB Netz AG | 1B35-003 | Magdeburg - Falkenberg | <> | Niederndodeleben | Niederndodeleben | 2023 | 2023 | 38 | 39 | 2023-09-24 | 22:30 | 2023-09-25 | 2:50 | 0d, 4h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 1B35-003 |  | 2022-07-13
DB Netz AG | 1B35-005 | Magdeburg - Falkenberg | <> | Wellen | Niederndodeleben | 2023 | 2023 | 39 | 39 | 2023-09-25 | 2:50 | 2023-09-25 | 3:45 | 0d, 0h | Continuous | Maintenance | T | [10 empty] | 80 | N | 1B35-005 |  | 2022-07-13
DB Netz AG | 1B35-006 | Magdeburg - Falkenberg | < | Wellen | Mg-Sudenburg | 2023 | 2023 | 39 | 39 | 2023-09-25 | 3:45 | 2023-09-25 | 5:30 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1B35-006 |  | 2022-07-13
DB Netz AG | 1B35-007 | Magdeburg - Falkenberg | <> | Niederndodeleben | Niederndodeleben | 2023 | 2023 | 39 | 39 | 2023-09-25 | 3:45 | 2023-09-25 | 5:30 | 0d, 1h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 1B35-007 |  | 2022-07-13
DB Netz AG | 1B43-001 | Bremen - Hannover | <> | Seelze Ost | Seelze Ost | 2023 | 2023 | 41 | 41 | 2023-10-10 | 23:00 | 2023-10-11 | 5:00 | 0d, 6h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 1B43-001 |  | 2022-06-09
DB Netz AG | 1B43-002 | Bremen - Hannover | <> | Seelze Ost | Seelze Ost | 2023 | 2023 | 41 | 41 | 2023-10-11 | 2:00 | 2023-10-11 | 5:00 | 0d, 3h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 1B43-002 |  | 2022-06-09
DB Netz AG | 1B43-003 | Bremen - Hannover | <> | Seelze West | Seelze Ost | 2023 | 2023 | 41 | 42 | 2023-10-11 | 5:00 | 2023-10-17 | 8:00 | 6d, 3h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 1B43-003 |  | 2022-06-09
DB Netz AG | 1B43-004 | Bremen - Hannover | <> | Seelze West | Letter Abzw | 2023 | 2023 | 41 | 42 | 2023-10-12 | 23:00 | 2023-10-16 | 2:00 | 3d, 3h | Continuous | Switch |  |  | S | [8 empty] | 80 | N | 1B43-004 |  | 2022-06-09
DB Netz AG | 1B43-005 | Bremen - Hannover | > | Letter Abzw | Seelze West | 2023 | 2023 | 41 | 41 | 2023-10-12 | 23:00 | 2023-10-13 | 2:00 | 0d, 3h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 1B43-005 |  | 2022-06-09
DB Netz AG | 1B43-006 | Bremen - Hannover | < | Han-Linden Hafen | Seelze West | 2023 | 2023 | 41 | 41 | 2023-10-13 | 20:00 | 2023-10-14 | 2:00 | 0d, 6h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 1B43-006 |  | 2022-06-09
DB Netz AG | 1B43-007 | Bremen - Hannover | <> | Seelze West | Seelze Ost | 2023 | 2023 | 41 | 41 | 2023-10-13 | 20:00 | 2023-10-14 | 2:00 | 0d, 6h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 1B43-007 |  | 2022-06-09
DB Netz AG | 1B43-009 | Bremen - Hannover | < | Seelze Ost | Seelze West | 2023 | 2023 | 41 | 41 | 2023-10-14 | 2:00 | 2023-10-15 | 15:00 | 1d, 13h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 1B43-009 |  | 2022-06-09
DB Netz AG | 1B43-010 | Bremen - Hannover | <> | Seelze Ost | Seelze Ost | 2023 | 2023 | 41 | 42 | 2023-10-14 | 2:00 | 2023-10-17 | 12:00 | 3d, 10h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 1B43-010 |  | 2022-06-09
DB Netz AG | 1B43-011 | Bremen - Hannover | < | Han-Linden Hafen | Seelze West | 2023 | 2023 | 41 | 41 | 2023-10-15 | 15:00 | 2023-10-15 | 18:00 | 0d, 3h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 1B43-011 |  | 2022-06-09
DB Netz AG | 1B43-012 | Bremen - Hannover | < | Seelze West | Letter Abzw | 2023 | 2023 | 41 | 42 | 2023-10-15 | 23:00 | 2023-10-16 | 3:00 | 0d, 4h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 1B43-012 |  | 2022-06-09
DB Netz AG | 1D90-001 | Bremen - Hannover | < | Han-Linden Hafen | Seelze West | 2023 | 2023 | 37 | 40 | 2023-09-17 | 7:00 | 2023-10-08 | 15:00 | 21d, 8h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 1D90-001 |  | 2022-07-19
DB Netz AG | 1D90-002 | Bremen - Hannover | < | Seelze West | Wunstorf | 2023 | 2023 | 37 | 40 | 2023-09-17 | 7:00 | 2023-10-08 | 15:00 | 21d, 8h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 1D90-002 |  | 2022-07-19
DB Netz AG | 1D90-003 | Bremen - Hannover | < | Gümmerwald | Wunstorf | 2023 | 2023 | 37 | 40 | 2023-09-17 | 7:00 | 2023-10-08 | 15:00 | 21d, 8h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 1D90-003 |  | 2022-07-19
DB Netz AG | 1D90-004 | Bremen - Hannover | <> | Seelze West | Seelze Ost | 2023 | 2023 | 37 | 40 | 2023-09-17 | 7:00 | 2023-10-08 | 15:00 | 21d, 8h | Periodical | Catenary |  |  |  | P | [7 empty] | 80 | N | 1D90-004 |  | 2022-07-19
DB Netz AG | 1DCE-001 | Bremerhaven - Bremen | < | Nienburg (Weser) | Hagen (Han) | 2023 | 2023 | 38 | 39 | 2023-09-23 | 23:40 | 2023-09-25 | 5:40 | 1d, 6h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 1DCE-001 |  | 2021-04-06
DB Netz AG | 1DD3-001 | Bremerhaven - Bremen | < | Bremen-Burg | Bremen Hbf | 2023 | 2023 | 37 | 37 | 2023-09-13 | 22:30 | 2023-09-15 | 4:30 | 1d, 6h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 1DD3-001 |  | 2021-04-06
DB Netz AG | 1DD3-002 | Bremerhaven - Bremen | < | Bremen-Burg | Bremen Hbf | 2023 | 2023 | 38 | 38 | 2023-09-18 | 22:30 | 2023-09-21 | 4:30 | 2d, 6h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 1DD3-002 |  | 2021-04-06
DB Netz AG | 1E6C-002 | Berlin - Dresden | > | Doberlug-K ob Bf | Doberlug-K ob Bf | 2023 | 2023 | 39 | 39 | 2023-09-29 | 9:00 | 2023-09-29 | 12:00 | 0d, 3h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 1E6C-002 |  | 2022-07-19
DB Netz AG | 1E6C-003 | Berlin - Dresden | <> | Doberlug-K ob Bf | Doberlug-K untBf | 2023 | 2023 | 39 | 39 | 2023-09-29 | 9:00 | 2023-09-29 | 12:00 | 0d, 3h | Continuous | Signal | T | [10 empty] | 80 | N | 1E6C-003 |  | 2022-07-19
DB Netz AG | 1E6C-004 | Berlin - Dresden | <> | Doberlug-Kh Nord | Rückersdorf NL | 2023 | 2023 | 39 | 39 | 2023-09-29 | 11:00 | 2023-09-29 | 12:00 | 0d, 1h | Continuous | Signal | T | [10 empty] | 80 | N | 1E6C-004 |  | 2022-07-19
DB Netz AG | 1E6C-006 | Berlin - Dresden | <> | Doberlug-K ob Bf | Doberlug-K untBf | 2023 | 2023 | 39 | 39 | 2023-09-29 | 11:00 | 2023-09-29 | 12:00 | 0d, 1h | Continuous | Signal | T | [10 empty] | 80 | N | 1E6C-006 |  | 2022-07-19
DB Netz AG | 1F57-001 | Bremerhaven - Bremen | < | Verden (Aller) | Dörverden | 2023 | 2023 | 37 | 37 | 2023-09-11 | 23:00 | 2023-09-13 | 5:00 | 1d, 6h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 1F57-001 |  | 2021-10-11
DB Netz AG | 1F57-002 | Bremerhaven - Bremen | > | Dörverden | Verden (Aller) | 2023 | 2023 | 39 | 39 | 2023-09-25 | 23:00 | 2023-09-27 | 5:00 | 1d, 6h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 1F57-002 |  | 2021-10-11
DB Netz AG | 1F58-001 | Bremerhaven - Bremen | <> | Bremen-Mahndorf | Bremen-Mahndorf | 2023 | 2023 | 37 | 38 | 2023-09-17 | 23:00 | 2023-09-18 | 5:00 | 0d, 6h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 1F58-001 |  | 2021-04-06
DB Netz AG | 1F58-002 | Bremerhaven - Bremen | < | Brm-Sebaldsbrück | Achim | 2023 | 2023 | 37 | 38 | 2023-09-17 | 23:00 | 2023-09-18 | 5:00 | 0d, 6h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 1F58-002 |  | 2021-04-06
DB Netz AG | 1F98-003 | Wilhelmshaven - Bremen | <> | Veddel | Hmb-Wlb Abzw | 2023 | 2023 | 36 | 37 | 2023-09-10 | 23:00 | 2023-09-11 | 5:00 | 0d, 6h | Continuous | Switch | T | [10 empty] | 80 | N | 1F98-003 |  | 2021-04-28
DB Netz AG | 1FFB-001 | Wilhelmshaven - Bremen | <> | Delmenhorst | Wildeshausen | 2023 | 2023 | 37 | 38 | 2023-09-16 | 1:30 | 2023-09-18 | 4:30 | 2d, 3h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | 1FFB-001 |  | 2021-05-04
DB Netz AG | 2093-001 | Wilhelmshaven - Bremen | < | Delmenhorst | Bookholzberg | 2023 | 2023 | 37 | 38 | 2023-09-17 | 22:10 | 2023-09-22 | 5:00 | 4d, 6h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 2093-001
DB Netz AG | 2065-001 | Bremerhaven - Bremen | <> | Etelsen | Etelsen | 2023 | 2023 | 41 | 41 | 2023-10-10 | 8:00 | 2023-10-10 | 14:30 | 0d, 6h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 2065-001 |  | 2021-04-06
DB Netz AG | 208D-014 | Rostock - Berlin | <> | Ro Seehf Süd | Ro Seehf Süd | 2023 | 2023 | 36 | 37 | 2023-09-10 | 8:00 | 2023-09-13 | 18:00 | 3d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 208D-014
DB Netz AG | 208D-015 | Rostock - Berlin | <> | Ro Seehf Süd | Ro Seehf Süd | 2023 | 2023 | 36 | 37 | 2023-09-10 | 8:00 | 2023-09-13 | 18:00 | 3d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 208D-015
DB Netz AG | 20A5-001 | Rostock - Berlin | <> | Ro Seehf Süd | Rostock Seehafen | 2023 | 2023 | 37 | 37 | 2023-09-14 | 8:00 | 2023-09-16 | 18:00 | 2d, 10h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | 20A5-001
DB Netz AG | 20A5-002 | Rostock - Berlin | <> | Ro Seehf Süd | Rostock Seehafen | 2023 | 2023 | 37 | 37 | 2023-09-14 | 8:00 | 2023-09-16 | 18:00 | 2d, 10h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | 20A5-002
DB Netz AG | 20A5-003 | Rostock - Berlin | <> | Ro Seehf Süd | Rostock Seehafen | 2023 | 2023 | 37 | 37 | 2023-09-14 | 8:00 | 2023-09-16 | 18:00 | 2d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 20A5-003
DB Netz AG | 20A5-004 | Rostock - Berlin | <> | Rostock Seehafen | Rostock Seehafen | 2023 | 2023 | 37 | 38 | 2023-09-17 | 8:00 | 2023-09-19 | 18:00 | 2d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 20A5-004
DB Netz AG | 20A5-005 | Rostock - Berlin | <> | Ro Seehf Süd | Rostock Seehafen | 2023 | 2023 | 38 | 38 | 2023-09-20 | 8:00 | 2023-09-22 | 18:00 | 2d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 20A5-005
DB Netz AG | 20A5-006 | Rostock - Berlin | <> | Rostock Seehafen | Rostock Seehafen | 2023 | 2023 | 38 | 38 | 2023-09-20 | 8:00 | 2023-09-22 | 18:00 | 2d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 20A5-006
DB Netz AG | 20A5-007 | Rostock - Berlin | <> | Ro Seehf Süd | Rostock Seehafen | 2023 | 2023 | 38 | 38 | 2023-09-23 | 8:00 | 2023-09-23 | 18:00 | 0d, 10h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | 20A5-007
DB Netz AG | 20A5-008 | Rostock - Berlin | <> | Ro Seehf Süd | Ro Seehf Süd | 2023 | 2023 | 38 | 38 | 2023-09-23 | 8:00 | 2023-09-23 | 18:00 | 0d, 10h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 20A5-008
DB Netz AG | 20A5-009 | Rostock - Berlin | <> | Rostock Seehafen | Rostock Seehafen | 2023 | 2023 | 38 | 38 | 2023-09-23 | 8:01 | 2023-09-23 | 18:00 | 0d, 9h | Continuous | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 20A5-009
DB Netz AG | 20A5-010 | Rostock - Berlin | <> | Kavelstorf | Ro Seehf Süd | 2023 | 2023 | 38 | 39 | 2023-09-24 | 8:00 | 2023-09-26 | 18:00 | 2d, 10h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | 20A5-010
DB Netz AG | 20A5-011 | Rostock - Berlin | <> | Kavelstorf | Rostock Seehafen | 2023 | 2023 | 39 | 39 | 2023-09-27 | 8:00 | 2023-09-29 | 18:00 | 2d, 10h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | 20A5-011
DB Netz AG | 20A5-012 | Rostock - Berlin | <> | Riekdahl | Ro Seehf Süd | 2023 | 2023 | 39 | 39 | 2023-09-27 | 8:00 | 2023-09-29 | 18:00 | 2d, 10h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | 20A5-012
DB Netz AG | 20A5-013 | Rostock - Berlin | <> | Ro Seehf Süd | Ro Seehf Süd | 2023 | 2023 | 39 | 39 | 2023-09-27 | 8:00 | 2023-09-29 | 18:00 | 2d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 20A5-013
DB Netz AG | 2114-001 | Rostock - Berlin | <> | Bentwisch | Ro Seehf Süd | 2023 | 2023 | 39 | 40 | 2023-09-30 | 7:00 | 2023-10-07 | 17:00 | 7d, 10h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | 2114-001
DB Netz AG | 2114-002 | Rostock - Berlin | <> | Ro Seehf Süd | Ro Seehf Süd | 2023 | 2023 | 39 | 40 | 2023-09-30 | 7:00 | 2023-10-07 | 17:00 | 7d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 2114-002
DB Netz AG | 2114-003 | Rostock - Berlin | <> | Bentwisch | Ro Seehf Süd | 2023 | 2023 | 40 | 41 | 2023-10-08 | 7:00 | 2023-10-10 | 17:00 | 2d, 10h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | 2114-003
DB Netz AG | 2114-004 | Rostock - Berlin | <> | Ro Seehf Süd | Ro Seehf Süd | 2023 | 2023 | 40 | 41 | 2023-10-08 | 7:00 | 2023-10-10 | 17:00 | 2d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 2114-004
DB Netz AG | 2114-005 | Rostock - Berlin | <> | Ro Seehf Süd | Ro Seehf Süd | 2023 | 2023 | 40 | 41 | 2023-10-08 | 7:00 | 2023-10-10 | 17:00 | 2d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 2114-005
DB Netz AG | 2114-006 | Rostock - Berlin | <> | Ro Seehf Süd | Ro Seehf Süd | 2023 | 2023 | 40 | 41 | 2023-10-08 | 7:00 | 2023-10-10 | 17:00 | 2d, 10h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 2114-006
DB Netz AG | 2114-007 | Rostock - Berlin | <> | Kavelstorf | Ro Seehf Süd | 2023 | 2023 | 40 | 41 | 2023-10-08 | 7:00 | 2023-10-10 | 17:00 | 2d, 10h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | 2114-007
DB Netz AG | 20BF-001 | Rostock - Berlin | > | Nassenheide | Löwenberg (Mark) | 2023 | 2023 | 37 | 37 | 2023-09-12 | 1:00 | 2023-09-12 | 5:00 | 0d, 4h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 20BF-001
DB Netz AG | 20BF-002 | Rostock - Berlin | > | Oranienburg | Löwenberg (Mark) | 2023 | 2023 | 37 | 37 | 2023-09-11 | 21:00 | 2023-09-12 | 1:00 | 0d, 4h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 20BF-002
DB Netz AG | 20BF-003 | Rostock - Berlin | <> | Nassenheide | Nassenheide | 2023 | 2023 | 37 | 37 | 2023-09-11 | 21:00 | 2023-09-12 | 1:00 | 0d, 4h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 20BF-003
DB Netz AG | 20BF-004 | Rostock - Berlin | > | Nassenheide | Löwenberg (Mark) | 2023 | 2023 | 37 | 37 | 2023-09-12 | 1:00 | 2023-09-12 | 5:00 | 0d, 4h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 20BF-004
DB Netz AG | 2114-008 | Rostock - Berlin | <> | Ro Seehf Süd | Ro Seehf Süd | 2023 | 2023 | 41 | 41 | 2023-10-11 | 7:00 | 2023-10-13 | 17:00 | 2d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 2114-008
DB Netz AG | 2114-009 | Rostock - Berlin | <> | Ro Seehf Süd | Ro Seehf Süd | 2023 | 2023 | 41 | 41 | 2023-10-11 | 7:00 | 2023-10-13 | 17:00 | 2d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 2114-009
DB Netz AG | 20BF-005 | Rostock - Berlin | <> | Löwenberg (Mark) | Löwenberg (Mark) | 2023 | 2023 | 37 | 37 | 2023-09-12 | 1:00 | 2023-09-12 | 5:00 | 0d, 4h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 20BF-005
DB Netz AG | 20BF-006 | Rostock - Berlin | <> | Nassenheide | Löwenberg (Mark) | 2023 | 2023 | 37 | 37 | 2023-09-11 | 21:00 | 2023-09-12 | 5:00 | 0d, 8h | Continuous | Track & Rail |  |  | S | [8 empty] | 80 | N | 20BF-006
DB Netz AG | 2114-010 | Rostock - Berlin | <> | Ro Seehf Süd | Ro Seehf Süd | 2023 | 2023 | 41 | 41 | 2023-10-14 | 7:00 | 2023-10-15 | 17:00 | 1d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 2114-010
DB Netz AG | 2114-011 | Rostock - Berlin | <> | Ro Seehf Süd | Ro Seehf Süd | 2023 | 2023 | 41 | 41 | 2023-10-14 | 7:01 | 2023-10-15 | 17:00 | 1d, 9h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 2114-011
DB Netz AG | 221B-001 | Berlin - Dresden | < | Hohenleipisch | Brenitz-Sonnew | 2023 | 2023 | 36 | 37 | 2023-09-10 | 22:00 | 2023-09-11 | 1:15 | 0d, 3h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 221B-001 |  | 2021-07-12
DB Netz AG | 221B-002 | Berlin - Dresden | <> | Walddrehna | Hohenleipisch | 2023 | 2023 | 36 | 37 | 2023-09-10 | 22:00 | 2023-09-11 | 5:00 | 0d, 7h | Continuous | Maintenance |  |  | S | [8 empty] | 80 | N | 221B-002 |  | 2021-07-12
DB Netz AG | 221B-003 | Berlin - Dresden | <> | Walddrehna | Hohenleipisch | 2023 | 2023 | 36 | 37 | 2023-09-10 | 22:00 | 2023-09-11 | 5:00 | 0d, 7h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 221B-003 |  | 2021-07-12
DB Netz AG | 221B-004 | Berlin - Dresden | < | Doberlug-K ob Bf | Walddrehna | 2023 | 2023 | 37 | 37 | 2023-09-11 | 1:15 | 2023-09-11 | 3:45 | 0d, 2h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 221B-004 |  | 2021-07-12
DB Netz AG | 221B-005 | Berlin - Dresden | < | Doberlug-Kh Nord | Walddrehna | 2023 | 2023 | 37 | 37 | 2023-09-11 | 3:45 | 2023-09-11 | 5:00 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 221B-005 |  | 2021-07-12
DB Netz AG | 222F-001 | Berlin - Dresden | < | Brenitz-Sonnew | Walddrehna | 2023 | 2023 | 37 | 37 | 2023-09-11 | 22:00 | 2023-09-11 | 23:59 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 222F-001 |  | 2021-07-12
DB Netz AG | 222F-002 | Berlin - Dresden | <> | Luckau-Uckro | Brenitz-Sonnew | 2023 | 2023 | 37 | 37 | 2023-09-11 | 22:00 | 2023-09-12 | 5:00 | 0d, 7h | Continuous | Maintenance |  |  | S | [8 empty] | 80 | N | 222F-002 |  | 2021-07-12
DB Netz AG | 222F-003 | Berlin - Dresden | <> | Luckau-Uckro | Brenitz-Sonnew | 2023 | 2023 | 37 | 37 | 2023-09-11 | 22:00 | 2023-09-12 | 5:00 | 0d, 7h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 222F-003 |  | 2021-07-12
DB Netz AG | 222F-004 | Berlin - Dresden | < | Brenitz-Sonnew | Luckau-Uckro | 2023 | 2023 | 37 | 37 | 2023-09-11 | 23:59 | 2023-09-12 | 3:30 | 0d, 3h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 222F-004 |  | 2021-07-12
DB Netz AG | 222F-005 | Berlin - Dresden | < | Walddrehna | Golßen NL | 2023 | 2023 | 37 | 37 | 2023-09-12 | 3:30 | 2023-09-12 | 5:00 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 222F-005 |  | 2021-07-12
DB Netz AG | 222F-006 | Berlin - Dresden | < | Luckau-Uckro | Luckau-Uckro | 2023 | 2023 | 37 | 37 | 2023-09-12 | 3:30 | 2023-09-12 | 5:00 | 0d, 1h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 222F-006 |  | 2021-07-12
DB Netz AG | 2231-001 | Berlin - Dresden | <> | Luckau-Uckro | Baruth (Mark) | 2023 | 2023 | 37 | 37 | 2023-09-12 | 22:00 | 2023-09-13 | 5:00 | 0d, 7h | Continuous | Maintenance |  |  | S | [8 empty] | 80 | N | 2231-001 |  | 2021-06-04
DB Netz AG | 2231-002 | Berlin - Dresden | <> | Luckau-Uckro | Baruth (Mark) | 2023 | 2023 | 37 | 37 | 2023-09-12 | 22:00 | 2023-09-13 | 5:00 | 0d, 7h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 2231-002 |  | 2021-06-04
DB Netz AG | 2231-003 | Berlin - Dresden | < | Walddrehna | Golßen NL | 2023 | 2023 | 37 | 37 | 2023-09-12 | 22:00 | 2023-09-12 | 23:15 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 2231-003 |  | 2021-06-04
DB Netz AG | 2231-004 | Berlin - Dresden | < | Luckau-Uckro | Golßen NL | 2023 | 2023 | 37 | 37 | 2023-09-12 | 23:15 | 2023-09-13 | 3:15 | 0d, 4h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 2231-004 |  | 2021-06-04
DB Netz AG | 2231-005 | Berlin - Dresden | < | Luckau-Uckro | Baruth (Mark) | 2023 | 2023 | 37 | 37 | 2023-09-13 | 3:15 | 2023-09-13 | 5:00 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 2231-005 |  | 2021-06-04
DB Netz AG | 2233-001 | Berlin - Dresden | < | Golßen NL | Wünsdorf-Waldst | 2023 | 2023 | 37 | 37 | 2023-09-13 | 22:00 | 2023-09-13 | 23:59 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 2233-001 |  | 2021-06-04
DB Netz AG | 2233-002 | Berlin - Dresden | <> | Wünsdorf-Waldst | Golßen NL | 2023 | 2023 | 37 | 37 | 2023-09-13 | 22:00 | 2023-09-14 | 5:15 | 0d, 7h | Continuous | Maintenance |  |  | S | [8 empty] | 80 | N | 2233-002 |  | 2021-06-04
DB Netz AG | 2233-003 | Berlin - Dresden | <> | Zossen | Golßen NL | 2023 | 2023 | 37 | 37 | 2023-09-13 | 22:00 | 2023-09-14 | 5:15 | 0d, 7h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 2233-003 |  | 2021-06-04
DB Netz AG | 2233-004 | Berlin - Dresden | < | Baruth (Mark) | Wünsdorf-Waldst | 2023 | 2023 | 37 | 37 | 2023-09-13 | 23:59 | 2023-09-14 | 4:00 | 0d, 4h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 2233-004 |  | 2021-06-04
DB Netz AG | 2233-005 | Berlin - Dresden | < | Zossen | Baruth (Mark) | 2023 | 2023 | 37 | 37 | 2023-09-14 | 4:00 | 2023-09-14 | 5:15 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 2233-005 |  | 2021-06-04
DB Netz AG | 2236-001 | Berlin - Dresden | <> | Rangsdorf | Wünsdorf-Waldst | 2023 | 2023 | 37 | 37 | 2023-09-14 | 22:00 | 2023-09-15 | 4:30 | 0d, 6h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 2236-001 |  | 2021-06-04
DB Netz AG | 2236-002 | Berlin - Dresden | < | Wünsdorf-Waldst | Zossen | 2023 | 2023 | 37 | 37 | 2023-09-14 | 22:00 | 2023-09-14 | 23:30 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 2236-002 |  | 2021-06-04
DB Netz AG | 2236-003 | Berlin - Dresden | < | Zossen | Zossen | 2023 | 2023 | 37 | 37 | 2023-09-14 | 22:00 | 2023-09-14 | 23:30 | 0d, 1h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 2236-003 |  | 2021-06-04
DB Netz AG | 2236-004 | Berlin - Dresden | < | Zossen | Rangsdorf | 2023 | 2023 | 37 | 37 | 2023-09-14 | 23:30 | 2023-09-15 | 2:30 | 0d, 3h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 2236-004 |  | 2021-06-04
DB Netz AG | 2236-005 | Berlin - Dresden | < | Zossen | Zossen | 2023 | 2023 | 37 | 37 | 2023-09-14 | 23:30 | 2023-09-15 | 2:30 | 0d, 3h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 2236-005 |  | 2021-06-04
DB Netz AG | 2236-006 | Berlin - Dresden | < | Rangsdorf | Glasow Damm Süd | 2023 | 2023 | 37 | 37 | 2023-09-15 | 2:30 | 2023-09-15 | 4:30 | 0d, 2h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 2236-006 |  | 2021-06-04
DB Netz AG | 2236-007 | Berlin - Dresden | <> | Zossen DB-Grenze | Zossen (Zoa) | 2023 | 2023 | 37 | 37 | 2023-09-14 | 23:30 | 2023-09-15 | 2:30 | 0d, 3h | Continuous | Maintenance | T | [10 empty] | 80 | N | 2236-007 |  | 2021-06-04
DB Netz AG | 2236-008 | Rostock - Berlin | < | Glasow Damm Süd | Glasow Damm Ost | 2023 | 2023 | 37 | 37 | 2023-09-15 | 2:30 | 2023-09-15 | 4:30 | 0d, 2h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 2236-008 |  | 2021-06-04
DB Netz AG | 190A-006 | Rostock - Berlin | < | Vollrathsruhe | Vollrathsruhe | 2023 | 2023 | 41 | 42 | 2023-10-14 | 22:00 | 2023-10-19 | 6:00 | 4d, 8h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 190A-006 |  | 2022-07-20
DB Netz AG | 190A-007 | Rostock - Berlin | < | Langhagen | Langhagen | 2023 | 2023 | 41 | 42 | 2023-10-14 | 22:00 | 2023-10-19 | 6:00 | 4d, 8h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 190A-007 |  | 2022-07-20
DB Netz AG | 22D3-001 | Rostock - Berlin | > | Nassenheide | Gransee | 2023 | 2023 | 37 | 37 | 2023-09-12 | 21:00 | 2023-09-13 | 1:00 | 0d, 4h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 22D3-001
DB Netz AG | 22D3-002 | Rostock - Berlin | <> | Löwenberg (Mark) | Löwenberg (Mark) | 2023 | 2023 | 37 | 37 | 2023-09-12 | 21:00 | 2023-09-13 | 1:00 | 0d, 4h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 22D3-002
DB Netz AG | 22D3-003 | Rostock - Berlin | > | Löwenberg (Mark) | Seilershof | 2023 | 2023 | 37 | 37 | 2023-09-13 | 1:00 | 2023-09-13 | 5:00 | 0d, 4h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 22D3-003
DB Netz AG | 22D3-004 | Rostock - Berlin | > | Gransee | Gransee | 2023 | 2023 | 37 | 37 | 2023-09-13 | 1:00 | 2023-09-13 | 5:00 | 0d, 4h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 22D3-004
DB Netz AG | 22D3-005 | Rostock - Berlin | <> | Löwenberg (Mark) | Gransee | 2023 | 2023 | 37 | 37 | 2023-09-12 | 21:00 | 2023-09-13 | 5:00 | 0d, 8h | Continuous | Track & Rail |  |  | S | [8 empty] | 80 | N | 22D3-005
DB Netz AG | 22DF-001 | Rostock - Berlin | > | Löwenberg (Mark) | Seilershof | 2023 | 2023 | 37 | 37 | 2023-09-13 | 21:00 | 2023-09-14 | 2:00 | 0d, 5h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 22DF-001
DB Netz AG | 22DF-002 | Rostock - Berlin | <> | Gransee | Gransee | 2023 | 2023 | 37 | 37 | 2023-09-13 | 21:00 | 2023-09-14 | 2:00 | 0d, 5h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 22DF-002
DB Netz AG | 22DF-003 | Rostock - Berlin | <> | Löwenberg (Mark) | Gransee | 2023 | 2023 | 37 | 37 | 2023-09-14 | 2:00 | 2023-09-14 | 5:00 | 0d, 3h | Continuous | Switch | T | [10 empty] | 80 | N | 22DF-003
DB Netz AG | 22F8-001 | Rostock - Berlin | > | Löwenberg (Mark) | Seilershof | 2023 | 2023 | 37 | 37 | 2023-09-14 | 21:00 | 2023-09-15 | 2:00 | 0d, 5h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 22F8-001
DB Netz AG | 22F8-002 | Rostock - Berlin | <> | Gransee | Gransee | 2023 | 2023 | 37 | 37 | 2023-09-14 | 21:00 | 2023-09-15 | 2:00 | 0d, 5h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 22F8-002
DB Netz AG | 22F8-003 | Rostock - Berlin | <> | Löwenberg (Mark) | Fürstenberg(H) | 2023 | 2023 | 37 | 37 | 2023-09-15 | 2:00 | 2023-09-15 | 5:00 | 0d, 3h | Continuous | Switch | T | [10 empty] | 80 | N | 22F8-003
DB Netz AG | 22FD-001 | Rostock - Berlin | > | Gransee | Fürstenberg(H) | 2023 | 2023 | 37 | 37 | 2023-09-15 | 20:30 | 2023-09-15 | 23:30 | 0d, 3h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 22FD-001
DB Netz AG | 22FD-002 | Rostock - Berlin | <> | Seilershof | Seilershof | 2023 | 2023 | 37 | 37 | 2023-09-15 | 20:30 | 2023-09-15 | 23:30 | 0d, 3h | Continuous | Switch |  |  | S | [8 empty] | 80 | N | 22FD-002
DB Netz AG | 22FD-003 | Rostock - Berlin | < | Fürstenberg(H) | Gransee | 2023 | 2023 | 37 | 37 | 2023-09-15 | 23:30 | 2023-09-16 | 2:30 | 0d, 3h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 22FD-003
DB Netz AG | 22FD-004 | Rostock - Berlin | < | Fürstenberg(H) | Fürstenberg(H) | 2023 | 2023 | 37 | 37 | 2023-09-15 | 23:30 | 2023-09-16 | 2:30 | 0d, 3h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 22FD-004
DB Netz AG | 22FD-005 | Rostock - Berlin | <> | Gransee | Gransee | 2023 | 2023 | 37 | 37 | 2023-09-15 | 23:30 | 2023-09-16 | 2:30 | 0d, 3h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 22FD-005
DB Netz AG | 22FD-006 | Rostock - Berlin | <> | Seilershof | Seilershof | 2023 | 2023 | 37 | 37 | 2023-09-15 | 23:30 | 2023-09-16 | 2:30 | 0d, 3h | Continuous | Switch |  |  | S | [8 empty] | 80 | N | 22FD-006
DB Netz AG | 22FD-007 | Rostock - Berlin | <> | Gransee | Fürstenberg(H) | 2023 | 2023 | 37 | 37 | 2023-09-16 | 2:30 | 2023-09-16 | 5:20 | 0d, 2h | Continuous | Switch | T | [10 empty] | 80 | N | 22FD-007
DB Netz AG | 2348-002 | Rostock - Berlin | > | Gransee | Fürstenberg(H) | 2023 | 2023 | 38 | 38 | 2023-09-18 | 21:00 | 2023-09-19 | 5:00 | 0d, 8h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 2348-002
DB Netz AG | 2348-003 | Rostock - Berlin | <> | Gransee | Seilershof | 2023 | 2023 | 38 | 38 | 2023-09-18 | 21:00 | 2023-09-19 | 5:00 | 0d, 8h | Continuous | Track & Rail |  |  | S | [8 empty] | 80 | N | 2348-003
DB Netz AG | 2348-004 | Rostock - Berlin | > | Gransee | Fürstenberg(H) | 2023 | 2023 | 38 | 38 | 2023-09-19 | 21:00 | 2023-09-20 | 5:00 | 0d, 8h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 2348-004
DB Netz AG | 2348-005 | Rostock - Berlin | <> | Gransee | Fürstenberg(H) | 2023 | 2023 | 38 | 38 | 2023-09-19 | 21:00 | 2023-09-20 | 5:00 | 0d, 8h | Continuous | Track & Rail |  |  | S | [8 empty] | 80 | N | 2348-005
DB Netz AG | 235A-001 | Rostock - Berlin | > | Seilershof | Drewin | 2023 | 2023 | 38 | 38 | 2023-09-21 | 21:00 | 2023-09-22 | 2:00 | 0d, 5h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 235A-001
DB Netz AG | 235A-002 | Rostock - Berlin | > | Fürstenberg(H) | Fürstenberg(H) | 2023 | 2023 | 38 | 38 | 2023-09-21 | 21:00 | 2023-09-22 | 2:00 | 0d, 5h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 235A-002
DB Netz AG | 235A-003 | Rostock - Berlin | <> | Fürstenberg(H) | Neustrelitz Hbf | 2023 | 2023 | 38 | 38 | 2023-09-22 | 2:00 | 2023-09-22 | 5:00 | 0d, 3h | Continuous | Switch | T | [10 empty] | 80 | N | 235A-003
DB Netz AG | 235A-004 | Rostock - Berlin | <> | Fürstenberg(H) | Fürstenberg(H) | 2023 | 2023 | 38 | 38 | 2023-09-22 | 2:00 | 2023-09-22 | 5:00 | 0d, 3h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 235A-004
DB Netz AG | 235B-001 | Rostock - Berlin | > | Fürstenberg(H) | Neustrelitz Hbf | 2023 | 2023 | 38 | 38 | 2023-09-22 | 21:00 | 2023-09-23 | 0:00 | 0d, 3h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 235B-001
DB Netz AG | 235B-002 | Rostock - Berlin | <> | Drewin | Neustrelitz Hbf | 2023 | 2023 | 38 | 38 | 2023-09-22 | 21:00 | 2023-09-23 | 0:00 | 0d, 3h | Continuous | Switch |  |  | S | [8 empty] | 80 | N | 235B-002
DB Netz AG | 235B-003 | Rostock - Berlin | < | Fürstenberg(H) | Neustrelitz Hbf | 2023 | 2023 | 38 | 38 | 2023-09-23 | 0:00 | 2023-09-23 | 3:00 | 0d, 3h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 235B-003
DB Netz AG | 235B-004 | Rostock - Berlin | < | Fürstenberg(H) | Fürstenberg(H) | 2023 | 2023 | 38 | 38 | 2023-09-23 | 0:00 | 2023-09-23 | 3:00 | 0d, 3h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 235B-004
DB Netz AG | 235B-005 | Rostock - Berlin | <> | Neustrelitz Hbf | Drewin | 2023 | 2023 | 38 | 38 | 2023-09-23 | 0:00 | 2023-09-23 | 3:00 | 0d, 3h | Continuous | Switch |  |  | S | [8 empty] | 80 | N | 235B-005
DB Netz AG | 235B-006 | Rostock - Berlin | <> | Fürstenberg(H) | Neustrelitz Hbf | 2023 | 2023 | 38 | 38 | 2023-09-23 | 3:00 | 2023-09-23 | 5:00 | 0d, 2h | Continuous | Switch | T | [10 empty] | 80 | N | 235B-006
DB Netz AG | 2361-001 | Rostock - Berlin | > | Fürstenberg(H) | Neustrelitz Hbf | 2023 | 2023 | 39 | 39 | 2023-09-25 | 21:00 | 2023-09-26 | 5:00 | 0d, 8h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 2361-001
DB Netz AG | 2361-002 | Rostock - Berlin | <> | Fürstenberg(H) | Neustrelitz Hbf | 2023 | 2023 | 39 | 39 | 2023-09-25 | 21:00 | 2023-09-26 | 5:00 | 0d, 8h | Continuous | Track & Rail |  |  | S | [8 empty] | 80 | N | 2361-002
DB Netz AG | 2363-001 | Rostock - Berlin | > | Drewin | Neustrelitz Hbf | 2023 | 2023 | 39 | 39 | 2023-09-26 | 20:30 | 2023-09-26 | 23:30 | 0d, 3h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 2363-001
DB Netz AG | 2363-002 | Rostock - Berlin | > | Neustrelitz Hbf | Neustrelitz Hbf | 2023 | 2023 | 39 | 39 | 2023-09-26 | 20:30 | 2023-09-26 | 23:30 | 0d, 3h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 2363-002
DB Netz AG | 2363-004 | Rostock - Berlin | <> | Bürgerhorst | Neustrelitz Hbf | 2023 | 2023 | 39 | 39 | 2023-09-26 | 20:30 | 2023-09-26 | 23:30 | 0d, 3h | Continuous | Switch | T | [10 empty] | 80 | N | 2363-004
DB Netz AG | 2363-005 | Rostock - Berlin | <> | Drewin | Neustrelitz Hbf | 2023 | 2023 | 39 | 39 | 2023-09-26 | 20:30 | 2023-09-26 | 23:30 | 0d, 3h | Continuous | Switch |  |  |  |  | X | [6 empty] | 80 | N | 2363-005
DB Netz AG | 2363-006 | Rostock - Berlin | < | Drewin | Neustrelitz Hbf | 2023 | 2023 | 39 | 39 | 2023-09-26 | 23:30 | 2023-09-27 | 2:30 | 0d, 3h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 2363-006
DB Netz AG | 2363-007 | Rostock - Berlin | < | Neustrelitz Hbf | Neustrelitz Hbf | 2023 | 2023 | 39 | 39 | 2023-09-26 | 23:30 | 2023-09-27 | 2:30 | 0d, 3h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 2363-007
DB Netz AG | 2363-008 | Rostock - Berlin | <> | Drewin | Neustrelitz Hbf | 2023 | 2023 | 39 | 39 | 2023-09-27 | 2:30 | 2023-09-27 | 5:30 | 0d, 3h | Continuous | Switch | T | [10 empty] | 80 | N | 2363-008
DB Netz AG | 2363-009 | Rostock - Berlin | <> | Drewin | Neustrelitz Hbf | 2023 | 2023 | 39 | 39 | 2023-09-27 | 2:30 | 2023-09-27 | 5:30 | 0d, 3h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 2363-009
DB Netz AG | 22DF-005 | Rostock - Berlin | <> | Löwenberg (Mark) | Gransee | 2023 | 2023 | 37 | 37 | 2023-09-14 | 2:00 | 2023-09-14 | 5:00 | 0d, 3h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 22DF-005
DB Netz AG | A4C-001 | Hannover - Magdeburg | <> | Magdeburg-Buckau | Mg-Sudenburg | 2023 | 2023 | 43 | 43 | 2023-10-23 | 8:00 | 2023-10-27 | 16:00 | 4d, 8h | Periodical | Catenary | T | [10 empty] | 80 | N | A4C-001 |  | 2021-06-01
DB Netz AG | A4C-004 | Hannover - Magdeburg | < | Magdeburg Hbf | Magdeburg-Buckau | 2023 | 2023 | 43 | 43 | 2023-10-23 | 8:00 | 2023-10-27 | 16:00 | 4d, 8h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | A4C-004 |  | 2021-05-18
DB Netz AG | AF1-003 | Hannover - Magdeburg | < | Lüneburg Nordk | Lüneburg Gbf | 2023 | 2023 | 43 | 43 | 2023-10-23 | 22:40 | 2023-10-28 | 5:15 | 4d, 6h | Periodical | Signal |  | ST | [9 empty] | 80 | N | AF1-003 |  | 2021-05-07
DB Netz AG | AF1-004 | Hannover - Magdeburg | <> | Lüneburg Gbf | Lüneburg Gbf | 2023 | 2023 | 43 | 43 | 2023-10-23 | 22:40 | 2023-10-28 | 5:15 | 4d, 6h | Periodical | Signal |  | ST | [9 empty] | 80 | N | AF1-004 |  | 2021-05-07
DB Netz AG | AF1-002 | Hannover - Magdeburg | <> | Lüneburg Gbf | Lüneburg Gbf | 2023 | 2023 | 43 | 43 | 2023-10-23 | 22:40 | 2023-10-28 | 5:15 | 4d, 6h | Periodical | Signal |  | ST | [9 empty] | 80 | N | AF1-002 |  | 2021-05-07
DB Netz AG | BC2-005 | Hannover - Magdeburg | <> | Magdeburg-Buckau | Mg-Sudenburg | 2023 | 2023 | 44 | 44 | 2023-10-30 | 8:00 | 2023-11-02 | 16:00 | 3d, 8h | Periodical | Catenary | T | [10 empty] | 80 | N | BC2-005 |  | 2021-06-02
DB Netz AG | BC2-003 | Hannover - Magdeburg | < | Magdeburg Hbf | Magdeburg-Buckau | 2023 | 2023 | 44 | 44 | 2023-10-30 | 8:00 | 2023-11-02 | 16:00 | 3d, 8h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | BC2-003 |  | 2021-06-02
DB Netz AG | BD0-013 | Bremerhaven - Bremen | > | Bremen-Burg | Osterholz-Scharm | 2023 | 2023 | 42 | 42 | 2023-10-16 | 23:00 | 2023-10-19 | 5:00 | 2d, 6h | Periodical | Signal |  | LT | [9 empty] | 80 | N | BD0-013 |  | 2021-05-26
DB Netz AG | BD0-001 | Bremerhaven - Bremen | < | Osterholz-Scharm | Bremen-Burg | 2023 | 2023 | 42 | 42 | 2023-10-19 | 23:00 | 2023-10-20 | 5:00 | 0d, 6h | Continuous | Signal |  | LT | [9 empty] | 80 | N | BD0-001 |  | 2021-05-26
DB Netz AG | BD0-023 | Bremerhaven - Bremen | <> | Bremen-Burg | Osterholz-Scharm | 2023 | 2023 | 42 | 42 | 2023-10-19 | 23:00 | 2023-10-20 | 5:00 | 0d, 6h | Continuous | Signal |  |  | S | [8 empty] | 80 | N | BD0-023 |  | 2021-07-21
DB Netz AG | BD0-011 | Bremerhaven - Bremen | > | Bremen-Burg | Osterholz-Scharm | 2023 | 2023 | 42 | 46 | 2023-10-20 | 23:00 | 2023-11-14 | 5:00 | 24d, 7h | Periodical | Signal |  | LT | [9 empty] | 80 | N | BD0-011 |  | 2021-05-26
DB Netz AG | BD0-004 | Bremerhaven - Bremen | <> | Osterholz-Scharm | Bremen-Burg | 2023 | 2023 | 42 | 42 | 2023-10-16 | 23:00 | 2023-10-19 | 5:00 | 2d, 6h | Periodical | Signal |  |  | S | [8 empty] | 80 | N | BD0-004 |  | 2021-05-26
DB Netz AG | BD0-009 | Bremerhaven - Bremen | <> | Osterholz-Scharm | Bremen-Burg | 2023 | 2023 | 42 | 46 | 2023-10-20 | 23:00 | 2023-11-14 | 5:00 | 24d, 7h | Periodical | Signal |  |  | S | [8 empty] | 80 | N | BD0-009 |  | 2021-07-21
DB Netz AG | C0B-005 | Hamburg - Magdeburg | > | Magdeburg-Buckau | Magdeburg Hbf | 2023 | 2023 | 42 | 42 | 2023-10-20 | 8:00 | 2023-10-20 | 16:00 | 0d, 8h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | C0B-005 |  | 2021-06-01
DB Netz AG | C4E-003 | Hamburg - Magdeburg | > | Magdeburg-Buckau | Magdeburg Hbf | 2023 | 2023 | 42 | 42 | 2023-10-20 | 8:00 | 2023-10-20 | 16:00 | 0d, 8h | Continuous | Catenary |  | LT | [9 empty] | 80 | N | C4E-003 |  | 2021-05-18
DB Netz AG | C7D-005 | Dresden - Děčín | <> | Pirna | Dürrröhrsdorf | 2023 | 2023 | 43 | 43 | 2023-10-25 | 20:00 | 2023-10-26 | 4:00 | 0d, 8h | Continuous | Signal | T | [10 empty] | 80 | N | C7D-005 |  | 2021-05-30
DB Netz AG | C7D-002 | Dresden - Děčín | <> | Dresden Hbf | Pirna | 2023 | 2023 | 43 | 43 | 2023-10-25 | 20:00 | 2023-10-26 | 4:00 | 0d, 8h | Continuous | Signal | T | [10 empty] | 80 | N | C7D-002 |  | 2021-06-03
DB Netz AG | C7D-006 | Dresden - Děčín | <> | Dresden Hbf | Bad Schandau Gr | 2023 | 2023 | 43 | 43 | 2023-10-25 | 20:00 | 2023-10-26 | 4:00 | 0d, 8h | Continuous | Signal | T | [10 empty] | 80,54 | N | C7D-006 |  | 2021-05-30
DB Netz AG | C7D-007 | Dresden - Děčín | <> | Bad Schandau | Sebnitz (Sachs) | 2023 | 2023 | 43 | 43 | 2023-10-25 | 20:00 | 2023-10-26 | 4:00 | 0d, 8h | Continuous | Signal | T | [10 empty] | 80 | N | C7D-007 |  | 2021-05-30
DB Netz AG | C7D-008 | Dresden - Děčín | <> | Dohna (Sachs) | Heidenau | 2023 | 2023 | 43 | 43 | 2023-10-25 | 20:00 | 2023-10-26 | 4:00 | 0d, 8h | Continuous | Signal | T | [10 empty] | 80 | N | C7D-008 |  | 2021-05-30
DB Netz AG | C7D-009 | Dresden - Děčín | <> | Bad Schandau | Schöna | 2023 | 2023 | 43 | 43 | 2023-10-25 | 20:00 | 2023-10-26 | 4:00 | 0d, 8h | Continuous | Signal |  | ST | [9 empty] | 80 | N | C7D-009 |  | 2021-05-30
DB Netz AG | D77-002 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 43 | 43 | 2023-10-23 | 8:00 | 2023-10-28 | 15:00 | 5d, 7h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | D77-002 |  | 2021-05-31
DB Netz AG | D77-001 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 43 | 43 | 2023-10-23 | 8:00 | 2023-10-28 | 15:00 | 5d, 7h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | D77-001 |  | 2021-05-31
DB Netz AG | D90-011 | Dresden - Děčín | <> | Dre-Friedrichst | Dre Freibg Str | 2023 | 2023 | 42 | 42 | 2023-10-21 | 7:00 | 2023-10-21 | 14:00 | 0d, 7h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | D90-011 |  | 2021-06-01
DB Netz AG | D90-009 | Dresden - Děčín | <> | Dre Freibg Str | Dresden Mitte | 2023 | 2023 | 42 | 42 | 2023-10-21 | 7:00 | 2023-10-21 | 14:00 | 0d, 7h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | D90-009 |  | 2021-06-01
DB Netz AG | D90-005 | Dresden - Děčín | <> | Dre Freibg Str | Dresden-Altstadt | 2023 | 2023 | 42 | 42 | 2023-10-21 | 7:00 | 2023-10-21 | 14:00 | 0d, 7h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | D90-005 |  | 2021-06-01
DB Netz AG | D90-012 | Dresden - Děčín | <> | Dresden-Reick | Dre-Neustadt | 2023 | 2023 | 42 | 42 | 2023-10-21 | 14:00 | 2023-10-22 | 6:00 | 0d, 16h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | D90-012 |  | 2021-06-01
DB Netz AG | D90-013 | Dresden - Děčín | <> | Dre-Friedrichst | Dre Freibg Str | 2023 | 2023 | 42 | 42 | 2023-10-21 | 14:00 | 2023-10-22 | 6:00 | 0d, 16h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | D90-013 |  | 2021-06-01
DB Netz AG | D90-006 | Dresden - Děčín | <> | Dresden-Altstadt | Dresden Hbf | 2023 | 2023 | 42 | 42 | 2023-10-21 | 14:00 | 2023-10-22 | 6:00 | 0d, 16h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | D90-006 |  | 2021-06-01
DB Netz AG | D90-002 | Dresden - Děčín | <> | Dre-Reick Abstbf | Dre-Neustadt | 2023 | 2023 | 42 | 42 | 2023-10-21 | 14:00 | 2023-10-22 | 6:00 | 0d, 16h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | D90-002 |  | 2021-06-01
DB Netz AG | D90-003 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 42 | 42 | 2023-10-21 | 14:00 | 2023-10-22 | 6:00 | 0d, 16h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | D90-003 |  | 2021-06-01
DB Netz AG | D90-014 | Dresden - Děčín | <> | Dresden Hbf | Dre-Neustadt | 2023 | 2023 | 42 | 42 | 2023-10-21 | 14:00 | 2023-10-22 | 6:00 | 0d, 16h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | D90-014 |  | 2021-06-01
DB Netz AG | D90-016 | Dresden - Děčín | <> | Dresden-Altstadt | Dre Freibg Str | 2023 | 2023 | 42 | 42 | 2023-10-21 | 14:00 | 2023-10-22 | 6:00 | 0d, 16h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | D90-016 |  | 2021-06-01
DB Netz AG | D90-004 | Berlin - Dresden | <> | Dre-Neustadt | Dre-Neustadt Gbf | 2023 | 2023 | 42 | 42 | 2023-10-21 | 14:00 | 2023-10-22 | 6:00 | 0d, 16h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | D90-004 |  | 2021-06-01
DB Netz AG | D90-010 | Dresden - Děčín | <> | Dre-Friedrichst | Dresden Mitte | 2023 | 2023 | 42 | 42 | 2023-10-21 | 14:00 | 2023-10-22 | 6:00 | 0d, 16h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | D90-010 |  | 2021-06-01
DB Netz AG | D90-015 | Dresden - Děčín | <> | Dresden Hbf | Freital Ost | 2023 | 2023 | 42 | 42 | 2023-10-21 | 10:00 | 2023-10-21 | 14:00 | 0d, 4h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | D90-015 |  | 2021-06-01
DB Netz AG | D90-008 | Dresden - Děčín | <> | Dresden-Altstadt | Dresden Hbf | 2023 | 2023 | 42 | 42 | 2023-10-21 | 10:00 | 2023-10-21 | 14:00 | 0d, 4h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | D90-008 |  | 2021-06-01
DB Netz AG | D90-001 | Dresden - Děčín | < | Dresden-Altstadt | Dresden Hbf | 2023 | 2023 | 42 | 42 | 2023-10-21 | 0:00 | 2023-10-21 | 14:00 | 0d, 14h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | D90-001 |  | 2021-06-01
DB Netz AG | D90-017 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 42 | 42 | 2023-10-21 | 0:00 | 2023-10-21 | 14:00 | 0d, 14h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | D90-017 |  | 2021-06-01
DB Netz AG | DC8-003 | Dresden - Děčín | <> | Bad Schandau Ost | Schöna | 2023 | 2023 | 43 | 48 | 2023-10-27 | 0:01 | 2023-11-28 | 23:59 | 33d, 0h | Continuous | Miscellaneous |  |  | S | [8 empty] | 80 | N | DC8-003 |  | 2021-05-30
DB Netz AG | DC8-001 | Dresden - Děčín | <> | Bad Schandau | Schöna | 2023 | 2023 | 43 | 48 | 2023-10-27 | 6:30 | 2023-11-27 | 7:30 | 31d, 2h | Periodical | Miscellaneous | T | [10 empty] | 80 | Y | DC8-001 |  | 2021-05-30
DB Netz AG | DC8-007 | Dresden - Děčín | <> | Krippen | Bad Schandau Ost | 2023 | 2023 | 43 | 43 | 2023-10-27 | 4:00 | 2023-10-29 | 10:00 | 2d, 7h | Continuous | Miscellaneous |  |  | S | [8 empty] | 80 | N | DC8-007 |  | 2021-05-30
DB Netz AG | DC8-006 | Dresden - Děčín | <> | Bad Schandau | Schöna | 2023 | 2023 | 43 | 48 | 2023-10-27 | 16:30 | 2023-11-27 | 17:30 | 31d, 2h | Periodical | Miscellaneous | T | [10 empty] | 80 | Y | DC8-006 |  | 2021-05-30
DB Netz AG | DC8-009 | Dresden - Děčín | > | Schöna | Bad Schandau Ost | 2023 | 2023 | 43 | 48 | 2023-10-27 | 0:01 | 2023-11-28 | 23:59 | 33d, 0h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | DC8-009 |  | 2021-05-30
DB Netz AG | DC8-004 | Dresden - Děčín | > | Schöna | Bad Schandau Ost | 2023 | 2023 | 43 | 48 | 2023-10-27 | 0:01 | 2023-11-28 | 23:59 | 33d, 0h | Continuous | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | DC8-004 |  | 2021-05-30
DB Netz AG | DC8-002 | Dresden - Děčín | <> | Bad Schandau Gr | Bad Schandau | 2023 | 2023 | 43 | 48 | 2023-10-27 | 0:01 | 2023-11-28 | 23:59 | 33d, 0h | Continuous | Miscellaneous |  |  |  | P | [7 empty] | 80,54 | N | DC8-002 |  | 2021-05-30
DB Netz AG | DC8-010 | Dresden - Děčín | <> | Schöna | Schöna | 2023 | 2023 | 43 | 48 | 2023-10-27 | 0:01 | 2023-11-28 | 23:59 | 33d, 0h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | DC8-010 |  | 2021-05-30
DB Netz AG | E26-001 | Dresden - Děčín | <> | Schöna | Schöna | 2023 | 2023 | 42 | 43 | 2023-10-17 | 20:00 | 2023-10-25 | 20:00 | 8d, 0h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | E26-001 |  | 2021-05-30
DB Netz AG | E26-003 | Dresden - Děčín | <> | Bad Schandau Gr | Bad Schandau | 2023 | 2023 | 42 | 43 | 2023-10-17 | 20:00 | 2023-10-25 | 20:00 | 8d, 0h | Continuous | Miscellaneous | T | [10 empty] | 80,54 | N | E26-003 |  | 2021-05-30
DB Netz AG | E26-002 | Dresden - Děčín | <> | Bad Schandau Ost | Bad Schandau Ost | 2023 | 2023 | 42 | 43 | 2023-10-17 | 20:00 | 2023-10-25 | 20:00 | 8d, 0h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | E26-002 |  | 2021-05-30
DB Netz AG | E44-003 | Dresden - Děčín | <> | Dresden Hbf | Dre-Neustadt | 2023 | 2023 | 42 | 42 | 2023-10-17 | 1:00 | 2023-10-18 | 5:00 | 1d, 4h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | E44-003 |  | 2021-06-02
DB Netz AG | E44-011 | Dresden - Děčín | <> | Dresden-Altstadt | Dre Freibg Str | 2023 | 2023 | 42 | 42 | 2023-10-17 | 1:00 | 2023-10-18 | 5:00 | 1d, 4h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | E44-011 |  | 2021-06-02
DB Netz AG | E44-006 | Dresden - Děčín | <> | Dre-Reick Abstbf | Dre-Neustadt | 2023 | 2023 | 42 | 42 | 2023-10-17 | 1:00 | 2023-10-18 | 5:00 | 1d, 4h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | E44-006 |  | 2021-06-02
DB Netz AG | E44-012 | Dresden - Děčín | <> | Dresden-Reick | Dre-Neustadt | 2023 | 2023 | 42 | 42 | 2023-10-17 | 1:00 | 2023-10-18 | 5:00 | 1d, 4h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | E44-012 |  | 2021-06-02
DB Netz AG | E44-017 | Dresden - Děčín | <> | Dre-Friedrichst | Dre Freibg Str | 2023 | 2023 | 42 | 42 | 2023-10-17 | 1:00 | 2023-10-18 | 5:00 | 1d, 4h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | E44-017 |  | 2021-06-02
DB Netz AG | E44-001 | Dresden - Děčín | <> | Dresden-Altstadt | Dresden Hbf | 2023 | 2023 | 42 | 42 | 2023-10-17 | 1:00 | 2023-10-18 | 5:00 | 1d, 4h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | E44-001 |  | 2021-06-02
DB Netz AG | E44-007 | Dresden - Děčín | <> | Dresden-Altstadt | Dresden Hbf | 2023 | 2023 | 42 | 42 | 2023-10-17 | 1:00 | 2023-10-18 | 5:00 | 1d, 4h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | E44-007 |  | 2021-06-02
DB Netz AG | E44-015 | Dresden - Děčín | <> | Dre-Neustadt | Dre-Neustadt Gbf | 2023 | 2023 | 42 | 42 | 2023-10-17 | 1:00 | 2023-10-18 | 5:00 | 1d, 4h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | E44-015 |  | 2021-07-01
DB Netz AG | E44-008 | Dresden - Děčín | <> | Dre-Friedrichst | Dresden Mitte | 2023 | 2023 | 42 | 42 | 2023-10-17 | 1:00 | 2023-10-18 | 5:00 | 1d, 4h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | E44-008 |  | 2021-06-02
DB Netz AG | E44-013 | Dresden - Děčín | <> | Dresden-Altstadt | Dresden Hbf | 2023 | 2023 | 42 | 42 | 2023-10-16 | 19:00 | 2023-10-18 | 1:00 | 1d, 6h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | E44-013 |  | 2021-06-02
DB Netz AG | E44-009 | Dresden - Děčín | <> | Dresden-Altstadt | Dre Freibg Str | 2023 | 2023 | 42 | 42 | 2023-10-16 | 19:00 | 2023-10-18 | 1:00 | 1d, 6h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | E44-009 |  | 2021-06-02
DB Netz AG | E44-002 | Dresden - Děčín | <> | Dre-Neustadt | Dre-Neustadt Gbf | 2023 | 2023 | 42 | 42 | 2023-10-16 | 19:00 | 2023-10-18 | 1:00 | 1d, 6h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | E44-002 |  | 2021-06-02
DB Netz AG | E44-005 | Dresden - Děčín | <> | Dre-Friedrichst | Dresden Mitte | 2023 | 2023 | 42 | 42 | 2023-10-16 | 19:00 | 2023-10-18 | 1:00 | 1d, 6h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | E44-005 |  | 2021-06-02
DB Netz AG | E44-016 | Dresden - Děčín | <> | Dresden Hbf | Dre-Neustadt | 2023 | 2023 | 42 | 42 | 2023-10-16 | 19:00 | 2023-10-18 | 1:00 | 1d, 6h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | E44-016 |  | 2021-06-02
DB Netz AG | E44-014 | Dresden - Děčín | <> | Dresden Hbf | Dre-Neustadt | 2023 | 2023 | 42 | 42 | 2023-10-16 | 19:00 | 2023-10-18 | 1:00 | 1d, 6h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | E44-014 |  | 2021-06-02
DB Netz AG | E44-018 | Dresden - Děčín | <> | Dre-Friedrichst | Dre Freibg Str | 2023 | 2023 | 42 | 42 | 2023-10-16 | 19:00 | 2023-10-18 | 1:00 | 1d, 6h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | E44-018 |  | 2021-06-02
DB Netz AG | E44-010 | Dresden - Děčín | <> | Dresden-Altstadt | Dresden Hbf | 2023 | 2023 | 42 | 42 | 2023-10-16 | 19:00 | 2023-10-18 | 1:00 | 1d, 6h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | E44-010 |  | 2021-06-02
DB Netz AG | EAE-002 | Hamburg - Magdeburg | < | Veddel | Hmb-Wlb Abzw | 2023 | 2023 | 43 | 43 | 2023-10-23 | 4:00 | 2023-10-29 | 4:00 | 6d, 1h | Continuous | Signal |  | LT | [9 empty] | 80 | N | EAE-002 |  | 2021-05-23
DB Netz AG | F74-001 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 43 | 43 | 2023-10-23 | 22:45 | 2023-10-28 | 4:15 | 4d, 5h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | F74-001 |  | 2021-05-31
DB Netz AG | F74-007 | Dresden - Děčín | <> | Dresden Hbf | Freital Ost | 2023 | 2023 | 43 | 43 | 2023-10-23 | 22:00 | 2023-10-27 | 22:45 | 4d, 0h | Periodical | Catenary | T | [10 empty] | 80 | N | F74-007 |  | 2021-05-31
DB Netz AG | F74-004 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 43 | 43 | 2023-10-23 | 22:00 | 2023-10-27 | 22:45 | 4d, 0h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | F74-004 |  | 2021-05-31
DB Netz AG | F74-003 | Dresden - Děčín | <> | Dresden Hbf | Freital Ost | 2023 | 2023 | 43 | 43 | 2023-10-24 | 4:15 | 2023-10-28 | 5:00 | 4d, 0h | Periodical | Catenary | T | [10 empty] | 80 | N | F74-003 |  | 2021-05-31
DB Netz AG | F74-006 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 43 | 43 | 2023-10-24 | 4:15 | 2023-10-28 | 5:00 | 4d, 0h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | F74-006 |  | 2021-05-31
DB Netz AG | FA4-001 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 44 | 44 | 2023-10-30 | 3:30 | 2023-10-30 | 5:30 | 0d, 2h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | FA4-001 |  | 2021-05-27
DB Netz AG | FA4-032 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 44 | 44 | 2023-10-30 | 3:30 | 2023-10-30 | 5:30 | 0d, 2h | Continuous | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | FA4-032 |  | 2021-05-27
DB Netz AG | FA4-011 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 42 | 43 | 2023-10-21 | 7:00 | 2023-10-25 | 20:00 | 4d, 13h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | FA4-011 |  | 2021-05-27
DB Netz AG | FD5-001 | Dresden - Děčín | <> | Bad Schandau | Sebnitz (Sachs) | 2023 | 2023 | 43 | 43 | 2023-10-27 | 0:00 | 2023-10-27 | 5:00 | 0d, 5h | Continuous | Bridge | T | [10 empty] | 80 | N | FD5-001 |  | 2021-05-21
DB Netz AG | FD5-003 | Dresden - Děčín | <> | Schöna | Dolni Zleb | 2023 | 2023 | 43 | 43 | 2023-10-27 | 4:00 | 2023-10-29 | 13:00 | 2d, 10h | Continuous | Bridge |  |  | S | [8 empty] | 80,54 | N | FD5-003 |  | 2021-05-21
DB Netz AG | FD5-007 | Dresden - Děčín | <> | Schöna | Schöna | 2023 | 2023 | 42 | 43 | 2023-10-17 | 20:00 | 2023-10-27 | 4:00 | 9d, 8h | Continuous | Bridge |  | ST | [9 empty] | 80 | N | FD5-007 |  | 2021-05-21
DB Netz AG | FD5-004 | Dresden - Děčín | <> | Schöna | Dolni Zleb | 2023 | 2023 | 42 | 43 | 2023-10-17 | 20:00 | 2023-10-27 | 4:00 | 9d, 8h | Continuous | Bridge | T | [10 empty] | 80,54 | N | FD5-004 |  | 2021-05-21
DB Netz AG | FD5-002 | Dresden - Děčín | <> | Sebnitz (Sachs) | Bad Schandau | 2023 | 2023 | 42 | 42 | 2023-10-17 | 16:00 | 2023-10-17 | 21:00 | 0d, 5h | Continuous | Bridge | T | [10 empty] | 80 | N | FD5-002 |  | 2021-05-21
DB Netz AG | 0.103 | Dresden - Děčín | <> | Bad Schandau Ost | Bad Schandau Ost | 2023 | 2023 | 43 | 43 | 2023-10-26 | 4:00 | 2023-10-26 | 20:00 | 0d, 16h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 0.103 |  | 2021-05-30
DB Netz AG | 10.3 | Dresden - Děčín | <> | Schöna | Schöna | 2023 | 2023 | 43 | 43 | 2023-10-26 | 4:00 | 2023-10-26 | 20:00 | 0d, 16h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 10.3 |  | 2021-05-30
DB Netz AG | 1.03 | Dresden - Děčín | <> | Bad Schandau | Bad Schandau Gr | 2023 | 2023 | 43 | 43 | 2023-10-26 | 4:00 | 2023-10-26 | 20:00 | 0d, 16h | Continuous | Miscellaneous | T | [10 empty] | 80,54 | N | 1.03 |  | 2021-05-30
DB Netz AG | 1098-005 | Dresden - Děčín | <> | Dresden Hbf | Dre Freibg Str | 2023 | 2023 | 42 | 49 | 2023-10-22 | 6:00 | 2023-12-09 | 23:59 | 48d, 18h | Continuous | Bridge |  | ST | [9 empty] | 80 | N | 1098-005 |  | 2021-05-31
DB Netz AG | 1098-003 | Dresden - Děčín | <> | Dresden Hbf | Dre Freibg Str | 2023 | 2023 | 42 | 49 | 2023-10-22 | 6:00 | 2023-12-09 | 23:59 | 48d, 18h | Continuous | Bridge |  | ST | [9 empty] | 80 | N | 1098-003 |  | 2021-05-31
DB Netz AG | 1098-004 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 42 | 49 | 2023-10-22 | 6:00 | 2023-12-09 | 23:59 | 48d, 18h | Continuous | Bridge | T | [10 empty] | 80 | N | 1098-004 |  | 2021-05-31
DB Netz AG | 1098-001 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 42 | 49 | 2023-10-22 | 6:00 | 2023-12-09 | 23:59 | 48d, 18h | Continuous | Bridge |  |  |  |  | X | [6 empty] | 80 | N | 1098-001 |  | 2021-05-31
DB Netz AG | 1098-002 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 42 | 49 | 2023-10-22 | 6:00 | 2023-12-09 | 23:59 | 48d, 18h | Continuous | Bridge |  | ST | [9 empty] | 80 | Y | 1098-002 |  | 2021-05-31
DB Netz AG | 10D3-004 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 44 | 44 | 2023-11-01 | 22:00 | 2023-11-04 | 5:00 | 2d, 7h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 10D3-004 |  | 2021-05-31
DB Netz AG | 10D3-002 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 44 | 44 | 2023-11-01 | 22:00 | 2023-11-04 | 5:00 | 2d, 7h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 10D3-002 |  | 2021-05-31
DB Netz AG | 1119-009 | Dresden - Děčín | <> | Dresden Hbf | Bad Schandau Gr | 2023 | 2023 | 43 | 43 | 2023-10-26 | 20:00 | 2023-10-27 | 4:00 | 0d, 8h | Continuous | Miscellaneous | T | [10 empty] | 80,54 | N | 1119-009 |  | 2021-05-30
DB Netz AG | 1119-005 | Dresden - Děčín | <> | Pirna | Dürrröhrsdorf | 2023 | 2023 | 43 | 43 | 2023-10-26 | 20:00 | 2023-10-27 | 4:00 | 0d, 8h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | 1119-005 |  | 2021-05-30
DB Netz AG | 1119-001 | Dresden - Děčín | <> | Dresden Hbf | Pirna | 2023 | 2023 | 43 | 43 | 2023-10-26 | 20:00 | 2023-10-27 | 4:00 | 0d, 8h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | 1119-001 |  | 2021-05-30
DB Netz AG | 1119-007 | Dresden - Děčín | <> | Bad Schandau | Schöna | 2023 | 2023 | 43 | 43 | 2023-10-26 | 20:00 | 2023-10-27 | 4:00 | 0d, 8h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 1119-007 |  | 2021-05-30
DB Netz AG | 1119-003 | Dresden - Děčín | <> | Heidenau | Dohna (Sachs) | 2023 | 2023 | 43 | 43 | 2023-10-26 | 20:00 | 2023-10-27 | 4:00 | 0d, 8h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | 1119-003 |  | 2021-05-30
DB Netz AG | 1119-004 | Dresden - Děčín | <> | Bad Schandau | Sebnitz (Sachs) | 2023 | 2023 | 43 | 43 | 2023-10-26 | 20:00 | 2023-10-27 | 4:00 | 0d, 8h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | 1119-004 |  | 2021-05-30
DB Netz AG | 11ED-001 | Bremerhaven - Bremen | > | Bremen Hbf | Brh-Speckenbütt | 2023 | 2023 | 43 | 45 | 2023-10-23 | 23:00 | 2023-11-06 | 5:00 | 13d, 7h | Periodical | Maintenance |  | LT | [9 empty] | 80 | N | 11ED-001 |  | 2021-01-12
DB Netz AG | 124D-001 | Bremen - Hannover | > | Seelze West | Waldhausen | 2023 | 2023 | 44 | 45 | 2023-10-31 | 23:00 | 2023-11-10 | 5:00 | 9d, 6h | Periodical | Maintenance |  | LT | [9 empty] | 80 | N | 124D-001 |  | 2022-06-15
DB Netz AG | E26-004 | Dresden - Děčín | <> | Bad Schandau Gr | Dolni Zleb | 2023 | 2023 | 42 | 43 | 2023-10-17 | 20:00 | 2023-10-25 | 20:00 | 8d, 0h | Continuous | Miscellaneous | T | [10 empty] | 80,54,80,54 | N | E26-004 |  | 2020-09-29
DB Netz AG | 0.0103 | Dresden - Děčín | <> | Bad Schandau Gr | Dolni Zleb | 2023 | 2023 | 43 | 43 | 2023-10-26 | 4:00 | 2023-10-26 | 20:00 | 0d, 16h | Continuous | Miscellaneous | T | [10 empty] | 80,54,80,54 | N | 0.0103 |  | 2021-05-30
DB Netz AG | DC8-011 | Dresden - Děčín | <> | Bad Schandau Ost | Bad Schandau Ost | 2023 | 2023 | 43 | 48 | 2023-10-27 | 0:01 | 2023-11-28 | 23:59 | 33d, 0h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | DC8-011 |  | 2021-05-30
DB Netz AG | C7D-011 | Dresden - Děčín | <> | Bad Schandau Gr | Bad Schandau | 2023 | 2023 | 43 | 43 | 2023-10-25 | 20:00 | 2023-10-26 | 4:00 | 0d, 8h | Continuous | Signal | T | [10 empty] | 80,54 | N | C7D-011 |  | 2020-09-29
DB Netz AG | 1119-011 | Dresden - Děčín | <> | Dolni Zleb | Bad Schandau Gr | 2023 | 2023 | 43 | 43 | 2023-10-26 | 20:00 | 2023-10-27 | 4:00 | 0d, 8h | Continuous | Miscellaneous | T | [10 empty] | 80,54,80,54 | N | 1119-011 |  | 2021-06-03
DB Netz AG | 1098-006 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 42 | 49 | 2023-10-22 | 6:00 | 2023-12-09 | 23:59 | 48d, 18h | Continuous | Bridge |  |  |  | P | [7 empty] | 80 | Y | 1098-006 |  | 2020-09-30
DB Netz AG | 1098-007 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 42 | 49 | 2023-10-22 | 6:00 | 2023-12-09 | 23:59 | 48d, 18h | Continuous | Bridge |  |  |  | P | [7 empty] | 80 | Y | 1098-007 |  | 2021-05-31
DB Netz AG | E44-019 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 42 | 42 | 2023-10-16 | 19:00 | 2023-10-18 | 1:00 | 1d, 6h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | E44-019 |  | 2021-06-02
DB Netz AG | C7D-012 | Dresden - Děčín | <> | Bad Schandau Gr | Dolni Zleb | 2023 | 2023 | 43 | 43 | 2023-10-25 | 20:00 | 2023-10-26 | 4:00 | 0d, 8h | Continuous | Signal | T | [10 empty] | 80,54,80,54 | N | C7D-012 |  | 2021-06-03
DB Netz AG | BD0-025 | Bremerhaven - Bremen | <> | Bremen-Burg | Bremen-Burg | 2023 | 2023 | 42 | 46 | 2023-10-20 | 23:00 | 2023-11-14 | 5:00 | 24d, 7h | Periodical | Signal |  |  | S | [8 empty] | 80 | N | BD0-025 |  | 2022-07-13
DB Netz AG | 16C2-001 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 42 | 42 | 2023-10-18 | 17:00 | 2023-10-20 | 5:00 | 1d, 12h | Periodical | Catenary | T | [10 empty] | 80 | N | 16C2-001 |  | 2021-05-21
DB Netz AG | 16C2-002 | Dresden - Děčín | < | Dresden Mitte | Dresden Hbf | 2023 | 2023 | 42 | 42 | 2023-10-18 | 17:00 | 2023-10-20 | 5:00 | 1d, 12h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 16C2-002 |  | 2021-05-21
DB Netz AG | 16C6-001 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 42 | 43 | 2023-10-22 | 17:00 | 2023-10-24 | 5:00 | 1d, 12h | Periodical | Catenary | T | [10 empty] | 80 | N | 16C6-001 |  | 2021-05-21
DB Netz AG | 16C6-002 | Dresden - Děčín | < | Dresden Mitte | Dresden Hbf | 2023 | 2023 | 42 | 43 | 2023-10-22 | 17:00 | 2023-10-24 | 5:00 | 1d, 12h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 16C6-002 |  | 2021-05-21
DB Netz AG | 16C7-001 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 43 | 43 | 2023-10-24 | 20:00 | 2023-10-25 | 5:00 | 0d, 9h | Continuous | Catenary | T | [10 empty] | 80 | N | 16C7-001 |  | 2021-05-21
DB Netz AG | 16C7-002 | Dresden - Děčín | < | Dresden Mitte | Dresden Hbf | 2023 | 2023 | 43 | 43 | 2023-10-24 | 20:00 | 2023-10-25 | 5:00 | 0d, 9h | Continuous | Catenary |  | ST | [9 empty] | 80 | N | 16C7-002 |  | 2021-05-21
DB Netz AG | 16C7-003 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 43 | 43 | 2023-10-25 | 2:00 | 2023-10-25 | 5:00 | 0d, 3h | Continuous | Catenary |  | ST | [9 empty] | 80 | N | 16C7-003 |  | 2021-05-21
DB Netz AG | 16C7-004 | Dresden - Děčín | <> | Dresden Mitte | Dresden Hbf | 2023 | 2023 | 43 | 43 | 2023-10-25 | 2:00 | 2023-10-25 | 5:00 | 0d, 3h | Continuous | Catenary | T | [10 empty] | 80 | N | 16C7-004 |  | 2021-05-21
DB Netz AG | 16C9-001 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 43 | 43 | 2023-10-27 | 20:00 | 2023-10-28 | 5:00 | 0d, 9h | Continuous | Catenary | T | [10 empty] | 80 | N | 16C9-001 |  | 2021-05-21
DB Netz AG | 16C9-002 | Dresden - Děčín | < | Dresden Mitte | Dresden Hbf | 2023 | 2023 | 43 | 43 | 2023-10-27 | 20:00 | 2023-10-28 | 5:00 | 0d, 9h | Continuous | Catenary |  | ST | [9 empty] | 80 | N | 16C9-002 |  | 2021-05-21
DB Netz AG | 16C9-003 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 43 | 43 | 2023-10-28 | 0:00 | 2023-10-28 | 5:00 | 0d, 5h | Continuous | Catenary |  | ST | [9 empty] | 80 | N | 16C9-003 |  | 2021-05-21
DB Netz AG | 16C9-004 | Dresden - Děčín | <> | Dresden Mitte | Dresden Hbf | 2023 | 2023 | 43 | 43 | 2023-10-28 | 0:00 | 2023-10-28 | 5:00 | 0d, 5h | Continuous | Catenary | T | [10 empty] | 80 | N | 16C9-004 |  | 2021-05-21
DB Netz AG | 16CA-001 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 43 | 44 | 2023-10-28 | 20:00 | 2023-10-30 | 5:00 | 1d, 10h | Periodical | Catenary | T | [10 empty] | 80 | N | 16CA-001 |  | 2021-05-21
DB Netz AG | 16CA-002 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 43 | 44 | 2023-10-28 | 20:00 | 2023-10-30 | 5:00 | 1d, 10h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 16CA-002 |  | 2021-05-21
DB Netz AG | 16CA-003 | Dresden - Děčín | <> | Dresden Mitte | Dresden Hbf | 2023 | 2023 | 43 | 44 | 2023-10-28 | 20:00 | 2023-10-30 | 5:00 | 1d, 10h | Periodical | Catenary | T | [10 empty] | 80 | N | 16CA-003 |  | 2021-05-21
DB Netz AG | 16E3-001 | Dresden - Děčín | <> | Schöna | Bad Schandau | 2023 | 2023 | 44 | 48 | 2023-10-30 | 8:50 | 2023-11-27 | 16:40 | 28d, 7h | Periodical | Catenary | T | [10 empty] | 80 | N | 16E3-001 |  | 2021-04-27
DB Netz AG | 16E3-003 | Dresden - Děčín | <> | Bad Schandau Gr | Bad Schandau | 2023 | 2023 | 44 | 48 | 2023-10-30 | 8:50 | 2023-11-27 | 16:40 | 28d, 7h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80,54 | N | 16E3-003 |  | 2021-04-27
DB Netz AG | 16E9-001 | Falkenberg - Dresden | <> | Dre-Friedrichst | Rückersdorf NL | 2023 | 2023 | 43 | 43 | 2023-10-26 | 0:01 | 2023-10-26 | 4:00 | 0d, 3h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 16E9-001 |  | 2021-04-23
DB Netz AG | 16E9-002 | Dresden - Děčín | <> | Bad Schandau Gr | Dre-Neustadt | 2023 | 2023 | 43 | 43 | 2023-10-26 | 0:01 | 2023-10-26 | 4:00 | 0d, 3h | Continuous | Signal |  | ST | [9 empty] | 80,54 | N | 16E9-002 |  | 2021-04-23
DB Netz AG | 16E9-003 | Dresden - Děčín | <> | Dresden Hbf | Dre-Neustadt | 2023 | 2023 | 43 | 43 | 2023-10-26 | 0:01 | 2023-10-26 | 4:00 | 0d, 3h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 16E9-003 |  | 2021-04-23
DB Netz AG | 16E9-004 | Dresden - Děčín | <> | Pirna | Coswig (bei Dre) | 2023 | 2023 | 43 | 43 | 2023-10-26 | 0:01 | 2023-10-26 | 4:00 | 0d, 3h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 16E9-004 |  | 2021-04-23
DB Netz AG | 16E9-005 | Falkenberg - Dresden | <> | Dre-Neustadt | Riesa | 2023 | 2023 | 43 | 43 | 2023-10-26 | 0:01 | 2023-10-26 | 4:00 | 0d, 3h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 16E9-005 |  | 2021-04-23
DB Netz AG | 16E9-006 | Dresden - Děčín | <> | Dresden Hbf | Klingenb-Colmn | 2023 | 2023 | 43 | 43 | 2023-10-26 | 0:01 | 2023-10-26 | 4:00 | 0d, 3h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 16E9-006 |  | 2021-04-23
DB Netz AG | 16E9-007 | Berlin - Dresden | <> | Az | Radebeul Nord | 2023 | 2023 | 43 | 43 | 2023-10-26 | 0:01 | 2023-10-26 | 4:00 | 0d, 3h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 16E9-007 |  | 2021-04-23
DB Netz AG | 16E9-008 | Dresden - Děčín | <> | Dre-Neustadt | Dre-Klotzsche | 2023 | 2023 | 43 | 43 | 2023-10-26 | 0:01 | 2023-10-26 | 4:00 | 0d, 3h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 16E9-008 |  | 2021-04-23
DB Netz AG | 16E9-009 | Falkenberg - Dresden | <> | Zeithain Bogendr | Elsterwerda | 2023 | 2023 | 43 | 43 | 2023-10-26 | 0:01 | 2023-10-26 | 4:00 | 0d, 3h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 16E9-009 |  | 2021-04-23
DB Netz AG | 16E9-010 | Dresden - Děčín | <> | Heidenau | Dohna (Sachs) | 2023 | 2023 | 43 | 43 | 2023-10-26 | 0:01 | 2023-10-26 | 4:00 | 0d, 3h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 16E9-010 |  | 2021-04-23
DB Netz AG | 16E9-011 | Dresden - Děčín | <> | Bad Schandau | Bad Schandau | 2023 | 2023 | 43 | 43 | 2023-10-26 | 0:01 | 2023-10-26 | 4:00 | 0d, 3h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 16E9-011 |  | 2021-04-23
DB Netz AG | 16E9-012 | Falkenberg - Dresden | <> | Leckwitz | Kottewitz | 2023 | 2023 | 43 | 43 | 2023-10-26 | 0:01 | 2023-10-26 | 4:00 | 0d, 3h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 16E9-012 |  | 2021-04-23
DB Netz AG | 16E9-013 | Berlin - Dresden | <> | Dre-Pieschen Abz | Dre-Neustadt | 2023 | 2023 | 43 | 43 | 2023-10-26 | 0:01 | 2023-10-26 | 4:00 | 0d, 3h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 16E9-013 |  | 2021-04-23
DB Netz AG | 16E9-015 | Berlin - Dresden | <> | Elsterwerda | Elsterw-Biehla | 2023 | 2023 | 43 | 43 | 2023-10-26 | 0:01 | 2023-10-26 | 4:00 | 0d, 3h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 16E9-015 |  | 2021-04-23
DB Netz AG | 16E9-016 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 43 | 43 | 2023-10-26 | 0:01 | 2023-10-26 | 4:00 | 0d, 3h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 16E9-016 |  | 2021-04-23
DB Netz AG | 16E9-017 | Falkenberg - Dresden | <> | Großenh Cott Bf | Priestewitz | 2023 | 2023 | 43 | 43 | 2023-10-26 | 0:01 | 2023-10-26 | 4:00 | 0d, 3h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 16E9-017 |  | 2021-04-23
DB Netz AG | 16E9-018 | Dresden - Děčín | <> | Dre-Friedrichst | Dresden Mitte | 2023 | 2023 | 43 | 43 | 2023-10-26 | 0:01 | 2023-10-26 | 4:00 | 0d, 3h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 16E9-018 |  | 2021-04-23
DB Netz AG | 16E9-019 | Berlin - Dresden | <> | Großenh Berl Bf | Großenh Cott Bf | 2023 | 2023 | 43 | 43 | 2023-10-26 | 0:01 | 2023-10-26 | 4:00 | 0d, 3h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 16E9-019 |  | 2021-04-23
DB Netz AG | 1732-001 | Dresden - Děčín | <> | Pirna Gbf | Pirna Gbf | 2023 | 2023 | 43 | 44 | 2023-10-27 | 8:00 | 2023-11-04 | 16:00 | 8d, 9h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 1732-001 |  | 2021-04-07
DB Netz AG | 1732-002 | Dresden - Děčín | <> | Pirna Gbf | Pirna Gbf | 2023 | 2023 | 43 | 43 | 2023-10-27 | 21:00 | 2023-10-28 | 5:00 | 0d, 8h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 1732-002 |  | 2021-04-07
DB Netz AG | 1732-003 | Dresden - Děčín | <> | Pirna | Pirna Gbf | 2023 | 2023 | 43 | 43 | 2023-10-27 | 21:00 | 2023-10-28 | 5:00 | 0d, 8h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 1732-003 |  | 2021-04-07
DB Netz AG | 1732-005 | Dresden - Děčín | <> | Pirna Gbf | Pirna Gbf | 2023 | 2023 | 43 | 43 | 2023-10-27 | 21:00 | 2023-10-28 | 5:00 | 0d, 8h | Continuous | Switch |  |  |  |  | X | [6 empty] | 80 | N | 1732-005 |  | 2021-04-07
DB Netz AG | 1732-006 | Dresden - Děčín | <> | Pirna | Pirna Gbf | 2023 | 2023 | 43 | 44 | 2023-10-28 | 21:00 | 2023-10-30 | 5:00 | 1d, 9h | Periodical | Switch |  | ST | [9 empty] | 80 | N | 1732-006 |  | 2021-04-07
DB Netz AG | 1732-007 | Dresden - Děčín | <> | Pirna | Pirna Gbf | 2023 | 2023 | 43 | 44 | 2023-10-28 | 21:00 | 2023-10-30 | 5:00 | 1d, 9h | Periodical | Switch |  | ST | [9 empty] | 80 | N | 1732-007 |  | 2021-04-07
DB Netz AG | 1732-009 | Dresden - Děčín | <> | Pirna | Pirna Gbf | 2023 | 2023 | 43 | 44 | 2023-10-28 | 21:00 | 2023-10-30 | 5:00 | 1d, 9h | Periodical | Switch |  |  |  |  | X | [6 empty] | 80 | N | 1732-009 |  | 2021-04-07
DB Netz AG | 1732-010 | Dresden - Děčín | <> | Pirna | Pirna Gbf | 2023 | 2023 | 43 | 44 | 2023-10-28 | 21:00 | 2023-10-30 | 5:00 | 1d, 9h | Periodical | Switch |  |  |  |  | X | [6 empty] | 80 | N | 1732-010 |  | 2021-04-07
DB Netz AG | 1732-011 | Dresden - Děčín | < | Heidenau | Pirna | 2023 | 2023 | 43 | 43 | 2023-10-28 | 22:00 | 2023-10-29 | 5:00 | 0d, 8h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 1732-011 |  | 2021-04-07
DB Netz AG | 1732-012 | Dresden - Děčín | < | Pirna Gbf | Pirna Gbf | 2023 | 2023 | 43 | 43 | 2023-10-28 | 22:00 | 2023-10-29 | 5:00 | 0d, 8h | Continuous | Switch |  |  |  |  | X | [6 empty] | 80 | N | 1732-012 |  | 2021-04-07
DB Netz AG | 1732-013 | Dresden - Děčín | < | Heidenau | Pirna | 2023 | 2023 | 44 | 44 | 2023-10-30 | 4:00 | 2023-10-30 | 5:00 | 0d, 1h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 1732-013 |  | 2021-04-07
DB Netz AG | 1732-014 | Dresden - Děčín | <> | Pirna Gbf | Pirna Gbf | 2023 | 2023 | 43 | 44 | 2023-10-28 | 21:00 | 2023-10-30 | 5:00 | 1d, 9h | Periodical | Switch |  |  |  | P | [7 empty] | 80 | N | 1732-014 |  | 2021-04-07
DB Netz AG | 1732-015 | Dresden - Děčín | <> | Pirna Gbf | Pirna Gbf | 2023 | 2023 | 43 | 43 | 2023-10-28 | 22:00 | 2023-10-29 | 5:00 | 0d, 8h | Continuous | Switch |  |  |  | P | [7 empty] | 80 | N | 1732-015 |  | 2021-04-07
DB Netz AG | 1769-001 | Rostock - Berlin | <> | Biesdf Kr Nord | Ahrensfelde | 2023 | 2023 | 42 | 45 | 2023-10-20 | 22:00 | 2023-11-06 | 4:00 | 16d, 7h | Continuous | Track & Rail | T | [10 empty] | 80 | N | 1769-001 |  | 2022-07-20
DB Netz AG | 1A8E-001 | Rostock - Berlin | < | Langhagen | Vollrathsruhe | 2023 | 2023 | 42 | 42 | 2023-10-19 | 22:30 | 2023-10-20 | 5:00 | 0d, 6h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1A8E-001 |  | 2021-10-14
DB Netz AG | 1A8E-002 | Rostock - Berlin | < | Langhagen | Langhagen | 2023 | 2023 | 42 | 42 | 2023-10-19 | 22:30 | 2023-10-20 | 5:00 | 0d, 6h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1A8E-002 |  | 2021-10-14
DB Netz AG | 1A8E-003 | Rostock - Berlin | < | Lalendorf Ost | Langhagen | 2023 | 2023 | 42 | 42 | 2023-10-19 | 22:30 | 2023-10-20 | 0:00 | 0d, 1h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1A8E-003 |  | 2021-10-14
DB Netz AG | 1A8E-004 | Rostock - Berlin | <> | Vollrathsruhe | Langhagen | 2023 | 2023 | 42 | 42 | 2023-10-19 | 22:30 | 2023-10-20 | 5:00 | 0d, 6h | Continuous | Track & Rail |  |  |  | P | [7 empty] | 80 | N | 1A8E-004 |  | 2021-10-14
DB Netz AG | 1A8E-005 | Rostock - Berlin | <> | Langhagen | Langhagen | 2023 | 2023 | 42 | 42 | 2023-10-19 | 22:30 | 2023-10-20 | 0:00 | 0d, 1h | Continuous | Track & Rail |  |  |  | P | [7 empty] | 80 | N | 1A8E-005 |  | 2021-10-14
DB Netz AG | 1A8E-006 | Rostock - Berlin | < | Langhagen | Vollrathsruhe | 2023 | 2023 | 42 | 42 | 2023-10-20 | 22:30 | 2023-10-21 | 5:00 | 0d, 6h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1A8E-006 |  | 2021-10-14
DB Netz AG | 1A8E-007 | Rostock - Berlin | < | Langhagen | Langhagen | 2023 | 2023 | 42 | 42 | 2023-10-20 | 22:30 | 2023-10-21 | 5:00 | 0d, 6h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1A8E-007 |  | 2021-10-14
DB Netz AG | 1A8E-008 | Rostock - Berlin | <> | Vollrathsruhe | Langhagen | 2023 | 2023 | 42 | 42 | 2023-10-20 | 22:30 | 2023-10-21 | 5:00 | 0d, 6h | Continuous | Track & Rail |  |  |  | P | [7 empty] | 80 | N | 1A8E-008 |  | 2021-10-14
DB Netz AG | 1A8E-009 | Rostock - Berlin | < | Langhagen | Grabowhöfe | 2023 | 2023 | 42 | 42 | 2023-10-20 | 22:30 | 2023-10-21 | 2:10 | 0d, 3h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1A8E-009 |  | 2021-10-14
DB Netz AG | 1A8E-010 | Rostock - Berlin | < | Vollrathsruhe | Vollrathsruhe | 2023 | 2023 | 42 | 42 | 2023-10-20 | 22:30 | 2023-10-21 | 2:10 | 0d, 3h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1A8E-010 |  | 2021-10-14
DB Netz AG | 1A8E-012 | Rostock - Berlin | <> | Vollrathsruhe | Vollrathsruhe | 2023 | 2023 | 42 | 42 | 2023-10-20 | 22:30 | 2023-10-21 | 2:10 | 0d, 3h | Continuous | Track & Rail |  |  |  | P | [7 empty] | 80 | N | 1A8E-012 |  | 2021-10-14
DB Netz AG | 1A8E-013 | Rostock - Berlin | > | Vollrathsruhe | Langhagen | 2023 | 2023 | 42 | 42 | 2023-10-22 | 0:35 | 2023-10-22 | 4:35 | 0d, 4h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1A8E-013 |  | 2021-10-14
DB Netz AG | 1A8E-014 | Rostock - Berlin | > | Vollrathsruhe | Vollrathsruhe | 2023 | 2023 | 42 | 42 | 2023-10-22 | 0:35 | 2023-10-22 | 4:35 | 0d, 4h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1A8E-014 |  | 2021-10-14
DB Netz AG | 1A8E-015 | Rostock - Berlin | <> | Vollrathsruhe | Vollrathsruhe | 2023 | 2023 | 42 | 42 | 2023-10-22 | 0:35 | 2023-10-22 | 4:35 | 0d, 4h | Continuous | Track & Rail |  |  |  | P | [7 empty] | 80 | N | 1A8E-015 |  | 2021-10-14
DB Netz AG | 1A8E-016 | Rostock - Berlin | > | Grabowhöfe | Vollrathsruhe | 2023 | 2023 | 42 | 42 | 2023-10-22 | 0:35 | 2023-10-22 | 1:35 | 0d, 1h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1A8E-016 |  | 2021-10-14
DB Netz AG | 1A8E-017 | Rostock - Berlin | <> | Vollrathsruhe | Vollrathsruhe | 2023 | 2023 | 42 | 42 | 2023-10-22 | 0:35 | 2023-10-22 | 1:35 | 0d, 1h | Continuous | Track & Rail |  |  |  | P | [7 empty] | 80 | N | 1A8E-017 |  | 2021-10-14
DB Netz AG | 1.93e-16 | Rostock - Berlin | < | Langhagen | Vollrathsruhe | 2023 | 2023 | 43 | 43 | 2023-10-28 | 21:15 | 2023-10-29 | 5:00 | 0d, 8h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1.93e-16 |  | 2021-10-14
DB Netz AG | 1.93e-17 | Rostock - Berlin | < | Langhagen | Langhagen | 2023 | 2023 | 43 | 43 | 2023-10-28 | 21:15 | 2023-10-29 | 5:00 | 0d, 8h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1.93e-17 |  | 2021-10-14
DB Netz AG | 1.93e-18 | Rostock - Berlin | <> | Vollrathsruhe | Langhagen | 2023 | 2023 | 43 | 43 | 2023-10-28 | 21:15 | 2023-10-29 | 5:00 | 0d, 8h | Continuous | Track & Rail |  |  |  | P | [7 empty] | 80 | N | 1.93e-18 |  | 2021-10-14
DB Netz AG | 1.93e-20 | Rostock - Berlin | < | Lalendorf Ost | Langhagen | 2023 | 2023 | 43 | 43 | 2023-10-28 | 21:15 | 2023-10-29 | 0:00 | 0d, 2h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1.93e-20 |  | 2021-10-14
DB Netz AG | 1.93e-21 | Rostock - Berlin | < | Langhagen | Langhagen | 2023 | 2023 | 43 | 43 | 2023-10-28 | 21:15 | 2023-10-29 | 0:00 | 0d, 2h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1.93e-21 |  | 2021-10-14
DB Netz AG | 1.93e-22 | Rostock - Berlin | <> | Langhagen | Langhagen | 2023 | 2023 | 43 | 43 | 2023-10-28 | 21:15 | 2023-10-29 | 0:00 | 0d, 2h | Continuous | Track & Rail |  |  |  | P | [7 empty] | 80 | N | 1.93e-22 |  | 2021-10-14
DB Netz AG | 1.93e-24 | Rostock - Berlin | < | Langhagen | Vollrathsruhe | 2023 | 2023 | 43 | 44 | 2023-10-29 | 21:00 | 2023-10-30 | 5:00 | 0d, 8h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1.93e-24 |  | 2021-10-14
DB Netz AG | 1.93e-25 | Rostock - Berlin | < | Langhagen | Langhagen | 2023 | 2023 | 43 | 44 | 2023-10-29 | 21:00 | 2023-10-30 | 5:00 | 0d, 8h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1.93e-25 |  | 2021-10-14
DB Netz AG | 1.93e-26 | Rostock - Berlin | <> | Vollrathsruhe | Langhagen | 2023 | 2023 | 43 | 44 | 2023-10-29 | 21:00 | 2023-10-30 | 5:00 | 0d, 8h | Continuous | Track & Rail |  |  |  | P | [7 empty] | 80 | N | 1.93e-26 |  | 2021-10-14
DB Netz AG | 1.93e-28 | Rostock - Berlin | < | Vollrathsruhe | Vollrathsruhe | 2023 | 2023 | 44 | 44 | 2023-10-30 | 2:30 | 2023-10-30 | 5:00 | 0d, 2h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1.93e-28 |  | 2021-10-14
DB Netz AG | 1.93e-29 | Rostock - Berlin | < | Vollrathsruhe | Grabowhöfe | 2023 | 2023 | 44 | 44 | 2023-10-30 | 2:30 | 2023-10-30 | 5:00 | 0d, 2h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1.93e-29 |  | 2021-10-14
DB Netz AG | 1.93e-31 | Rostock - Berlin | <> | Vollrathsruhe | Vollrathsruhe | 2023 | 2023 | 44 | 44 | 2023-10-30 | 2:30 | 2023-10-30 | 5:00 | 0d, 2h | Continuous | Track & Rail |  |  |  | P | [7 empty] | 80 | N | 1.93e-31 |  | 2021-10-14
DB Netz AG | 1.93e-32 | Rostock - Berlin | < | Langhagen | Grabowhöfe | 2023 | 2023 | 44 | 44 | 2023-10-30 | 21:00 | 2023-10-31 | 5:00 | 0d, 8h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1.93e-32 |  | 2021-10-14
DB Netz AG | 1.93e-33 | Rostock - Berlin | < | Vollrathsruhe | Vollrathsruhe | 2023 | 2023 | 44 | 44 | 2023-10-30 | 21:00 | 2023-10-31 | 5:00 | 0d, 8h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1.93e-33 |  | 2021-10-14
DB Netz AG | 1.93e-37 | Rostock - Berlin | <> | Vollrathsruhe | Langhagen | 2023 | 2023 | 44 | 44 | 2023-10-30 | 21:00 | 2023-10-31 | 5:00 | 0d, 8h | Continuous | Track & Rail |  |  |  | P | [7 empty] | 80 | N | 1.93e-37 |  | 2021-10-14
DB Netz AG | 1.93e-38 | Rostock - Berlin | > | Vollrathsruhe | Vollrathsruhe | 2023 | 2023 | 44 | 44 | 2023-10-31 | 23:00 | 2023-11-01 | 5:00 | 0d, 6h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1.93e-38 |  | 2021-10-14
DB Netz AG | 1.93e-40 | Rostock - Berlin | <> | Vollrathsruhe | Vollrathsruhe | 2023 | 2023 | 44 | 44 | 2023-10-31 | 23:00 | 2023-11-01 | 5:00 | 0d, 6h | Continuous | Track & Rail |  |  |  | P | [7 empty] | 80 | N | 1.93e-40 |  | 2021-10-14
DB Netz AG | 1.93e-41 | Rostock - Berlin | > | Vollrathsruhe | Langhagen | 2023 | 2023 | 44 | 44 | 2023-10-31 | 23:00 | 2023-11-01 | 2:00 | 0d, 3h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1.93e-41 |  | 2021-10-14
DB Netz AG | 1.93e-43 | Rostock - Berlin | <> | Vollrathsruhe | Vollrathsruhe | 2023 | 2023 | 44 | 44 | 2023-10-31 | 23:00 | 2023-11-01 | 2:00 | 0d, 3h | Continuous | Track & Rail |  |  |  | P | [7 empty] | 80 | N | 1.93e-43 |  | 2021-10-14
DB Netz AG | 1.93e-44 | Rostock - Berlin | > | Grabowhöfe | Vollrathsruhe | 2023 | 2023 | 44 | 44 | 2023-11-01 | 2:00 | 2023-11-01 | 5:00 | 0d, 3h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1.93e-44 |  | 2021-10-14
DB Netz AG | 1.93e-46 | Rostock - Berlin | <> | Vollrathsruhe | Vollrathsruhe | 2023 | 2023 | 44 | 44 | 2023-11-01 | 2:00 | 2023-11-01 | 5:00 | 0d, 3h | Continuous | Track & Rail |  |  |  | P | [7 empty] | 80 | N | 1.93e-46 |  | 2021-10-14
DB Netz AG | 1.93e-47 | Rostock - Berlin | < | Langhagen | Vollrathsruhe | 2023 | 2023 | 44 | 44 | 2023-11-01 | 21:15 | 2023-11-02 | 5:00 | 0d, 7h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1.93e-47 |  | 2021-10-14
DB Netz AG | 1.93e-48 | Rostock - Berlin | < | Langhagen | Langhagen | 2023 | 2023 | 44 | 44 | 2023-11-01 | 21:15 | 2023-11-02 | 5:00 | 0d, 7h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1.93e-48 |  | 2021-10-14
DB Netz AG | 1.93e-50 | Rostock - Berlin | <> | Vollrathsruhe | Langhagen | 2023 | 2023 | 44 | 44 | 2023-11-01 | 21:15 | 2023-11-02 | 5:00 | 0d, 7h | Continuous | Track & Rail |  |  |  | P | [7 empty] | 80 | N | 1.93e-50 |  | 2021-10-14
DB Netz AG | 19F8-001 | Hamburg - Magdeburg | <> | Lüneburg Gbf | Lüneburg Gbf | 2023 | 2023 | 42 | 43 | 2023-10-22 | 22:40 | 2023-10-28 | 5:15 | 5d, 6h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 19F8-001 |  | 2021-05-14
DB Netz AG | 19F8-002 | Hamburg - Magdeburg | <> | Lüneburg Gbf | Lüneburg Gbf | 2023 | 2023 | 43 | 43 | 2023-10-23 | 21:40 | 2023-10-23 | 22:40 | 0d, 1h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 19F8-002 |  | 2021-05-14
DB Netz AG | 19F8-003 | Hamburg - Magdeburg | <> | Lüneburg Gbf | Lüneburg Gbf | 2023 | 2023 | 43 | 43 | 2023-10-23 | 21:40 | 2023-10-23 | 22:40 | 0d, 1h | Continuous | Signal |  |  |  |  | X | [6 empty] | 80 | N | 19F8-003 |  | 2021-05-14
DB Netz AG | 19F8-004 | Hamburg - Magdeburg | <> | Lüneburg Gbf | Lüneburg Gbf | 2023 | 2023 | 43 | 43 | 2023-10-28 | 5:15 | 2023-10-28 | 6:15 | 0d, 1h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 19F8-004 |  | 2021-05-14
DB Netz AG | 19F8-005 | Hamburg - Magdeburg | <> | Lüneburg Gbf | Lüneburg Gbf | 2023 | 2023 | 43 | 43 | 2023-10-28 | 5:15 | 2023-10-28 | 6:15 | 0d, 1h | Periodical | Signal |  |  |  |  | X | [6 empty] | 80 | N | 19F8-005 |  | 2021-05-14
DB Netz AG | 1B0C-001 | Rostock - Berlin | > | Grabowhöfe | Langhagen | 2023 | 2023 | 42 | 43 | 2023-10-22 | 22:00 | 2023-10-27 | 6:00 | 4d, 8h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 1B0C-001 |  | 2022-07-20
DB Netz AG | 1B0C-002 | Rostock - Berlin | > | Vollrathsruhe | Vollrathsruhe | 2023 | 2023 | 42 | 43 | 2023-10-22 | 22:00 | 2023-10-27 | 6:00 | 4d, 8h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 1B0C-002 |  | 2022-07-20
DB Netz AG | 1B0C-003 | Rostock - Berlin | <> | Grabowhöfe | Vollrathsruhe | 2023 | 2023 | 43 | 43 | 2023-10-23 | 2:00 | 2023-10-23 | 5:00 | 0d, 3h | Continuous | Catenary | T | [10 empty] | 80 | N | 1B0C-003 |  | 2022-07-20
DB Netz AG | 1B0C-004 | Rostock - Berlin | < | Vollrathsruhe | Vollrathsruhe | 2023 | 2023 | 43 | 43 | 2023-10-23 | 2:00 | 2023-10-23 | 5:00 | 0d, 3h | Continuous | Catenary |  | ST | [9 empty] | 80 | N | 1B0C-004 |  | 2022-07-20
DB Netz AG | 1B0C-005 | Rostock - Berlin | <> | Langhagen | Vollrathsruhe | 2023 | 2023 | 43 | 43 | 2023-10-27 | 2:00 | 2023-10-27 | 5:00 | 0d, 3h | Continuous | Catenary | T | [10 empty] | 80 | N | 1B0C-005 |  | 2022-07-20
DB Netz AG | 1B0C-006 | Rostock - Berlin | < | Vollrathsruhe | Vollrathsruhe | 2023 | 2023 | 43 | 43 | 2023-10-27 | 2:00 | 2023-10-27 | 5:00 | 0d, 3h | Continuous | Catenary |  | ST | [9 empty] | 80 | N | 1B0C-006 |  | 2022-07-20
DB Netz AG | 1B43-013 | Bremen - Hannover | <> | Seelze Ost | Seelze Ost | 2023 | 2023 | 42 | 42 | 2023-10-17 | 8:00 | 2023-10-17 | 12:00 | 0d, 4h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 1B43-013 |  | 2022-06-09
DB Netz AG | 1B43-014 | Bremen - Hannover | <> | Seelze Ost | Seelze Ost | 2023 | 2023 | 42 | 42 | 2023-10-17 | 12:00 | 2023-10-17 | 15:00 | 0d, 3h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 1B43-014 |  | 2022-06-09
DB Netz AG | 1D91-001 | Bremen - Hannover | > | Kurve | Seelze Ost | 2023 | 2023 | 42 | 43 | 2023-10-22 | 7:00 | 2023-10-29 | 15:00 | 7d, 9h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 1D91-001 |  | 2022-06-09
DB Netz AG | 1D91-002 | Bremen - Hannover | <> | Seelze Ost | Seelze Ost | 2023 | 2023 | 42 | 43 | 2023-10-22 | 7:00 | 2023-10-29 | 15:00 | 7d, 9h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 1D91-002 |  | 2022-06-09
DB Netz AG | 1D91-003 | Bremen - Hannover | <> | Kurve | Seelze Ost | 2023 | 2023 | 42 | 42 | 2023-10-16 | 7:00 | 2023-10-16 | 15:00 | 0d, 8h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 1D91-003 |  | 2022-06-09
DB Netz AG | 1D91-004 | Bremen - Hannover | <> | Seelze Ost | Seelze Ost | 2023 | 2023 | 42 | 42 | 2023-10-16 | 7:00 | 2023-10-16 | 15:00 | 0d, 8h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 1D91-004 |  | 2022-06-09
DB Netz AG | 1D91-005 | Bremen - Hannover | <> | Seelze Ost | Seelze Ost | 2023 | 2023 | 42 | 43 | 2023-10-22 | 7:00 | 2023-10-29 | 15:00 | 7d, 9h | Periodical | Catenary |  |  |  | P | [7 empty] | 80 | N | 1D91-005 |  | 2022-06-09
DB Netz AG | 1D91-006 | Bremen - Hannover | <> | Seelze Ost | Seelze Ost | 2023 | 2023 | 42 | 42 | 2023-10-22 | 7:00 | 2023-10-22 | 15:00 | 0d, 8h | Periodical | Catenary |  |  |  | P | [7 empty] | 80 | N | 1D91-006 |  | 2022-06-09
DB Netz AG | 2114-012 | Rostock - Berlin | <> | Ro Seehf Süd | Ro Seehf Süd | 2023 | 2023 | 42 | 42 | 2023-10-16 | 7:00 | 2023-10-18 | 17:00 | 2d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 2114-012
DB Netz AG | 2114-013 | Rostock - Berlin | <> | Ro Seehf Süd | Rostock Seehafen | 2023 | 2023 | 42 | 42 | 2023-10-19 | 7:00 | 2023-10-21 | 17:00 | 2d, 10h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | 2114-013
DB Netz AG | 2114-014 | Rostock - Berlin | <> | Ro Seehf Süd | Rostock Seehafen | 2023 | 2023 | 42 | 42 | 2023-10-19 | 7:00 | 2023-10-21 | 17:00 | 2d, 10h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | 2114-014
DB Netz AG | 2114-015 | Rostock - Berlin | <> | Ro Seehf Süd | Ro Seehf Süd | 2023 | 2023 | 42 | 42 | 2023-10-19 | 7:00 | 2023-10-21 | 17:00 | 2d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 2114-015
DB Netz AG | 2114-016 | Rostock - Berlin | <> | Ro Seehf Süd | Rostock Seehafen | 2023 | 2023 | 42 | 42 | 2023-10-19 | 7:00 | 2023-10-21 | 17:00 | 2d, 10h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 2114-016
DB Netz AG | 2114-017 | Rostock - Berlin | <> | Rostock Seehafen | Riekdahl | 2023 | 2023 | 42 | 43 | 2023-10-22 | 8:00 | 2023-10-29 | 18:00 | 7d, 11h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | 2114-017
DB Netz AG | 2114-018 | Rostock - Berlin | <> | Ro Seehf Süd | Ro Seehf Süd | 2023 | 2023 | 42 | 43 | 2023-10-22 | 8:00 | 2023-10-29 | 18:00 | 7d, 11h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 2114-018
DB Netz AG | 2114-019 | Rostock - Berlin | <> | Ro Seehf Süd | Ro Seehf Süd | 2023 | 2023 | 42 | 43 | 2023-10-22 | 8:00 | 2023-10-29 | 18:00 | 7d, 11h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 2114-019
DB Netz AG | 2114-020 | Rostock - Berlin | <> | Ro Seehf Süd | Ro Seehf Süd | 2023 | 2023 | 42 | 43 | 2023-10-22 | 8:00 | 2023-10-29 | 18:00 | 7d, 11h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 2114-020
DB Netz AG | 2171-001 | Rostock - Berlin | <> | Ro Seehf Süd | Rostock Seehafen | 2023 | 2023 | 44 | 44 | 2023-10-30 | 8:00 | 2023-11-03 | 18:00 | 4d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 2171-001
DB Netz AG | 2171-002 | Rostock - Berlin | <> | Ro Seehf Süd | Ro Seehf Süd | 2023 | 2023 | 44 | 44 | 2023-10-30 | 8:01 | 2023-11-03 | 18:00 | 4d, 9h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 2171-002
DB Netz AG | 2171-003 | Rostock - Berlin | <> | Ro Seehf Süd | Ro Seehf Süd | 2023 | 2023 | 44 | 44 | 2023-10-30 | 8:02 | 2023-11-02 | 18:00 | 3d, 9h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 2171-003
DB Netz AG | 2171-004 | Rostock - Berlin | <> | Riekdahl | Ro Seehf Süd | 2023 | 2023 | 44 | 44 | 2023-10-30 | 8:02 | 2023-11-02 | 18:00 | 3d, 9h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | 2171-004
DB Netz AG | A4C-006 | Hamburg - Magdeburg | < | Magdeburg Hbf | Magdeburg-Buckau | 2023 | 2023 | 47 | 48 | 2023-11-21 | 8:00 | 2023-11-27 | 16:00 | 6d, 8h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | A4C-006 |  | 2021-05-18
DB Netz AG | A4C-008 | Hannover - Magdeburg | <> | Magdeburg-Buckau | Mg-Sudenburg | 2023 | 2023 | 47 | 48 | 2023-11-21 | 8:00 | 2023-11-27 | 16:00 | 6d, 8h | Periodical | Catenary | T | [10 empty] | 80 | N | A4C-008 |  | 2021-06-01
DB Netz AG | A6A-002 | Bremen - Hannover | <> | Ahlem | Hannover-Linden | 2023 | 2023 | 44 | 44 | 2023-11-04 | 1:00 | 2023-11-04 | 6:00 | 0d, 5h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | A6A-002 |  | 2021-05-17
DB Netz AG | A6A-001 | Bremen - Hannover | <> | Han-Linden Hafen | Empelde Abzw | 2023 | 2023 | 44 | 44 | 2023-11-04 | 1:00 | 2023-11-04 | 6:00 | 0d, 5h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | A6A-001 |  | 2021-05-17
DB Netz AG | A6A-003 | Bremen - Hannover | <> | Ahlem | Hannover-Linden | 2023 | 2023 | 46 | 46 | 2023-11-13 | 23:00 | 2023-11-14 | 4:00 | 0d, 5h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | A6A-003 |  | 2021-05-17
DB Netz AG | A6A-004 | Bremen - Hannover | <> | Han-Linden Hafen | Empelde Abzw | 2023 | 2023 | 46 | 46 | 2023-11-13 | 23:00 | 2023-11-14 | 4:00 | 0d, 5h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | A6A-004 |  | 2021-05-17
DB Netz AG | A6A-005 | Bremen - Hannover | > | Han-Linden Hafen | Han-Linden Hafen | 2023 | 2023 | 44 | 46 | 2023-11-04 | 6:00 | 2023-11-13 | 23:00 | 9d, 17h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | A6A-005 |  | 2021-05-17
DB Netz AG | AB9-004 | Falkenberg - Dresden | <> | Coswig Stw 1 | Miltitz-Roitzsch | 2023 | 2023 | 47 | 47 | 2023-11-23 | 23:30 | 2023-11-24 | 4:00 | 0d, 4h | Continuous | Signal | T | [10 empty] | 80 | N | AB9-004 |  | 2022-06-22
DB Netz AG | ACE-006 | Bremen - Hannover | <> | Bremen Hbf | Bremen Hbf | 2023 | 2023 | 47 | 49 | 2023-11-25 | 22:00 | 2023-12-06 | 5:00 | 10d, 7h | Periodical | Signal |  | ST | [9 empty] | 80 | N | ACE-006 |  | 2021-05-27
DB Netz AG | AF1-009 | Hamburg - Magdeburg | < | Lüneburg Nordk | Lüneburg Gbf | 2023 | 2023 | 48 | 48 | 2023-11-27 | 22:40 | 2023-12-02 | 5:15 | 4d, 6h | Periodical | Signal |  | ST | [9 empty] | 80 | N | AF1-009 |  | 2021-05-07
DB Netz AG | AF1-007 | Hamburg - Magdeburg | <> | Lüneburg Gbf | Lüneburg Gbf | 2023 | 2023 | 48 | 48 | 2023-11-27 | 22:40 | 2023-12-02 | 5:15 | 4d, 6h | Periodical | Signal |  | ST | [9 empty] | 80 | N | AF1-007 |  | 2021-05-07
DB Netz AG | AF1-008 | Hamburg - Magdeburg | <> | Lüneburg Gbf | Lüneburg Gbf | 2023 | 2023 | 48 | 48 | 2023-11-27 | 22:40 | 2023-12-02 | 5:15 | 4d, 6h | Periodical | Signal |  | ST | [9 empty] | 80 | N | AF1-008 |  | 2021-05-07
DB Netz AG | B4E-005 | Rostock - Berlin | < | Grün Kreuz Süd | Grün Kreuz West | 2023 | 2023 | 45 | 47 | 2023-11-10 | 22:00 | 2023-11-24 | 22:00 | 14d, 0h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | B4E-005 |  | 2021-04-26
DB Netz AG | B4E-004 | Rostock - Berlin | > | Grün Kreuz Nord | Bln-Grünau | 2023 | 2023 | 45 | 47 | 2023-11-10 | 22:00 | 2023-11-24 | 22:00 | 14d, 0h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | B4E-004 |  | 2021-04-30
DB Netz AG | BC2-006 | Hannover - Magdeburg | <> | Magdeburg-Buckau | Mg-Sudenburg | 2023 | 2023 | 48 | 48 | 2023-11-28 | 8:00 | 2023-11-30 | 16:00 | 2d, 8h | Periodical | Catenary | T | [10 empty] | 80 | N | BC2-006 |  | 2021-06-02
DB Netz AG | BC2-004 | Hamburg - Magdeburg | < | Magdeburg Hbf | Magdeburg-Buckau | 2023 | 2023 | 48 | 48 | 2023-11-28 | 8:00 | 2023-11-30 | 16:00 | 2d, 8h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | BC2-004 |  | 2021-05-18
DB Netz AG | BC3-001 | Hamburg - Magdeburg | < | Celle | Lehrte | 2023 | 2023 | 44 | 46 | 2023-11-03 | 23:00 | 2023-11-17 | 5:00 | 13d, 6h | Periodical | Maintenance |  | LT | [9 empty] | 80 | N | BC3-001 |  | 2021-05-12
DB Netz AG | BC4-001 | Hamburg - Magdeburg | < | Hmb-Harburg | Celle | 2023 | 2023 | 44 | 46 | 2023-11-03 | 23:00 | 2023-11-17 | 5:00 | 13d, 6h | Periodical | Maintenance |  | LT | [9 empty] | 80 | N | BC4-001 |  | 2021-06-18
DB Netz AG | BD0-010 | Bremerhaven - Bremen | > | Bremen-Burg | Osterholz-Scharm | 2023 | 2023 | 47 | 47 | 2023-11-24 | 23:00 | 2023-11-25 | 2:00 | 0d, 3h | Continuous | Signal |  | LT | [9 empty] | 80 | N | BD0-010 |  | 2021-05-26
DB Netz AG | BD0-020 | Bremerhaven - Bremen | < | Osterholz-Scharm | Bremen-Burg | 2023 | 2023 | 47 | 47 | 2023-11-25 | 2:00 | 2023-11-25 | 5:00 | 0d, 3h | Continuous | Signal |  | LT | [9 empty] | 80 | N | BD0-020 |  | 2021-05-26
DB Netz AG | BD0-003 | Bremerhaven - Bremen | <> | Bremen-Burg | Osterholz-Scharm | 2023 | 2023 | 47 | 47 | 2023-11-25 | 2:00 | 2023-11-25 | 5:00 | 0d, 3h | Continuous | Signal |  |  | S | [8 empty] | 80 | N | BD0-003 |  | 2021-07-21
DB Netz AG | BD0-008 | Bremerhaven - Bremen | <> | Osterholz-Scharm | Bremen-Burg | 2023 | 2023 | 47 | 47 | 2023-11-24 | 23:00 | 2023-11-25 | 2:00 | 0d, 3h | Continuous | Signal |  |  | S | [8 empty] | 80 | N | BD0-008 |  | 2021-07-21
DB Netz AG | BD0-016 | Bremerhaven - Bremen | <> | Bremen-Burg | Osterholz-Scharm | 2023 | 2023 | 46 | 47 | 2023-11-14 | 23:00 | 2023-11-24 | 5:00 | 9d, 6h | Periodical | Signal |  |  | S | [8 empty] | 80 | N | BD0-016 |  | 2021-07-21
DB Netz AG | BD0-005 | Bremerhaven - Bremen | < | Osterholz-Scharm | Bremen-Burg | 2023 | 2023 | 46 | 47 | 2023-11-14 | 23:00 | 2023-11-24 | 5:00 | 9d, 6h | Periodical | Signal |  | LT | [9 empty] | 80 | N | BD0-005 |  | 2021-05-26
DB Netz AG | C4E-001 | Hamburg - Magdeburg | > | Magdeburg-Buckau | Magdeburg Hbf | 2023 | 2023 | 47 | 47 | 2023-11-20 | 8:00 | 2023-11-20 | 16:00 | 0d, 8h | Continuous | Catenary |  | LT | [9 empty] | 80 | N | C4E-001 |  | 2021-05-18
DB Netz AG | C4E-004 | Hamburg - Magdeburg | > | Magdeburg-Buckau | Magdeburg Hbf | 2023 | 2023 | 46 | 46 | 2023-11-17 | 6:00 | 2023-11-17 | 18:00 | 0d, 12h | Continuous | Catenary |  | LT | [9 empty] | 80 | N | C4E-004 |  | 2021-05-18
DB Netz AG | 130A-001 | Rostock - Berlin | <> | Schönfließ West | Hohen Neuend Sw | 2023 | 2023 | 45 | 46 | 2023-11-10 | 22:00 | 2023-11-13 | 4:00 | 2d, 6h | Continuous | Signal | T | [10 empty] | 80 | N | 130A-001 |  | 2021-09-07
DB Netz AG | 130A-005 | Rostock - Berlin | <> | Birkenwerd b Bln | Oranienburg | 2023 | 2023 | 45 | 46 | 2023-11-10 | 22:00 | 2023-11-13 | 4:00 | 2d, 6h | Continuous | Signal | T | [10 empty] | 80 | N | 130A-005 |  | 2021-09-07
DB Netz AG | 130A-004 | Rostock - Berlin | <> | Hohen Neuend W | Birkenwerd b Bln | 2023 | 2023 | 45 | 46 | 2023-11-10 | 22:00 | 2023-11-13 | 4:00 | 2d, 6h | Continuous | Signal | T | [10 empty] | 80 | N | 130A-004 |  | 2021-11-15
DB Netz AG | 130A-002 | Rostock - Berlin | <> | Schönfließ West | Birkenwerd b Bln | 2023 | 2023 | 45 | 46 | 2023-11-10 | 22:00 | 2023-11-13 | 4:00 | 2d, 6h | Continuous | Signal | T | [10 empty] | 80 | N | 130A-002 |  | 2021-11-15
DB Netz AG | 130A-003 | Rostock - Berlin | <> | Bergfelde Ost | Hohen Neuend Sw | 2023 | 2023 | 45 | 46 | 2023-11-10 | 22:00 | 2023-11-13 | 4:00 | 2d, 6h | Continuous | Signal | T | [10 empty] | 80 | N | 130A-003 |  | 2021-09-07
DB Netz AG | 1965-001 | Rostock - Berlin | <> | Bergfelde Ost | Hohen Neuend Sw | 2023 | 2023 | 47 | 48 | 2023-11-25 | 8:00 | 2023-11-27 | 18:00 | 2d, 10h | Periodical | Signal | T | [10 empty] | 80 | N | 1965-001 |  | 2021-08-05
DB Netz AG | 1965-002 | Rostock - Berlin | <> | Birkenwerd b Bln | Birkenwerd b Bln | 2023 | 2023 | 47 | 48 | 2023-11-25 | 8:00 | 2023-11-27 | 18:00 | 2d, 10h | Periodical | Signal |  | ST | [9 empty] | 80 | N | 1965-002 |  | 2021-05-05
DB Netz AG | 1965-003 | Rostock - Berlin | <> | Birkenwerd b Bln | Birkenwerd b Bln | 2023 | 2023 | 48 | 48 | 2023-11-28 | 8:00 | 2023-12-01 | 18:00 | 3d, 10h | Periodical | Signal |  | ST | [9 empty] | 80 | N | 1965-003 |  | 2021-05-06
DB Netz AG | 1965-004 | Rostock - Berlin | <> | Schönfließ West | Birkenwerd b Bln | 2023 | 2023 | 47 | 48 | 2023-11-25 | 8:00 | 2023-11-27 | 18:00 | 2d, 10h | Periodical | Signal | T | [10 empty] | 80 | N | 1965-004 |  | 2021-08-05
DB Netz AG | 1965-005 | Rostock - Berlin | <> | Hohen Neuend Sw | Schönfließ West | 2023 | 2023 | 47 | 47 | 2023-11-20 | 8:00 | 2023-11-24 | 18:00 | 4d, 10h | Periodical | Signal | T | [10 empty] | 80 | N | 1965-005 |  | 2021-09-15
DB Netz AG | 1965-006 | Rostock - Berlin | <> | Birkenwerd b Bln | Birkenwerd b Bln | 2023 | 2023 | 47 | 47 | 2023-11-20 | 8:00 | 2023-11-24 | 18:00 | 4d, 10h | Periodical | Signal |  | ST | [9 empty] | 80 | N | 1965-006 |  | 2021-08-20
DB Netz AG | 1965-007 | Rostock - Berlin | <> | Birkenwerd b Bln | Hohen Neuend W | 2023 | 2023 | 47 | 47 | 2023-11-20 | 8:00 | 2023-11-24 | 18:00 | 4d, 10h | Periodical | Signal | T | [10 empty] | 80 | N | 1965-007 |  | 2021-09-15
DB Netz AG | 1965-008 | Rostock - Berlin | <> | Birkenwerd b Bln | Birkenwerd b Bln | 2023 | 2023 | 46 | 46 | 2023-11-17 | 8:00 | 2023-11-19 | 18:00 | 2d, 10h | Periodical | Signal |  | ST | [9 empty] | 80 | N | 1965-008 |  | 2021-05-06
DB Netz AG | 1965-009 | Rostock - Berlin | <> | Schönfließ West | Birkenwerd b Bln | 2023 | 2023 | 46 | 46 | 2023-11-17 | 8:00 | 2023-11-19 | 18:00 | 2d, 10h | Periodical | Signal | T | [10 empty] | 80 | N | 1965-009 |  | 2021-05-06
DB Netz AG | 1965-010 | Rostock - Berlin | > | Birkenwerd b Bln | Oranienburg | 2023 | 2023 | 46 | 46 | 2023-11-17 | 8:00 | 2023-11-19 | 18:00 | 2d, 10h | Periodical | Signal |  | LT | [9 empty] | 80 | N | 1965-010 |  | 2021-10-26
DB Netz AG | 1965-011 | Rostock - Berlin | <> | Oranienburg | Oranienburg | 2023 | 2023 | 46 | 46 | 2023-11-13 | 8:00 | 2023-11-16 | 18:00 | 3d, 10h | Periodical | Signal |  | ST | [9 empty] | 80 | N | 1965-011 |  | 2021-05-06
DB Netz AG | 1965-012 | Rostock - Berlin | <> | Birkenwerd b Bln | Birkenwerd b Bln | 2023 | 2023 | 46 | 46 | 2023-11-13 | 8:00 | 2023-11-16 | 18:00 | 3d, 10h | Periodical | Signal |  | ST | [9 empty] | 80 | N | 1965-012 |  | 2021-05-06
DB Netz AG | 1965-013 | Rostock - Berlin | < | Oranienburg | Birkenwerd b Bln | 2023 | 2023 | 46 | 46 | 2023-11-13 | 8:00 | 2023-11-16 | 18:00 | 3d, 10h | Periodical | Signal |  | LT | [9 empty] | 80 | N | 1965-013 |  | 2021-10-26
DB Netz AG | 130B-004 | Rostock - Berlin | <> | Birkenwerd b Bln | Birkenwerder N | 2023 | 2023 | 44 | 45 | 2023-11-03 | 22:00 | 2023-11-06 | 4:00 | 2d, 6h | Continuous |  |  | ST | [9 empty] | 80 | N | 130B-004 |  | 2021-05-07
DB Netz AG | DC8-008 | Dresden - Děčín | <> | Bad Schandau Ost | Bad Schandau Gr | 2023 | 2023 | 46 | 46 | 2023-11-13 | 9:00 | 2023-11-17 | 15:00 | 4d, 6h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80,54 | N | DC8-008 |  | 2021-05-30
DB Netz AG | DC8-005 | Dresden - Děčín | <> | Bad Schandau Ost | Schöna | 2023 | 2023 | 46 | 46 | 2023-11-13 | 9:00 | 2023-11-17 | 15:00 | 4d, 6h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | DC8-005 |  | 2021-05-30
DB Netz AG | FFE-002 | Dresden - Děčín | <> | Dresden Hbf | Bad Schandau Ost | 2023 | 2023 | 48 | 48 | 2023-11-28 | 23:00 | 2023-11-29 | 4:00 | 0d, 5h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | FFE-002 |  | 2021-05-30
DB Netz AG | FFE-007 | Dresden - Děčín | <> | Bad Schandau | Sebnitz (Sachs) | 2023 | 2023 | 48 | 48 | 2023-11-28 | 23:00 | 2023-11-29 | 4:00 | 0d, 5h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | FFE-007 |  | 2021-05-30
DB Netz AG | FFE-003 | Dresden - Děčín | <> | Pirna | Dürrröhrsdorf | 2023 | 2023 | 48 | 48 | 2023-11-28 | 23:00 | 2023-11-29 | 4:00 | 0d, 5h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | FFE-003 |  | 2021-05-30
DB Netz AG | FFE-009 | Dresden - Děčín | <> | Dresden Hbf | Pirna | 2023 | 2023 | 48 | 48 | 2023-11-28 | 23:00 | 2023-11-29 | 4:00 | 0d, 5h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | FFE-009 |  | 2021-05-30
DB Netz AG | FFE-008 | Dresden - Děčín | <> | Heidenau | Dohna (Sachs) | 2023 | 2023 | 48 | 48 | 2023-11-28 | 23:00 | 2023-11-29 | 4:00 | 0d, 5h | Continuous | Miscellaneous | T | [10 empty] | 80 | N | FFE-008 |  | 2021-05-30
DB Netz AG | FFE-010 | Dresden - Děčín | <> | Bad Schandau Ost | Bad Schandau Ost | 2023 | 2023 | 48 | 48 | 2023-11-28 | 7:00 | 2023-11-29 | 7:00 | 1d, 0h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | FFE-010 |  | 2021-05-30
DB Netz AG | FFE-006 | Dresden - Děčín | <> | Schöna | Schöna | 2023 | 2023 | 48 | 48 | 2023-11-28 | 7:00 | 2023-11-29 | 7:00 | 1d, 0h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | FFE-006 |  | 2021-05-30
DB Netz AG | FFE-001 | Dresden - Děčín | <> | Bad Schandau | Bad Schandau | 2023 | 2023 | 48 | 48 | 2023-11-28 | 7:00 | 2023-11-29 | 7:00 | 1d, 0h | Continuous | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | FFE-001 |  | 2021-05-30
DB Netz AG | FFE-004 | Dresden - Děčín | <> | Bad Schandau | Bad Schandau Gr | 2023 | 2023 | 48 | 48 | 2023-11-28 | 7:00 | 2023-11-29 | 7:00 | 1d, 0h | Continuous | Miscellaneous | T | [10 empty] | 80,54 | N | FFE-004 |  | 2021-05-30
DB Netz AG | 1082-014 | Bremen - Hannover | > | Bremen-Mahndorf | Bremen Hbf | 2023 | 2023 | 45 | 45 | 2023-11-10 | 0:00 | 2023-11-11 | 5:30 | 1d, 5h | Periodical | Bridge |  | LT | [9 empty] | 80 | N | 1082-014 |  | 2021-05-27
DB Netz AG | 10D3-003 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 44 | 44 | 2023-11-02 | 22:00 | 2023-11-04 | 5:00 | 1d, 7h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 10D3-003 |  | 2021-05-31
DB Netz AG | 10D3-001 | Dresden - Děčín | <> | Dresden Hbf | Dre Freibg Str | 2023 | 2023 | 44 | 44 | 2023-11-02 | 22:00 | 2023-11-04 | 5:00 | 1d, 7h | Periodical | Catenary | T | [10 empty] | 80 | N | 10D3-001 |  | 2021-07-01
DB Netz AG | 118B-001 | Hannover - Magdeburg | > | Braunschweig Hbf | Helmstedt | 2023 | 2023 | 48 | 48 | 2023-11-28 | 23:00 | 2023-12-03 | 5:00 | 4d, 6h | Periodical | Maintenance |  | LT | [9 empty] | 80 | N | 118B-001 |  | 2022-06-07
DB Netz AG | 11D9-002 | Magdeburg - Falkenberg | > | Magdeburg Hbf | Helmstedt | 2023 | 2023 | 46 | 48 | 2023-11-16 | 21:00 | 2023-11-30 | 5:00 | 13d, 8h | Periodical | Maintenance |  | LT | [9 empty] | 80 | N | 11D9-002 |  | 2022-05-19
DB Netz AG | 1225-001 | Bremen - Hannover | > | Wunstorf | Minden (Westf) | 2023 | 2023 | 46 | 48 | 2023-11-13 | 23:00 | 2023-11-27 | 5:00 | 13d, 6h | Periodical | Maintenance |  | LT | [9 empty] | 80 | N | 1225-001 |  | 2021-01-12
DB Netz AG | FFE-011 | Dresden - Děčín | <> | Bad Schandau Gr | Dolni Zleb | 2023 | 2023 | 48 | 48 | 2023-11-28 | 7:00 | 2023-11-29 | 7:00 | 1d, 0h | Continuous | Miscellaneous | T | [10 empty] | 80,54,80,54 | N | FFE-011 |  | 2021-06-03
DB Netz AG | DC8-012 | Dresden - Děčín | <> | Bad Schandau Gr | Dolni Zleb | 2023 | 2023 | 46 | 46 | 2023-11-13 | 9:00 | 2023-11-17 | 15:00 | 4d, 6h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80,54,80,54 | N | DC8-012 |  | 2021-05-31
DB Netz AG | 1544-001 | Magdeburg - Falkenberg | < | Coswig (Anh) Gbf | Lu Wb-P Wbf West | 2023 | 2023 | 46 | 47 | 2023-11-13 | 7:00 | 2023-11-23 | 13:00 | 10d, 6h | Periodical | Bridge |  | LT | [9 empty] | 80 | N | 1544-001 |  | 2021-05-20
DB Netz AG | 1544-002 | Magdeburg - Falkenberg | > | Lu Wb-P Wbf West | Coswig (Anh) Gbf | 2023 | 2023 | 48 | 48 | 2023-11-27 | 7:00 | 2023-11-30 | 13:00 | 3d, 6h | Periodical | Bridge |  | LT | [9 empty] | 80 | N | 1544-002 |  | 2021-05-20
DB Netz AG | 1544-003 | Magdeburg - Falkenberg | <> | Coswig (Anh) Gbf | Coswig (Anh) Gbf | 2023 | 2023 | 45 | 45 | 2023-11-11 | 7:00 | 2023-11-12 | 11:00 | 1d, 4h | Periodical | Bridge |  | ST | [9 empty] | 80 | N | 1544-003 |  | 2021-05-20
DB Netz AG | 1544-005 | Magdeburg - Falkenberg | > | Lu Wb-P Wbf West | Coswig (Anh) Gbf | 2023 | 2023 | 45 | 45 | 2023-11-11 | 7:00 | 2023-11-12 | 11:00 | 1d, 4h | Periodical | Bridge |  | LT | [9 empty] | 80 | N | 1544-005 |  | 2021-05-20
DB Netz AG | 1544-006 | Magdeburg - Falkenberg | > | Lu Wb-P Wbf West | Coswig (Anh) Gbf | 2023 | 2023 | 45 | 45 | 2023-11-11 | 7:00 | 2023-11-12 | 11:00 | 1d, 4h | Periodical | Bridge |  | LT | [9 empty] | 80 | N | 1544-006 |  | 2021-05-20
DB Netz AG | 16CB-001 | Dresden - Děčín | <> | Dresden Hbf | Dre Freibg Str | 2023 | 2023 | 44 | 45 | 2023-11-04 | 4:00 | 2023-11-09 | 5:00 | 5d, 1h | Periodical | Catenary | T | [10 empty] | 80 | N | 16CB-001 |  | 2021-09-10
DB Netz AG | 16CB-002 | Dresden - Děčín | <> | Dresden Hbf | Dre Freibg Str | 2023 | 2023 | 44 | 45 | 2023-11-04 | 4:00 | 2023-11-09 | 5:00 | 5d, 1h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 16CB-002 |  | 2021-09-10
DB Netz AG | 16CB-003 | Dresden - Děčín | <> | Dre Freibg Str | Dresden-Altstadt | 2023 | 2023 | 44 | 45 | 2023-11-04 | 4:00 | 2023-11-09 | 5:00 | 5d, 1h | Periodical | Catenary | T | [10 empty] | 80 | N | 16CB-003 |  | 2021-09-10
DB Netz AG | 16CB-004 | Dresden - Děčín | <> | Dre-Friedrichst | Dre Freibg Str | 2023 | 2023 | 44 | 45 | 2023-11-04 | 4:00 | 2023-11-09 | 5:00 | 5d, 1h | Periodical | Catenary | T | [10 empty] | 80 | N | 16CB-004 |  | 2021-09-10
DB Netz AG | 16CB-005 | Dresden - Děčín | <> | Dresden Hbf | Dre Freibg Str | 2023 | 2023 | 44 | 45 | 2023-11-04 | 4:00 | 2023-11-09 | 5:00 | 5d, 1h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 16CB-005 |  | 2021-09-10
DB Netz AG | 16CB-006 | Dresden - Děčín | <> | Dresden Hbf | Dre Freibg Str | 2023 | 2023 | 44 | 45 | 2023-11-04 | 4:00 | 2023-11-09 | 5:00 | 5d, 1h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 16CB-006 |  | 2021-09-10
DB Netz AG | 16CB-007 | Dresden - Děčín | <> | Dresden Hbf | Dre Freibg Str | 2023 | 2023 | 44 | 45 | 2023-11-04 | 19:00 | 2023-11-09 | 20:00 | 5d, 1h | Periodical | Catenary | T | [10 empty] | 80 | N | 16CB-007 |  | 2021-09-10
DB Netz AG | 16CB-008 | Dresden - Děčín | <> | Dresden Hbf | Dre Freibg Str | 2023 | 2023 | 44 | 45 | 2023-11-04 | 19:00 | 2023-11-09 | 20:00 | 5d, 1h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 16CB-008 |  | 2021-09-10
DB Netz AG | 16CB-009 | Dresden - Děčín | <> | Dresden-Altstadt | Dre Freibg Str | 2023 | 2023 | 44 | 45 | 2023-11-04 | 19:00 | 2023-11-09 | 20:00 | 5d, 1h | Periodical | Catenary | T | [10 empty] | 80 | N | 16CB-009 |  | 2021-09-10
DB Netz AG | 16CB-010 | Dresden - Děčín | <> | Dre-Friedrichst | Dre Freibg Str | 2023 | 2023 | 44 | 45 | 2023-11-04 | 19:00 | 2023-11-09 | 20:00 | 5d, 1h | Periodical | Catenary | T | [10 empty] | 80 | N | 16CB-010 |  | 2021-09-10
DB Netz AG | 16CB-011 | Dresden - Děčín | <> | Dresden Hbf | Dre Freibg Str | 2023 | 2023 | 44 | 45 | 2023-11-04 | 19:00 | 2023-11-09 | 20:00 | 5d, 1h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 16CB-011 |  | 2021-09-10
DB Netz AG | 16CB-012 | Dresden - Děčín | <> | Dresden Hbf | Dre Freibg Str | 2023 | 2023 | 44 | 45 | 2023-11-04 | 19:00 | 2023-11-09 | 20:00 | 5d, 1h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 16CB-012 |  | 2021-09-10
DB Netz AG | 16CB-013 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 44 | 45 | 2023-11-04 | 5:00 | 2023-11-09 | 19:00 | 5d, 14h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 16CB-013 |  | 2021-09-10
DB Netz AG | 16CB-014 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 44 | 45 | 2023-11-04 | 5:00 | 2023-11-09 | 19:00 | 5d, 14h | Periodical | Catenary | T | [10 empty] | 80 | N | 16CB-014 |  | 2021-09-10
DB Netz AG | 16CB-015 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 44 | 45 | 2023-11-04 | 5:00 | 2023-11-09 | 19:00 | 5d, 14h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 16CB-015 |  | 2021-09-10
DB Netz AG | 16CE-001 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 48 | 49 | 2023-11-27 | 4:00 | 2023-12-05 | 20:00 | 8d, 16h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 16CE-001 |  | 2021-09-10
DB Netz AG | 16CE-002 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 48 | 49 | 2023-11-27 | 4:00 | 2023-12-05 | 20:00 | 8d, 16h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 16CE-002 |  | 2021-09-10
DB Netz AG | 1708-001 | Dresden - Děčín | > | Pirna | Heidenau | 2023 | 2023 | 46 | 46 | 2023-11-13 | 21:00 | 2023-11-13 | 23:00 | 0d, 2h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1708-001 |  | 2021-04-07
DB Netz AG | 1708-002 | Dresden - Děčín | <> | Heidenau | Pirna Gbf | 2023 | 2023 | 46 | 46 | 2023-11-13 | 23:00 | 2023-11-14 | 0:30 | 0d, 1h | Continuous | Maintenance | T | [10 empty] | 80 | N | 1708-002 |  | 2021-04-07
DB Netz AG | 1708-003 | Dresden - Děčín | < | Dre-Niedersedl | Pirna Gbf | 2023 | 2023 | 46 | 46 | 2023-11-14 | 0:30 | 2023-11-14 | 4:30 | 0d, 4h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1708-003 |  | 2021-04-07
DB Netz AG | 1708-004 | Dresden - Děčín | <> | Heidenau | Heidenau | 2023 | 2023 | 46 | 46 | 2023-11-14 | 0:30 | 2023-11-14 | 4:30 | 0d, 4h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 1708-004 |  | 2021-04-07
DB Netz AG | 1708-005 | Dresden - Děčín | > | Heidenau | Dre-Niedersedl | 2023 | 2023 | 46 | 46 | 2023-11-14 | 21:00 | 2023-11-15 | 0:00 | 0d, 3h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1708-005 |  | 2021-04-07
DB Netz AG | 1708-006 | Dresden - Děčín | <> | Heidenau | Dre-Niedersedl | 2023 | 2023 | 46 | 46 | 2023-11-15 | 0:00 | 2023-11-15 | 1:30 | 0d, 1h | Continuous | Maintenance | T | [10 empty] | 80 | N | 1708-006 |  | 2021-04-07
DB Netz AG | 1708-007 | Dresden - Děčín | < | Dre-Niedersedl | Heidenau | 2023 | 2023 | 46 | 46 | 2023-11-15 | 1:30 | 2023-11-15 | 4:30 | 0d, 3h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1708-007 |  | 2021-04-07
DB Netz AG | 1708-008 | Dresden - Děčín | <> | Heidenau | Heidenau | 2023 | 2023 | 46 | 46 | 2023-11-15 | 1:30 | 2023-11-15 | 4:30 | 0d, 3h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 1708-008 |  | 2021-04-07
DB Netz AG | 1708-009 | Dresden - Děčín | > | Pirna | Dresden-Reick | 2023 | 2023 | 46 | 46 | 2023-11-15 | 21:00 | 2023-11-16 | 0:00 | 0d, 3h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1708-009 |  | 2021-04-07
DB Netz AG | 1708-010 | Dresden - Děčín | < | Dresden-Reick | Pirna | 2023 | 2023 | 46 | 46 | 2023-11-16 | 0:00 | 2023-11-16 | 4:30 | 0d, 4h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1708-010 |  | 2021-04-07
DB Netz AG | 1708-011 | Dresden - Děčín | < | Dresden-Reick | Pirna | 2023 | 2023 | 46 | 46 | 2023-11-16 | 21:00 | 2023-11-17 | 4:30 | 0d, 7h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1708-011 |  | 2021-04-07
DB Netz AG | 1708-012 | Dresden - Děčín | > | Heidenau | Dre-Niedersedl | 2023 | 2023 | 46 | 46 | 2023-11-17 | 0:30 | 2023-11-17 | 2:00 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1708-012 |  | 2021-04-07
DB Netz AG | 1708-013 | Dresden - Děčín | <> | Pirna | Dresden-Reick | 2023 | 2023 | 46 | 46 | 2023-11-17 | 2:00 | 2023-11-17 | 4:30 | 0d, 2h | Continuous | Maintenance | T | [10 empty] | 80 | N | 1708-013 |  | 2021-04-07
DB Netz AG | 1708-014 | Dresden - Děčín | > | Pirna | Dresden-Reick | 2023 | 2023 | 46 | 46 | 2023-11-17 | 21:00 | 2023-11-18 | 4:00 | 0d, 7h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1708-014 |  | 2021-04-07
DB Netz AG | 1708-015 | Dresden - Děčín | <> | Heidenau | Dresden-Reick | 2023 | 2023 | 46 | 46 | 2023-11-18 | 1:30 | 2023-11-18 | 4:00 | 0d, 2h | Continuous | Maintenance | T | [10 empty] | 80 | N | 1708-015 |  | 2021-04-07
DB Netz AG | 1714-001 | Dresden - Děčín | < | Kurort Rathen | Bad Schandau | 2023 | 2023 | 46 | 46 | 2023-11-18 | 20:00 | 2023-11-18 | 23:00 | 0d, 3h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1714-001 |  | 2021-12-23
DB Netz AG | 1714-002 | Dresden - Děčín | > | Bad Schandau | Kurort Rathen | 2023 | 2023 | 46 | 46 | 2023-11-18 | 23:00 | 2023-11-19 | 4:00 | 0d, 5h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1714-002 |  | 2021-04-07
DB Netz AG | 1714-003 | Dresden - Děčín | <> | Kurort Rathen | Bad Schandau | 2023 | 2023 | 46 | 46 | 2023-11-19 | 1:00 | 2023-11-19 | 4:00 | 0d, 3h | Continuous | Maintenance | T | [10 empty] | 80 | N | 1714-003 |  | 2021-04-07
DB Netz AG | 1716-001 | Dresden - Děčín | < | Dre-Niedersedl | Obervogelgesang | 2023 | 2023 | 46 | 46 | 2023-11-19 | 21:00 | 2023-11-19 | 23:00 | 0d, 2h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1716-001 |  | 2021-04-07
DB Netz AG | 1716-002 | Dresden - Děčín | > | Obervogelgesang | Pirna | 2023 | 2023 | 46 | 47 | 2023-11-19 | 23:00 | 2023-11-20 | 2:00 | 0d, 3h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1716-002 |  | 2021-04-07
DB Netz AG | 1716-003 | Dresden - Děčín | <> | Pirna | Pirna | 2023 | 2023 | 46 | 47 | 2023-11-19 | 23:00 | 2023-11-20 | 2:00 | 0d, 3h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 1716-003 |  | 2021-04-07
DB Netz AG | 1716-004 | Dresden - Děčín | <> | Pirna | Pirna | 2023 | 2023 | 46 | 47 | 2023-11-19 | 23:00 | 2023-11-20 | 2:00 | 0d, 3h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 1716-004 |  | 2021-04-07
DB Netz AG | 1716-005 | Dresden - Děčín | <> | Pirna | Obervogelgesang | 2023 | 2023 | 47 | 47 | 2023-11-20 | 2:00 | 2023-11-20 | 4:00 | 0d, 2h | Continuous | Maintenance | T | [10 empty] | 80 | N | 1716-005 |  | 2021-04-07
DB Netz AG | 1716-006 | Dresden - Děčín | < | Dre-Niedersedl | Pirna | 2023 | 2023 | 47 | 47 | 2023-11-20 | 21:00 | 2023-11-21 | 0:00 | 0d, 3h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1716-006 |  | 2021-04-07
DB Netz AG | 1716-007 | Dresden - Děčín | < | Dre-Niedersedl | Obervogelgesang | 2023 | 2023 | 47 | 47 | 2023-11-21 | 0:00 | 2023-11-21 | 3:00 | 0d, 3h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1716-007 |  | 2021-04-07
DB Netz AG | 1716-008 | Dresden - Děčín | <> | Pirna Gbf | Obervogelgesang | 2023 | 2023 | 47 | 47 | 2023-11-21 | 2:00 | 2023-11-21 | 3:00 | 0d, 1h | Continuous | Maintenance | T | [10 empty] | 80 | N | 1716-008 |  | 2021-04-07
DB Netz AG | 1716-009 | Dresden - Děčín | > | Obervogelgesang | Pirna Gbf | 2023 | 2023 | 47 | 47 | 2023-11-21 | 3:00 | 2023-11-21 | 4:30 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1716-009 |  | 2021-04-07
DB Netz AG | 1716-010 | Dresden - Děčín | > | Pirna | Pirna Gbf | 2023 | 2023 | 47 | 47 | 2023-11-21 | 21:00 | 2023-11-22 | 3:00 | 0d, 6h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 1716-010 |  | 2021-04-07
DB Netz AG | 1716-011 | Dresden - Děčín | < | Heidenau | Pirna | 2023 | 2023 | 47 | 47 | 2023-11-22 | 0:00 | 2023-11-22 | 1:30 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1716-011 |  | 2021-04-07
DB Netz AG | 1716-012 | Dresden - Děčín | <> | Pirna Gbf | Pirna | 2023 | 2023 | 47 | 47 | 2023-11-22 | 1:30 | 2023-11-22 | 3:00 | 0d, 1h | Continuous | Maintenance | T | [10 empty] | 80 | N | 1716-012 |  | 2021-04-07
DB Netz AG | 1716-013 | Dresden - Děčín | < | Dre-Niedersedl | Pirna | 2023 | 2023 | 47 | 47 | 2023-11-22 | 3:00 | 2023-11-22 | 4:30 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1716-013 |  | 2021-04-07
DB Netz AG | 1716-014 | Dresden - Děčín | > | Pirna | Heidenau | 2023 | 2023 | 47 | 47 | 2023-11-22 | 21:00 | 2023-11-22 | 23:00 | 0d, 2h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1716-014 |  | 2021-04-07
DB Netz AG | 1716-015 | Dresden - Děčín | < | Heidenau | Pirna | 2023 | 2023 | 47 | 47 | 2023-11-22 | 23:00 | 2023-11-23 | 4:00 | 0d, 5h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1716-015 |  | 2021-04-07
DB Netz AG | 1716-016 | Dresden - Děčín | <> | Pirna | Pirna Gbf | 2023 | 2023 | 47 | 47 | 2023-11-22 | 23:00 | 2023-11-23 | 4:00 | 0d, 5h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 1716-016 |  | 2021-04-07
DB Netz AG | 1716-017 | Dresden - Děčín | <> | Pirna | Heidenau | 2023 | 2023 | 47 | 47 | 2023-11-23 | 2:30 | 2023-11-23 | 4:00 | 0d, 1h | Continuous | Maintenance | T | [10 empty] | 80 | N | 1716-017 |  | 2021-04-07
DB Netz AG | 1732-016 | Dresden - Děčín | <> | Pirna Gbf | Pirna | 2023 | 2023 | 44 | 44 | 2023-11-02 | 21:00 | 2023-11-03 | 3:00 | 0d, 6h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 1732-016 |  | 2021-04-07
DB Netz AG | 1732-017 | Dresden - Děčín | <> | Pirna Gbf | Pirna | 2023 | 2023 | 44 | 44 | 2023-11-02 | 21:00 | 2023-11-03 | 3:00 | 0d, 6h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 1732-017 |  | 2021-04-07
DB Netz AG | 1732-019 | Dresden - Děčín | <> | Pirna Gbf | Pirna | 2023 | 2023 | 44 | 44 | 2023-11-03 | 2:30 | 2023-11-03 | 5:00 | 0d, 2h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 1732-019 |  | 2021-04-07
DB Netz AG | 1732-020 | Dresden - Děčín | <> | Pirna Gbf | Pirna | 2023 | 2023 | 44 | 44 | 2023-11-03 | 20:00 | 2023-11-04 | 5:00 | 0d, 9h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 1732-020 |  | 2021-04-07
DB Netz AG | 1732-021 | Dresden - Děčín | <> | Pirna Gbf | Pirna | 2023 | 2023 | 44 | 44 | 2023-11-03 | 20:00 | 2023-11-04 | 5:00 | 0d, 9h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 1732-021 |  | 2021-04-07
DB Netz AG | 1732-023 | Dresden - Děčín | < | Heidenau | Pirna | 2023 | 2023 | 44 | 44 | 2023-11-04 | 3:00 | 2023-11-04 | 5:00 | 0d, 2h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 1732-023 |  | 2021-04-07
DB Netz AG | 1732-024 | Dresden - Děčín | <> | Pirna Gbf | Pirna Gbf | 2023 | 2023 | 44 | 44 | 2023-11-03 | 20:00 | 2023-11-04 | 5:00 | 0d, 9h | Continuous | Switch |  |  |  | P | [7 empty] | 80 | N | 1732-024 |  | 2021-04-07
DB Netz AG | 1732-025 | Dresden - Děčín | <> | Pirna Gbf | Pirna Gbf | 2023 | 2023 | 44 | 44 | 2023-11-04 | 3:00 | 2023-11-04 | 5:00 | 0d, 2h | Continuous | Switch |  |  |  | P | [7 empty] | 80 | N | 1732-025 |  | 2021-04-07
DB Netz AG | 1779-024 | Rostock - Berlin | <> | Biesdf Kr Nord | Bln Nordost | 2023 | 2023 | 46 | 46 | 2023-11-13 | 12:00 | 2023-11-14 | 18:00 | 1d, 6h | Periodical | Bridge | T | [10 empty] | 80 | N | 1779-024
DB Netz AG | 17C9-003 | Rostock - Berlin | <> | Waren (Müritz) | Waren (Müritz) | 2023 | 2023 | 46 | 46 | 2023-11-13 | 8:00 | 2023-11-13 | 18:00 | 0d, 10h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 17C9-003 |  | 2021-04-23
DB Netz AG | 1845-001 | Hamburg - Magdeburg | <> | Lüneburg | Lüneburg | 2023 | 2023 | 44 | 45 | 2023-11-05 | 23:00 | 2023-11-06 | 5:00 | 0d, 6h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 1845-001 |  | 2021-04-23
DB Netz AG | 1845-002 | Hamburg - Magdeburg | <> | Lüneburg | Adendorf | 2023 | 2023 | 45 | 45 | 2023-11-06 | 0:00 | 2023-11-06 | 5:00 | 0d, 5h | Continuous | Switch | T | [10 empty] | 80 | N | 1845-002 |  | 2021-04-23
DB Netz AG | 1845-003 | Hamburg - Magdeburg | > | Lüneburg Gbf | Lüneburg Nordk | 2023 | 2023 | 45 | 45 | 2023-11-06 | 3:00 | 2023-11-06 | 5:00 | 0d, 2h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 1845-003 |  | 2021-08-18
DB Netz AG | 1870-001 | Bremerhaven - Bremen | < | Brh-Speckenbütt | Brh-Lehe Pbf | 2023 | 2023 | 46 | 46 | 2023-11-13 | 23:00 | 2023-11-14 | 5:00 | 0d, 6h | Continuous | Miscellaneous |  | LT | [9 empty] | 80 | N | 1870-001 |  | 2021-05-04
DB Netz AG | 1870-002 | Bremerhaven - Bremen | < | Brh-Lehe Pbf | Brh-Lehe Pbf | 2023 | 2023 | 46 | 46 | 2023-11-14 | 23:00 | 2023-11-16 | 4:00 | 1d, 5h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1870-002 |  | 2021-05-04
DB Netz AG | 1870-003 | Bremerhaven - Bremen | <> | Brh-Lehe Pbf | Brh-Lehe Pbf | 2023 | 2023 | 46 | 46 | 2023-11-16 | 4:00 | 2023-11-16 | 6:00 | 0d, 2h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 1870-003 |  | 2021-05-04
DB Netz AG | 1870-005 | Bremerhaven - Bremen | < | Brh-Lehe Pbf | Brh-Lehe Pbf | 2023 | 2023 | 46 | 46 | 2023-11-16 | 22:00 | 2023-11-18 | 3:00 | 1d, 5h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1870-005 |  | 2021-05-04
DB Netz AG | 1870-006 | Bremerhaven - Bremen | <> | Brh-Lehe Pbf | Brh-Lehe Pbf | 2023 | 2023 | 46 | 46 | 2023-11-18 | 3:00 | 2023-11-18 | 5:00 | 0d, 2h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 1870-006 |  | 2021-05-04
DB Netz AG | 1870-008 | Bremerhaven - Bremen | < | Brh-Lehe Pbf | Brh-Lehe Pbf | 2023 | 2023 | 46 | 46 | 2023-11-18 | 22:00 | 2023-11-19 | 3:00 | 0d, 5h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1870-008 |  | 2021-05-04
DB Netz AG | 1870-009 | Bremerhaven - Bremen | <> | Brh-Lehe Pbf | Brh-Lehe Pbf | 2023 | 2023 | 46 | 46 | 2023-11-19 | 3:00 | 2023-11-19 | 5:00 | 0d, 2h | Continuous | Miscellaneous |  | ST | [9 empty] | 80 | N | 1870-009 |  | 2021-05-04
DB Netz AG | 18A4-001 | Berlin - Dresden | <> | Glasow Damm Süd | Dahlewitz | 2023 | 2023 | 45 | 46 | 2023-11-10 | 21:00 | 2023-11-13 | 21:00 | 3d, 0h | Continuous | Miscellaneous |  |  | S | [8 empty] | 80 | N | 18A4-001 |  | 2021-05-17
DB Netz AG | 18A4-002 | Berlin - Dresden | <> | Glasow Damm Süd | Dahlewitz | 2023 | 2023 | 45 | 46 | 2023-11-10 | 21:00 | 2023-11-13 | 21:00 | 3d, 0h | Continuous | Miscellaneous |  |  | S | [8 empty] | 80 | N | 18A4-002 |  | 2021-05-17
DB Netz AG | 18A4-003 | Berlin - Dresden | <> | Glasow Damm Süd | Dahlewitz | 2023 | 2023 | 45 | 46 | 2023-11-10 | 21:00 | 2023-11-13 | 21:00 | 3d, 0h | Continuous | Miscellaneous |  |  | S | [8 empty] | 80 | N | 18A4-003 |  | 2021-05-17
DB Netz AG | 18A4-004 | Berlin - Dresden | <> | Glasow Damm Süd | Glasow Damm Ost | 2023 | 2023 | 45 | 46 | 2023-11-10 | 21:00 | 2023-11-13 | 21:00 | 3d, 0h | Continuous | Miscellaneous |  |  | S | [8 empty] | 80 | N | 18A4-004 |  | 2021-05-17
DB Netz AG | 18A4-005 | Berlin - Dresden | <> | Glasow Damm Süd | Dahlewitz | 2023 | 2023 | 45 | 46 | 2023-11-10 | 21:00 | 2023-11-13 | 21:00 | 3d, 0h | Continuous | Miscellaneous |  |  | S | [8 empty] | 80 | N | 18A4-005 |  | 2021-05-17
DB Netz AG | 18A4-006 | Berlin - Dresden | <> | Glasow Damm Süd | Glasow Damm Süd | 2023 | 2023 | 45 | 46 | 2023-11-10 | 21:00 | 2023-11-13 | 21:00 | 3d, 0h | Continuous | Miscellaneous |  |  | S | [8 empty] | 80 | N | 18A4-006 |  | 2021-05-17
DB Netz AG | 19A8-001 | Falkenberg - Dresden | < | Coswig (bei Dre) | Niederau | 2023 | 2023 | 47 | 47 | 2023-11-20 | 22:00 | 2023-11-21 | 0:00 | 0d, 2h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 19A8-001 |  | 2021-04-07
DB Netz AG | 19A8-002 | Falkenberg - Dresden | > | Niederau | Coswig (bei Dre) | 2023 | 2023 | 47 | 47 | 2023-11-21 | 0:00 | 2023-11-21 | 2:00 | 0d, 2h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 19A8-002 |  | 2021-04-07
DB Netz AG | 19A8-003 | Falkenberg - Dresden | > | Meißen | Coswig Stw 1 | 2023 | 2023 | 47 | 47 | 2023-11-21 | 2:00 | 2023-11-21 | 4:00 | 0d, 2h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 19A8-003 |  | 2021-04-07
DB Netz AG | 19A8-004 | Falkenberg - Dresden | <> | Coswig Stw 1 | Coswig (bei Dre) | 2023 | 2023 | 47 | 47 | 2023-11-21 | 2:00 | 2023-11-21 | 4:00 | 0d, 2h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 19A8-004 |  | 2021-04-07
DB Netz AG | 19A8-005 | Falkenberg - Dresden | <> | Coswig Stw 1 | Coswig (bei Dre) | 2023 | 2023 | 47 | 47 | 2023-11-21 | 2:00 | 2023-11-21 | 4:00 | 0d, 2h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 19A8-005 |  | 2021-04-07
DB Netz AG | 19A8-006 | Falkenberg - Dresden | > | Niederau | Coswig (bei Dre) | 2023 | 2023 | 47 | 47 | 2023-11-21 | 21:00 | 2023-11-21 | 22:00 | 0d, 1h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 19A8-006 |  | 2021-04-07
DB Netz AG | 19A8-007 | Falkenberg - Dresden | > | Niederau | Coswig (bei Dre) | 2023 | 2023 | 47 | 47 | 2023-11-21 | 21:00 | 2023-11-21 | 22:00 | 0d, 1h | Continuous | Switch |  |  |  |  | X | [6 empty] | 80 | N | 19A8-007 |  | 2021-04-07
DB Netz AG | 19A8-008 | Falkenberg - Dresden | <> | Niederau | Coswig (bei Dre) | 2023 | 2023 | 47 | 47 | 2023-11-21 | 22:00 | 2023-11-22 | 4:30 | 0d, 6h | Continuous | Switch | T | [10 empty] | 80 | N | 19A8-008 |  | 2021-04-07
DB Netz AG | 19A8-009 | Falkenberg - Dresden | <> | Niederau | Coswig (bei Dre) | 2023 | 2023 | 47 | 47 | 2023-11-21 | 22:00 | 2023-11-22 | 4:30 | 0d, 6h | Continuous | Switch |  |  |  |  | X | [6 empty] | 80 | N | 19A8-009 |  | 2021-04-07
DB Netz AG | 19A8-010 | Falkenberg - Dresden | <> | Meißen | Coswig Stw 1 | 2023 | 2023 | 47 | 47 | 2023-11-22 | 0:30 | 2023-11-22 | 4:30 | 0d, 4h | Continuous | Switch | T | [10 empty] | 80 | N | 19A8-010 |  | 2021-04-07
DB Netz AG | 19A8-011 | Falkenberg - Dresden | <> | Coswig Stw 1 | Coswig (bei Dre) | 2023 | 2023 | 47 | 47 | 2023-11-22 | 0:30 | 2023-11-22 | 4:30 | 0d, 4h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 19A8-011 |  | 2021-04-07
DB Netz AG | 19A8-012 | Falkenberg - Dresden | <> | Coswig Stw 1 | Coswig (bei Dre) | 2023 | 2023 | 47 | 47 | 2023-11-22 | 0:30 | 2023-11-22 | 4:30 | 0d, 4h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 19A8-012 |  | 2021-04-07
DB Netz AG | 19A8-013 | Falkenberg - Dresden | > | Meißen | Coswig Stw 1 | 2023 | 2023 | 47 | 47 | 2023-11-22 | 22:00 | 2023-11-23 | 0:30 | 0d, 2h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 19A8-013 |  | 2021-04-07
DB Netz AG | 19A8-014 | Falkenberg - Dresden | > | Niederau | Coswig (bei Dre) | 2023 | 2023 | 47 | 47 | 2023-11-22 | 22:00 | 2023-11-23 | 0:30 | 0d, 2h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 19A8-014 |  | 2021-04-07
DB Netz AG | 19A8-015 | Falkenberg - Dresden | <> | Coswig Stw 1 | Coswig (bei Dre) | 2023 | 2023 | 47 | 47 | 2023-11-22 | 22:00 | 2023-11-23 | 0:30 | 0d, 2h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 19A8-015 |  | 2021-04-07
DB Netz AG | 19A8-016 | Falkenberg - Dresden | <> | Coswig Stw 1 | Coswig (bei Dre) | 2023 | 2023 | 47 | 47 | 2023-11-22 | 22:00 | 2023-11-23 | 0:30 | 0d, 2h | Continuous | Switch |  |  |  |  | X | [6 empty] | 80 | N | 19A8-016 |  | 2021-04-07
DB Netz AG | 19A8-017 | Falkenberg - Dresden | <> | Meißen | Coswig Stw 1 | 2023 | 2023 | 47 | 47 | 2023-11-23 | 0:30 | 2023-11-23 | 4:30 | 0d, 4h | Continuous | Switch | T | [10 empty] | 80 | N | 19A8-017 |  | 2021-04-07
DB Netz AG | 19A8-018 | Falkenberg - Dresden | <> | Niederau | Coswig (bei Dre) | 2023 | 2023 | 47 | 47 | 2023-11-23 | 0:30 | 2023-11-23 | 4:30 | 0d, 4h | Continuous | Switch | T | [10 empty] | 80 | N | 19A8-018 |  | 2021-04-07
DB Netz AG | 19A8-019 | Falkenberg - Dresden | <> | Meißen | Coswig (bei Dre) | 2023 | 2023 | 47 | 47 | 2023-11-23 | 0:30 | 2023-11-23 | 4:30 | 0d, 4h | Continuous | Switch |  |  |  |  | X | [6 empty] | 80 | N | 19A8-019 |  | 2021-04-07
DB Netz AG | 19A8-020 | Falkenberg - Dresden | <> | Coswig Stw 1 | Coswig (bei Dre) | 2023 | 2023 | 47 | 47 | 2023-11-23 | 0:30 | 2023-11-23 | 4:30 | 0d, 4h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 19A8-020 |  | 2021-04-07
DB Netz AG | 19B5-001 | Falkenberg - Dresden | < | Coswig Stw 1 | Niederau | 2023 | 2023 | 47 | 47 | 2023-11-23 | 21:00 | 2023-11-23 | 23:30 | 0d, 2h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 19B5-001 |  | 2021-04-07
DB Netz AG | 19B5-002 | Falkenberg - Dresden | < | Coswig (bei Dre) | Priestewitz | 2023 | 2023 | 47 | 47 | 2023-11-23 | 21:00 | 2023-11-23 | 23:30 | 0d, 2h | Continuous | Switch |  |  |  |  | X | [6 empty] | 80 | N | 19B5-002 |  | 2021-04-07
DB Netz AG | 19B5-003 | Falkenberg - Dresden | > | Priestewitz | Niederau | 2023 | 2023 | 47 | 47 | 2023-11-23 | 23:30 | 2023-11-24 | 2:00 | 0d, 2h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 19B5-003 |  | 2021-04-07
DB Netz AG | 19B5-004 | Falkenberg - Dresden | > | Niederau | Niederau | 2023 | 2023 | 47 | 47 | 2023-11-23 | 23:30 | 2023-11-24 | 2:00 | 0d, 2h | Continuous | Switch |  | ST | [9 empty] | 80 | N | 19B5-004 |  | 2021-04-07
DB Netz AG | 19B5-006 | Falkenberg - Dresden | > | Niederau | Coswig (bei Dre) | 2023 | 2023 | 47 | 47 | 2023-11-23 | 23:30 | 2023-11-24 | 2:00 | 0d, 2h | Continuous | Switch |  | LT | [9 empty] | 80 | N | 19B5-006 |  | 2021-04-07
DB Netz AG | 19B5-007 | Falkenberg - Dresden | > | Priestewitz | Coswig Stw 1 | 2023 | 2023 | 47 | 47 | 2023-11-23 | 23:30 | 2023-11-24 | 2:00 | 0d, 2h | Continuous | Switch |  |  |  |  | X | [6 empty] | 80 | N | 19B5-007 |  | 2021-04-07
DB Netz AG | 19B5-008 | Falkenberg - Dresden | <> | Priestewitz | Coswig Stw 1 | 2023 | 2023 | 47 | 47 | 2023-11-24 | 2:00 | 2023-11-24 | 4:30 | 0d, 2h | Continuous | Switch | T | [10 empty] | 80 | N | 19B5-008 |  | 2021-04-07
DB Netz AG | 19B5-010 | Falkenberg - Dresden | <> | Niederau | Niederau | 2023 | 2023 | 47 | 47 | 2023-11-24 | 2:00 | 2023-11-24 | 4:30 | 0d, 2h | Continuous | Switch |  |  |  |  | X | [6 empty] | 80 | N | 19B5-010 |  | 2021-04-07
DB Netz AG | 1A01-001 | Hamburg - Magdeburg | <> | Lüneburg Gbf | Lüneburg Gbf | 2023 | 2023 | 48 | 49 | 2023-11-27 | 4:40 | 2023-12-09 | 8:00 | 12d, 3h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 1A01-001 |  | 2021-05-14
DB Netz AG | 1A01-002 | Hamburg - Magdeburg | <> | Lüneburg Gbf | Lüneburg Gbf | 2023 | 2023 | 48 | 49 | 2023-11-27 | 5:40 | 2023-12-09 | 8:00 | 12d, 2h | Continuous | Signal |  |  |  |  | X | [6 empty] | 80 | N | 1A01-002 |  | 2021-05-14
DB Netz AG | 1A01-003 | Hamburg - Magdeburg | <> | Lüneburg Gbf | Lüneburg Gbf | 2023 | 2023 | 48 | 48 | 2023-11-27 | 18:00 | 2023-11-27 | 22:40 | 0d, 4h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 1A01-003 |  | 2021-05-14
DB Netz AG | 1A01-004 | Hamburg - Magdeburg | <> | Lüneburg Gbf | Lüneburg Gbf | 2023 | 2023 | 48 | 48 | 2023-11-27 | 18:00 | 2023-11-27 | 22:40 | 0d, 4h | Continuous | Signal |  |  |  |  | X | [6 empty] | 80 | N | 1A01-004 |  | 2021-05-14
DB Netz AG | 1A08-005 | Dresden - Děčín | <> | Dresden Hbf | Freital Ost | 2023 | 2023 | 44 | 44 | 2023-11-03 | 18:00 | 2023-11-03 | 21:00 | 0d, 3h | Continuous | Switch | T | [10 empty] | 80 | N | 1A08-005 |  | 2021-04-27
DB Netz AG | 1A08-006 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 44 | 44 | 2023-11-03 | 18:00 | 2023-11-03 | 21:00 | 0d, 3h | Continuous | Switch | T | [10 empty] | 80 | N | 1A08-006 |  | 2021-04-27
DB Netz AG | 1A08-008 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 44 | 44 | 2023-11-03 | 18:00 | 2023-11-03 | 21:00 | 0d, 3h | Continuous | Switch |  |  |  |  | X | [6 empty] | 80 | N | 1A08-008 |  | 2021-04-27
DB Netz AG | 1A08-009 | Dresden - Děčín | < | Dresden-Altstadt | Dre Freibg Str | 2023 | 2023 | 44 | 44 | 2023-11-03 | 18:00 | 2023-11-03 | 21:00 | 0d, 3h | Continuous | Switch |  |  |  |  | X | [6 empty] | 80 | N | 1A08-009 |  | 2021-04-27
DB Netz AG | 1A08-011 | Dresden - Děčín | <> | Dresden Hbf | Freital Ost | 2023 | 2023 | 45 | 45 | 2023-11-06 | 3:00 | 2023-11-06 | 6:00 | 0d, 3h | Continuous | Switch | T | [10 empty] | 80 | N | 1A08-011 |  | 2021-04-27
DB Netz AG | 1A08-012 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 45 | 45 | 2023-11-06 | 3:00 | 2023-11-06 | 6:00 | 0d, 3h | Continuous | Switch | T | [10 empty] | 80 | N | 1A08-012 |  | 2021-04-27
DB Netz AG | 1A08-016 | Dresden - Děčín | < | Dresden-Altstadt | Dre Freibg Str | 2023 | 2023 | 45 | 45 | 2023-11-06 | 3:00 | 2023-11-06 | 6:00 | 0d, 3h | Continuous | Switch |  |  |  |  | X | [6 empty] | 80 | N | 1A08-016 |  | 2021-04-27
DB Netz AG | 1A08-017 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 44 | 45 | 2023-11-03 | 21:00 | 2023-11-06 | 3:00 | 2d, 6h | Continuous | Switch | T | [10 empty] | 80 | N | 1A08-017 |  | 2021-04-27
DB Netz AG | 1A08-020 | Dresden - Děčín | <> | Dresden Hbf | Dresden-Altstadt | 2023 | 2023 | 44 | 45 | 2023-11-03 | 21:00 | 2023-11-06 | 3:00 | 2d, 6h | Continuous | Switch | T | [10 empty] | 80 | N | 1A08-020 |  | 2021-04-27
DB Netz AG | 16CB-016 | Dresden - Děčín | <> | Dresden Hbf | Dre Freibg Str | 2023 | 2023 | 46 | 47 | 2023-11-18 | 4:00 | 2023-11-25 | 5:00 | 7d, 1h | Periodical | Catenary | T | [10 empty] | 80 | N | 16CB-016 |  | 2021-05-21
DB Netz AG | 16CB-017 | Dresden - Děčín | <> | Dresden Hbf | Dre Freibg Str | 2023 | 2023 | 46 | 47 | 2023-11-18 | 4:00 | 2023-11-25 | 5:00 | 7d, 1h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 16CB-017 |  | 2021-05-21
DB Netz AG | 16CB-018 | Dresden - Děčín | <> | Dre Freibg Str | Dresden-Altstadt | 2023 | 2023 | 46 | 47 | 2023-11-18 | 4:00 | 2023-11-25 | 5:00 | 7d, 1h | Periodical | Catenary | T | [10 empty] | 80 | N | 16CB-018 |  | 2021-05-21
DB Netz AG | 16CB-019 | Dresden - Děčín | <> | Dre-Friedrichst | Dre Freibg Str | 2023 | 2023 | 46 | 47 | 2023-11-18 | 4:00 | 2023-11-25 | 5:00 | 7d, 1h | Periodical | Catenary | T | [10 empty] | 80 | N | 16CB-019 |  | 2021-05-21
DB Netz AG | 16CB-020 | Dresden - Děčín | <> | Dresden Hbf | Dre Freibg Str | 2023 | 2023 | 46 | 47 | 2023-11-18 | 4:00 | 2023-11-25 | 5:00 | 7d, 1h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 16CB-020 |  | 2021-05-21
DB Netz AG | 16CB-021 | Dresden - Děčín | <> | Dresden Hbf | Dre Freibg Str | 2023 | 2023 | 46 | 47 | 2023-11-18 | 4:00 | 2023-11-25 | 5:00 | 7d, 1h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 16CB-021 |  | 2021-05-21
DB Netz AG | 16CB-022 | Dresden - Děčín | <> | Dresden Hbf | Dre Freibg Str | 2023 | 2023 | 46 | 47 | 2023-11-18 | 19:00 | 2023-11-25 | 20:00 | 7d, 1h | Periodical | Catenary | T | [10 empty] | 80 | N | 16CB-022 |  | 2021-05-21
DB Netz AG | 16CB-023 | Dresden - Děčín | <> | Dresden Hbf | Dre Freibg Str | 2023 | 2023 | 46 | 47 | 2023-11-18 | 19:00 | 2023-11-25 | 20:00 | 7d, 1h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 16CB-023 |  | 2021-05-21
DB Netz AG | 16CB-024 | Dresden - Děčín | <> | Dresden-Altstadt | Dre Freibg Str | 2023 | 2023 | 46 | 47 | 2023-11-18 | 19:00 | 2023-11-25 | 20:00 | 7d, 1h | Periodical | Catenary | T | [10 empty] | 80 | N | 16CB-024 |  | 2021-05-21
DB Netz AG | 16CB-025 | Dresden - Děčín | <> | Dre-Friedrichst | Dre Freibg Str | 2023 | 2023 | 46 | 47 | 2023-11-18 | 19:00 | 2023-11-25 | 20:00 | 7d, 1h | Periodical | Catenary | T | [10 empty] | 80 | N | 16CB-025 |  | 2021-05-21
DB Netz AG | 16CB-026 | Dresden - Děčín | <> | Dresden Hbf | Dre Freibg Str | 2023 | 2023 | 46 | 47 | 2023-11-18 | 19:00 | 2023-11-25 | 20:00 | 7d, 1h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 16CB-026 |  | 2021-05-21
DB Netz AG | 16CB-027 | Dresden - Děčín | <> | Dresden Hbf | Dre Freibg Str | 2023 | 2023 | 46 | 47 | 2023-11-18 | 19:00 | 2023-11-25 | 20:00 | 7d, 1h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 16CB-027 |  | 2021-05-21
DB Netz AG | 16CB-028 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 46 | 47 | 2023-11-18 | 5:00 | 2023-11-25 | 19:00 | 7d, 14h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 16CB-028 |  | 2021-05-21
DB Netz AG | 16CB-029 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 46 | 47 | 2023-11-18 | 5:00 | 2023-11-25 | 19:00 | 7d, 14h | Periodical | Catenary | T | [10 empty] | 80 | N | 16CB-029 |  | 2021-05-21
DB Netz AG | 16CB-030 | Dresden - Děčín | <> | Dresden Hbf | Dresden Hbf | 2023 | 2023 | 46 | 47 | 2023-11-18 | 5:00 | 2023-11-25 | 19:00 | 7d, 14h | Periodical | Catenary |  |  |  |  | X | [6 empty] | 80 | N | 16CB-030 |  | 2021-05-21
DB Netz AG | 1CBD-002 | Hannover - Magdeburg | < | Schandelah | Schmiedekamp | 2023 | 2023 | 47 | 48 | 2023-11-26 | 21:40 | 2023-11-27 | 5:20 | 0d, 7h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 1CBD-002 |  | 2021-09-27
DB Netz AG | 1CBD-003 | Hannover - Magdeburg | <> | Weddel Abzw | Lehre/Braunschw | 2023 | 2023 | 47 | 48 | 2023-11-26 | 21:40 | 2023-11-27 | 5:20 | 0d, 7h | Periodical | Catenary | T | [10 empty] | 80 | N | 1CBD-003 |  | 2021-09-27
DB Netz AG | 1CBD-004 | Hannover - Magdeburg | <> | Weddel Abzw | Weddel Abzw | 2023 | 2023 | 47 | 48 | 2023-11-26 | 21:40 | 2023-11-27 | 5:20 | 0d, 7h | Periodical | Catenary |  |  |  | P | [7 empty] | 80 | N | 1CBD-004 |  | 2021-09-27
DB Netz AG | 1CBD-005 | Hannover - Magdeburg | <> | Schandelah | Buchhorst Abzw | 2023 | 2023 | 48 | 48 | 2023-11-27 | 0:10 | 2023-11-27 | 3:10 | 0d, 3h | Periodical | Catenary | T | [10 empty] | 80 | N | 1CBD-005 |  | 2021-09-27
DB Netz AG | 1CBD-006 | Hannover - Magdeburg | <> | Weddel Abzw | Lehre/Braunschw | 2023 | 2023 | 48 | 48 | 2023-11-27 | 0:10 | 2023-11-27 | 3:10 | 0d, 3h | Periodical | Catenary | T | [10 empty] | 80 | N | 1CBD-006 |  | 2021-09-27
DB Netz AG | 1CBD-007 | Hannover - Magdeburg | > | Buchhorst Abzw | Schandelah | 2023 | 2023 | 48 | 48 | 2023-11-27 | 21:40 | 2023-11-28 | 5:20 | 0d, 7h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 1CBD-007 |  | 2021-09-27
DB Netz AG | 1CBD-008 | Hannover - Magdeburg | <> | Weddel Abzw | Weddel Abzw | 2023 | 2023 | 48 | 48 | 2023-11-27 | 21:40 | 2023-11-28 | 5:20 | 0d, 7h | Periodical | Catenary |  |  |  | P | [7 empty] | 80 | N | 1CBD-008 |  | 2021-09-27
DB Netz AG | 1CBD-009 | Hannover - Magdeburg | <> | Buchhorst Abzw | Schandelah | 2023 | 2023 | 48 | 48 | 2023-11-28 | 2:20 | 2023-11-28 | 5:00 | 0d, 2h | Periodical | Catenary | T | [10 empty] | 80 | N | 1CBD-009
DB Netz AG | 1CBD-010 | Hannover - Magdeburg | <> | Weddel Abzw | Lehre/Braunschw | 2023 | 2023 | 48 | 48 | 2023-11-28 | 2:20 | 2023-11-28 | 5:00 | 0d, 2h | Periodical | Catenary | T | [10 empty] | 80 | N | 1CBD-010 |  | 2021-09-27
DB Netz AG | 1D02-002 | Hannover - Magdeburg | <> | Braunschweig Hbf | Braunschweig Hbf | 2023 | 2023 | 45 | 46 | 2023-11-12 | 21:00 | 2023-11-14 | 5:00 | 1d, 8h | Periodical | Catenary |  |  |  | P | [7 empty] | 80 | N | 1D02-002
DB Netz AG | 1D02-003 | Hannover - Magdeburg | > | Groß Gleidingen | Braunschweig Hbf | 2023 | 2023 | 46 | 46 | 2023-11-13 | 2:00 | 2023-11-14 | 4:30 | 1d, 2h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 1D02-003
DB Netz AG | 1D02-004 | Hannover - Magdeburg | > | Braunschweig Hbf | Schmiedekamp | 2023 | 2023 | 46 | 46 | 2023-11-13 | 2:00 | 2023-11-14 | 4:30 | 1d, 2h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 1D02-004
DB Netz AG | 1D02-006 | Hannover - Magdeburg | <> | Braunschweig Hbf | Braunschweig Hbf | 2023 | 2023 | 46 | 46 | 2023-11-13 | 2:00 | 2023-11-14 | 4:30 | 1d, 2h | Periodical | Catenary |  |  |  | P | [7 empty] | 80 | N | 1D02-006
DB Netz AG | 1D02-007 | Hannover - Magdeburg | > | Braunschweig Hbf | Braunschweig Hbf | 2023 | 2023 | 46 | 46 | 2023-11-14 | 22:20 | 2023-11-16 | 5:20 | 1d, 7h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 1D02-007
DB Netz AG | 1D02-008 | Hannover - Magdeburg | > | Groß Gleidingen | Braunschweig Hbf | 2023 | 2023 | 46 | 46 | 2023-11-14 | 23:50 | 2023-11-16 | 4:50 | 1d, 5h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 1D02-008
DB Netz AG | 1D02-011 | Hannover - Magdeburg | > | Braunschweig Hbf | Schmiedekamp | 2023 | 2023 | 46 | 46 | 2023-11-14 | 23:50 | 2023-11-16 | 4:50 | 1d, 5h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 1D02-011
DB Netz AG | 1D02-012 | Hannover - Magdeburg | <> | Braunschweig Hbf | Braunschweig Hbf | 2023 | 2023 | 46 | 46 | 2023-11-14 | 23:50 | 2023-11-16 | 4:50 | 1d, 5h | Periodical | Catenary |  |  |  | P | [7 empty] | 80 | N | 1D02-012
DB Netz AG | 1D02-013 | Hannover - Magdeburg | <> | Braunschweig Hbf | Braunschweig Hbf | 2023 | 2023 | 46 | 46 | 2023-11-14 | 23:50 | 2023-11-16 | 4:50 | 1d, 5h | Periodical | Catenary |  |  |  | P | [7 empty] | 80 | N | 1D02-013
DB Netz AG | 1D02-014 | Hannover - Magdeburg | > | Braunschweig Hbf | Schmiedekamp | 2023 | 2023 | 46 | 46 | 2023-11-16 | 22:20 | 2023-11-17 | 5:20 | 0d, 7h | Continuous | Catenary |  | LT | [9 empty] | 80 | N | 1D02-014
DB Netz AG | 1D02-015 | Hannover - Magdeburg | <> | Braunschweig Hbf | Braunschweig Hbf | 2023 | 2023 | 46 | 46 | 2023-11-16 | 22:20 | 2023-11-17 | 5:20 | 0d, 7h | Continuous | Catenary |  | ST | [9 empty] | 80 | N | 1D02-015
DB Netz AG | 1D02-016 | Hannover - Magdeburg | <> | Braunschweig Hbf | Braunschweig Hbf | 2023 | 2023 | 46 | 46 | 2023-11-16 | 22:20 | 2023-11-17 | 5:20 | 0d, 7h | Continuous | Catenary |  |  |  | P | [7 empty] | 80 | N | 1D02-016
DB Netz AG | 1D02-017 | Hannover - Magdeburg | <> | Braunschweig Hbf | Braunschweig Hbf | 2023 | 2023 | 46 | 46 | 2023-11-16 | 22:20 | 2023-11-17 | 5:20 | 0d, 7h | Continuous | Catenary |  |  |  | P | [7 empty] | 80 | N | 1D02-017
DB Netz AG | 1D02-018 | Hannover - Magdeburg | <> | Braunschweig Hbf | Braunschweig Hbf | 2023 | 2023 | 46 | 47 | 2023-11-19 | 22:00 | 2023-11-22 | 5:20 | 2d, 7h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 1D02-018
DB Netz AG | 1D02-019 | Hannover - Magdeburg | < | Buchhorst Abzw | Braunschweig Hbf | 2023 | 2023 | 46 | 47 | 2023-11-19 | 23:50 | 2023-11-22 | 4:50 | 2d, 5h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 1D02-019
DB Netz AG | 1D02-020 | Hannover - Magdeburg | < | Braunschweig Hbf | Gabelung (Brg) | 2023 | 2023 | 46 | 47 | 2023-11-19 | 23:50 | 2023-11-22 | 4:50 | 2d, 5h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 1D02-020
DB Netz AG | 1D02-021 | Hannover - Magdeburg | > | Braunschweig Hbf | Gabelung (Brg) | 2023 | 2023 | 46 | 47 | 2023-11-19 | 23:50 | 2023-11-22 | 4:50 | 2d, 5h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 1D02-021
DB Netz AG | 1D02-023 | Hannover - Magdeburg | <> | Braunschweig Hbf | Buchhorst Abzw | 2023 | 2023 | 47 | 47 | 2023-11-20 | 0:50 | 2023-11-20 | 3:10 | 0d, 2h | Periodical | Catenary | T | [10 empty] | 80 | N | 1D02-023
DB Netz AG | 1D02-024 | Hannover - Magdeburg | <> | Braunschweig Hbf | Braunschweig Hbf | 2023 | 2023 | 47 | 47 | 2023-11-20 | 0:50 | 2023-11-20 | 3:10 | 0d, 2h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 1D02-024
DB Netz AG | 1D02-025 | Hannover - Magdeburg | <> | Braunschweig Hbf | Braunschweig Hbf | 2023 | 2023 | 47 | 47 | 2023-11-20 | 0:50 | 2023-11-20 | 3:10 | 0d, 2h | Periodical | Catenary |  |  |  | P | [7 empty] | 80 | N | 1D02-025
DB Netz AG | 1D02-026 | Hannover - Magdeburg | <> | Braunschweig Hbf | Braunschweig Hbf | 2023 | 2023 | 47 | 47 | 2023-11-21 | 2:00 | 2023-11-21 | 4:15 | 0d, 2h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 1D02-026
DB Netz AG | 1D02-027 | Hannover - Magdeburg | <> | Braunschweig Hbf | Braunschweig Hbf | 2023 | 2023 | 47 | 47 | 2023-11-21 | 2:00 | 2023-11-21 | 4:15 | 0d, 2h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 1D02-027
DB Netz AG | 1D02-028 | Hannover - Magdeburg | <> | Braunschweig Hbf | Braunschweig Hbf | 2023 | 2023 | 47 | 47 | 2023-11-21 | 2:00 | 2023-11-21 | 4:15 | 0d, 2h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 1D02-028
DB Netz AG | 1D02-029 | Hannover - Magdeburg | <> | Braunschweig Hbf | Braunschweig Hbf | 2023 | 2023 | 47 | 47 | 2023-11-20 | 0:50 | 2023-11-20 | 3:10 | 0d, 2h | Periodical | Catenary |  |  |  | P | [7 empty] | 80 | N | 1D02-029
DB Netz AG | 1D92-001 | Bremen - Hannover | < | Seelze Ost | Letter Abzw | 2023 | 2023 | 44 | 46 | 2023-11-05 | 7:00 | 2023-11-19 | 15:00 | 14d, 8h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 1D92-001 |  | 2022-07-19
DB Netz AG | 1D92-002 | Bremen - Hannover | <> | Seelze Ost | Seelze Ost | 2023 | 2023 | 44 | 46 | 2023-11-05 | 7:00 | 2023-11-19 | 15:00 | 14d, 8h | Periodical | Catenary |  | ST | [9 empty] | 80 | N | 1D92-002 |  | 2022-07-19
DB Netz AG | 1D92-003 | Bremen - Hannover | <> | Seelze Ost | Seelze Ost | 2023 | 2023 | 44 | 46 | 2023-11-05 | 7:00 | 2023-11-19 | 15:00 | 14d, 8h | Periodical | Catenary |  |  |  | P | [7 empty] | 80 | N | 1D92-003 |  | 2022-07-19
DB Netz AG | 1FDF-001 | Hamburg - Magdeburg | <> | Maschen Rbf Mnwf | Hmb-Roth Tk | 2023 | 2023 | 46 | 46 | 2023-11-18 | 22:00 | 2023-11-19 | 5:00 | 0d, 7h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 1FDF-001
DB Netz AG | 1FDF-008 | Hamburg - Magdeburg | <> | Veddel | Hmb-Harburg | 2023 | 2023 | 46 | 46 | 2023-11-19 | 0:20 | 2023-11-19 | 2:05 | 0d, 1h | Continuous | Maintenance | T | [10 empty] | 80 | N | 1FDF-008
DB Netz AG | 1FDF-009 | Hamburg - Magdeburg | <> | Oberhafen | Hmb-Wlb Abzw | 2023 | 2023 | 46 | 46 | 2023-11-18 | 23:35 | 2023-11-19 | 0:35 | 0d, 1h | Continuous | Maintenance | T | [10 empty] | 80 | N | 1FDF-009
DB Netz AG | 1FDF-010 | Hamburg - Magdeburg | <> | Hmb-Wlb Abzw | Meckelfeld | 2023 | 2023 | 46 | 46 | 2023-11-19 | 1:50 | 2023-11-19 | 3:50 | 0d, 2h | Continuous | Maintenance | T | [10 empty] | 80 | N | 1FDF-010
DB Netz AG | 1FDF-011 | Hamburg - Magdeburg | <> | Hmb-Harburg | Maschen Rbf Mnwf | 2023 | 2023 | 46 | 46 | 2023-11-19 | 3:35 | 2023-11-19 | 5:00 | 0d, 1h | Continuous | Maintenance | T | [10 empty] | 80 | N | 1FDF-011
DB Netz AG | 1FDF-012 | Hamburg - Magdeburg | < | Hmb-Harb Bbf Süd | Meckelfeld | 2023 | 2023 | 46 | 46 | 2023-11-19 | 3:35 | 2023-11-19 | 5:00 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1FDF-012
DB Netz AG | 1FDF-013 | Hamburg - Magdeburg | < | Meckelfeld | Maschen Rbf Mnwf | 2023 | 2023 | 46 | 46 | 2023-11-19 | 3:35 | 2023-11-19 | 5:00 | 0d, 1h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 1FDF-013
DB Netz AG | 202D-001 | Hamburg - Magdeburg | > | Jesteburg | Maschen Rbf Msof | 2023 | 2023 | 47 | 47 | 2023-11-25 | 22:00 | 2023-11-26 | 1:00 | 0d, 3h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 202D-001 |  | 2021-09-30
DB Netz AG | 202D-002 | Hamburg - Magdeburg | > | Stelle | Maschen Rbf Mswf | 2023 | 2023 | 47 | 47 | 2023-11-26 | 0:45 | 2023-11-26 | 1:30 | 0d, 0h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 202D-002 |  | 2021-09-30
DB Netz AG | 202D-003 | Hamburg - Magdeburg | > | Jesteburg | Maschen Rbf Msof | 2023 | 2023 | 47 | 47 | 2023-11-26 | 0:45 | 2023-11-26 | 1:30 | 0d, 0h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 202D-003 |  | 2021-09-30
DB Netz AG | 202D-004 | Hamburg - Magdeburg | > | Maschen Rbf Msof | Maschen Rbf Mnwf | 2023 | 2023 | 47 | 47 | 2023-11-26 | 1:15 | 2023-11-26 | 2:00 | 0d, 0h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 202D-004 |  | 2021-09-30
DB Netz AG | 202D-005 | Hamburg - Magdeburg | > | Maschen Rbf Mnof | Meckelfeld | 2023 | 2023 | 47 | 47 | 2023-11-26 | 2:00 | 2023-11-26 | 2:45 | 0d, 0h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 202D-005 |  | 2021-09-30
DB Netz AG | 202D-006 | Hamburg - Magdeburg | > | Meckelfeld | Hmb-Harb Bbf Süd | 2023 | 2023 | 47 | 47 | 2023-11-26 | 2:00 | 2023-11-26 | 2:45 | 0d, 0h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 202D-006 |  | 2021-09-30
DB Netz AG | 204A-001 | Hamburg - Magdeburg | <> | Ashausen Abzw | Maschen Rbf Msof | 2023 | 2023 | 47 | 47 | 2023-11-26 | 22:00 | 2023-11-26 | 23:30 | 0d, 1h | Continuous | Maintenance | T | [10 empty] | 80 | N | 204A-001
DB Netz AG | 204A-002 | Hamburg - Magdeburg | > | Meckelfeld | Hmb-Wlb Abzw | 2023 | 2023 | 48 | 48 | 2023-11-27 | 0:00 | 2023-11-27 | 0:45 | 0d, 0h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 204A-002
DB Netz AG | 204A-003 | Hamburg - Magdeburg | > | Meckelfeld | Hmb-Wlb Abzw | 2023 | 2023 | 48 | 48 | 2023-11-27 | 0:30 | 2023-11-27 | 1:45 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 204A-003
DB Netz AG | 2171-005 | Rostock - Berlin | <> | Ro Seehf Süd | Ro Seehf Süd | 2023 | 2023 | 44 | 45 | 2023-11-03 | 8:00 | 2023-11-06 | 18:00 | 3d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 2171-005
DB Netz AG | 2171-006 | Rostock - Berlin | <> | Rostock Seehafen | Ro Seehf Süd | 2023 | 2023 | 44 | 45 | 2023-11-04 | 8:00 | 2023-11-06 | 18:00 | 2d, 10h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | 2171-006
DB Netz AG | 2171-007 | Rostock - Berlin | <> | Rostock Seehafen | Rostock Seehafen | 2023 | 2023 | 44 | 45 | 2023-11-04 | 8:00 | 2023-11-06 | 18:00 | 2d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 2171-007
DB Netz AG | 2171-008 | Rostock - Berlin | <> | Rostock Seehafen | Rostock Seehafen | 2023 | 2023 | 44 | 45 | 2023-11-04 | 8:01 | 2023-11-06 | 18:00 | 2d, 9h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 2171-008
DB Netz AG | 2171-009 | Rostock - Berlin | <> | Rostock Seehafen | Rostock Seehafen | 2023 | 2023 | 44 | 45 | 2023-11-04 | 8:01 | 2023-11-06 | 18:00 | 2d, 9h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 2171-009
DB Netz AG | 2171-010 | Rostock - Berlin | <> | Rostock Seehafen | Rostock Seehafen | 2023 | 2023 | 45 | 45 | 2023-11-07 | 8:00 | 2023-11-11 | 18:00 | 4d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 2171-010
DB Netz AG | 2171-011 | Rostock - Berlin | <> | Rostock Seehafen | Rostock Seehafen | 2023 | 2023 | 45 | 45 | 2023-11-07 | 8:01 | 2023-11-11 | 18:00 | 4d, 9h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 2171-011
DB Netz AG | 2171-012 | Rostock - Berlin | <> | Rostock Seehafen | Rostock Seehafen | 2023 | 2023 | 45 | 45 | 2023-11-07 | 8:01 | 2023-11-11 | 18:00 | 4d, 9h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 2171-012
DB Netz AG | 2171-013 | Rostock - Berlin | <> | Rostock Seehafen | Rostock Seehafen | 2023 | 2023 | 45 | 45 | 2023-11-07 | 8:01 | 2023-11-08 | 18:00 | 1d, 9h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 2171-013
DB Netz AG | 2171-014 | Rostock - Berlin | <> | Rostock Seehafen | Riekdahl | 2023 | 2023 | 45 | 45 | 2023-11-07 | 8:02 | 2023-11-12 | 18:00 | 5d, 9h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | 2171-014
DB Netz AG | 2171-015 | Rostock - Berlin | <> | Ro Seehf Süd | Ro Seehf Süd | 2023 | 2023 | 45 | 45 | 2023-11-07 | 8:02 | 2023-11-12 | 18:00 | 5d, 9h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 2171-015
DB Netz AG | 2171-016 | Rostock - Berlin | <> | Ro Seehf Süd | Rostock Seehafen | 2023 | 2023 | 45 | 45 | 2023-11-09 | 8:00 | 2023-11-11 | 18:00 | 2d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 2171-016
DB Netz AG | 2171-017 | Rostock - Berlin | <> | Ro Seehf Süd | Rostock Seehafen | 2023 | 2023 | 45 | 45 | 2023-11-11 | 8:00 | 2023-11-12 | 18:00 | 1d, 10h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | 2171-017
DB Netz AG | 2171-018 | Rostock - Berlin | <> | Rostock Seehafen | Rostock Seehafen | 2023 | 2023 | 45 | 45 | 2023-11-11 | 8:00 | 2023-11-12 | 18:00 | 1d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 2171-018
DB Netz AG | 2171-019 | Rostock - Berlin | <> | Rostock Seehafen | Rostock Seehafen | 2023 | 2023 | 45 | 45 | 2023-11-11 | 8:01 | 2023-11-12 | 18:00 | 1d, 9h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 2171-019
DB Netz AG | 2171-020 | Rostock - Berlin | <> | Rostock Seehafen | Rostock Seehafen | 2023 | 2023 | 45 | 45 | 2023-11-11 | 8:01 | 2023-11-12 | 18:00 | 1d, 9h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 2171-020
DB Netz AG | 2173-001 | Rostock - Berlin | <> | Rostock Seehafen | Rostock Seehafen | 2023 | 2023 | 45 | 46 | 2023-11-12 | 8:00 | 2023-11-13 | 18:00 | 1d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 2173-001
DB Netz AG | 2173-002 | Rostock - Berlin | <> | Rostock Seehafen | Rostock Seehafen | 2023 | 2023 | 46 | 46 | 2023-11-13 | 8:00 | 2023-11-15 | 18:00 | 2d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 2173-002
DB Netz AG | 2173-003 | Rostock - Berlin | <> | Rostock Seehafen | Rostock Seehafen | 2023 | 2023 | 46 | 46 | 2023-11-13 | 8:00 | 2023-11-15 | 18:00 | 2d, 10h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 2173-003
DB Netz AG | 2173-004 | Rostock - Berlin | <> | Rostock Seehafen | Rostock Seehafen | 2023 | 2023 | 46 | 46 | 2023-11-13 | 8:00 | 2023-11-15 | 18:00 | 2d, 10h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 2173-004
DB Netz AG | 2173-005 | Rostock - Berlin | <> | Kavelstorf | Ro Seehf Süd | 2023 | 2023 | 46 | 46 | 2023-11-13 | 8:00 | 2023-11-14 | 18:00 | 1d, 10h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | 2173-005
DB Netz AG | 2173-006 | Rostock - Berlin | <> | Ro Seehf Süd | Ro Seehf Süd | 2023 | 2023 | 46 | 46 | 2023-11-13 | 8:02 | 2023-11-13 | 18:00 | 0d, 9h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 2173-006
DB Netz AG | 2173-007 | Rostock - Berlin | <> | Riekdahl | Ro Seehf Süd | 2023 | 2023 | 46 | 46 | 2023-11-13 | 8:02 | 2023-11-13 | 18:00 | 0d, 9h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | 2173-007
DB Netz AG | 2173-008 | Rostock - Berlin | <> | Ro Seehf Süd | Ro Seehf Süd | 2023 | 2023 | 46 | 46 | 2023-11-14 | 8:00 | 2023-11-15 | 18:00 | 1d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 2173-008
DB Netz AG | 2173-009 | Rostock - Berlin | <> | Ro Seehf Süd | Ro Seehf Süd | 2023 | 2023 | 46 | 46 | 2023-11-14 | 8:00 | 2023-11-15 | 18:00 | 1d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 2173-009
DB Netz AG | 2173-010 | Rostock - Berlin | <> | Rostock Seehafen | Ro Seehf Süd | 2023 | 2023 | 46 | 46 | 2023-11-14 | 8:00 | 2023-11-15 | 18:00 | 1d, 10h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | 2173-010
DB Netz AG | 2173-011 | Rostock - Berlin | <> | Kavelstorf | Rostock Seehafen | 2023 | 2023 | 46 | 46 | 2023-11-15 | 8:00 | 2023-11-16 | 18:00 | 1d, 10h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | 2173-011
DB Netz AG | 2173-012 | Rostock - Berlin | <> | Ro Seehf Süd | Ro Seehf Süd | 2023 | 2023 | 46 | 46 | 2023-11-15 | 8:00 | 2023-11-16 | 18:00 | 1d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 2173-012
DB Netz AG | 2173-013 | Rostock - Berlin | <> | Rostock Seehafen | Rostock Seehafen | 2023 | 2023 | 46 | 46 | 2023-11-16 | 8:00 | 2023-11-16 | 18:00 | 0d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 2173-013
DB Netz AG | 2173-014 | Rostock - Berlin | <> | Bentwisch | Ro Seehf Süd | 2023 | 2023 | 46 | 47 | 2023-11-17 | 7:00 | 2023-11-21 | 18:00 | 4d, 11h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | 2173-014
DB Netz AG | 2173-015 | Rostock - Berlin | <> | Rostock Seehafen | Rostock Seehafen | 2023 | 2023 | 46 | 46 | 2023-11-17 | 8:00 | 2023-11-17 | 18:00 | 0d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 2173-015
DB Netz AG | 2173-016 | Rostock - Berlin | <> | Rostock Seehafen | Rostock Seehafen | 2023 | 2023 | 46 | 46 | 2023-11-18 | 8:00 | 2023-11-18 | 18:00 | 0d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 2173-016
DB Netz AG | 1FDE-094 | Rostock - Berlin | <> | Bentwisch | Ro Seehf Süd | 2023 | 2023 | 47 | 47 | 2023-11-22 | 7:00 | 2023-11-23 | 18:00 | 1d, 11h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | 1FDE-094
DB Netz AG | 1FDE-095 | Rostock - Berlin | <> | Ro Seehf Süd | Ro Seehf Süd | 2023 | 2023 | 47 | 47 | 2023-11-22 | 7:00 | 2023-11-23 | 18:00 | 1d, 11h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 1FDE-095
DB Netz AG | 1FDE-096 | Rostock - Berlin | <> | Kavelstorf | Ro Seehf Süd | 2023 | 2023 | 47 | 47 | 2023-11-22 | 8:00 | 2023-11-23 | 18:00 | 1d, 10h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | 1FDE-096
DB Netz AG | 1FDE-098 | Rostock - Berlin | <> | Ro Seehf Süd | Rostock Seehafen | 2023 | 2023 | 47 | 47 | 2023-11-22 | 8:00 | 2023-11-23 | 18:00 | 1d, 10h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 1FDE-098
DB Netz AG | 2174-001 | Rostock - Berlin | <> | Rostock Seehafen | Rostock Seehafen | 2023 | 2023 | 47 | 47 | 2023-11-23 | 8:00 | 2023-11-24 | 18:00 | 1d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 2174-001
DB Netz AG | 2174-002 | Rostock - Berlin | <> | Rostock Seehafen | Rostock Seehafen | 2023 | 2023 | 47 | 47 | 2023-11-23 | 8:01 | 2023-11-24 | 18:00 | 1d, 9h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 2174-002
DB Netz AG | 2174-003 | Rostock - Berlin | <> | Rostock Seehafen | Rostock Seehafen | 2023 | 2023 | 47 | 47 | 2023-11-23 | 8:01 | 2023-11-24 | 18:00 | 1d, 9h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 2174-003
DB Netz AG | 2174-004 | Rostock - Berlin | <> | Ro Seehf Süd | Rostock Seehafen | 2023 | 2023 | 47 | 47 | 2023-11-24 | 7:00 | 2023-11-26 | 18:00 | 2d, 11h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 2174-004
DB Netz AG | 2174-005 | Rostock - Berlin | <> | Ro Seehf Süd | Rostock Seehafen | 2023 | 2023 | 47 | 47 | 2023-11-24 | 8:00 | 2023-11-26 | 18:00 | 2d, 10h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 2174-005
DB Netz AG | 2174-006 | Rostock - Berlin | <> | Rostock Seehafen | Rostock Seehafen | 2023 | 2023 | 47 | 48 | 2023-11-25 | 8:00 | 2023-11-27 | 18:00 | 2d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 2174-006
DB Netz AG | 2174-007 | Rostock - Berlin | <> | Rostock Seehafen | Rostock Seehafen | 2023 | 2023 | 47 | 48 | 2023-11-25 | 8:01 | 2023-11-27 | 18:00 | 2d, 9h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 2174-007
DB Netz AG | 2174-008 | Rostock - Berlin | <> | Rostock Seehafen | Rostock Seehafen | 2023 | 2023 | 47 | 48 | 2023-11-25 | 8:01 | 2023-11-27 | 18:00 | 2d, 9h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 2174-008
DB Netz AG | 2174-009 | Rostock - Berlin | <> | Ro Seehf Süd | Ro Seehf Süd | 2023 | 2023 | 48 | 48 | 2023-11-27 | 7:00 | 2023-11-28 | 17:00 | 1d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 2174-009
DB Netz AG | 2174-010 | Rostock - Berlin | <> | Ro Seehf Süd | Rostock Seehafen | 2023 | 2023 | 48 | 48 | 2023-11-27 | 7:01 | 2023-11-28 | 17:00 | 1d, 9h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 2174-010
DB Netz AG | 2174-011 | Rostock - Berlin | <> | Rostock Seehafen | Rostock Seehafen | 2023 | 2023 | 48 | 48 | 2023-11-29 | 7:00 | 2023-12-01 | 17:00 | 2d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 2174-011
DB Netz AG | 1965-021 | Rostock - Berlin | <> | Birkenwerder N | Birkenwerd b Bln | 2023 | 2023 | 47 | 47 | 2023-11-20 | 8:00 | 2023-11-24 | 18:00 | 4d, 10h | Periodical | Signal |  |  |  |  | X | [6 empty] | 80 | N | 1965-021 |  | 2021-11-15
DB Netz AG | 23DA-001 | Rostock - Berlin | < | Bln-Karow Ost | Biesdf Kr N Strw | 2023 | 2023 | 48 | 48 | 2023-11-27 | 20:00 | 2023-11-27 | 23:00 | 0d, 3h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 23DA-001 |  | 2021-03-11
DB Netz AG | 23DA-002 | Rostock - Berlin | < | Biesdf Kr N Strw | Biesdf Kr Nord | 2023 | 2023 | 48 | 48 | 2023-11-27 | 20:00 | 2023-11-27 | 23:00 | 0d, 3h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 23DA-002 |  | 2021-03-11
DB Netz AG | 23DA-003 | Rostock - Berlin | < | Biesdf Kr Nord | Biesdf Kr Nord | 2023 | 2023 | 48 | 48 | 2023-11-27 | 20:00 | 2023-11-27 | 23:00 | 0d, 3h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 23DA-003 |  | 2021-03-11
DB Netz AG | 23DA-005 | Rostock - Berlin | < | Bln-Karow Ost | Biesdf Kr N Strw | 2023 | 2023 | 48 | 48 | 2023-11-27 | 23:00 | 2023-11-28 | 3:00 | 0d, 4h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 23DA-005 |  | 2021-03-11
DB Netz AG | 23DA-006 | Rostock - Berlin | < | Biesdf Kr N Strw | Biesdf Kr Mitte | 2023 | 2023 | 48 | 48 | 2023-11-27 | 23:00 | 2023-11-28 | 3:00 | 0d, 4h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 23DA-006 |  | 2021-03-11
DB Netz AG | 23DA-007 | Rostock - Berlin | < | Biesdf Kr Nord | Biesdf Kr Nord | 2023 | 2023 | 48 | 48 | 2023-11-27 | 23:00 | 2023-11-28 | 3:00 | 0d, 4h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 23DA-007 |  | 2021-03-11
DB Netz AG | 23DA-008 | Rostock - Berlin | <> | Biesdf Kr Nord | Bln Nordost | 2023 | 2023 | 48 | 48 | 2023-11-27 | 23:00 | 2023-11-28 | 3:00 | 0d, 4h | Continuous | Track & Rail | T | [10 empty] | 80 | N | 23DA-008 |  | 2021-03-11
DB Netz AG | 23DA-009 | Rostock - Berlin | <> | Biesdf Kr Nord | Biesdf Kr SW | 2023 | 2023 | 48 | 48 | 2023-11-27 | 23:00 | 2023-11-28 | 3:00 | 0d, 4h | Continuous | Track & Rail | T | [10 empty] | 80 | N | 23DA-009 |  | 2021-03-11
DB Netz AG | 23DA-010 | Rostock - Berlin | <> | Biesdf Kr West | Biesdf Kr Nord | 2023 | 2023 | 48 | 48 | 2023-11-27 | 23:00 | 2023-11-28 | 3:00 | 0d, 4h | Continuous | Track & Rail | T | [10 empty] | 80 | N | 23DA-010 |  | 2021-03-11
DB Netz AG | 23DA-011 | Rostock - Berlin | < | Biesdf Kr Nord | Eichgestell | 2023 | 2023 | 48 | 48 | 2023-11-28 | 2:00 | 2023-11-28 | 6:00 | 0d, 4h | Periodical | Track & Rail |  | LT | [9 empty] | 80 | N | 23DA-011 |  | 2021-03-11
DB Netz AG | 23DA-012 | Rostock - Berlin | <> | Biesdf Kr SW | Biesdf Kr Süd | 2023 | 2023 | 48 | 48 | 2023-11-28 | 2:00 | 2023-11-28 | 6:00 | 0d, 4h | Periodical | Track & Rail | T | [10 empty] | 80 | N | 23DA-012 |  | 2021-03-11
DB Netz AG | 1965-023 | Rostock - Berlin | <> | Birkenwerder S-B | Birkenwerder N | 2023 | 2023 | 46 | 46 | 2023-11-13 | 8:00 | 2023-11-16 | 18:00 | 3d, 10h | Periodical | Signal |  | LT | [9 empty] | 80 | N | 1965-023 |  | 2021-11-15
DB Netz AG | 130A-007 | Rostock - Berlin | <> | Birkenwerder N | Birkenwerd b Bln | 2023 | 2023 | 45 | 46 | 2023-11-10 | 22:00 | 2023-11-13 | 4:00 | 2d, 6h | Continuous | Signal | T | [10 empty] | 80 | N | 130A-007 |  | 2021-11-15
DB Netz AG | 247F-003 | Rostock - Berlin | <> | Oranienburg | Hohen Neuend Sw | 2023 | 2023 | 46 | 47 | 2023-11-18 | 8:00 | 2023-11-25 | 20:00 | 7d, 12h | Periodical | Signal | T | [10 empty] | 80 | N | 247F-003 |  | 2022-05-02
DB Netz AG | 247F-004 | Rostock - Berlin | <> | Birkenwerd b Bln | Hohen Neuend W | 2023 | 2023 | 46 | 47 | 2023-11-18 | 8:00 | 2023-11-25 | 20:00 | 7d, 12h | Periodical | Signal | T | [10 empty] | 80 | N | 247F-004 |  | 2022-05-02
DB Netz AG | 247F-005 | Rostock - Berlin | <> | Hohen Neuend Sw | Bergfelde Ost | 2023 | 2023 | 46 | 47 | 2023-11-18 | 8:00 | 2023-11-25 | 20:00 | 7d, 12h | Periodical | Signal | T | [10 empty] | 80 | N | 247F-005 |  | 2022-05-02
DB Netz AG | 247F-006 | Rostock - Berlin | <> | Birkenwerd b Bln | Schönfließ West | 2023 | 2023 | 46 | 47 | 2023-11-18 | 8:00 | 2023-11-25 | 20:00 | 7d, 12h | Periodical | Signal | T | [10 empty] | 80 | N | 247F-006 |  | 2022-05-02
DB Netz AG | 247F-007 | Rostock - Berlin | <> | Hohen Neuend Sw | Schönfließ West | 2023 | 2023 | 46 | 47 | 2023-11-18 | 8:00 | 2023-11-25 | 20:00 | 7d, 12h | Periodical | Signal | T | [10 empty] | 80 | N | 247F-007 |  | 2022-05-02
DB Netz AG | 247F-008 | Rostock - Berlin | <> | Birkenwerder N | Birkenwerd b Bln | 2023 | 2023 | 46 | 47 | 2023-11-18 | 8:00 | 2023-11-25 | 20:00 | 7d, 12h | Periodical | Signal | T | [10 empty] | 80 | N | 247F-008 |  | 2022-05-02
DB Netz AG | 247F-009 | Rostock - Berlin | <> | Oranienburg | Oranienburg | 2023 | 2023 | 46 | 47 | 2023-11-18 | 8:00 | 2023-11-25 | 20:00 | 7d, 12h | Periodical | Signal |  | ST | [9 empty] | 80 | N | 247F-009 |  | 2022-05-02
DB Netz AG | AF1-005 | Hamburg - Magdeburg | <> | Lüneburg Gbf | Lüneburg Gbf | 2023 | 2023 | 49 | 49 | 2023-12-04 | 22:40 | 2023-12-09 | 5:15 | 4d, 6h | Periodical | Signal |  | ST | [9 empty] | 80 | N | AF1-005 |  | 2021-05-07
DB Netz AG | AF1-006 | Hamburg - Magdeburg | < | Lüneburg Nordk | Lüneburg Gbf | 2023 | 2023 | 49 | 49 | 2023-12-04 | 22:40 | 2023-12-09 | 5:15 | 4d, 6h | Periodical | Signal |  | ST | [9 empty] | 80 | N | AF1-006 |  | 2021-05-07
DB Netz AG | AF1-001 | Hamburg - Magdeburg | <> | Lüneburg Gbf | Lüneburg Gbf | 2023 | 2023 | 49 | 49 | 2023-12-04 | 22:40 | 2023-12-09 | 5:15 | 4d, 6h | Periodical | Signal |  | ST | [9 empty] | 80 | N | AF1-001 |  | 2021-05-07
DB Netz AG | 1965-014 | Rostock - Berlin | <> | Birkenwerd b Bln | Hohen Neuend W | 2023 | 2023 | 48 | 48 | 2023-12-02 | 8:00 | 2023-12-02 | 16:00 | 0d, 8h | Continuous | Signal | T | [10 empty] | 80 | N | 1965-014 |  | 2021-09-16
DB Netz AG | 1965-015 | Rostock - Berlin | <> | Birkenwerd b Bln | Birkenwerd b Bln | 2023 | 2023 | 48 | 48 | 2023-12-02 | 8:00 | 2023-12-02 | 16:00 | 0d, 8h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 1965-015 |  | 2021-09-16
DB Netz AG | 1965-016 | Rostock - Berlin | <> | Hohen Neuend Sw | Schönfließ West | 2023 | 2023 | 48 | 48 | 2023-12-02 | 8:00 | 2023-12-02 | 16:00 | 0d, 8h | Continuous | Signal | T | [10 empty] | 80 | N | 1965-016 |  | 2021-09-16
DB Netz AG | 12E2-004 | Magdeburg - Falkenberg | <> | Lu Wb-Labetz | Lu Wittenb Altst | 2023 | 2023 | 48 | 49 | 2023-12-02 | 4:00 | 2023-12-04 | 10:00 | 2d, 6h | Continuous | Signal | T | [10 empty] | 80 | N | 12E2-004 |  | 2022-06-17
DB Netz AG | 12F4-002 | Magdeburg - Falkenberg | < | Lu Wittenberg | Lu Wittenberg | 2023 | 2023 | 49 | 49 | 2023-12-06 | 9:00 | 2023-12-09 | 15:00 | 3d, 6h | Periodical | Signal |  | ST | [9 empty] | 80 | N | 12F4-002 |  | 2022-06-07
DB Netz AG | 15.2 | Magdeburg - Falkenberg | > | Elster (Elbe) | Lu Wittenberg | 2023 | 2023 | 48 | 49 | 2023-12-03 | 9:00 | 2023-12-09 | 15:00 | 6d, 6h | Periodical | Signal |  | LT | [9 empty] | 80 | N | 15.2 |  | 2021-08-23
DB Netz AG | 1.52 | Magdeburg - Falkenberg | <> | Lu Wittenberg | Lu Wittenberg | 2023 | 2023 | 48 | 49 | 2023-12-03 | 9:00 | 2023-12-09 | 15:00 | 6d, 6h | Periodical | Signal |  | ST | [9 empty] | 80 | N | 1.52 |  | 2021-07-20
DB Netz AG | 0.0152 | Magdeburg - Falkenberg | <> | Lu Wittenberg | Lu Wittenberg | 2023 | 2023 | 48 | 49 | 2023-12-03 | 9:00 | 2023-12-09 | 15:00 | 6d, 6h | Periodical | Signal |  | ST | [9 empty] | 80 | N | 0.0152 |  | 2021-05-17
DB Netz AG | 16E5-001 | Dresden - Děčín | <> | Bad Schandau Gr | Bad Schandau | 2023 | 2023 | 49 | 49 | 2023-12-04 | 8:50 | 2023-12-04 | 16:40 | 0d, 7h | Continuous | Catenary | T | [10 empty] | 80,54 | N | 16E5-001 |  | 2021-04-27
DB Netz AG | 16E5-003 | Dresden - Děčín | <> | Bad Schandau Gr | Bad Schandau | 2023 | 2023 | 49 | 49 | 2023-12-04 | 8:50 | 2023-12-04 | 16:40 | 0d, 7h | Continuous | Catenary |  |  |  |  | X | [6 empty] | 80,54 | N | 16E5-003 |  | 2021-04-27
DB Netz AG | 1854-001 | Hamburg - Magdeburg | > | Winsen (Luhe) | Winsen (Luhe) | 2023 | 2023 | 49 | 49 | 2023-12-04 | 8:00 | 2023-12-04 | 14:00 | 0d, 6h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1854-001 |  | 2021-04-28
DB Netz AG | 1854-002 | Hamburg - Magdeburg | > | Winsen (Luhe) | Winsen (Luhe) | 2023 | 2023 | 49 | 49 | 2023-12-04 | 8:00 | 2023-12-04 | 14:00 | 0d, 6h | Continuous | Track & Rail |  |  | S | [8 empty] | 80 | N | 1854-002 |  | 2021-04-28
DB Netz AG | 1888-003 | Hannover - Magdeburg | > | Hannover Hbf | Lehrte West | 2023 | 2023 | 49 | 49 | 2023-12-09 | 0:40 | 2023-12-09 | 1:50 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1888-003 |  | 2022-07-15
DB Netz AG | 1888-004 | Hannover - Magdeburg | > | Han K-Wiechert-A | Lehrte West | 2023 | 2023 | 49 | 49 | 2023-12-09 | 1:50 | 2023-12-09 | 4:40 | 0d, 2h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1888-004 |  | 2022-07-15
DB Netz AG | 1888-005 | Hannover - Magdeburg | > | Han K-Wiechert-A | Hämelerwald | 2023 | 2023 | 49 | 49 | 2023-12-09 | 4:40 | 2023-12-09 | 5:55 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1888-005 |  | 2022-07-15
DB Netz AG | 1888-006 | Hannover - Magdeburg | > | Lehrte | Lehrte | 2023 | 2023 | 49 | 49 | 2023-12-09 | 4:40 | 2023-12-09 | 5:55 | 0d, 1h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 1888-006 |  | 2022-07-15
DB Netz AG | 1888-007 | Hannover - Magdeburg | < | Lehrte | Lehrte | 2023 | 2023 | 49 | 49 | 2023-12-09 | 4:40 | 2023-12-09 | 5:55 | 0d, 1h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 1888-007 |  | 2022-07-15
DB Netz AG | 1888-008 | Hannover - Magdeburg | > | Lehrte | Hämelerwald | 2023 | 2023 | 49 | 49 | 2023-12-09 | 5:55 | 2023-12-09 | 6:40 | 0d, 0h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1888-008 |  | 2022-07-15
DB Netz AG | 1892-001 | Bremen - Hannover | < | Hannover-Linden | Seelze Ost | 2023 | 2023 | 49 | 49 | 2023-12-09 | 22:00 | 2023-12-09 | 23:45 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1892-001
DB Netz AG | 1892-002 | Bremen - Hannover | < | Han-Linden Hafen | Seelze Ost | 2023 | 2023 | 49 | 49 | 2023-12-09 | 23:45 | 2023-12-09 | 23:59 | 0d, 0h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 1892-002
DB Netz AG | 1892-003 | Bremen - Hannover | <> | Ahlem | Kurve | 2023 | 2023 | 49 | 49 | 2023-12-09 | 22:00 | 2023-12-09 | 23:45 | 0d, 1h | Continuous | Maintenance | T | [10 empty] | 80 | N | 1892-003
DB Netz AG | 1892-004 | Bremen - Hannover | <> | Ahlem | Kurve | 2023 | 2023 | 49 | 49 | 2023-12-09 | 23:45 | 2023-12-09 | 23:59 | 0d, 0h | Continuous | Maintenance | T | [10 empty] | 80 | N | 1892-004
DB Netz AG | 18.9 | Bremerhaven - Bremen | > | Brm-Sebaldsbrück | Bremen Hbf | 2023 | 2023 | 48 | 49 | 2023-12-03 | 23:00 | 2023-12-04 | 5:00 | 0d, 6h | Continuous | Bridge |  | LT | [9 empty] | 80 | N | 18.9 |  | 2021-11-29
DB Netz AG | 0.189 | Bremerhaven - Bremen | > | Brm-Sebaldsbrück | Bremen Hbf | 2023 | 2023 | 48 | 48 | 2023-12-03 | 3:00 | 2023-12-03 | 8:00 | 0d, 5h | Continuous | Bridge |  | LT | [9 empty] | 80 | N | 0.189 |  | 2021-05-18
DB Netz AG | 0.00189 | Bremerhaven - Bremen | < | Bremen Hbf | Brm-Sebaldsbrück | 2023 | 2023 | 48 | 48 | 2023-12-02 | 22:00 | 2023-12-03 | 3:00 | 0d, 5h | Continuous | Bridge |  | LT | [9 empty] | 80 | N | 0.00189 |  | 2021-05-18
DB Netz AG | 0.000189 | Bremerhaven - Bremen | <> | Brm-Sebaldsbrück | Bremen Hbf | 2023 | 2023 | 48 | 48 | 2023-12-03 | 0:00 | 2023-12-03 | 3:00 | 0d, 3h | Continuous | Bridge | T | [10 empty] | 80 | N | 0.000189 |  | 2021-05-18
DB Netz AG | 19C6-001 | Falkenberg - Dresden | > | Riesa | Zeithain Bogendr | 2023 | 2023 | 49 | 49 | 2023-12-04 | 21:00 | 2023-12-04 | 23:00 | 0d, 2h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 19C6-001 |  | 2021-05-02
DB Netz AG | 19C6-002 | Falkenberg - Dresden | < | Zeithain Bogendr | Riesa | 2023 | 2023 | 49 | 49 | 2023-12-04 | 23:00 | 2023-12-05 | 2:30 | 0d, 3h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 19C6-002 |  | 2021-05-02
DB Netz AG | 19C6-003 | Falkenberg - Dresden | <> | Riesa | Röderau | 2023 | 2023 | 49 | 49 | 2023-12-04 | 23:00 | 2023-12-05 | 4:30 | 0d, 5h | Continuous | Maintenance | T | [10 empty] | 80 | N | 19C6-003 |  | 2021-05-02
DB Netz AG | 19C6-004 | Falkenberg - Dresden | <> | Riesa | Zeithain Bogendr | 2023 | 2023 | 49 | 49 | 2023-12-05 | 2:30 | 2023-12-05 | 4:30 | 0d, 2h | Continuous | Maintenance | T | [10 empty] | 80 | N | 19C6-004 |  | 2021-05-02
DB Netz AG | 19C9-001 | Magdeburg - Falkenberg | <> | Röderau | Zeithain Bogendr | 2023 | 2023 | 49 | 49 | 2023-12-05 | 20:30 | 2023-12-07 | 21:00 | 2d, 0h | Periodical | Maintenance | T | [10 empty] | 80 | N | 19C9-001 |  | 2021-06-22
DB Netz AG | 19C9-002 | Magdeburg - Falkenberg | <> | Röderau | Zeithain Bogendr | 2023 | 2023 | 49 | 49 | 2023-12-06 | 4:00 | 2023-12-08 | 4:30 | 2d, 0h | Periodical | Maintenance | T | [10 empty] | 80 | N | 19C9-002 |  | 2021-06-22
DB Netz AG | 19C9-003 | Falkenberg - Dresden | > | Röderau Bogendr | Zeithain Bogendr | 2023 | 2023 | 49 | 49 | 2023-12-05 | 21:00 | 2023-12-05 | 23:00 | 0d, 2h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 19C9-003 |  | 2021-06-22
DB Netz AG | 19C9-004 | Falkenberg - Dresden | > | Zeithain Bogendr | Leckwitz | 2023 | 2023 | 49 | 49 | 2023-12-05 | 21:00 | 2023-12-05 | 23:00 | 0d, 2h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 19C9-004 |  | 2021-06-22
DB Netz AG | 19C9-005 | Magdeburg - Falkenberg | <> | Röderau | Zeithain Bogendr | 2023 | 2023 | 49 | 49 | 2023-12-05 | 23:00 | 2023-12-06 | 4:00 | 0d, 5h | Continuous | Maintenance | T | [10 empty] | 80 | N | 19C9-005 |  | 2021-06-22
DB Netz AG | 19C9-006 | Falkenberg - Dresden | <> | Rohrwerk | Zeithain Bogendr | 2023 | 2023 | 49 | 49 | 2023-12-05 | 23:00 | 2023-12-06 | 4:00 | 0d, 5h | Continuous | Maintenance | T | [10 empty] | 80 | N | 19C9-006 |  | 2021-06-22
DB Netz AG | 19C9-007 | Falkenberg - Dresden | < | Leckwitz | Zeithain Bogendr | 2023 | 2023 | 49 | 49 | 2023-12-05 | 23:00 | 2023-12-06 | 2:00 | 0d, 3h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 19C9-007 |  | 2021-06-22
DB Netz AG | 19C9-008 | Falkenberg - Dresden | < | Zeithain Bogendr | Riesa | 2023 | 2023 | 49 | 49 | 2023-12-05 | 23:00 | 2023-12-06 | 2:00 | 0d, 3h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 19C9-008 |  | 2021-06-22
DB Netz AG | 19C9-009 | Falkenberg - Dresden | <> | Weißig (b Groß) | Röderau Bogendr | 2023 | 2023 | 49 | 49 | 2023-12-06 | 2:00 | 2023-12-06 | 4:00 | 0d, 2h | Continuous | Maintenance | T | [10 empty] | 80 | N | 19C9-009 |  | 2021-06-22
DB Netz AG | 19C9-010 | Magdeburg - Falkenberg | <> | Röderau | Zeithain Bogendr | 2023 | 2023 | 49 | 49 | 2023-12-06 | 21:00 | 2023-12-07 | 4:00 | 0d, 7h | Continuous | Maintenance | T | [10 empty] | 80 | N | 19C9-010 |  | 2021-06-22
DB Netz AG | 19C9-011 | Falkenberg - Dresden | <> | Zeithain Bogendr | Rohrwerk | 2023 | 2023 | 49 | 49 | 2023-12-06 | 21:00 | 2023-12-07 | 4:00 | 0d, 7h | Continuous | Maintenance | T | [10 empty] | 80 | N | 19C9-011 |  | 2021-06-22
DB Netz AG | 19C9-012 | Falkenberg - Dresden | < | Leckwitz | Zeithain Bogendr | 2023 | 2023 | 49 | 49 | 2023-12-06 | 21:00 | 2023-12-07 | 2:00 | 0d, 5h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 19C9-012 |  | 2021-06-22
DB Netz AG | 19C9-013 | Falkenberg - Dresden | < | Zeithain Bogendr | Riesa | 2023 | 2023 | 49 | 49 | 2023-12-06 | 21:00 | 2023-12-07 | 2:00 | 0d, 5h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 19C9-013 |  | 2021-06-22
DB Netz AG | 19C9-014 | Falkenberg - Dresden | <> | Weißig (b Groß) | Röderau Bogendr | 2023 | 2023 | 49 | 49 | 2023-12-07 | 2:00 | 2023-12-07 | 4:00 | 0d, 2h | Continuous | Maintenance | T | [10 empty] | 80 | N | 19C9-014 |  | 2021-06-22
DB Netz AG | 19C9-015 | Falkenberg - Dresden | > | Röderau Bogendr | Zeithain Bogendr | 2023 | 2023 | 49 | 49 | 2023-12-07 | 21:00 | 2023-12-08 | 0:00 | 0d, 3h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 19C9-015 |  | 2021-06-22
DB Netz AG | 19C9-016 | Falkenberg - Dresden | > | Zeithain Bogendr | Leckwitz | 2023 | 2023 | 49 | 49 | 2023-12-07 | 21:00 | 2023-12-08 | 0:00 | 0d, 3h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 19C9-016 |  | 2021-06-22
DB Netz AG | 19C9-017 | Magdeburg - Falkenberg | <> | Röderau | Zeithain Bogendr | 2023 | 2023 | 49 | 49 | 2023-12-08 | 0:00 | 2023-12-08 | 4:00 | 0d, 4h | Continuous | Maintenance | T | [10 empty] | 80 | N | 19C9-017 |  | 2021-06-22
DB Netz AG | 19C9-018 | Falkenberg - Dresden | <> | Zeithain Bogendr | Rohrwerk | 2023 | 2023 | 49 | 49 | 2023-12-08 | 0:00 | 2023-12-08 | 4:00 | 0d, 4h | Continuous | Maintenance | T | [10 empty] | 80 | N | 19C9-018 |  | 2021-06-22
DB Netz AG | 19C9-019 | Falkenberg - Dresden | < | Leckwitz | Zeithain Bogendr | 2023 | 2023 | 49 | 49 | 2023-12-08 | 0:00 | 2023-12-08 | 2:00 | 0d, 2h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 19C9-019 |  | 2021-06-22
DB Netz AG | 19C9-020 | Falkenberg - Dresden | < | Zeithain Bogendr | Riesa | 2023 | 2023 | 49 | 49 | 2023-12-08 | 0:00 | 2023-12-08 | 2:00 | 0d, 2h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 19C9-020 |  | 2021-06-22
DB Netz AG | 19C9-021 | Falkenberg - Dresden | <> | Röderau Bogendr | Weißig (b Groß) | 2023 | 2023 | 49 | 49 | 2023-12-08 | 2:00 | 2023-12-08 | 4:00 | 0d, 2h | Continuous | Maintenance | T | [10 empty] | 80 | N | 19C9-021 |  | 2021-06-22
DB Netz AG | 1A01-005 | Hamburg - Magdeburg | <> | Lüneburg Gbf | Lüneburg Gbf | 2023 | 2023 | 49 | 49 | 2023-12-09 | 5:15 | 2023-12-09 | 7:15 | 0d, 2h | Continuous | Signal |  | ST | [9 empty] | 80 | N | 1A01-005 |  | 2021-05-14
DB Netz AG | 1A01-006 | Hamburg - Magdeburg | <> | Lüneburg Gbf | Lüneburg Gbf | 2023 | 2023 | 49 | 49 | 2023-12-09 | 5:15 | 2023-12-09 | 7:15 | 0d, 2h | Continuous | Signal |  |  |  |  | X | [6 empty] | 80 | N | 1A01-006 |  | 2021-05-14
DB Netz AG | 1C8C-001 | Hamburg - Magdeburg | > | Dollbergen | Lehrte | 2023 | 2023 | 48 | 49 | 2023-12-03 | 22:10 | 2023-12-06 | 5:45 | 2d, 7h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 1C8C-001 |  | 2022-07-15
DB Netz AG | 1C8C-004 | Hamburg - Magdeburg | <> | Lehrte | Dollbergen | 2023 | 2023 | 49 | 49 | 2023-12-04 | 1:50 | 2023-12-04 | 4:50 | 0d, 3h | Continuous | Catenary | T | [10 empty] | 80 | N | 1C8C-004 |  | 2022-07-15
DB Netz AG | 1C8C-005 | Hamburg - Magdeburg | < | Lehrte | Dollbergen | 2023 | 2023 | 49 | 49 | 2023-12-06 | 22:10 | 2023-12-08 | 5:55 | 1d, 7h | Periodical | Catenary |  | LT | [9 empty] | 80 | N | 1C8C-005 |  | 2022-07-15
DB Netz AG | 2052-001 | Bremen - Hannover | <> | Bremen Hbf | Bremen Hbf | 2023 | 2023 | 48 | 48 | 2023-12-02 | 20:00 | 2023-12-03 | 8:30 | 0d, 12h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 2052-001 |  | 2021-04-26
DB Netz AG | 2052-002 | Bremen - Hannover | < | Bremen Rbf Ausf | Bremen Hbf | 2023 | 2023 | 48 | 48 | 2023-12-02 | 20:00 | 2023-12-03 | 8:30 | 0d, 12h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 2052-002 |  | 2021-12-02
DB Netz AG | 2052-003 | Bremen - Hannover | <> | Bremen Hbf | Bremen Hbf | 2023 | 2023 | 48 | 48 | 2023-12-03 | 0:00 | 2023-12-03 | 8:30 | 0d, 8h | Continuous | Track & Rail | T | [10 empty] | 80 | N | 2052-003 |  | 2021-04-26
DB Netz AG | 2052-004 | Bremen - Hannover | < | Brm Hbf ehem Bwn | Bremen Hbf | 2023 | 2023 | 48 | 48 | 2023-12-03 | 0:00 | 2023-12-03 | 8:30 | 0d, 8h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 2052-004 |  | 2021-12-02
DB Netz AG | 1D8A-005 | Bremen - Hannover | < | Bremen Rbf Ausf | Bremen Hbf | 2023 | 2023 | 48 | 49 | 2023-12-03 | 20:00 | 2023-12-04 | 6:30 | 0d, 10h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1D8A-005 |  | 2021-12-02
DB Netz AG | 1D8A-006 | Bremen - Hannover | <> | Bremen Hbf | Bremen Hbf | 2023 | 2023 | 48 | 49 | 2023-12-03 | 20:00 | 2023-12-04 | 6:30 | 0d, 10h | Continuous | Track & Rail |  | ST | [9 empty] | 80 | N | 1D8A-006 |  | 2021-04-26
DB Netz AG | 1D8A-007 | Bremen - Hannover | < | Brm Hbf ehem Bwn | Bremen Hbf | 2023 | 2023 | 49 | 49 | 2023-12-04 | 0:00 | 2023-12-04 | 6:30 | 0d, 6h | Continuous | Track & Rail |  | LT | [9 empty] | 80 | N | 1D8A-007 |  | 2021-12-02
DB Netz AG | 1D8A-008 | Bremen - Hannover | <> | Bremen Hbf | Bremen Hbf | 2023 | 2023 | 49 | 49 | 2023-12-04 | 0:00 | 2023-12-04 | 6:30 | 0d, 6h | Continuous | Track & Rail | T | [10 empty] | 80 | N | 1D8A-008 |  | 2021-04-26
DB Netz AG | 2174-012 | Rostock - Berlin | <> | Rostock Seehafen | Rostock Seehafen | 2023 | 2023 | 48 | 48 | 2023-12-02 | 7:00 | 2023-12-03 | 17:00 | 1d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 2174-012
DB Netz AG | 2174-013 | Rostock - Berlin | <> | Ro Seehf Süd | Rostock Seehafen | 2023 | 2023 | 48 | 48 | 2023-12-02 | 7:00 | 2023-12-03 | 17:00 | 1d, 10h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | 2174-013
DB Netz AG | 2174-014 | Rostock - Berlin | <> | Ro Seehf Süd | Rostock Seehafen | 2023 | 2023 | 48 | 48 | 2023-12-02 | 7:01 | 2023-12-03 | 17:00 | 1d, 9h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 2174-014
DB Netz AG | 2174-015 | Rostock - Berlin | <> | Kavelstorf | Ro Seehf Süd | 2023 | 2023 | 49 | 49 | 2023-12-04 | 8:00 | 2023-12-05 | 18:00 | 1d, 10h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | 2174-015
DB Netz AG | 2174-016 | Rostock - Berlin | <> | Ro Seehf Süd | Ro Seehf Süd | 2023 | 2023 | 49 | 49 | 2023-12-04 | 8:00 | 2023-12-06 | 18:00 | 2d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 2174-016
DB Netz AG | 2174-017 | Rostock - Berlin | <> | Ro Seehf Süd | Ro Seehf Süd | 2023 | 2023 | 49 | 49 | 2023-12-04 | 8:00 | 2023-12-05 | 18:00 | 1d, 10h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 2174-017
DB Netz AG | 2174-018 | Rostock - Berlin | <> | Kavelstorf | Rostock Seehafen | 2023 | 2023 | 49 | 49 | 2023-12-06 | 8:00 | 2023-12-07 | 18:00 | 1d, 10h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | 2174-018
DB Netz AG | 2174-020 | Rostock - Berlin | <> | Ro Seehf Süd | Ro Seehf Süd | 2023 | 2023 | 49 | 49 | 2023-12-06 | 8:00 | 2023-12-07 | 18:00 | 1d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 2174-020
DB Netz AG | 2174-021 | Rostock - Berlin | <> | Riekdahl | Rostock Seehafen | 2023 | 2023 | 49 | 49 | 2023-12-06 | 8:00 | 2023-12-07 | 18:00 | 1d, 10h | Periodical | Miscellaneous | T | [10 empty] | 80 | N | 2174-021
DB Netz AG | 2174-022 | Rostock - Berlin | <> | Ro Seehf Süd | Rostock Seehafen | 2023 | 2023 | 49 | 49 | 2023-12-06 | 8:00 | 2023-12-07 | 18:00 | 1d, 10h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 2174-022
DB Netz AG | 2174-023 | Rostock - Berlin | <> | Ro Seehf Süd | Rostock Seehafen | 2023 | 2023 | 49 | 49 | 2023-12-07 | 8:00 | 2023-12-09 | 18:00 | 2d, 10h | Periodical | Miscellaneous |  | ST | [9 empty] | 80 | N | 2174-023
DB Netz AG | 2174-024 | Rostock - Berlin | <> | Ro Seehf Süd | Rostock Seehafen | 2023 | 2023 | 49 | 49 | 2023-12-07 | 8:01 | 2023-12-09 | 18:00 | 2d, 9h | Periodical | Miscellaneous |  |  |  |  | X | [6 empty] | 80 | N | 2174-024
DB Netz AG | 1965-017 | Rostock - Berlin | <> | Schönfließ West | Hohen Neuend W | 2023 | 2023 | 48 | 48 | 2023-12-02 | 8:00 | 2023-12-02 | 16:00 | 0d, 8h | Continuous | Signal |  |  |  |  | X | [6 empty] | 80 | N | 1965-017 |  | 2022-05-16
DB Netz AG | 1965-018 | Rostock - Berlin | <> | Birkenwerder N | Birkenwerd b Bln | 2023 | 2023 | 48 | 48 | 2023-12-02 | 8:00 | 2023-12-02 | 16:00 | 0d, 8h | Continuous | Signal |  |  |  |  | X | [6 empty] | 80 | N | 1965-018 |  | 2022-05-16
DB Netz AG | 1965-019 | Rostock - Berlin | <> | Birkenwerd b Bln | Birkenwerder N | 2023 | 2023 | 48 | 48 | 2023-12-02 | 8:00 | 2023-12-02 | 16:00 | 0d, 8h | Continuous | Signal |  |  |  |  | X | [6 empty] | 80 | N | 1965-019 |  | 2022-05-16
DB Netz AG | 12F4-002 | Magdeburg - Falkenberg | < | Lu Wittenberg | Lu Wittenberg | 2023 | 2023 | 49 | 49 | 2023-12-06 | 9:00 | 2023-12-09 | 15:00 | 3d, 6h | Periodical | Signal |  | ST | [9 empty] | 80 | N | 12F4-002 |  | 2022-06-07
DB Netz AG | 15.2 | Magdeburg - Falkenberg | > | Elster (Elbe) | Lu Wittenberg | 2023 | 2023 | 48 | 49 | 2023-12-03 | 9:00 | 2023-12-09 | 15:00 | 6d, 6h | Periodical | Signal |  | LT | [9 empty] | 80 | N | 15.2 |  | 2021-08-23
DB Netz AG | 1.52 | Magdeburg - Falkenberg | <> | Lu Wittenberg | Lu Wittenberg | 2023 | 2023 | 48 | 49 | 2023-12-03 | 9:00 | 2023-12-09 | 15:00 | 6d, 6h | Periodical | Signal |  | ST | [9 empty] | 80 | N | 1.52 |  | 2021-07-20
DB Netz AG | 0.0152 | Magdeburg - Falkenberg | <> | Lu Wittenberg | Lu Wittenberg | 2023 | 2023 | 48 | 49 | 2023-12-03 | 9:00 | 2023-12-09 | 15:00 | 6d, 6h | Periodical | Signal |  | ST | [9 empty] | 80 | N | 0.0152 |  | 2021-05-17
DB Netz AG | 3C1F-001 | Bremen - Hannover | < | Han-Linden Hafen | Seelze Ost | 2023 | 2023 | 49 | 49 | 2023-12-10 | 0:00 | 2023-12-10 | 0:45 | 0d, 0h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 3C1F-001 |  | 2022-05-25
DB Netz AG | 3C1F-002 | Bremen - Hannover | <> | Ahlem | Kurve | 2023 | 2023 | 49 | 49 | 2023-12-10 | 0:00 | 2023-12-10 | 0:45 | 0d, 0h | Continuous | Maintenance | T | [10 empty] | 80 | N | 3C1F-002 |  | 2022-05-25
DB Netz AG | 3C1F-003 | Bremen - Hannover | <> | Seelze Ost | Han-Linden Hafen | 2023 | 2023 | 49 | 49 | 2023-12-10 | 0:00 | 2023-12-10 | 0:45 | 0d, 0h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 3C1F-003 |  | 2022-05-25
DB Netz AG | 3C1F-004 | Bremen - Hannover | <> | Ahlem | Ahlem | 2023 | 2023 | 49 | 49 | 2023-12-10 | 0:00 | 2023-12-10 | 0:45 | 0d, 0h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 3C1F-004 |  | 2022-05-25
DB Netz AG | 3C1F-006 | Bremen - Hannover | < | Seelze Ost | Seelze West | 2023 | 2023 | 49 | 49 | 2023-12-10 | 0:45 | 2023-12-10 | 1:30 | 0d, 0h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 3C1F-006 |  | 2022-05-25
DB Netz AG | 3C1F-008 | Bremen - Hannover | <> | Seelze West | Seelze Ost | 2023 | 2023 | 49 | 49 | 2023-12-10 | 0:45 | 2023-12-10 | 1:30 | 0d, 0h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 3C1F-008 |  | 2022-05-25
DB Netz AG | 3C1F-009 | Bremen - Hannover | <> | Seelze West | Letter Abzw | 2023 | 2023 | 49 | 49 | 2023-12-10 | 0:45 | 2023-12-10 | 1:30 | 0d, 0h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 3C1F-009 |  | 2022-05-25
DB Netz AG | 3C1F-010 | Bremen - Hannover | < | Seelze Mitte | Wunstorf | 2023 | 2023 | 49 | 49 | 2023-12-10 | 1:30 | 2023-12-10 | 4:00 | 0d, 2h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 3C1F-010 |  | 2022-05-25
DB Netz AG | 3C1F-011 | Bremen - Hannover | < | Gümmerwald | Wunstorf | 2023 | 2023 | 49 | 49 | 2023-12-10 | 1:30 | 2023-12-10 | 4:00 | 0d, 2h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 3C1F-011 |  | 2022-05-25
DB Netz AG | 3C1F-012 | Bremen - Hannover | <> | Seelze West | Wunstorf | 2023 | 2023 | 49 | 49 | 2023-12-10 | 1:30 | 2023-12-10 | 4:00 | 0d, 2h | Continuous | Maintenance |  |  | S | [8 empty] | 80 | N | 3C1F-012 |  | 2022-05-25
DB Netz AG | 3C1F-013 | Bremen - Hannover | <> | Seelze Mitte | Seelze West | 2023 | 2023 | 49 | 49 | 2023-12-10 | 1:30 | 2023-12-10 | 4:00 | 0d, 2h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 3C1F-013 |  | 2022-05-25
DB Netz AG | 3C1F-014 | Bremen - Hannover | <> | Wunstorf | Seelze West | 2023 | 2023 | 49 | 49 | 2023-12-10 | 1:30 | 2023-12-10 | 4:00 | 0d, 2h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 3C1F-014 |  | 2022-05-25
DB Netz AG | 3C1F-015 | Bremen - Hannover | < | Seelze West | Wunstorf | 2023 | 2023 | 49 | 49 | 2023-12-10 | 4:00 | 2023-12-10 | 5:00 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 3C1F-015 |  | 2022-05-25
DB Netz AG | 3C1F-016 | Bremen - Hannover | < | Gümmerwald | Wunstorf | 2023 | 2023 | 49 | 49 | 2023-12-10 | 4:00 | 2023-12-10 | 5:00 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 3C1F-016 |  | 2022-05-25
DB Netz AG | 3C1F-017 | Bremen - Hannover | <> | Wunstorf | Seelze West | 2023 | 2023 | 49 | 49 | 2023-12-10 | 4:00 | 2023-12-10 | 5:00 | 0d, 1h | Continuous | Maintenance |  |  | S | [8 empty] | 80 | N | 3C1F-017 |  | 2022-05-25
DB Netz AG | 3C1F-018 | Bremen - Hannover | <> | Wunstorf | Seelze West | 2023 | 2023 | 49 | 49 | 2023-12-10 | 4:00 | 2023-12-10 | 5:00 | 0d, 1h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 3C1F-018 |  | 2022-05-25
DB Netz AG | 3C1F-019 | Bremen - Hannover | <> | Wunstorf | Seelze West | 2023 | 2023 | 49 | 49 | 2023-12-10 | 4:00 | 2023-12-10 | 5:00 | 0d, 1h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 3C1F-019 |  | 2022-05-25
DB Netz AG | 3C1F-020 | Bremen - Hannover | <> | Wunstorf | Gümmerwald | 2023 | 2023 | 49 | 49 | 2023-12-10 | 5:00 | 2023-12-10 | 5:45 | 0d, 0h | Continuous | Maintenance | T | [10 empty] | 80 | N | 3C1F-020 |  | 2022-05-25
DB Netz AG | 3C1F-021 | Bremen - Hannover | < | Haste | Wunstorf | 2023 | 2023 | 49 | 49 | 2023-12-10 | 5:00 | 2023-12-10 | 5:45 | 0d, 0h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 3C1F-021 |  | 2022-05-25
DB Netz AG | 3C1F-022 | Bremen - Hannover | <> | Wunstorf | Seelze West | 2023 | 2023 | 49 | 49 | 2023-12-10 | 5:00 | 2023-12-10 | 5:45 | 0d, 0h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 3C1F-022 |  | 2022-05-25
DB Netz AG | 3C1F-024 | Bremen - Hannover | <> | Wunstorf | Gümmerwald | 2023 | 2023 | 49 | 49 | 2023-12-10 | 5:00 | 2023-12-10 | 5:45 | 0d, 0h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 3C1F-024 |  | 2022-05-25
DB Netz AG | 3CB0-001 | Bremen - Hannover | > | Wunstorf | Seelze West | 2023 | 2023 | 50 | 50 | 2023-12-11 | 0:10 | 2023-12-11 | 1:25 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 3CB0-001 |  | 2022-05-25
DB Netz AG | 3CB0-002 | Bremen - Hannover | < | Haste | Wunstorf | 2023 | 2023 | 50 | 50 | 2023-12-11 | 0:10 | 2023-12-11 | 1:25 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 3CB0-002 |  | 2022-05-25
DB Netz AG | 3CB0-003 | Bremen - Hannover | <> | Wunstorf | Wunstorf | 2023 | 2023 | 50 | 50 | 2023-12-11 | 0:10 | 2023-12-11 | 1:25 | 0d, 1h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 3CB0-003 |  | 2022-05-25
DB Netz AG | 3CB0-004 | Bremen - Hannover | <> | Wunstorf | Gümmerwald | 2023 | 2023 | 50 | 50 | 2023-12-11 | 0:10 | 2023-12-11 | 1:25 | 0d, 1h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 3CB0-004 |  | 2022-05-25
DB Netz AG | 3CB0-005 | Bremen - Hannover | > | Wunstorf | Seelze West | 2023 | 2023 | 50 | 50 | 2023-12-11 | 1:25 | 2023-12-11 | 3:40 | 0d, 2h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 3CB0-005 |  | 2022-05-25
DB Netz AG | 3CB0-006 | Bremen - Hannover | <> | Wunstorf | Seelze West | 2023 | 2023 | 50 | 50 | 2023-12-11 | 1:25 | 2023-12-11 | 3:40 | 0d, 2h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 3CB0-006 |  | 2022-05-25
DB Netz AG | 3CB0-007 | Bremen - Hannover | > | Seelze West | Ahlem | 2023 | 2023 | 50 | 50 | 2023-12-11 | 3:40 | 2023-12-11 | 5:40 | 0d, 2h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 3CB0-007 |  | 2022-05-25
DB Netz AG | 3CB0-008 | Bremen - Hannover | <> | Ahlem | Seelze West | 2023 | 2023 | 50 | 50 | 2023-12-11 | 3:40 | 2023-12-11 | 5:40 | 0d, 2h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 3CB0-008 |  | 2022-05-25
DB Netz AG | 3CB0-009 | Bremen - Hannover | > | Seelze West | Hannover-Linden | 2023 | 2023 | 50 | 50 | 2023-12-11 | 5:40 | 2023-12-11 | 7:10 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 3CB0-009 |  | 2022-05-25
DB Netz AG | 3CB0-010 | Bremen - Hannover | <> | Han-Linden Hafen | Empelde Abzw | 2023 | 2023 | 50 | 50 | 2023-12-11 | 5:40 | 2023-12-11 | 7:10 | 0d, 1h | Continuous | Maintenance | T | [10 empty] | 80 | N | 3CB0-010 |  | 2022-05-25
DB Netz AG | 3CB0-011 | Bremen - Hannover | <> | Hannover-Linden | Ahlem | 2023 | 2023 | 50 | 50 | 2023-12-11 | 5:40 | 2023-12-11 | 7:10 | 0d, 1h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 3CB0-011 |  | 2022-05-25
DB Netz AG | 3E90-001 | Hannover - Magdeburg | > | Lehrte | Hämelerwald | 2023 | 2023 | 50 | 50 | 2023-12-11 | 22:20 | 2023-12-12 | 0:05 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 3E90-001 |  | 2022-05-25
DB Netz AG | 3E90-002 | Hannover - Magdeburg | <> | Hämelerwald | Lehrte | 2023 | 2023 | 50 | 50 | 2023-12-11 | 22:20 | 2023-12-12 | 0:05 | 0d, 1h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 3E90-002 |  | 2022-05-25
DB Netz AG | 3E90-003 | Hannover - Magdeburg | > | Hämelerwald | Peine | 2023 | 2023 | 50 | 50 | 2023-12-12 | 0:05 | 2023-12-12 | 3:05 | 0d, 3h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 3E90-003 |  | 2022-05-25
DB Netz AG | 3E90-004 | Hannover - Magdeburg | <> | Peine | Hämelerwald | 2023 | 2023 | 50 | 50 | 2023-12-12 | 0:05 | 2023-12-12 | 3:05 | 0d, 3h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 3E90-004 |  | 2022-05-25
DB Netz AG | 3E90-005 | Hannover - Magdeburg | > | Hämelerwald | Vechelde | 2023 | 2023 | 50 | 50 | 2023-12-12 | 3:05 | 2023-12-12 | 4:05 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 3E90-005 |  | 2022-05-25
DB Netz AG | 3E90-006 | Hannover - Magdeburg | <> | Peine Gbf | Hämelerwald | 2023 | 2023 | 50 | 50 | 2023-12-12 | 3:05 | 2023-12-12 | 4:05 | 0d, 1h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 3E90-006 |  | 2022-05-25
DB Netz AG | 3E90-007 | Hannover - Magdeburg | > | Hämelerwald | Vechelde | 2023 | 2023 | 50 | 50 | 2023-12-12 | 4:05 | 2023-12-12 | 5:05 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 3E90-007 |  | 2022-05-25
DB Netz AG | 3E90-008 | Hannover - Magdeburg | <> | Vechelde | Peine Gbf | 2023 | 2023 | 50 | 50 | 2023-12-12 | 4:05 | 2023-12-12 | 5:05 | 0d, 1h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 3E90-008 |  | 2022-05-25
DB Netz AG | 3F5F-001 | Hannover - Magdeburg | < | Vechelde | Peine | 2023 | 2023 | 50 | 50 | 2023-12-12 | 22:40 | 2023-12-13 | 0:15 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 3F5F-001 |  | 2022-05-25
DB Netz AG | 3F5F-002 | Hannover - Magdeburg | <> | Peine | Vechelde | 2023 | 2023 | 50 | 50 | 2023-12-12 | 22:40 | 2023-12-13 | 0:15 | 0d, 1h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 3F5F-002 |  | 2022-05-25
DB Netz AG | 3F5F-003 | Hannover - Magdeburg | <> | Hämelerwald | Peine | 2023 | 2023 | 50 | 50 | 2023-12-13 | 0:15 | 2023-12-13 | 3:30 | 0d, 3h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 3F5F-003 |  | 2022-05-25
DB Netz AG | 3F5F-004 | Hannover - Magdeburg | < | Peine Gbf | Hämelerwald | 2023 | 2023 | 50 | 50 | 2023-12-13 | 0:15 | 2023-12-13 | 3:30 | 0d, 3h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 3F5F-004 |  | 2022-05-25
DB Netz AG | 3F5F-005 | Hannover - Magdeburg | < | Peine Gbf | Lehrte | 2023 | 2023 | 50 | 50 | 2023-12-13 | 3:30 | 2023-12-13 | 4:15 | 0d, 0h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 3F5F-005 |  | 2022-05-25
DB Netz AG | 3F5F-006 | Hannover - Magdeburg | <> | Ramhorst | Peine | 2023 | 2023 | 50 | 50 | 2023-12-13 | 3:30 | 2023-12-13 | 4:15 | 0d, 0h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 3F5F-006 |  | 2022-05-25
DB Netz AG | 3F5F-007 | Hannover - Magdeburg | < | Hämelerwald | Lehrte | 2023 | 2023 | 50 | 50 | 2023-12-13 | 4:15 | 2023-12-13 | 5:30 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 3F5F-007 |  | 2022-05-25
DB Netz AG | 3F5F-008 | Hannover - Magdeburg | <> | Lehrte | Hämelerwald | 2023 | 2023 | 50 | 50 | 2023-12-13 | 4:15 | 2023-12-13 | 5:30 | 0d, 1h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 3F5F-008 |  | 2022-05-25
DB Netz AG | 41.1 | Hannover - Magdeburg | > | Peine Gbf | Vechelde | 2023 | 2023 | 50 | 50 | 2023-12-14 | 22:10 | 2023-12-14 | 23:40 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 41.1 |  | 2022-05-17
DB Netz AG | 4.11 | Hannover - Magdeburg | <> | Vechelde | Peine Gbf | 2023 | 2023 | 50 | 50 | 2023-12-14 | 22:10 | 2023-12-14 | 23:40 | 0d, 1h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 4.11 |  | 2022-05-17
DB Netz AG | 0.411 | Hannover - Magdeburg | > | Peine Gbf | Groß Gleidingen | 2023 | 2023 | 50 | 50 | 2023-12-14 | 23:40 | 2023-12-15 | 2:05 | 0d, 2h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 0.411 |  | 2022-05-17
DB Netz AG | 0.0411 | Hannover - Magdeburg | <> | Groß Gleidingen | Peine Gbf | 2023 | 2023 | 50 | 50 | 2023-12-14 | 23:40 | 2023-12-15 | 2:05 | 0d, 2h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 0.0411 |  | 2022-05-17
DB Netz AG | 0.00411 | Hannover - Magdeburg | > | Vechelde | Groß Gleidingen | 2023 | 2023 | 50 | 50 | 2023-12-15 | 2:05 | 2023-12-15 | 3:35 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 0.00411 |  | 2022-05-17
DB Netz AG | 0.000411 | Hannover - Magdeburg | > | Groß Gleidingen | Gabelung (Brg) | 2023 | 2023 | 50 | 50 | 2023-12-15 | 2:05 | 2023-12-15 | 3:35 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 0.000411 |  | 2022-05-17
DB Netz AG | 4.11e-05 | Hannover - Magdeburg | <> | Groß Gleidingen | Bedding Nordkopf | 2023 | 2023 | 50 | 50 | 2023-12-15 | 2:05 | 2023-12-15 | 3:35 | 0d, 1h | Continuous | Maintenance | T | [10 empty] | 80 | N | 4.11e-05 |  | 2022-05-17
DB Netz AG | 4.11e-06 | Hannover - Magdeburg | <> | Gabelung (Brg) | Vechelde | 2023 | 2023 | 50 | 50 | 2023-12-15 | 2:05 | 2023-12-15 | 3:35 | 0d, 1h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 4.11e-06 |  | 2022-05-17
DB Netz AG | 4.11e-07 | Hannover - Magdeburg | <> | Gr Gleid Ostkopf | Gabelung (Brg) | 2023 | 2023 | 50 | 50 | 2023-12-15 | 2:05 | 2023-12-15 | 3:35 | 0d, 1h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 4.11e-07 |  | 2022-05-17
DB Netz AG | 4.11e-08 | Hannover - Magdeburg | > | Gr Gleid Ostkopf | Braunschweig Hbf | 2023 | 2023 | 50 | 50 | 2023-12-15 | 3:35 | 2023-12-15 | 4:50 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 4.11e-08 |  | 2022-05-17
DB Netz AG | 4.11e-09 | Hannover - Magdeburg | <> | Braunschweig Hbf | Braunschweig Hbf | 2023 | 2023 | 50 | 50 | 2023-12-15 | 3:35 | 2023-12-15 | 4:50 | 0d, 1h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 4.11e-09 |  | 2022-05-17
DB Netz AG | 4.11e-10 | Hannover - Magdeburg | > | Groß Gleidingen | Braunschweig Hbf | 2023 | 2023 | 50 | 50 | 2023-12-15 | 3:35 | 2023-12-15 | 4:50 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 4.11e-10 |  | 2022-05-17
DB Netz AG | 4.11e-11 | Hannover - Magdeburg | <> | Gr Gleid Ostkopf | Braunschweig Hbf | 2023 | 2023 | 50 | 50 | 2023-12-15 | 3:35 | 2023-12-15 | 4:50 | 0d, 1h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 4.11e-11 |  | 2022-05-17
DB Netz AG | 4.11e-12 | Hannover - Magdeburg | <> | Braunschweig Hbf | Braunschweig Hbf | 2023 | 2023 | 50 | 50 | 2023-12-15 | 3:35 | 2023-12-15 | 4:50 | 0d, 1h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 4.11e-12 |  | 2022-05-17
DB Netz AG | 4.11e-13 | Hannover - Magdeburg | <> | Gr Gleid Ostkopf | Okerbrücke | 2023 | 2023 | 50 | 50 | 2023-12-15 | 3:35 | 2023-12-15 | 4:50 | 0d, 1h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 4.11e-13 |  | 2022-05-17
DB Netz AG | 4.11e-14 | Hannover - Magdeburg | <> | Okerbrücke | Braunschweig Hbf | 2023 | 2023 | 50 | 50 | 2023-12-15 | 3:35 | 2023-12-15 | 4:50 | 0d, 1h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 4.11e-14 |  | 2022-05-17
DB Netz AG | 4126-001 | Hannover - Magdeburg | < | Braunschweig Hbf | Gabelung (Brg) | 2023 | 2023 | 50 | 50 | 2023-12-15 | 23:25 | 2023-12-16 | 0:25 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 4126-001 |  | 2022-05-17
DB Netz AG | 4126-002 | Hannover - Magdeburg | <> | Braunschweig Hbf | Braunschweig Hbf | 2023 | 2023 | 50 | 50 | 2023-12-15 | 23:25 | 2023-12-16 | 0:25 | 0d, 1h | Continuous | Maintenance |  | ST | [9 empty] | 80 | N | 4126-002 |  | 2022-05-17
DB Netz AG | 4126-003 | Hannover - Magdeburg | <> | Braunschweig Hbf | Gabelung (Brg) | 2023 | 2023 | 50 | 50 | 2023-12-15 | 23:25 | 2023-12-16 | 0:25 | 0d, 1h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 4126-003 |  | 2022-05-17
DB Netz AG | 4126-004 | Hannover - Magdeburg | <> | Braunschweig Hbf | Braunschweig Hbf | 2023 | 2023 | 50 | 50 | 2023-12-15 | 23:25 | 2023-12-16 | 0:25 | 0d, 1h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 4126-004 |  | 2022-05-17
DB Netz AG | 4126-005 | Hannover - Magdeburg | < | Braunschweig Hbf | Groß Gleidingen | 2023 | 2023 | 50 | 50 | 2023-12-16 | 0:25 | 2023-12-16 | 1:50 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 4126-005 |  | 2022-05-17
DB Netz AG | 4126-006 | Hannover - Magdeburg | <> | Groß Gleidingen | Braunschweig Hbf | 2023 | 2023 | 50 | 50 | 2023-12-16 | 0:25 | 2023-12-16 | 1:50 | 0d, 1h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 4126-006 |  | 2022-05-17
DB Netz AG | 4126-007 | Hannover - Magdeburg | < | Gr Gleid Ostkopf | Vechelde | 2023 | 2023 | 50 | 50 | 2023-12-16 | 1:50 | 2023-12-16 | 4:20 | 0d, 2h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 4126-007 |  | 2022-05-17
DB Netz AG | 4126-008 | Hannover - Magdeburg | <> | Vechelde | Gr Gleid Ostkopf | 2023 | 2023 | 50 | 50 | 2023-12-16 | 1:50 | 2023-12-16 | 4:20 | 0d, 2h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 4126-008 |  | 2022-05-17
DB Netz AG | 4126-009 | Hannover - Magdeburg | < | Groß Gleidingen | Peine Gbf | 2023 | 2023 | 50 | 50 | 2023-12-16 | 4:20 | 2023-12-16 | 6:20 | 0d, 2h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 4126-009 |  | 2022-05-17
DB Netz AG | 4126-010 | Hannover - Magdeburg | <> | Peine Gbf | Vechelde | 2023 | 2023 | 50 | 50 | 2023-12-16 | 4:20 | 2023-12-16 | 6:20 | 0d, 2h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 4126-010 |  | 2022-05-17
DB Netz AG | 4134-001 | Hannover - Magdeburg | < | Ramhorst | Lehrte | 2023 | 2023 | 50 | 50 | 2023-12-16 | 23:15 | 2023-12-17 | 0:30 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 4134-001 |  | 2022-05-25
DB Netz AG | 4134-002 | Hannover - Magdeburg | > | Immensen-Arpke | Lehrte | 2023 | 2023 | 50 | 50 | 2023-12-16 | 23:15 | 2023-12-17 | 0:30 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 4134-002 |  | 2022-05-25
DB Netz AG | 4134-003 | Hannover - Magdeburg | <> | Lehrte | Ramhorst | 2023 | 2023 | 50 | 50 | 2023-12-16 | 23:15 | 2023-12-17 | 0:30 | 0d, 1h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 4134-003 |  | 2022-05-25
DB Netz AG | 4134-004 | Hannover - Magdeburg | <> | Lehrte | Lehrte | 2023 | 2023 | 50 | 50 | 2023-12-16 | 23:15 | 2023-12-17 | 0:30 | 0d, 1h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 4134-004 |  | 2022-05-25
DB Netz AG | 4134-005 | Hannover - Magdeburg | <> | Lehrte | Lehrte | 2023 | 2023 | 50 | 50 | 2023-12-16 | 23:15 | 2023-12-17 | 0:30 | 0d, 1h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 4134-005 |  | 2022-05-25
DB Netz AG | 4134-006 | Hannover - Magdeburg | <> | Han K-Wiechert-A | Lehrte | 2023 | 2023 | 50 | 50 | 2023-12-17 | 0:30 | 2023-12-17 | 4:00 | 0d, 3h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 4134-006 |  | 2022-05-25
DB Netz AG | 4134-007 | Hannover - Magdeburg | <> | Lehrte West | Lehrte West | 2023 | 2023 | 50 | 50 | 2023-12-17 | 0:30 | 2023-12-17 | 4:00 | 0d, 3h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 4134-007 |  | 2022-05-25
DB Netz AG | 4134-008 | Hannover - Magdeburg | <> | Lehrte West | Lehrte West | 2023 | 2023 | 50 | 50 | 2023-12-17 | 0:30 | 2023-12-17 | 4:00 | 0d, 3h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 4134-008 |  | 2022-05-25
DB Netz AG | 4134-009 | Hannover - Magdeburg | <> | Lehrte West | Lehrte | 2023 | 2023 | 50 | 50 | 2023-12-17 | 0:30 | 2023-12-17 | 4:00 | 0d, 3h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 4134-009 |  | 2022-05-25
DB Netz AG | 4134-010 | Hannover - Magdeburg | < | Lehrte | Hannover Hbf | 2023 | 2023 | 50 | 50 | 2023-12-17 | 0:30 | 2023-12-17 | 4:00 | 0d, 3h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 4134-010 |  | 2022-05-25
DB Netz AG | 4134-011 | Hannover - Magdeburg | <> | Hannover Hbf | Lehrte West | 2023 | 2023 | 50 | 50 | 2023-12-17 | 4:00 | 2023-12-17 | 4:55 | 0d, 0h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 4134-011 |  | 2022-05-25
DB Netz AG | 4134-013 | Hannover - Magdeburg | < | Lehrte West | Hannover Hbf | 2023 | 2023 | 50 | 50 | 2023-12-17 | 4:00 | 2023-12-17 | 4:55 | 0d, 0h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 4134-013 |  | 2022-05-25
DB Netz AG | 4180-007 | Hannover - Magdeburg | > | Hildesheim Hbf | Groß Gleidingen | 2023 | 2023 | 51 | 51 | 2023-12-18 | 5:00 | 2023-12-18 | 5:50 | 0d, 0h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 4180-007 |  | 2022-05-25
DB Netz AG | 4187-001 | Hannover - Magdeburg | > | Hoheneggelsen | Groß Gleidingen | 2023 | 2023 | 51 | 51 | 2023-12-18 | 22:00 | 2023-12-19 | 1:35 | 0d, 3h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 4187-001 |  | 2022-05-25
DB Netz AG | 4187-002 | Hannover - Magdeburg | <> | Groß Gleidingen | Hoheneggelsen | 2023 | 2023 | 51 | 51 | 2023-12-18 | 22:00 | 2023-12-19 | 1:35 | 0d, 3h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 4187-002 |  | 2022-05-25
DB Netz AG | 4187-003 | Hannover - Magdeburg | <> | Groß Gleidingen | Hoheneggelsen | 2023 | 2023 | 51 | 51 | 2023-12-19 | 1:35 | 2023-12-19 | 2:35 | 0d, 1h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 4187-003 |  | 2022-05-25
DB Netz AG | 4187-004 | Hannover - Magdeburg | > | Hoheneggelsen | Groß Gleidingen | 2023 | 2023 | 51 | 51 | 2023-12-19 | 1:35 | 2023-12-19 | 2:35 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 4187-004 |  | 2022-05-25
DB Netz AG | 4187-005 | Hannover - Magdeburg | <> | Bedding Nordkopf | Groß Gleidingen | 2023 | 2023 | 51 | 51 | 2023-12-19 | 1:35 | 2023-12-19 | 2:35 | 0d, 1h | Continuous | Maintenance | T | [10 empty] | 80 | N | 4187-005 |  | 2022-05-25
DB Netz AG | 4187-006 | Hannover - Magdeburg | < | Groß Gleidingen | Hoheneggelsen | 2023 | 2023 | 51 | 51 | 2023-12-19 | 2:35 | 2023-12-19 | 4:35 | 0d, 2h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 4187-006 |  | 2022-05-25
DB Netz AG | 4187-007 | Hannover - Magdeburg | <> | Hoheneggelsen | Groß Gleidingen | 2023 | 2023 | 51 | 51 | 2023-12-19 | 2:35 | 2023-12-19 | 4:35 | 0d, 2h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 4187-007 |  | 2022-05-25
DB Netz AG | 4187-008 | Hannover - Magdeburg | < | Groß Gleidingen | Hildesheim Hbf | 2023 | 2023 | 51 | 51 | 2023-12-19 | 4:35 | 2023-12-19 | 5:35 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 4187-008 |  | 2022-05-25
DB Netz AG | 4187-009 | Hannover - Magdeburg | <> | Hoheneggelsen | Groß Gleidingen | 2023 | 2023 | 51 | 51 | 2023-12-19 | 4:35 | 2023-12-19 | 5:35 | 0d, 1h | Continuous | Maintenance |  |  |  | P | [7 empty] | 80 | N | 4187-009 |  | 2022-05-25
DB Netz AG | 41AA-001 | Hannover - Magdeburg | < | Groß Gleidingen | Hildesheim Hbf | 2023 | 2023 | 51 | 51 | 2023-12-19 | 23:05 | 2023-12-20 | 0:05 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 41AA-001 |  | 2022-05-25
DB Netz AG | 41DF-009 | Hannover - Magdeburg | <> | Hannover-Wülfel | Waldheim | 2023 | 2023 | 51 | 51 | 2023-12-23 | 2:00 | 2023-12-23 | 3:45 | 0d, 1h | Continuous | Maintenance | T | [10 empty] | 80 | N | 41DF-009 |  | 2022-05-19
DB Netz AG | 41DF-011 | Hannover - Magdeburg | < | Hannover-Wülfel | Waldhausen | 2023 | 2023 | 51 | 51 | 2023-12-23 | 2:00 | 2023-12-23 | 3:45 | 0d, 1h | Continuous | Maintenance |  | LT | [9 empty] | 80 | N | 41DF-011 |  | 2022-05-19
SZCZ | V-026819/20 | Praha-Libeň - Česká Třebová | < > | Ústí nad Orlicí | Ústí nad Orlicí | 2023 | 2023 | 15 | 20 | 2023-04-12 | 0:00 | 2023-05-16 | 0:00 | 35 days | Continuous | Track & Rail |  | ST | [5 empty] | , X, X |  |  | záhlaví 2. TK směr Bezpráví |  |  |  |  | 2022-12-15
SZCZ | V-026819/20 | Praha-Libeň - Česká Třebová | < > | Odb Bezpráví | Odb Bezpráví | 2023 | 2023 | 15 | 20 | 2023-04-12 | 0:00 | 2023-05-16 | 0:00 | 35 days | Continuous | Track & Rail |  | ST | [5 empty] | , X, X |  |  | záhlaví 2. TK směr Ústí nad Orlicí od náv. 2L po LIS v km 261,265 |  |  |  |  | 2022-12-15
SZCZ | V-026818/20 | Praha-Libeň - Česká Třebová | < > | Brandýs nad Orlicí | Odb Bezpráví | 2023 | 2023 | 10 | 15 | 2023-03-08 | 0:00 | 2023-04-11 | 0:00 | 35 days | Continuous | Track & Rail |  | LT | [8 empty] | 1 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-026818/20 | Praha-Libeň - Česká Třebová | < > | Brandýs nad Orlicí | Brandýs nad Orlicí | 2023 | 2023 | 10 | 15 | 2023-03-08 | 0:00 | 2023-04-11 | 0:00 | 35 days | Continuous | Track & Rail |  | ST | [8 empty] | záhlaví 1. TK směr Bezpráví |  |  |  |  | 2022-12-15
SZCZ | V-026818/20 | Praha-Libeň - Česká Třebová | < > | Odb Bezpráví | Odb Bezpráví | 2023 | 2023 | 10 | 15 | 2023-03-08 | 0:00 | 2023-04-11 | 0:00 | 35 days | Continuous | Track & Rail |  | ST | [8 empty] | záhlaví 1. TK směr Brandýs nad Orlicí |  |  |  |  | 2022-12-15
SZCZ | V-026816/20 | Praha-Libeň - Česká Třebová | < > | Odb Bezpráví | Ústí nad Orlicí | 2023 | 2023 | 5 | 10 | 2023-02-01 | 0:00 | 2023-03-07 | 0:00 | 35 days | Continuous | Track & Rail |  | LT | [5 empty] | , X, X |  |  | 1 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-026816/20 | Praha-Libeň - Česká Třebová | < > | Odb Bezpráví | Odb Bezpráví | 2023 | 2023 | 5 | 10 | 2023-02-01 | 0:00 | 2023-03-07 | 0:00 | 35 days | Continuous | Track & Rail |  | ST | [5 empty] | , X, X |  |  | záhlaví 1. TK směr Ústí nad Orlicí od LIS v km 260,734 po náv. 1L |  |  |  |  | 2022-12-15
SZCZ | V-026816/20 | Praha-Libeň - Česká Třebová | < > | Ústí nad Orlicí | Ústí nad Orlicí | 2023 | 2023 | 5 | 10 | 2023-02-01 | 0:00 | 2023-03-07 | 0:00 | 35 days | Continuous | Track & Rail |  | ST | [5 empty] | , X, X |  |  | záhlaví 1. TK směr Bezpráví |  |  |  |  | 2022-12-15
SZCZ | V-025434/18 | Břeclav - Kúty | < > | Lanžhot | Lanžhot st.hr. | 2023 | 2023 | 26 | 52 | 2023-06-30 | 0:00 | 2023-12-31 | 0:00 | 185 days | Continuous | Miscellaneous |  | LT | [8 empty] | 1 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-008605/22 | Praha-Libeň - Česká Třebová | < > | Choceň | Zámrsk | 2023 | 2023 | 17 | 17 | 2023-04-26 | 0:00 | 2023-04-26 | 0:00 | 2 x 4 hours | Periodical | Signal | T | LT | [5 empty] | , X, X |  |  | zab. zař. TZZ. |  |  |  |  | 2022-12-15
SZCZ | V-008607/22 | Praha-Libeň - Česká Třebová | < > | Uhersko | Moravany | 2023 | 2023 | 18 | 18 | 2023-05-03 | 0:00 | 2023-05-03 | 0:00 | 2 x 4 hours | Periodical | Signal | T | LT | [5 empty] | , X, X |  |  | zab. zař. TZZ. |  |  |  |  | 2022-12-15
SZCZ | V-008609/22 | Praha-Libeň - Česká Třebová | < > | Uhersko | Moravany | 2023 | 2023 | 19 | 19 | 2023-05-10 | 0:00 | 2023-05-10 | 0:00 | 2 x 4 hours | Periodical | Signal | T | LT | [5 empty] | , X, X |  |  | zab. zař. TZZ. |  |  |  |  | 2022-12-15
SZCZ | V-008610/22 | Praha-Libeň - Česká Třebová | < > | Moravany | Kostěnice | 2023 | 2023 | 20 | 20 | 2023-05-17 | 0:00 | 2023-05-17 | 0:00 | 2 x 4 hours | Periodical | Signal | T | LT | [5 empty] | , X, X |  |  | zab. zař. TZZ. |  |  |  |  | 2022-12-15
SZCZ | V-008604/22 | Praha-Libeň - Česká Třebová | < > | Choceň | Zámrsk | 2023 | 2023 | 17 | 17 | 2023-04-25 | 0:00 | 2023-04-25 | 0:00 | 2 x 1 hours | Periodical | Signal |  | LT | [5 empty] | , X, X |  |  | zab. zař. TZZ. |  |  |  |  | 2022-12-15
SZCZ | V-008606/22 | Praha-Libeň - Česká Třebová | < > | Zámrsk | Uhersko | 2023 | 2023 | 18 | 18 | 2023-05-02 | 0:00 | 2023-05-02 | 0:00 | 2 x 1 hours | Periodical | Signal |  | LT | [5 empty] | , X, X |  |  | zab. zař. TZZ. |  |  |  |  | 2022-12-15
SZCZ | V-008608/22 | Praha-Libeň - Česká Třebová | < > | Uhersko | Moravany | 2023 | 2023 | 19 | 19 | 2023-05-09 | 0:00 | 2023-05-09 | 0:00 | 2 x 1 hours | Periodical | Signal |  | LT | [5 empty] | , X, X |  |  | zab. zař. TZZ. |  |  |  |  | 2022-12-15
SZCZ | V-008611/22 | Praha-Libeň - Česká Třebová | < > | Moravany | Kostěnice | 2023 | 2023 | 20 | 20 | 2023-05-16 | 0:00 | 2023-05-16 | 0:00 | 2 x 1 hours | Periodical | Signal |  | LT | [5 empty] | , X, X |  |  | zab. zař. TZZ. |  |  |  |  | 2022-12-15
SZCZ | V-008604/22 | Praha-Libeň - Česká Třebová | < > | Zámrsk | Zámrsk | 2023 | 2023 | 17 | 17 | 2023-04-25 | 0:00 | 2023-04-25 | 0:00 | 1 x 1 hours | Periodical | Signal |  | ST | [5 empty] | , X, X |  |  | zab. zař. SZZ. |  |  |  |  | 2022-12-15
SZCZ | V-008606/22 | Praha-Libeň - Česká Třebová | < > | Uhersko | Uhersko | 2023 | 2023 | 18 | 18 | 2023-05-02 | 0:00 | 2023-05-02 | 0:00 | 1 x 1 hours | Periodical | Signal |  | ST | [5 empty] | , X, X |  |  | zab. zař. SZZ. |  |  |  |  | 2022-12-15
SZCZ | V-008608/22 | Praha-Libeň - Česká Třebová | < > | Moravany | Moravany | 2023 | 2023 | 19 | 19 | 2023-05-09 | 0:00 | 2023-05-09 | 0:00 | 1 x 1 hours | Periodical | Signal |  | ST | [5 empty] | , X, X |  |  | zab. zař. SZZ. |  |  |  |  | 2022-12-15
SZCZ | V-008611/22 | Praha-Libeň - Česká Třebová | < > | Kostěnice | Kostěnice | 2023 | 2023 | 20 | 20 | 2023-05-16 | 0:00 | 2023-05-16 | 0:00 | 1 x 1 hours | Periodical | Signal |  | ST | [5 empty] | , X, X |  |  | zab. zař. SZZ. |  |  |  |  | 2022-12-15
SZCZ | V-008605/22 | Praha-Libeň - Česká Třebová | < > | Zámrsk | Zámrsk | 2023 | 2023 | 17 | 17 | 2023-04-26 | 0:00 | 2023-04-26 | 0:00 | 1 x 4 hours | Periodical | Signal |  | ST | [5 empty] | , X, X |  |  | zab. zař. SZZ. |  |  |  |  | 2022-12-15
SZCZ | V-008607/22 | Praha-Libeň - Česká Třebová | < > | Uhersko | Uhersko | 2023 | 2023 | 18 | 18 | 2023-05-03 | 0:00 | 2023-05-03 | 0:00 | 1 x 4 hours | Periodical | Signal |  | ST | [5 empty] | , X, X |  |  | zab. zař. SZZ. |  |  |  |  | 2022-12-15
SZCZ | V-008609/22 | Praha-Libeň - Česká Třebová | < > | Moravany | Moravany | 2023 | 2023 | 19 | 19 | 2023-05-10 | 0:00 | 2023-05-10 | 0:00 | 1 x 4 hours | Periodical | Signal |  | ST | [5 empty] | , X, X |  |  | zab. zař. SZZ. |  |  |  |  | 2022-12-15
SZCZ | V-008610/22 | Praha-Libeň - Česká Třebová | < > | Kostěnice | Kostěnice | 2023 | 2023 | 20 | 20 | 2023-05-17 | 0:00 | 2023-05-17 | 0:00 | 1 x 4 hours | Periodical | Signal |  | ST | [5 empty] | , X, X |  |  | zab. zař. SZZ. |  |  |  |  | 2022-12-15
SZCZ | V-026820/20 | Praha-Libeň - Česká Třebová | < > | Odb Bezpráví | Brandýs nad Orlicí | 2023 | 2023 | 20 | 25 | 2023-05-17 | 0:00 | 2023-06-20 | 0:00 | 35 days | Continuous | Track & Rail |  | LT | [8 empty] | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-026820/20 | Praha-Libeň - Česká Třebová | < > | Odb Bezpráví | Odb Bezpráví | 2023 | 2023 | 20 | 25 | 2023-05-17 | 0:00 | 2023-06-20 | 0:00 | 35 days | Continuous | Track & Rail |  | ST | [8 empty] | záhlaví 2. TK směr Brandýs nad Orlicí |  |  |  |  | 2022-12-15
SZCZ | V-026820/20 | Praha-Libeň - Česká Třebová | < > | Brandýs nad Orlicí | Brandýs nad Orlicí | 2023 | 2023 | 20 | 25 | 2023-05-17 | 0:00 | 2023-06-20 | 0:00 | 35 days | Continuous | Track & Rail |  | ST | [8 empty] | záhlaví 2. TK směr Bezpráví |  |  |  |  | 2022-12-15
SZCZ | V-026819/20 | Praha-Libeň - Česká Třebová | < > | Ústí nad Orlicí | Odb Bezpráví | 2023 | 2023 | 15 | 20 | 2023-04-12 | 0:00 | 2023-05-16 | 0:00 | 35 days | Continuous | Track & Rail |  | LT | [5 empty] | , X, X |  |  | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007459/22 | Kolín - Brno-Maloměřice | < > | Přibyslav | Pohled | 2023 | 2023 | 44 | 46 | 2023-11-01 18:00 | 0:00 | 2023-11-13 06:00 | 0:00 | 12 x 7 hours | Periodical | Catenary | T | LT | [5 empty] | , X, X |  |  | 2,1 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-009451/21 | Praha-Libeň - Česká Třebová | < > | Brandýs nad Orlicí | Brandýs nad Orlicí | 2023 | 2023 | 21 | 21 | 2023-05-24 | 0:00 | 2023-05-26 | 0:00 | 3 days | Continuous | Miscellaneous |  | ST | [8 empty] | zhlaví 2. TK směr Bezpráví. |  |  |  |  | 2022-12-15
SZCZ | V-009448/21 | Praha-Libeň - Česká Třebová | < > | Odb Bezpráví | Odb Bezpráví | 2023 | 2023 | 24 | 25 | 2023-06-18 | 0:00 | 2023-06-20 | 0:00 | 3 x 12 hours | Periodical | Miscellaneous |  | ST | [5 empty] | , X, X |  |  | záhlaví 2. TK směr Ústí n. O. od náv 2L po náv. S2 |  |  |  |  | 2022-12-15
SZCZ | V-007456/22 | Kolín - Brno-Maloměřice | < > | Přibyslav | Pohled | 2023 | 2023 | 37 | 37 | 2023-09-15 18:00 | 0:00 | 2023-09-17 06:00 | 0:00 | 2 x 7 hours | Periodical | Bridge | T | LT | [5 empty] | , X, X |  |  | 2,1 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007458/22 | Kolín - Brno-Maloměřice | < > | Přibyslav | Pohled | 2023 | 2023 | 40 | 40 | 2023-10-05 18:00 | 0:00 | 2023-10-07 06:00 | 0:00 | 2 x 7 hours | Periodical | Bridge | T | LT | [5 empty] | , X, X |  |  | 2,1 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007397/22 | Kolín - Brno-Maloměřice | < > | Pohled | Přibyslav | 2023 | 2023 | 36 | 41 | 2023-09-08 | 0:00 | 2023-10-13 | 0:00 | 36 x 12 hours | Periodical | Miscellaneous |  | LT | [8 empty] | 1 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007433/22 | Kolín - Brno-Maloměřice | < > | Pohled | Přibyslav | 2023 | 2023 | 41 | 43 | 2023-10-15 | 0:00 | 2023-10-28 | 0:00 | 14 x 12 hours | Periodical | Miscellaneous |  | LT | [8 empty] | 1 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007447/22 | Kolín - Brno-Maloměřice | < > | Pohled | Přibyslav | 2023 | 2023 | 46 | 47 | 2023-11-14 | 0:00 | 2023-11-22 | 0:00 | 9 x 12 hours | Periodical | Miscellaneous |  | LT | [8 empty] | 1 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-009446/21 | Praha-Libeň - Česká Třebová | < > | Odb Bezpráví | Odb Bezpráví | 2023 | 2023 | 36 | 36 | 2023-09-04 18:00 | 0:00 | 2023-09-05 06:00 | 0:00 | 1 x 3 hours | Periodical | Miscellaneous |  | ST | [8 empty] | záhlaví 2. TK směr Ústí n. O. od náv. 2L po náv. S2 |  |  |  |  | 2022-12-15
SZCZ | V-009445/21 | Praha-Libeň - Česká Třebová | < > | Odb Bezpráví | Odb Bezpráví | 2023 | 2023 | 22 | 22 | 2023-05-29 | 0:00 | 2023-05-30 | 0:00 | 2 days | Continuous | Miscellaneous |  | ST | [5 empty] | , X, X |  |  | záhlaví 2. TK směr Ústí n. O. od náv 2L po náv. S2 |  |  |  |  | 2022-12-15
SZCZ | V-009444/21 | Praha-Libeň - Česká Třebová | < > | Odb Bezpráví | Odb Bezpráví | 2023 | 2023 | 20 | 20 | 2023-05-19 | 0:00 | 2023-05-20 | 0:00 | 2 days | Continuous | Miscellaneous |  | ST | [5 empty] | , X, X |  |  | záhlaví 2. TK směr Ústí n. O. od náv 2L po náv. S2 |  |  |  |  | 2022-12-15
SZCZ | V-009441/21 | Praha-Libeň - Česká Třebová | < > | Odb Bezpráví | Odb Bezpráví | 2023 | 2023 | 9 | 10 | 2023-03-05 | 0:00 | 2023-03-07 | 0:00 | 3 x 12 hours | Periodical | Miscellaneous |  | ST | [5 empty] | , X, X |  |  | záhlaví 1. TK směr Ústí n. O. od náv. S1 po LIS v km 260,734 |  |  |  |  | 2022-12-15
SZCZ | V-009440/21 | Praha-Libeň - Česká Třebová | < > | Odb Bezpráví | Odb Bezpráví | 2023 | 2023 | 8 | 8 | 2023-02-25 | 0:00 | 2023-02-25 | 0:00 | 1 x 12 hours | Periodical | Miscellaneous |  | ST | [5 empty] | , X, X |  |  | záhlaví 1. TK směr Ústí n. O. od náv. S1 po LIS v km 260,734 |  |  |  |  | 2022-12-15
SZCZ | V-009439/21 | Praha-Libeň - Česká Třebová | < > | Odb Bezpráví | Odb Bezpráví | 2023 | 2023 | 7 | 7 | 2023-02-13 | 0:00 | 2023-02-14 | 0:00 | 2 days | Continuous | Miscellaneous |  | ST | [5 empty] | , X, X |  |  | záhlaví 1. TK směr Ústí n. O. od náv. S1 po LIS v km 260,734 |  |  |  |  | 2022-12-15
SZCZ | V-009438/21 | Praha-Libeň - Česká Třebová | < > | Odb Bezpráví | Odb Bezpráví | 2023 | 2023 | 6 | 6 | 2023-02-08 | 0:00 | 2023-02-10 | 0:00 | 3 days | Continuous | Miscellaneous |  | ST | [5 empty] | , X, X |  |  | záhlaví 1. TK směr Ústí n. O. od náv. S1 po LIS v km 260,734 |  |  |  |  | 2022-12-15
SZCZ | V-009429/21 | Praha-Libeň - Česká Třebová | < > | Odb Bezpráví | Odb Bezpráví | 2023 | 2023 | 19 | 20 | 2023-05-14 | 0:00 | 2023-05-16 | 0:00 | 3 x 12 hours | Periodical | Miscellaneous |  | ST | [5 empty] | , X, X |  |  | záhlaví 2. TK směr Ústí nad Orlicí od LIS v km 261,265 po náv. S2 |  |  |  |  | 2022-12-15
SZCZ | V-009427/21 | Praha-Libeň - Česká Třebová | < > | Odb Bezpráví | Odb Bezpráví | 2023 | 2023 | 37 | 37 | 2023-09-11 18:00 | 0:00 | 2023-09-12 06:00 | 0:00 | 1 x 3 hours | Periodical | Miscellaneous |  | ST | [8 empty] | záhlaví 1. TK směr Ústí n. O. |  |  |  |  | 2022-12-15
SZCZ | V-009425/21 | Praha-Libeň - Česká Třebová | < > | Odb Bezpráví | Odb Bezpráví | 2023 | 2023 | 16 | 16 | 2023-04-20 | 0:00 | 2023-04-21 | 0:00 | 2 days | Continuous | Miscellaneous |  | ST | [5 empty] | , X, X |  |  | záhlaví 2. TK směr Ústí nad Orlicí od LIS v km 261,265 po náv. S2 |  |  |  |  | 2022-12-15
SZCZ | V-007402/21 | Brno - Břeclav | < > | Brno-Maloměřice stavědlo 3 | Brno-Židenice | 2023 | 2023 | 26 | 30 | 2023-07-01 | 0:00 | 2023-07-30 | 0:00 | 30 days | Continuous | Track & Rail |  | LT | [8 empty] | 1K + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007401/21 | Brno - Břeclav | < > | Brno-Židenice | Brno-Maloměřice stavědlo 3 | 2023 | 2023 | 31 | 35 | 2023-07-31 | 0:00 | 2023-08-30 | 0:00 | 31 days | Continuous | Track & Rail |  | LT | [8 empty] | 2K + TV. |  |  |  |  | 2022-12-15
SZCZ | V-009422/21 | Praha-Libeň - Česká Třebová | < > | Ústí nad Orlicí | Ústí nad Orlicí | 2023 | 2023 | 19 | 19 | 2023-05-08 | 0:00 | 2023-05-10 | 0:00 | 3 x 12 hours | Periodical | Miscellaneous |  | ST | [8 empty] | zhlaví SK 2 směr Bezpráví. |  |  |  |  | 2022-12-15
SZCZ | V-007382/22 | Kolín - Brno-Maloměřice | < > | Přibyslav | Pohled | 2023 | 2023 | 28 | 28 | 2023-07-12 | 0:00 | 2023-07-15 | 0:00 | 4 x 12 hours | Periodical | Miscellaneous |  | LT | [8 empty] | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007386/22 | Kolín - Brno-Maloměřice | < > | Přibyslav | Pohled | 2023 | 2023 | 35 | 36 | 2023-09-01 | 0:00 | 2023-09-07 | 0:00 | 7 x 12 hours | Periodical | Miscellaneous |  | LT | [8 empty] | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007393/22 | Kolín - Brno-Maloměřice | < > | Přibyslav | Pohled | 2023 | 2023 | 41 | 41 | 2023-10-14 | 0:00 | 2023-10-14 | 0:00 | 1 x 12 hours | Periodical | Miscellaneous |  | LT | [8 empty] | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007394/22 | Kolín - Brno-Maloměřice | < > | Přibyslav | Pohled | 2023 | 2023 | 43 | 44 | 2023-10-29 | 0:00 | 2023-10-31 | 0:00 | 3 x 12 hours | Periodical | Miscellaneous |  | LT | [8 empty] | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-009419/21 | Praha-Libeň - Česká Třebová | < > | Ústí nad Orlicí | Ústí nad Orlicí | 2023 | 2023 | 17 | 17 | 2023-04-26 | 0:00 | 2023-04-27 | 0:00 | 2 days | Continuous | Miscellaneous |  | ST | [8 empty] | zhlaví SK 2 směr Bezpráví. |  |  |  |  | 2022-12-15
SZCZ | V-009414/21 | Praha-Libeň - Česká Třebová | < > | Ústí nad Orlicí | Ústí nad Orlicí | 2023 | 2023 | 15 | 15 | 2023-04-14 | 0:00 | 2023-04-15 | 0:00 | 2 days | Continuous | Miscellaneous |  | ST | [8 empty] | zhlaví SK 2 směr Bezpráví. |  |  |  |  | 2022-12-15
SZCZ | V-009261/22 | Kolín - Brno-Maloměřice | < > | Brno-Královo Pole | Brno-Maloměřice stavědlo 3 | 2023 | 2023 | 30 | 31 | 2023-07-30 18:00 | 0:00 | 2023-07-31 06:00 | 0:00 | 1 x 8 hours | Periodical | Others | T | LT | [5 empty] | , X, X |  |  | 1.,2. bez TV. |  |  |  |  | 2022-12-15
SZCZ | V-009262/22 | Kolín - Brno-Maloměřice | < > | Brno-Královo Pole | Brno-Maloměřice stavědlo 3 | 2023 | 2023 | 33 | 34 | 2023-08-20 18:00 | 0:00 | 2023-08-21 06:00 | 0:00 | 1 x 8 hours | Periodical | Others | T | LT | [5 empty] | , X, X |  |  | 1.,2. bez TV. |  |  |  |  | 2022-12-15
SZCZ | V-009263/22 | Kolín - Brno-Maloměřice | < > | Brno-Královo Pole | Brno-Maloměřice stavědlo 3 | 2023 | 2023 | 42 | 43 | 2023-10-22 18:00 | 0:00 | 2023-10-23 06:00 | 0:00 | 1 x 8 hours | Periodical | Others | T | LT | [5 empty] | , X, X |  |  | 1.,2. bez TV. |  |  |  |  | 2022-12-15
SZCZ | V-007381/22 | Kolín - Brno-Maloměřice | < > | Přibyslav | Pohled | 2023 | 2023 | 27 | 28 | 2023-07-05 | 0:00 | 2023-07-10 | 0:00 | 6 days | Continuous | Bridge | T | LT | [5 empty] | , X, X |  |  | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-022947/21 | Kolín - Brno-Maloměřice | < > | Brno-Královo Pole | Kuřim | 2023 | 2023 | 22 | 22 | 2023-06-03 18:00 | 0:00 | 2023-06-04 06:00 | 0:00 | 1 x 10 hours | Periodical | Catenary |  | LT | [8 empty] | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-009260/22 | Kolín - Brno-Maloměřice | < > | Brno-Maloměřice stavědlo 3 | Brno-Královo Pole | 2023 | 2023 | 28 | 28 | 2023-07-15 18:00 | 0:00 | 2023-07-16 06:00 | 0:00 | 1 x 5 hours | Periodical | Catenary |  | LT | [8 empty] | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-009259/22 | Kolín - Brno-Maloměřice | < > | Brno-Maloměřice stavědlo 3 | Brno-Královo Pole | 2023 | 2023 | 27 | 27 | 2023-07-08 18:00 | 0:00 | 2023-07-09 06:00 | 0:00 | 1 x 5 hours | Periodical | Catenary |  | LT |  |  | X | [5 empty] | 1. jen TV, 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-009258/22 | Kolín - Brno-Maloměřice | < > | Brno-Královo Pole | Brno-Maloměřice stavědlo 3 | 2023 | 2023 | 27 | 27 | 2023-07-05 18:00 | 0:00 | 2023-07-06 06:00 | 0:00 | 1 x 8 hours | Periodical | Catenary |  | LT | [8 empty] | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007380/22 | Kolín - Brno-Maloměřice | < > | Pohled | Přibyslav | 2023 | 2023 | 27 | 28 | 2023-07-03 | 0:00 | 2023-07-11 | 0:00 | 9 days | Continuous | Miscellaneous |  | LT | [8 empty] | 1 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007379/22 | Kolín - Brno-Maloměřice | < > | Přibyslav | Pohled | 2023 | 2023 | 26 | 26 | 2023-07-01 | 0:00 | 2023-07-02 | 0:00 | 2 days | Continuous | Bridge |  | LT | [8 empty] | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007376/22 | Kolín - Brno-Maloměřice | < > | Přibyslav | Pohled | 2023 | 2023 | 26 | 26 | 2023-07-01 | 0:00 | 2023-07-01 | 0:00 | 1 x 12 hours | Periodical | Catenary |  | LT | [8 empty] | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007378/22 | Kolín - Brno-Maloměřice | < > | Přibyslav | Pohled | 2023 | 2023 | 48 | 48 | 2023-11-30 | 0:00 | 2023-11-30 | 0:00 | 1 x 12 hours | Periodical | Catenary |  | LT | [8 empty] | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007377/22 | Kolín - Brno-Maloměřice | < > | Přibyslav | Přibyslav | 2023 | 2023 | 28 | 35 | 2023-07-16 | 0:00 | 2023-08-31 | 0:00 | 47 days | Continuous | Miscellaneous |  | ST | [8 empty] | záhlaví 2. TK směr Pohled |  |  |  |  | 2022-12-15
SZCZ | V-007377/22 | Kolín - Brno-Maloměřice | < > | Přibyslav | Pohled | 2023 | 2023 | 28 | 35 | 2023-07-16 | 0:00 | 2023-08-31 | 0:00 | 47 days | Continuous | Miscellaneous |  | LT | [8 empty] | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007372/22 | Kolín - Brno-Maloměřice | < > | Pohled | Přibyslav | 2023 | 2023 | 7 | 7 | 2023-02-18 | 0:00 | 2023-02-18 | 0:00 | 1 x 10 hours | Periodical | Miscellaneous |  | LT | [8 empty] | 1 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007373/22 | Kolín - Brno-Maloměřice | < > | Pohled | Přibyslav | 2023 | 2023 | 8 | 8 | 2023-02-25 | 0:00 | 2023-02-26 | 0:00 | 2 x 10 hours | Periodical | Miscellaneous |  | LT | [8 empty] | 1 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007375/22 | Kolín - Brno-Maloměřice | < > | Pohled | Přibyslav | 2023 | 2023 | 10 | 10 | 2023-03-12 | 0:00 | 2023-03-12 | 0:00 | 1 x 10 hours | Periodical | Miscellaneous |  | LT | [8 empty] | 1 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007362/22 | Kolín - Brno-Maloměřice | < > | Přibyslav | Pohled | 2023 | 2023 | 4 | 4 | 2023-01-28 | 0:00 | 2023-01-29 | 0:00 | 2 x 10 hours | Periodical | Miscellaneous |  | LT | [8 empty] | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007364/22 | Kolín - Brno-Maloměřice | < > | Přibyslav | Pohled | 2023 | 2023 | 5 | 5 | 2023-02-04 | 0:00 | 2023-02-05 | 0:00 | 2 x 10 hours | Periodical | Miscellaneous |  | LT | [8 empty] | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007366/22 | Kolín - Brno-Maloměřice | < > | Přibyslav | Pohled | 2023 | 2023 | 6 | 6 | 2023-02-11 | 0:00 | 2023-02-12 | 0:00 | 2 x 10 hours | Periodical | Miscellaneous |  | LT | [8 empty] | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007368/22 | Kolín - Brno-Maloměřice | < > | Přibyslav | Pohled | 2023 | 2023 | 7 | 7 | 2023-02-19 | 0:00 | 2023-02-19 | 0:00 | 1 x 10 hours | Periodical | Miscellaneous |  | LT | [8 empty] | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007369/22 | Kolín - Brno-Maloměřice | < > | Přibyslav | Pohled | 2023 | 2023 | 9 | 9 | 2023-03-04 | 0:00 | 2023-03-05 | 0:00 | 2 x 10 hours | Periodical | Miscellaneous |  | LT | [8 empty] | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007371/22 | Kolín - Brno-Maloměřice | < > | Přibyslav | Pohled | 2023 | 2023 | 10 | 10 | 2023-03-11 | 0:00 | 2023-03-11 | 0:00 | 1 x 10 hours | Periodical | Miscellaneous |  | LT | [8 empty] | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-022941/21 | Kolín - Brno-Maloměřice | < > | Brno-Královo Pole | Kuřim | 2023 | 2023 | 18 | 19 | 2023-05-05 18:00 | 0:00 | 2023-05-10 06:00 | 0:00 | 5 x 8 hours | Periodical | Catenary |  | LT | [8 empty] | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-022946/21 | Kolín - Brno-Maloměřice | < > | Brno-Královo Pole | Kuřim | 2023 | 2023 | 19 | 19 | 2023-05-12 18:00 | 0:00 | 2023-05-13 06:00 | 0:00 | 1 x 8 hours | Periodical | Catenary |  | LT | [8 empty] | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-022939/21 | Kolín - Brno-Maloměřice | < > | Kuřim | Brno-Královo Pole | 2023 | 2023 | 20 | 20 | 2023-05-20 18:00 | 0:00 | 2023-05-21 06:00 | 0:00 | 1 x 10 hours | Periodical | Catenary |  | LT | [8 empty] | 1 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-022931/21 | Kolín - Brno-Maloměřice | < > | Kuřim | Brno-Královo Pole | 2023 | 2023 | 13 | 14 | 2023-03-29 18:00 | 0:00 | 2023-04-03 06:00 | 0:00 | 5 x 8 hours | Periodical | Catenary |  | LT | [8 empty] | 1 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-022936/21 | Kolín - Brno-Maloměřice | < > | Kuřim | Brno-Královo Pole | 2023 | 2023 | 14 | 14 | 2023-04-07 18:00 | 0:00 | 2023-04-09 06:00 | 0:00 | 2 x 8 hours | Periodical | Catenary |  | LT | [8 empty] | 1 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-022881/20 | Děčín - Praha-Libeň | < > | Praha-Bubeneč | Praha-Bubeneč | 2023 | 2023 | 28 | 29 | 2023-07-15 | 0:00 | 2023-07-21 | 0:00 | 7 days | Continuous | Track & Rail |  | ST | [8 empty] | záhlaví roztocké navazující na 2.TK Praha Bubeneč - Roztoky u Prahy |  |  |  |  | 2022-12-15
SZCZ | V-022881/20 | Děčín - Praha-Libeň | < > | Praha-Bubeneč | Roztoky u Prahy | 2023 | 2023 | 28 | 29 | 2023-07-15 | 0:00 | 2023-07-21 | 0:00 | 7 days | Continuous | Track & Rail |  | LT | [8 empty] | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-022881/20 | Děčín - Praha-Libeň | < > | Roztoky u Prahy | Roztoky u Prahy | 2023 | 2023 | 28 | 29 | 2023-07-15 | 0:00 | 2023-07-21 | 0:00 | 7 days | Continuous | Track & Rail |  | ST | [8 empty] | záhlaví bubenečské navazující na 2.TK Praha Bubeneč - Roztoky u Prahy |  |  |  |  | 2022-12-15
SZCZ | V-007361/22 | Kolín - Brno-Maloměřice | < > | Přibyslav | Přibyslav | 2023 | 2023 | 47 | 47 | 2023-11-23 | 0:00 | 2023-11-26 | 0:00 | 4 days | Continuous | Track & Rail |  | ST | [5 empty] | , X, X |  |  | sudá + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007361/22 | Kolín - Brno-Maloměřice | < > | Přibyslav | Pohled | 2023 | 2023 | 47 | 47 | 2023-11-23 | 0:00 | 2023-11-26 | 0:00 | 4 days | Continuous | Track & Rail | T | LT | [5 empty] | , X, X |  |  | 2,1 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-022879/20 | Děčín - Praha-Libeň | < > | Roztoky u Prahy | Roztoky u Prahy | 2023 | 2023 | 29 | 30 | 2023-07-22 | 0:00 | 2023-07-28 | 0:00 | 7 days | Continuous | Track & Rail |  | ST | [8 empty] | záhlaví bubenečské navazující na 1.TK Roztoky u Prahy - Praha Bubeneč |  |  |  |  | 2022-12-15
SZCZ | V-022879/20 | Děčín - Praha-Libeň | < > | Roztoky u Prahy | Praha-Bubeneč | 2023 | 2023 | 29 | 30 | 2023-07-22 | 0:00 | 2023-07-28 | 0:00 | 7 days | Continuous | Track & Rail |  | LT | [8 empty] | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-022879/20 | Děčín - Praha-Libeň | < > | Praha-Bubeneč | Praha-Bubeneč | 2023 | 2023 | 29 | 30 | 2023-07-22 | 0:00 | 2023-07-28 | 0:00 | 7 days | Continuous | Track & Rail |  | ST | [8 empty] | záhlaví roztocké navazující na 1.TK Roztoky u Prahy - Praha Bubeneč |  |  |  |  | 2022-12-15
SZCZ | V-022878/20 | Děčín - Praha-Libeň | < > | Kralupy nad Vltavou | Kralupy nad Vltavou | 2023 | 2023 | 28 | 28 | 2023-07-10 | 0:00 | 2023-07-14 | 0:00 | 5 days | Continuous | Track & Rail |  | ST | [8 empty] | záhlaví libčické navazující na 1.TK Kralupy nad Vltavou - Libčice nad Vltavou |  |  |  |  | 2022-12-15
SZCZ | V-022878/20 | Děčín - Praha-Libeň | < > | Kralupy nad Vltavou | Libčice nad Vltavou | 2023 | 2023 | 28 | 28 | 2023-07-10 | 0:00 | 2023-07-14 | 0:00 | 5 days | Continuous | Track & Rail |  | LT | [8 empty] | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-022878/20 | Děčín - Praha-Libeň | < > | Libčice nad Vltavou | Libčice nad Vltavou | 2023 | 2023 | 28 | 28 | 2023-07-10 | 0:00 | 2023-07-14 | 0:00 | 5 days | Continuous | Track & Rail |  | ST | [8 empty] | záhlaví kralupské navazující na 1.TK Kralupy nad Vltavou - Libčice nad Vltavou |  |  |  |  | 2022-12-15
SZCZ | V-007310/22 | Kolín - Brno-Maloměřice | < > | Přibyslav | Přibyslav | 2023 | 2023 | 26 | 48 | 2023-07-02 | 0:00 | 2023-11-29 | 0:00 | 151 days | Continuous | Bridge |  | ST | [8 empty] | zhlaví 2. TK směr Pohled, jeho část mezi výh. č. 14 a výh. č. 17. |  |  |  |  | 2022-12-15
SZCZ | V-007309/22 | Kolín - Brno-Maloměřice | < > | Přibyslav | Přibyslav | 2023 | 2023 | 27 | 28 | 2023-07-05 | 0:00 | 2023-07-10 | 0:00 | 6 days | Continuous | Bridge |  | ST | [5 empty] | , X, X |  |  | celá + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007309/22 | Kolín - Brno-Maloměřice | < > | Pohled | Pohled | 2023 | 2023 | 27 | 28 | 2023-07-05 | 0:00 | 2023-07-10 | 0:00 | 6 days | Continuous | Bridge |  | ST | [5 empty] | , X, X |  |  | celá + TV. |  |  |  |  | 2022-12-15
SZCZ | V-022875/20 | Děčín - Praha-Libeň | < > | Roztoky u Prahy | Roztoky u Prahy | 2023 | 2023 | 30 | 31 | 2023-07-29 | 0:00 | 2023-08-04 | 0:00 | 7 days | Continuous | Track & Rail |  | ST | [8 empty] | záhlaví libčické navazující na 2.TK Roztoky u Prahy - Libčice nad Vltavou |  |  |  |  | 2022-12-15
SZCZ | V-022875/20 | Děčín - Praha-Libeň | < > | Roztoky u Prahy | Libčice nad Vltavou | 2023 | 2023 | 30 | 31 | 2023-07-29 | 0:00 | 2023-08-04 | 0:00 | 7 days | Continuous | Track & Rail |  | LT | [8 empty] | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-022875/20 | Děčín - Praha-Libeň | < > | Libčice nad Vltavou | Libčice nad Vltavou | 2023 | 2023 | 30 | 31 | 2023-07-29 | 0:00 | 2023-08-04 | 0:00 | 7 days | Continuous | Track & Rail |  | ST | [8 empty] | záhlaví roztocké navazující na 2.TK Roztoky u Prahy - Libčice nad Vltavou |  |  |  |  | 2022-12-15
SZCZ | V-010473/22 | Česká Třebová - Brno | < > | Svitavy | Opatov | 2023 | 2023 | 1 | 26 | 2023-01-01 | 0:00 | 2023-06-30 | 0:00 | 181 days | Continuous | Others |  | LT | [8 empty] | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007179/22 | Děčín - Praha-Libeň | < > | Roudnice nad Labem | Hněvice | 2023 | 2023 | 14 | 15 | 2023-04-09 | 0:00 | 2023-04-12 | 0:00 | 4 x 10 hours | Periodical | Track & Rail |  | LT | [8 empty] | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007183/22 | Děčín - Praha-Libeň | < > | Roudnice nad Labem | Roudnice nad Labem | 2023 | 2023 | 15 | 15 | 2023-04-11 | 0:00 | 2023-04-12 | 0:00 | 2 x 10 hours | Periodical | Track & Rail |  | ST | [8 empty] | záhlaví hrobecké 1.traťové koleje a navazující zhlaví lichých staničních kolejí |  |  |  |  | 2022-12-15
SZCZ | V-007177/22 | Děčín - Praha-Libeň | < > | Hněvice | Roudnice nad Labem | 2023 | 2023 | 14 | 14 | 2023-04-05 | 0:00 | 2023-04-08 | 0:00 | 4 x 10 hours | Periodical | Track & Rail |  | LT | [8 empty] | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007181/22 | Děčín - Praha-Libeň | < > | Roudnice nad Labem | Roudnice nad Labem | 2023 | 2023 | 14 | 14 | 2023-04-05 | 0:00 | 2023-04-06 | 0:00 | 2 x 10 hours | Periodical | Track & Rail |  | ST | [8 empty] | záhlaví hrobecké 2.traťové koleje a navazující zhlaví sudých staničních kolejí |  |  |  |  | 2022-12-15
SZCZ | V-007179/22 | Děčín - Praha-Libeň | < > | Roudnice nad Labem | Roudnice nad Labem | 2023 | 2023 | 14 | 15 | 2023-04-09 | 0:00 | 2023-04-10 | 0:00 | 2 x 10 hours | Periodical | Track & Rail |  | ST | [8 empty] | záhlaví hněvické 1.traťové koleje a navazující zhlaví lichých staničních kolejí |  |  |  |  | 2022-12-15
SZCZ | V-010366/22 | Česká Třebová - Brno | < > | Adamov | Brno-Maloměřice stavědlo 6 | 2023 | 2023 | 12 | 12 | 2023-03-22 | 0:00 | 2023-03-26 | 0:00 | 5 days | Continuous | Miscellaneous |  | LT | [5 empty] | , X, X |  |  | 1 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-010365/22 | Česká Třebová - Brno | < > | Brno-Maloměřice stavědlo 6 | Adamov | 2023 | 2023 | 11 | 12 | 2023-03-17 | 0:00 | 2023-03-21 | 0:00 | 5 days | Continuous | Miscellaneous |  | LT | [8 empty] | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-010364/22 | Česká Třebová - Brno | < > | Adamov | Brno-Maloměřice stavědlo 6 | 2023 | 2023 | 11 | 11 | 2023-03-15 | 0:00 | 2023-03-16 | 0:00 | 2 days | Continuous | Catenary |  | LT | [5 empty] | , X, X |  |  | 1 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007177/22 | Děčín - Praha-Libeň | < > | Roudnice nad Labem | Roudnice nad Labem | 2023 | 2023 | 14 | 14 | 2023-04-07 | 0:00 | 2023-04-08 | 0:00 | 2 x 10 hours | Periodical | Track & Rail |  | ST | [8 empty] | záhlaví hněvické 2.traťové koleje a navazující zhlaví sudých staničních kolejí |  |  |  |  | 2022-12-15
SZCZ | V-010363/22 | Česká Třebová - Brno | < > | Adamov | Brno-Maloměřice stavědlo 6 | 2023 | 2023 | 9 | 9 | 2023-03-05 | 0:00 | 2023-03-05 | 0:00 | 1 x 6 hours | Periodical | Track & Rail |  | LT | [5 empty] | , X, X |  |  | 1 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-010362/22 | Česká Třebová - Brno | < > | Brno-Maloměřice stavědlo 6 | Adamov | 2023 | 2023 | 10 | 10 | 2023-03-08 | 0:00 | 2023-03-09 | 0:00 | 2 days | Continuous | Catenary |  | LT | [5 empty] | , X, X |  |  | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-010361/22 | Česká Třebová - Brno | < > | Brno-Maloměřice stavědlo 6 | Adamov | 2023 | 2023 | 9 | 9 | 2023-03-05 | 0:00 | 2023-03-05 | 0:00 | 1 x 6 hours | Periodical | Miscellaneous |  | LT | [5 empty] | , X, X |  |  | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007146/22 | Děčín - Praha-Libeň | < > | Ústí nad Labem západ | Ústí nad Labem hlavní nádraží | 2023 | 2023 | 18 | 18 | 2023-05-02 | 0:00 | 2023-05-04 | 0:00 | 3 days | Continuous | Switch |  | LT | [8 empty] | 901. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007142/22 | Česká Třebová - Brno | < > | Rájec-Jestřebí | Blansko | 2023 | 2023 | 17 | 17 | 2023-04-25 | 0:00 | 2023-04-29 | 0:00 | 5 days | Continuous | Track & Rail |  | LT | [8 empty] | 1 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-021373/20 | Praha-Libeň - Česká Třebová | < > | Poříčany | Český Brod | 2023 | 2023 | 28 | 28 | 2023-07-13 | 0:00 | 2023-07-16 | 0:00 | 4 days | Continuous | Track & Rail |  | LT | [8 empty] | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-021372/20 | Praha-Libeň - Česká Třebová | < > | Úvaly | Český Brod | 2023 | 2023 | 27 | 28 | 2023-07-09 | 0:00 | 2023-07-12 | 0:00 | 4 days | Continuous | Track & Rail |  | LT | [5 empty] | , X, X |  |  | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-021371/20 | Praha-Libeň - Česká Třebová | < > | Praha-Běchovice | Úvaly | 2023 | 2023 | 27 | 27 | 2023-07-05 | 0:00 | 2023-07-08 | 0:00 | 4 days | Continuous | Track & Rail |  | LT | [8 empty] | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-021370/20 | Praha-Libeň - Česká Třebová | < > | Praha-Libeň | Praha-Běchovice | 2023 | 2023 | 26 | 27 | 2023-07-01 | 0:00 | 2023-07-04 | 0:00 | 4 days | Continuous | Track & Rail |  | LT | [8 empty] | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-021368/20 | Praha-Libeň - Česká Třebová | < > | Český Brod | Poříčany | 2023 | 2023 | 33 | 33 | 2023-08-14 | 0:00 | 2023-08-17 | 0:00 | 4 days | Continuous | Track & Rail |  | LT | [8 empty] | 0. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-021367/20 | Praha-Libeň - Česká Třebová | < > | Úvaly | Český Brod | 2023 | 2023 | 32 | 32 | 2023-08-10 | 0:00 | 2023-08-13 | 0:00 | 4 days | Continuous | Track & Rail |  | LT | [8 empty] | 0. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-021366/20 | Praha-Libeň - Česká Třebová | < > | Praha-Běchovice | Úvaly | 2023 | 2023 | 31 | 32 | 2023-08-06 | 0:00 | 2023-08-09 | 0:00 | 4 days | Continuous | Track & Rail |  | LT | [8 empty] | 0. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-021365/20 | Praha-Libeň - Česká Třebová | < > | Praha-Libeň | Praha-Běchovice | 2023 | 2023 | 31 | 31 | 2023-08-02 | 0:00 | 2023-08-05 | 0:00 | 4 days | Continuous | Track & Rail |  | LT | [8 empty] | 0. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-021364/20 | Praha-Libeň - Česká Třebová | < > | Český Brod | Poříčany | 2023 | 2023 | 30 | 31 | 2023-07-29 | 0:00 | 2023-08-01 | 0:00 | 4 days | Continuous | Track & Rail |  | LT | [8 empty] | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-021363/20 | Praha-Libeň - Česká Třebová | < > | Český Brod | Úvaly | 2023 | 2023 | 30 | 30 | 2023-07-25 | 0:00 | 2023-07-28 | 0:00 | 4 days | Continuous | Track & Rail |  | LT | [5 empty] | , X, X |  |  | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-021362/20 | Praha-Libeň - Česká Třebová | < > | Úvaly | Praha-Běchovice | 2023 | 2023 | 29 | 30 | 2023-07-21 | 0:00 | 2023-07-24 | 0:00 | 4 days | Continuous | Track & Rail |  | LT | [8 empty] | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-021361/20 | Praha-Libeň - Česká Třebová | < > | Praha-Libeň | Praha-Běchovice | 2023 | 2023 | 29 | 29 | 2023-07-17 | 0:00 | 2023-07-20 | 0:00 | 4 days | Continuous | Track & Rail |  | LT | [8 empty] | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-010139/22 | Děčín - Kolín | < > | Liběchov | Štětí | 2023 | 2023 | 7 | 7 | 2023-02-13 | 0:00 | 2023-02-17 | 0:00 | 5 x 10 hours | Periodical | Catenary |  | LT | [8 empty] | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007142/22 | Česká Třebová - Brno | < > | Rájec-Jestřebí | Rájec-Jestřebí | 2023 | 2023 | 17 | 17 | 2023-04-25 | 0:00 | 2023-04-29 | 0:00 | 5 days | Continuous | Track & Rail |  | ST | [8 empty] | lichá jen TV. záhlaví 1. traťové koleje směr Blansko |  |  |  |  | 2022-12-15
SZCZ | V-007136/22 | Česká Třebová - Brno | < > | Blansko | Rájec-Jestřebí | 2023 | 2023 | 16 | 17 | 2023-04-20 | 0:00 | 2023-04-24 | 0:00 | 5 days | Continuous | Track & Rail |  | LT | [8 empty] | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-010134/22 | Děčín - Kolín | < > | Štětí | Liběchov | 2023 | 2023 | 6 | 6 | 2023-02-06 | 0:00 | 2023-02-10 | 0:00 | 5 x 10 hours | Periodical | Catenary |  | LT | [8 empty] | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-010134/22 | Děčín - Kolín | < > | Liběchov | Liběchov | 2023 | 2023 | 6 | 6 | 2023-02-06 | 0:00 | 2023-02-10 | 0:00 | 5 x 10 hours | Periodical | Catenary |  | ST | [8 empty] | lichá + TV. záhlaví a zhlaví štětské lichých kolejí. |  |  |  |  | 2022-12-15
SZCZ | V-007136/22 | Česká Třebová - Brno | < > | Rájec-Jestřebí | Rájec-Jestřebí | 2023 | 2023 | 16 | 17 | 2023-04-20 | 0:00 | 2023-04-24 | 0:00 | 5 days | Continuous | Track & Rail |  | ST | [8 empty] | sudá jen TV. záhlaví 2. traťové koleje směr Blansko |  |  |  |  | 2022-12-15
SZCZ | V-007135/22 | Kolín - Brno-Maloměřice | < > | Kutná Hora hlavní nádraží | Kolín seřaďovací nádraží | 2023 | 2023 | 28 | 29 | 2023-07-11 | 0:00 | 2023-07-20 | 0:00 | 10 days | Continuous | Track & Rail |  | LT | [8 empty] | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007135/22 | Praha-Libeň - Česká Třebová | < > | Kolín seřaďovací nádraží | Kolín seřaďovací nádraží | 2023 | 2023 | 28 | 29 | 2023-07-11 | 0:00 | 2023-07-20 | 0:00 | 10 days | Continuous | Track & Rail |  | ST | [8 empty] | záhlaví a zhlaví směr Kutná Hora hl.n.. |  |  |  |  | 2022-12-15
SZCZ | V-007135/22 | Kolín - Brno-Maloměřice | < > | Kutná Hora hlavní nádraží | Kutná Hora hlavní nádraží | 2023 | 2023 | 28 | 29 | 2023-07-11 | 0:00 | 2023-07-20 | 0:00 | 10 days | Continuous | Track & Rail |  | ST | [8 empty] | záhlaví a zhlaví směr Kolín. |  |  |  |  | 2022-12-15
SZCZ | V-007134/22 | Kolín - Brno-Maloměřice | < > | Kolín seřaďovací nádraží | Kutná Hora hlavní nádraží | 2023 | 2023 | 26 | 28 | 2023-07-01 | 0:00 | 2023-07-10 | 0:00 | 10 days | Continuous | Track & Rail |  | LT | [8 empty] | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-008941/21 | Praha-Libeň - Česká Třebová | < > | Český Brod | Český Brod | 2023 | 2023 | 21 | 22 | 2023-05-26 18:00 | 0:00 | 2023-05-30 06:00 | 0:00 | 4 x 7 hours | Periodical | Catenary |  | ST | [5 empty] | , X, X |  |  | 2. jen TV, 0. + TV. záhlaví a zhlaví 0. TK ze směru od žst. Úvaly. |  |  |  |  | 2022-12-15
SZCZ | V-008928/21 | Praha-Libeň - Česká Třebová | < > | Český Brod | Český Brod | 2023 | 2023 | 18 | 18 | 2023-05-03 | 0:00 | 2023-05-06 | 0:00 | 4 x 10 hours | Periodical | Catenary |  | ST | [5 empty] | , X, X |  |  | 2. jen TV, 4. + TV. záhlaví a zhlaví 2. TK ze směru od žst. Úvaly. |  |  |  |  | 2022-12-15
SZCZ | V-008937/21 | Praha-Libeň - Česká Třebová | < > | Český Brod | Český Brod | 2023 | 2023 | 20 | 21 | 2023-05-21 | 0:00 | 2023-05-24 | 0:00 | 4 x 10 hours | Periodical | Catenary |  | ST | [5 empty] | , X, X |  |  | 2. jen TV, 4. + TV. záhlaví a zhlaví 2. TK ze směru od žst. Úvaly. |  |  |  |  | 2022-12-15
SZCZ | V-010130/22 | Děčín - Kolín | < > | Liběchov | Liběchov | 2023 | 2023 | 5 | 6 | 2023-02-04 18:00 | 0:00 | 2023-02-06 06:00 | 0:00 | 2 x 6 hours | Periodical | Catenary |  | ST | [5 empty] | , X, X |  |  | celá + TV. |  |  |  |  | 2022-12-15
SZCZ | V-010125/22 | Děčín - Kolín | < > | Liběchov | Štětí | 2023 | 2023 | 5 | 5 | 2023-01-30 | 0:00 | 2023-02-03 | 0:00 | 5 x 10 hours | Periodical | Catenary |  | LT | [8 empty] | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-008932/21 | Praha-Libeň - Česká Třebová | < > | Český Brod | Český Brod | 2023 | 2023 | 18 | 19 | 2023-05-07 | 0:00 | 2023-05-09 | 0:00 | 3 x 10 hours | Periodical | Catenary |  | ST | [5 empty] | , X, X |  |  | 1. jen TV, 3. + TV. záhlaví a zhlaví 1. TK ze směru od žst. Úvaly. |  |  |  |  | 2022-12-15
SZCZ | V-008935/21 | Praha-Libeň - Česká Třebová | < > | Český Brod | Český Brod | 2023 | 2023 | 21 | 21 | 2023-05-25 | 0:00 | 2023-05-26 | 0:00 | 2 x 10 hours | Periodical | Catenary |  | ST | [5 empty] | , X, X |  |  | 1. jen TV, 3. + TV. záhlaví a zhlaví 1. TK ze směru od žst. Úvaly. |  |  |  |  | 2022-12-15
SZCZ | V-007134/22 | Praha-Libeň - Česká Třebová | < > | Kolín seřaďovací nádraží | Kolín seřaďovací nádraží | 2023 | 2023 | 26 | 28 | 2023-07-01 | 0:00 | 2023-07-10 | 0:00 | 10 days | Continuous | Track & Rail |  | ST | [8 empty] | záhlaví a zhlaví směr Kutná Hora hl.n.. |  |  |  |  | 2022-12-15
SZCZ | V-007134/22 | Kolín - Brno-Maloměřice | < > | Kutná Hora hlavní nádraží | Kutná Hora hlavní nádraží | 2023 | 2023 | 26 | 28 | 2023-07-01 | 0:00 | 2023-07-10 | 0:00 | 10 days | Continuous | Track & Rail |  | ST | [8 empty] | záhlaví a zhlaví směr Kolín seř.n.. |  |  |  |  | 2022-12-15
SZCZ | V-007121/22 | Kolín - Brno-Maloměřice | < > | Brno-Královo Pole | Kuřim | 2023 | 2023 | 36 | 36 | 2023-09-04 18:00 | 0:00 | 2023-09-06 06:00 | 0:00 | 2 x 5 hours | Periodical | Bridge |  | LT |  |  | X | [5 empty] | 2 jen TV. |  |  |  |  | 2022-12-15
SZCZ | V-007120/22 | Kolín - Brno-Maloměřice | < > | Brno-Královo Pole | Kuřim | 2023 | 2023 | 35 | 36 | 2023-09-03 18:00 | 0:00 | 2023-09-04 06:00 | 0:00 | 1 x 6 hours | Periodical | Bridge | T | LT | [5 empty] | , X, X |  |  | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007120/22 | Kolín - Brno-Maloměřice | < > | Kuřim | Kuřim | 2023 | 2023 | 35 | 36 | 2023-09-03 18:00 | 0:00 | 2023-09-04 06:00 | 0:00 | 1 x 6 hours | Periodical | Bridge |  | ST | [5 empty] | , X, X |  |  | celá jen TV. záhlaví 2.,1. TK směr Brno-Kr. Pole |  |  |  |  | 2022-12-15
SZCZ | V-007119/22 | Kolín - Brno-Maloměřice | < > | Brno-Královo Pole | Kuřim | 2023 | 2023 | 35 | 35 | 2023-09-01 | 0:00 | 2023-09-03 | 0:00 | 3 days | Continuous | Bridge |  | LT |  |  | X |  |  | , X, X |  |  | 2 jen TV. |  |  |  |  | 2022-12-15
SZCZ | V-007119/22 | Kolín - Brno-Maloměřice | < > | Kuřim | Kuřim | 2023 | 2023 | 35 | 35 | 2023-09-01 | 0:00 | 2023-09-03 | 0:00 | 3 days | Continuous | Bridge |  | ST |  |  | X |  |  | , X, X |  |  | celá jen TV. záhlaví 1. TK směr Brno-Kr. Pole |  |  |  |  | 2022-12-15
SZCZ | V-007116/22 | Česká Třebová - Brno | < > | Brno-Maloměřice | Brno-Královo Pole | 2023 | 2023 | 51 | 51 | 2023-12-22 | 0:00 | 2023-12-23 | 0:00 | 2 days | Continuous | Bridge |  | LT |  |  | X |  |  | , X, X |  |  | 2 jen TV. |  |  |  |  | 2022-12-15
SZCZ | V-007116/22 | Kolín - Brno-Maloměřice | < > | Brno-Královo Pole | Brno-Královo Pole | 2023 | 2023 | 51 | 51 | 2023-12-22 | 0:00 | 2023-12-23 | 0:00 | 2 days | Continuous | Bridge |  | ST |  |  | X |  |  | , X, X |  |  | sudá jen TV. zhlaví 1. TK směr Kuřim od náv. L1, L5, L7, L9, Se10 po nám. výh. č. 24n. |  |  |  |  | 2022-12-15
SZCZ | V-010119/22 | Děčín - Kolín | < > | Štětí | Liběchov | 2023 | 2023 | 4 | 4 | 2023-01-23 | 0:00 | 2023-01-27 | 0:00 | 5 x 10 hours | Periodical | Catenary |  | LT | [8 empty] | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-010119/22 | Děčín - Kolín | < > | Liběchov | Liběchov | 2023 | 2023 | 4 | 4 | 2023-01-23 | 0:00 | 2023-01-27 | 0:00 | 5 x 10 hours | Periodical | Catenary |  | ST | [8 empty] | lichá + TV. záhlaví a zhlaví štětské lichých kolejí. |  |  |  |  | 2022-12-15
SZCZ | V-008920/21 | Praha-Libeň - Česká Třebová | < > | Český Brod | Český Brod | 2023 | 2023 | 22 | 23 | 2023-05-30 18:00 | 0:00 | 2023-06-05 06:00 | 0:00 | 6 x 5 hours | Periodical | Catenary |  | ST | [8 empty] | celá jen TV. záhlaví a zhlaví 0., 1. a 2. TK ze směru od žst. Úvaly. |  |  |  |  | 2022-12-15
SZCZ | V-020900/21 | Brno - Břeclav | < > | Břeclav přednádraží | Břeclav přednádraží | 2023 | 2023 | 44 | 48 | 2023-11-01 | 0:00 | 2023-11-30 | 0:00 | 30 days | Continuous | Switch |  | ST |  |  | X | [5 empty] | 204.,204a,204b,206.,208.,210.,212.,214.,216.,218.,418.,420a,420b,420c jen TV. zhlaví severní kolejí 208,210,212,214,216,218. |  |  |  |  | 2022-12-15
SZCZ | V-008916/21 | Praha-Libeň - Česká Třebová | < > | Český Brod | Český Brod | 2023 | 2023 | 19 | 20 | 2023-05-11 18:00 | 0:00 | 2023-05-15 06:00 | 0:00 | 4 x 5 hours | Periodical | Catenary |  | ST | [8 empty] | celá jen TV. záhlaví a zhlaví 0., 1. a 2. TK ze směru od žst. Úvaly. |  |  |  |  | 2022-12-15
SZCZ | V-010091/22 | Břeclav - Kúty | < > | Lanžhot st.hr. | Lanžhot | 2023 | 2023 | 24 | 25 | 2023-06-16 | 0:00 | 2023-06-19 | 0:00 | 4 days | Continuous | Track & Rail | T | LT | [8 empty] | 1,2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-020754/21 | Kolín - Brno-Maloměřice | < > | Velké Meziříčí | Křižanov | 2023 | 2023 | 31 | 33 | 2023-08-01 | 0:00 | 2023-08-14 | 0:00 | 14 days | Continuous | Track & Rail | T | LT | [5 empty] | , X, X |  |  | traťová bez TV. |  |  |  |  | 2022-12-15
SZCZ | V-020747/21 | Kolín - Brno-Maloměřice | < > | Brno-Královo Pole | Brno-Královo Pole | 2023 | 2023 | 48 | 49 | 2023-12-01 | 0:00 | 2023-12-04 | 0:00 | 4 days | Continuous | Miscellaneous |  | ST | [5 empty] | , X, X |  |  | zhlaví SK 2 směr Kuřim. |  |  |  |  | 2022-12-15
SZCZ | V-020746/21 | Kolín - Brno-Maloměřice | < > | Brno-Královo Pole | Kuřim | 2023 | 2023 | 46 | 47 | 2023-11-16 | 0:00 | 2023-11-20 | 0:00 | 5 days | Continuous | Miscellaneous | T | LT | [5 empty] | , X, X |  |  | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-020745/21 | Kolín - Brno-Maloměřice | < > | Brno-Královo Pole | Kuřim | 2023 | 2023 | 33 | 33 | 2023-08-20 | 0:00 | 2023-08-20 | 0:00 | 1 x 16 hours | Periodical | Miscellaneous | T | LT | [5 empty] | , X, X |  |  | 2,1 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-020743/21 | Česká Třebová - Brno | < > | Brno-Maloměřice | Brno-Královo Pole | 2023 | 2023 | 10 | 12 | 2023-03-11 | 0:00 | 2023-03-24 | 0:00 | 14 days | Continuous | Signal |  | LT | [5 empty] | , X, X |  |  | zab. zař. TZZ. |  |  |  |  | 2022-12-15
SZCZ | V-020743/21 | Kolín - Brno-Maloměřice | < > | Brno-Královo Pole | Brno-Královo Pole | 2023 | 2023 | 10 | 12 | 2023-03-11 | 0:00 | 2023-03-24 | 0:00 | 14 days | Continuous | Signal |  | ST | [5 empty] | , X, X |  |  | zab. zař. SZZ celá. |  |  |  |  | 2022-12-15
SZCZ | V-020743/21 | Kolín - Brno-Maloměřice | < > | Brno-Královo Pole | Kuřim | 2023 | 2023 | 10 | 12 | 2023-03-11 | 0:00 | 2023-03-24 | 0:00 | 14 days | Continuous | Signal |  | LT | [5 empty] | , X, X |  |  | zab. zař. TZZ. |  |  |  |  | 2022-12-15
SZCZ | V-020740/21 | Česká Třebová - Brno | < > | Svitavy | Březová nad Svitavou | 2023 | 2023 | 14 | 14 | 2023-04-05 | 0:00 | 2023-04-05 | 0:00 | 1 x 8 hours | Periodical | Track & Rail |  | LT | [8 empty] | 1 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-010006/22 | Břeclav - Kúty | < > | Lanžhot st.hr. | Lanžhot | 2023 | 2023 | 26 | 26 | 2023-06-26 | 0:00 | 2023-06-30 | 0:00 | 5 days | Continuous | Track & Rail | T | LT | [8 empty] | 1,2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-010005/22 | Břeclav - Kúty | < > | Lanžhot st.hr. | Lanžhot | 2023 | 2023 | 25 | 26 | 2023-06-20 | 0:00 | 2023-06-26 | 0:00 | 7 days | Continuous | Signal |  | LT | [8 empty] | zab. zař. TZZ TK1 + TK2. |  |  |  |  | 2022-12-15
SZCZ | V-020739/21 | Česká Třebová - Brno | < > | Březová nad Svitavou | Svitavy | 2023 | 2023 | 14 | 14 | 2023-04-04 | 0:00 | 2023-04-04 | 0:00 | 1 x 8 hours | Periodical | Track & Rail |  | LT | [8 empty] | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-020730/21 | Brno - Břeclav | < > | Brno hlavní nádraží | Brno-Černovice odb. | 2023 | 2023 | 40 | 40 | 2023-10-07 | 0:00 | 2023-10-08 | 0:00 | 2 days | Continuous | Track & Rail | T | LT | [8 empty] | traťová + TV. záhlaví odb.Brno-Černovice |  |  |  |  | 2022-12-15
SZCZ | V-020704/21 | Praha-Libeň - Česká Třebová | < > | Kostěnice | Pardubice hlavní nádraží | 2023 | 2023 | 49 | 50 | 2023-12-10 | 0:00 | 2023-12-16 | 0:00 | 7 days | Continuous | Signal |  | LT | [5 empty] | , X, X |  |  | zab. zař. TZZ. |  |  |  |  | 2022-12-15
SZCZ | V-020704/21 | Praha-Libeň - Česká Třebová | < > | Pardubice hlavní nádraží | Pardubice hlavní nádraží | 2023 | 2023 | 49 | 50 | 2023-12-10 | 0:00 | 2023-12-16 | 0:00 | 7 days | Continuous | Signal |  | ST | [5 empty] | , X, X |  |  | zab. zař. SZZ - zhlaví směr Kostěnice. |  |  |  |  | 2022-12-15
SZCZ | V-008907/21 | Děčín - Praha-Libeň | < > | Kralupy nad Vltavou | Kralupy nad Vltavou | 2023 | 2023 | 40 | 41 | 2023-10-08 18:00 | 0:00 | 2023-10-14 06:00 | 0:00 | 6 x 4 hours | Periodical | Catenary |  | ST |  |  | X | [5 empty] | celá jen TV. |  |  |  |  | 2022-12-15
SZCZ | V-009506/21 | Praha-Libeň - Česká Třebová | < > | Brandýs nad Orlicí | Brandýs nad Orlicí | 2023 | 2023 | 37 | 37 | 2023-09-14 18:00 | 0:00 | 2023-09-17 06:00 | 0:00 | 3 x 10 hours | Periodical | Track & Rail |  | ST | [5 empty] | , X, X |  |  | sudá + TV. |  |  |  |  | 2022-12-15
SZCZ | V-009506/21 | Praha-Libeň - Česká Třebová | < > | Brandýs nad Orlicí | Brandýs nad Orlicí | 2023 | 2023 | 37 | 37 | 2023-09-14 18:00 | 0:00 | 2023-09-17 06:00 | 0:00 | 3 x 10 hours | Periodical | Track & Rail |  | ST | [5 empty] | , X, X |  |  | záhlaví a zhlaví 2. TK směr Choceň; záhlaví a zhlaví 2. TK směr Bezpráví. |  |  |  |  | 2022-12-15
SZCZ | V-009504/21 | Praha-Libeň - Česká Třebová | < > | Odb Bezpráví | Brandýs nad Orlicí | 2023 | 2023 | 37 | 37 | 2023-09-12 18:00 | 0:00 | 2023-09-14 06:00 | 0:00 | 2 x 10 hours | Periodical | Track & Rail |  | LT | [5 empty] | , X, X |  |  | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-009504/21 | Praha-Libeň - Česká Třebová | < > | Odb Bezpráví | Odb Bezpráví | 2023 | 2023 | 37 | 37 | 2023-09-12 18:00 | 0:00 | 2023-09-14 06:00 | 0:00 | 2 x 10 hours | Periodical | Track & Rail |  | ST | [5 empty] | , X, X |  |  | záhlaví 2. TK směr Brandýs nad Orlicí |  |  |  |  | 2022-12-15
SZCZ | V-009504/21 | Praha-Libeň - Česká Třebová | < > | Brandýs nad Orlicí | Brandýs nad Orlicí | 2023 | 2023 | 37 | 37 | 2023-09-12 18:00 | 0:00 | 2023-09-14 06:00 | 0:00 | 2 x 10 hours | Periodical | Track & Rail |  | ST | [5 empty] | , X, X |  |  | záhlaví 2. TK směr Bezpráví |  |  |  |  | 2022-12-15
SZCZ | V-009504/21 | Praha-Libeň - Česká Třebová | < > | Odb Bezpráví | Odb Bezpráví | 2023 | 2023 | 37 | 37 | 2023-09-12 18:00 | 0:00 | 2023-09-14 06:00 | 0:00 | 2 x 10 hours | Periodical | Track & Rail |  | ST | [5 empty] | , X, X |  |  | záhlaví 2. TK směr Ústí n. O. |  |  |  |  | 2022-12-15
SZCZ | V-009502/21 | Praha-Libeň - Česká Třebová | < > | Ústí nad Orlicí | Odb Bezpráví | 2023 | 2023 | 36 | 37 | 2023-09-10 18:00 | 0:00 | 2023-09-12 06:00 | 0:00 | 2 x 10 hours | Periodical | Track & Rail |  | LT | [5 empty] | , X, X |  |  | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-009502/21 | Praha-Libeň - Česká Třebová | < > | Ústí nad Orlicí | Ústí nad Orlicí | 2023 | 2023 | 36 | 37 | 2023-09-10 18:00 | 0:00 | 2023-09-12 06:00 | 0:00 | 2 x 10 hours | Periodical | Track & Rail |  | ST | [5 empty] | , X, X |  |  | záhlaví 2. TK směr Bezpráví |  |  |  |  | 2022-12-15
SZCZ | V-009502/21 | Praha-Libeň - Česká Třebová | < > | Odb Bezpráví | Odb Bezpráví | 2023 | 2023 | 36 | 37 | 2023-09-10 18:00 | 0:00 | 2023-09-12 06:00 | 0:00 | 2 x 10 hours | Periodical | Track & Rail |  | ST | [5 empty] | , X, X |  |  | záhlaví 2. TK směr Ústí n. O. |  |  |  |  | 2022-12-15
SZCZ | V-009499/21 | Praha-Libeň - Česká Třebová | < > | Brandýs nad Orlicí | Brandýs nad Orlicí | 2023 | 2023 | 36 | 36 | 2023-09-07 18:00 | 0:00 | 2023-09-10 06:00 | 0:00 | 3 x 10 hours | Periodical | Track & Rail |  | ST | [8 empty] | záhlaví a zhlaví 1. TK směr Choceň; zhlaví a záhlaví 1. TK směr Bezpráví. |  |  |  |  | 2022-12-15
SZCZ | V-009499/21 | Praha-Libeň - Česká Třebová | < > | Odb Bezpráví | Odb Bezpráví | 2023 | 2023 | 36 | 36 | 2023-09-07 18:00 | 0:00 | 2023-09-10 06:00 | 0:00 | 3 x 10 hours | Periodical | Track & Rail |  | ST | [8 empty] | záhlaví 1.TK směr Brandýs n. O. |  |  |  |  | 2022-12-15
SZCZ | V-009496/21 | Praha-Libeň - Česká Třebová | < > | Brandýs nad Orlicí | Odb Bezpráví | 2023 | 2023 | 36 | 36 | 2023-09-05 18:00 | 0:00 | 2023-09-07 06:00 | 0:00 | 2 x 10 hours | Periodical | Track & Rail |  | LT | [5 empty] | , X, X |  |  | 1 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-009496/21 | Praha-Libeň - Česká Třebová | < > | Brandýs nad Orlicí | Brandýs nad Orlicí | 2023 | 2023 | 36 | 36 | 2023-09-05 18:00 | 0:00 | 2023-09-07 06:00 | 0:00 | 2 x 10 hours | Periodical | Track & Rail |  | ST | [5 empty] | , X, X |  |  | záhlaví 1. TK směr Bezpráví |  |  |  |  | 2022-12-15
SZCZ | V-009496/21 | Praha-Libeň - Česká Třebová | < > | Odb Bezpráví | Odb Bezpráví | 2023 | 2023 | 36 | 36 | 2023-09-05 18:00 | 0:00 | 2023-09-07 06:00 | 0:00 | 2 x 10 hours | Periodical | Track & Rail |  | ST | [5 empty] | , X, X |  |  | záhlaví 1. TK směr Brandýs nad Orlicí |  |  |  |  | 2022-12-15
SZCZ | V-009496/21 | Praha-Libeň - Česká Třebová | < > | Odb Bezpráví | Odb Bezpráví | 2023 | 2023 | 36 | 36 | 2023-09-05 18:00 | 0:00 | 2023-09-07 06:00 | 0:00 | 2 x 10 hours | Periodical | Track & Rail |  | ST | [5 empty] | , X, X |  |  | záhlaví 1. TK směr Ústí n. O. od náv. S1 po náv. 1L |  |  |  |  | 2022-12-15
SZCZ | V-017479/20 | Kolín - Brno-Maloměřice | < > | Havlíčkův Brod | Ždírec nad Doubravou | 2023 | 2023 | 18 | 22 | 2023-05-02 | 0:00 | 2023-05-31 | 0:00 | 30 days | Continuous | Track & Rail | T | LT | [5 empty] | , X, X |  |  | traťová bez TV. |  |  |  |  | 2022-12-15
SZCZ | V-017474/20 | Kolín - Brno-Maloměřice | < > | Jihlava | Havlíčkův Brod | 2023 | 2023 | 16 | 17 | 2023-04-21 | 0:00 | 2023-04-30 | 0:00 | 10 days | Continuous | Track & Rail | T | LT | [5 empty] | , X, X |  |  | traťová + TV. |  |  |  |  | 2022-12-15
SZCZ | V-009492/21 | Praha-Libeň - Česká Třebová | < > | Odb Bezpráví | Ústí nad Orlicí | 2023 | 2023 | 35 | 36 | 2023-09-03 18:00 | 0:00 | 2023-09-05 06:00 | 0:00 | 2 x 10 hours | Periodical | Track & Rail |  | LT | [5 empty] | , X, X |  |  | 1 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-009492/21 | Praha-Libeň - Česká Třebová | < > | Odb Bezpráví | Odb Bezpráví | 2023 | 2023 | 35 | 36 | 2023-09-03 18:00 | 0:00 | 2023-09-05 06:00 | 0:00 | 2 x 10 hours | Periodical | Track & Rail |  | ST | [5 empty] | , X, X |  |  | záhlaví 1. TK směr Ústí n. O. |  |  |  |  | 2022-12-15
SZCZ | V-009492/21 | Praha-Libeň - Česká Třebová | < > | Ústí nad Orlicí | Ústí nad Orlicí | 2023 | 2023 | 35 | 36 | 2023-09-03 18:00 | 0:00 | 2023-09-05 06:00 | 0:00 | 2 x 10 hours | Periodical | Track & Rail |  | ST | [5 empty] | , X, X |  |  | záhlaví 1. TK směr Bezpráví |  |  |  |  | 2022-12-15
SZCZ | V-020194/21 | Praha-Libeň - Česká Třebová | < > | Pardubice hlavní nádraží | Přelouč nákladní nádraží | 2023 | 2023 | 47 | 49 | 2023-11-20 | 0:00 | 2023-12-09 | 0:00 | 20 days | Continuous | Signal |  | LT | [5 empty] | , X, X |  |  | zab. zař. TZZ. |  |  |  |  | 2022-12-15
SZCZ | V-020194/21 | Praha-Libeň - Česká Třebová | < > | Pardubice hlavní nádraží | Pardubice hlavní nádraží | 2023 | 2023 | 47 | 49 | 2023-11-20 | 0:00 | 2023-12-09 | 0:00 | 20 days | Continuous | Signal |  | ST | [5 empty] | , X, X |  |  | zab. zař. SZZ - zhlaví směr Přelouč, zhlaví směr Pardubice-Rosice nad Labem. |  |  |  |  | 2022-12-15
SZCZ | V-020193/21 | Praha-Libeň - Česká Třebová | < > | Pardubice hlavní nádraží | Přelouč nákladní nádraží | 2023 | 2023 | 49 | 49 | 2023-12-06 | 0:00 | 2023-12-09 | 0:00 | 4 days | Continuous | Catenary |  | LT | [5 empty] | , X, X |  |  | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-020193/21 | Praha-Libeň - Česká Třebová | < > | Pardubice hlavní nádraží | Pardubice hlavní nádraží | 2023 | 2023 | 49 | 49 | 2023-12-06 | 0:00 | 2023-12-09 | 0:00 | 4 days | Continuous | Catenary |  | ST | [5 empty] | , X, X |  |  | záhlaví a zhlaví 2. TK směr Přelouč. |  |  |  |  | 2022-12-15
SZCZ | V-009466/21 | Praha-Libeň - Česká Třebová | < > | Ústí nad Orlicí | Odb Bezpráví | 2023 | 2023 | 5 | 5 | 2023-01-31 18:00 | 0:00 | 2023-02-01 06:00 | 0:00 | 1 x 8 hours | Periodical | Track & Rail |  | LT | [5 empty] | , X, X |  |  | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-009467/21 | Praha-Libeň - Česká Třebová | < > | Ústí nad Orlicí | Odb Bezpráví | 2023 | 2023 | 10 | 10 | 2023-03-07 18:00 | 0:00 | 2023-03-08 06:00 | 0:00 | 2 x 12 hours | Periodical | Track & Rail |  | LT | [5 empty] | , X, X |  |  | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-009471/21 | Praha-Libeň - Česká Třebová | < > | Odb Bezpráví | Brandýs nad Orlicí | 2023 | 2023 | 25 | 25 | 2023-06-20 18:00 | 0:00 | 2023-06-21 06:00 | 0:00 | 1 x 8 hours | Periodical | Track & Rail |  | LT | [5 empty] | , X, X |  |  | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-009471/21 | Praha-Libeň - Česká Třebová | < > | Odb Bezpráví | Odb Bezpráví | 2023 | 2023 | 25 | 25 | 2023-06-20 18:00 | 0:00 | 2023-06-21 06:00 | 0:00 | 1 x 8 hours | Periodical | Track & Rail |  | ST | [5 empty] | , X, X |  |  | záhlaví 2. TK směr Brandýs nad Orlicí |  |  |  |  | 2022-12-15
SZCZ | V-009466/21 | Praha-Libeň - Česká Třebová | < > | Ústí nad Orlicí | Ústí nad Orlicí | 2023 | 2023 | 5 | 5 | 2023-01-31 18:00 | 0:00 | 2023-02-01 06:00 | 0:00 | 1 x 8 hours | Periodical | Track & Rail |  | ST | [5 empty] | , X, X |  |  | záhlaví 2. TK směr Bezpráví |  |  |  |  | 2022-12-15
SZCZ | V-009467/21 | Praha-Libeň - Česká Třebová | < > | Ústí nad Orlicí | Ústí nad Orlicí | 2023 | 2023 | 10 | 10 | 2023-03-07 18:00 | 0:00 | 2023-03-08 06:00 | 0:00 | 2 x 12 hours | Periodical | Track & Rail |  | ST | [5 empty] | , X, X |  |  | záhlaví 2. TK směr Bezpráví |  |  |  |  | 2022-12-15
SZCZ | V-009471/21 | Praha-Libeň - Česká Třebová | < > | Brandýs nad Orlicí | Brandýs nad Orlicí | 2023 | 2023 | 25 | 25 | 2023-06-20 18:00 | 0:00 | 2023-06-21 06:00 | 0:00 | 1 x 8 hours | Periodical | Track & Rail |  | ST | [5 empty] | , X, X |  |  | záhlaví 2. TK směr Bezpráví |  |  |  |  | 2022-12-15
SZCZ | V-009471/21 | Praha-Libeň - Česká Třebová | < > | Odb Bezpráví | Odb Bezpráví | 2023 | 2023 | 25 | 25 | 2023-06-20 18:00 | 0:00 | 2023-06-21 06:00 | 0:00 | 1 x 8 hours | Periodical | Track & Rail |  | ST | [5 empty] | , X, X |  |  | záhlaví 2. TK směr Ústí nad Orlicí od LIS v km 261,265 po náv. S2 |  |  |  |  | 2022-12-15
SZCZ | V-009470/21 | Praha-Libeň - Česká Třebová | < > | Brandýs nad Orlicí | Odb Bezpráví | 2023 | 2023 | 20 | 20 | 2023-05-16 18:00 | 0:00 | 2023-05-17 06:00 | 0:00 | 2 x 12 hours | Periodical | Track & Rail |  | LT | [5 empty] | , X, X |  |  | 1 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-009470/21 | Praha-Libeň - Česká Třebová | < > | Brandýs nad Orlicí | Brandýs nad Orlicí | 2023 | 2023 | 20 | 20 | 2023-05-16 18:00 | 0:00 | 2023-05-17 06:00 | 0:00 | 2 x 12 hours | Periodical | Track & Rail |  | ST | [5 empty] | , X, X |  |  | záhlaví 1. TK směr Bezpráví |  |  |  |  | 2022-12-15
SZCZ | V-009470/21 | Praha-Libeň - Česká Třebová | < > | Odb Bezpráví | Odb Bezpráví | 2023 | 2023 | 20 | 20 | 2023-05-16 18:00 | 0:00 | 2023-05-17 06:00 | 0:00 | 1 x 12 hours | Periodical | Track & Rail |  | ST | [5 empty] | , X, X |  |  | záhlaví 1. TK směr Brandýs nad Orlicí, záhlaví 1. TK směr Ústí nad Orlicí |  |  |  |  | 2022-12-15
SZCZ | V-020192/21 | Praha-Libeň - Česká Třebová | < > | Přelouč nákladní nádraží | Pardubice hlavní nádraží | 2023 | 2023 | 23 | 23 | 2023-06-07 | 0:00 | 2023-06-09 | 0:00 | 3 days | Continuous | Catenary |  | LT | [5 empty] | , X, X |  |  | 1 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-020192/21 | Praha-Libeň - Česká Třebová | < > | Pardubice hlavní nádraží | Pardubice hlavní nádraží | 2023 | 2023 | 23 | 23 | 2023-06-07 | 0:00 | 2023-06-09 | 0:00 | 3 days | Continuous | Catenary |  | ST | [5 empty] | , X, X |  |  | záhlaví a zhlaví 1. TK směr Přelouč. |  |  |  |  | 2022-12-15
SZCZ | V-020190/21 | Praha-Libeň - Česká Třebová | < > | Kostěnice | Pardubice hlavní nádraží | 2023 | 2023 | 1 | 52 | 2023-01-01 | 0:00 | 2023-12-31 | 0:00 | 365 days | Continuous | Signal |  | LT | [8 empty] | zab. zař. ETCS mezi dopravnami. |  |  |  |  | 2022-12-15
SZCZ | V-020190/21 | Praha-Libeň - Česká Třebová | < > | Pardubice hlavní nádraží | Přelouč nákladní nádraží | 2023 | 2023 | 1 | 52 | 2023-01-01 | 0:00 | 2023-12-31 | 0:00 | 365 days | Continuous | Signal |  | LT | [8 empty] | zab. zař. ETCS mezi dopravnami. |  |  |  |  | 2022-12-15
SZCZ | V-020188/21 | Praha-Libeň - Česká Třebová | < > | Pardubice hlavní nádraží | Pardubice-Rosice nad Labem | 2023 | 2023 | 42 | 42 | 2023-10-20 | 0:00 | 2023-10-22 | 0:00 | 3 days | Continuous | Miscellaneous | T | LT | [5 empty] | , X, X |  |  | traťová + TV. |  |  |  |  | 2022-12-15
SZCZ | V-020188/21 | Praha-Libeň - Česká Třebová | < > | Pardubice hlavní nádraží | Pardubice hlavní nádraží | 2023 | 2023 | 42 | 42 | 2023-10-20 | 0:00 | 2023-10-22 | 0:00 | 3 days | Continuous | Miscellaneous |  | ST | [5 empty] | , X, X |  |  | zhlaví SK 2,4 směr Pardubice-Rosice nad Labem. |  |  |  |  | 2022-12-15
SZCZ | V-020186/21 | Praha-Libeň - Česká Třebová | < > | Ústí nad Orlicí | Odb Bezpráví | 2023 | 2023 | 1 | 51 | 2023-01-01 | 0:00 | 2023-12-21 | 0:00 | 355 days | Continuous | Signal |  | LT | [8 empty] | zab. zař. ETCS. |  |  |  |  | 2022-12-15
SZCZ | V-016661/21 | Praha-Libeň - Česká Třebová | < > | Pardubice hlavní nádraží | Pardubice hlavní nádraží | 2023 | 2023 | 26 | 43 | 2023-07-01 | 0:00 | 2023-10-25 | 0:00 | 117 days | Continuous | Miscellaneous |  | ST | [8 empty] | zhlaví SK 2 směr Přelouč po nám. výh. č. 90. |  |  |  |  | 2022-12-15
SZCZ | V-016660/21 | Praha-Libeň - Česká Třebová | < > | Pardubice hlavní nádraží | Pardubice hlavní nádraží | 2023 | 2023 | 41 | 52 | 2023-10-12 | 0:00 | 2023-12-31 | 0:00 | 81 days | Continuous | Miscellaneous |  | ST | [8 empty] | zhlaví SK 12,14 směr Pardubice-Rosice n. L.. |  |  |  |  | 2022-12-15
SZCZ | V-020186/21 | Praha-Libeň - Česká Třebová | < > | Odb Bezpráví | Brandýs nad Orlicí | 2023 | 2023 | 1 | 51 | 2023-01-01 | 0:00 | 2023-12-21 | 0:00 | 355 days | Continuous | Signal |  | LT | [8 empty] | zab. zař. ETCS. |  |  |  |  | 2022-12-15
SZCZ | V-013283/22 | Česká Třebová - Brno | < > | Letovice | Březová nad Svitavou | 2023 | 2023 | 25 | 25 | 2023-06-21 | 0:00 | 2023-06-25 | 0:00 | 5 days | Continuous | Signal |  | LT | [8 empty] | zab. zař. PZS v km 204,614 (P6816), PZS v km 208,144 (P6818). |  |  |  |  | 2022-12-15
SZCZ | V-013260/22 | Kolín - Brno-Maloměřice | < > | Vlkov u Tišnova | Křižanov | 2023 | 2023 | 32 | 33 | 2023-08-10 | 0:00 | 2023-08-14 | 0:00 | 5 x 8 hours | Periodical | Track & Rail |  | LT | [5 empty] | , X, X |  |  | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-013265/22 | Kolín - Brno-Maloměřice | < > | Vlkov u Tišnova | Křižanov | 2023 | 2023 | 34 | 35 | 2023-08-22 | 0:00 | 2023-08-31 | 0:00 | 10 x 8 hours | Periodical | Track & Rail |  | LT | [5 empty] | , X, X |  |  | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-020125/20 | Praha-Libeň - Česká Třebová | < > | Pardubice hlavní nádraží | Pardubice-Rosice nad Labem | 2023 | 2023 | 41 | 49 | 2023-10-09 | 0:00 | 2023-12-09 | 0:00 | 62 days | Continuous | Miscellaneous | T | LT | [5 empty] | , X, X |  |  | 2,1 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-020060/20 | Česká Třebová - Brno | < > | Letovice | Březová nad Svitavou | 2023 | 2023 | 17 | 17 | 2023-04-24 | 0:00 | 2023-04-28 | 0:00 | 5 days | Continuous | Signal |  | LT | [8 empty] | zab. zař. PZS v km 204,614 (P6816), PZS v km 208,144 (P6818), PZS v km 208,487 (P6819), PZS v km 210,738 (P6822). |  |  |  |  | 2022-12-15
SZCZ | V-020058/20 | Česká Třebová - Brno | < > | Březová nad Svitavou | Svitavy | 2023 | 2023 | 18 | 19 | 2023-05-07 | 0:00 | 2023-05-11 | 0:00 | 5 days | Continuous | Signal |  | LT | [8 empty] | zab. zař. PZS v km 214,484 (P6825). |  |  |  |  | 2022-12-15
SZCZ | V-020030/20 | Praha-Libeň - Česká Třebová | < > | Pardubice hlavní nádraží | Pardubice hlavní nádraží | 2023 | 2023 | 41 | 49 | 2023-10-12 | 0:00 | 2023-12-09 | 0:00 | 59 days | Continuous | Miscellaneous |  | ST | [5 empty] | , X, X |  |  | 10 + TV. zhlaví směr Pardubice-Rosice n. L.. |  |  |  |  | 2022-12-15
SZCZ | V-020026/20 | Praha-Libeň - Česká Třebová | < > | Pardubice hlavní nádraží | Přelouč | 2023 | 2023 | 23 | 26 | 2023-06-10 | 0:00 | 2023-06-30 | 0:00 | 21 days | Continuous | Miscellaneous |  | LT | [5 empty] | , X, X |  |  | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-020021/20 | Praha-Libeň - Česká Třebová | < > | Pardubice hlavní nádraží | Pardubice hlavní nádraží | 2023 | 2023 | 19 | 23 | 2023-05-11 | 0:00 | 2023-06-09 | 0:00 | 30 days | Continuous | Miscellaneous |  | ST | [8 empty] | zhlaví LKS směr Přelouč po nám. výh. č. 94X. |  |  |  |  | 2022-12-15
SZCZ | V-008680/22 | Praha-Libeň - Česká Třebová | < > | Česká Třebová | Česká Třebová | 2023 | 2023 | 35 | 47 | 2023-08-28 | 0:00 | 2023-11-24 | 0:00 | 89 days | Continuous | Track & Rail |  | ST | [8 empty] | zhlaví střední od námezníků výhybek č. 146, 205 a 220 po návěstila Se233, Se 234, Se 240 a Se 250. |  |  |  |  | 2022-12-15
SZCZ | V-009469/21 | Praha-Libeň - Česká Třebová | < > | Odb Bezpráví | Ústí nad Orlicí | 2023 | 2023 | 15 | 15 | 2023-04-11 18:00 | 0:00 | 2023-04-12 06:00 | 0:00 | 1 x 8 hours | Periodical | Track & Rail |  | LT | [5 empty] | , X, X |  |  | 1 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-009469/21 | Praha-Libeň - Česká Třebová | < > | Odb Bezpráví | Odb Bezpráví | 2023 | 2023 | 15 | 15 | 2023-04-11 18:00 | 0:00 | 2023-04-12 06:00 | 0:00 | 1 x 8 hours | Periodical | Track & Rail |  | ST | [5 empty] | , X, X |  |  | záhlaví 1. TK směr Ústí nad Orlicí od náv. S1 po náv. 1L |  |  |  |  | 2022-12-15
SZCZ | V-009469/21 | Praha-Libeň - Česká Třebová | < > | Ústí nad Orlicí | Ústí nad Orlicí | 2023 | 2023 | 15 | 15 | 2023-04-11 18:00 | 0:00 | 2023-04-12 06:00 | 0:00 | 1 x 8 hours | Periodical | Track & Rail |  | ST | [5 empty] | , X, X |  |  | záhlaví 1. TK směr Bezpráví |  |  |  |  | 2022-12-15
SZCZ | V-009468/21 | Praha-Libeň - Česká Třebová | < > | Odb Bezpráví | Brandýs nad Orlicí | 2023 | 2023 | 15 | 15 | 2023-04-11 18:00 | 0:00 | 2023-04-12 06:00 | 0:00 | 1 x 8 hours | Periodical | Track & Rail |  | LT | [5 empty] | , X, X |  |  | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-020011/20 | Praha-Libeň - Česká Třebová | < > | Pardubice hlavní nádraží | Pardubice hlavní nádraží | 2023 | 2023 | 1 | 19 | 2023-01-01 | 0:00 | 2023-05-10 | 0:00 | 130 days | Continuous | Miscellaneous |  | ST | [8 empty] | zhlaví SK 1 směr Přelouč po nám. výh. č. 88. |  |  |  |  | 2022-12-15
SZCZ | V-019754/21 | Děčín - Kolín | < > | Ústí nad Labem-Střekov | Ústí nad Labem západ | 2023 | 2023 | 21 | 45 | 2023-05-24 | 0:00 | 2023-11-07 | 0:00 | 168 days | Continuous | Bridge |  | LT | [8 empty] | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-013244/22 | Kolín - Brno-Maloměřice | < > | Křižanov | Vlkov u Tišnova | 2023 | 2023 | 29 | 30 | 2023-07-20 | 0:00 | 2023-07-29 | 0:00 | 10 x 8 hours | Periodical | Track & Rail |  | LT | [5 empty] | , X, X |  |  | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-013254/22 | Kolín - Brno-Maloměřice | < > | Křižanov | Vlkov u Tišnova | 2023 | 2023 | 31 | 32 | 2023-08-05 | 0:00 | 2023-08-09 | 0:00 | 5 x 8 hours | Periodical | Track & Rail |  | LT | [5 empty] | , X, X |  |  | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007014/22 | Kolín - Brno-Maloměřice | < > | Brno-Maloměřice stavědlo 3 | Brno-Maloměřice stavědlo 3 | 2023 | 2023 | 52 | 52 | 2023-12-27 | 0:00 | 2023-12-30 | 0:00 | 4 x 12 hours | Periodical | Bridge |  | ST |  |  | X |  |  | , X, X |  |  | záhlaví 1. traťové koleje směr Brno-Královo Pole |  |  |  |  | 2022-12-15
SZCZ | V-007014/22 | Brno - Břeclav | < > | Brno-Maloměřice stavědlo 3 | Brno-Židenice | 2023 | 2023 | 52 | 52 | 2023-12-27 | 0:00 | 2023-12-30 | 0:00 | 4 x 12 hours | Periodical | Bridge |  | LT |  |  | X |  |  | , X, X |  |  | 1K,2K jen TV. |  |  |  |  | 2022-12-15
SZCZ | V-007014/22 | Kolín - Brno-Maloměřice | < > | Brno-Maloměřice stavědlo 3 | Brno-Královo Pole | 2023 | 2023 | 52 | 52 | 2023-12-27 | 0:00 | 2023-12-30 | 0:00 | 4 x 12 hours | Periodical | Bridge |  | LT |  |  | X |  |  | , X, X |  |  | 2 jen TV. |  |  |  |  | 2022-12-15
SZCZ | V-007014/22 | Kolín - Brno-Maloměřice | < > | Brno-Královo Pole | Brno-Královo Pole | 2023 | 2023 | 52 | 52 | 2023-12-27 | 0:00 | 2023-12-30 | 0:00 | 4 x 12 hours | Periodical | Bridge |  | ST |  |  | X |  |  | , X, X |  |  | sudá jen TV. |  |  |  |  | 2022-12-15
SZCZ | V-008603/22 | Praha-Libeň - Česká Třebová | < > | Brandýs nad Orlicí | Choceň | 2023 | 2023 | 16 | 16 | 2023-04-19 | 0:00 | 2023-04-19 | 0:00 | 3 x 4 hours | Periodical | Signal | T | LT | [5 empty] | , X, X |  |  | zab. zař. TZZ. |  |  |  |  | 2022-12-15
SZCZ | V-008620/22 | Praha-Libeň - Česká Třebová | < > | Pardubice hlavní nádraží | Přelouč | 2023 | 2023 | 21 | 21 | 2023-05-24 | 0:00 | 2023-05-24 | 0:00 | 3 x 4 hours | Periodical | Signal | T | LT | [5 empty] | , X, X |  |  | zab. zař. TZZ. |  |  |  |  | 2022-12-15
SZCZ | V-008626/22 | Praha-Libeň - Česká Třebová | < > | Přelouč | Řečany nad Labem | 2023 | 2023 | 22 | 22 | 2023-05-31 | 0:00 | 2023-05-31 | 0:00 | 2 x 4 hours | Periodical | Signal | T | LT | [5 empty] | , X, X |  |  | zab. zař. TZZ. |  |  |  |  | 2022-12-15
SZCZ | V-008634/22 | Praha-Libeň - Česká Třebová | < > | Řečany nad Labem | Záboří nad Labem | 2023 | 2023 | 23 | 23 | 2023-06-07 | 0:00 | 2023-06-07 | 0:00 | 2 x 4 hours | Periodical | Signal | T | LT | [5 empty] | , X, X |  |  | zab. zař. TZZ. |  |  |  |  | 2022-12-15
SZCZ | V-008603/22 | Praha-Libeň - Česká Třebová | < > | Choceň | Choceň | 2023 | 2023 | 16 | 16 | 2023-04-19 | 0:00 | 2023-04-19 | 0:00 | 1 x 4 hours | Periodical | Signal |  | ST | [5 empty] | , X, X |  |  | zab. zař. SZZ. |  |  |  |  | 2022-12-15
SZCZ | V-008620/22 | Praha-Libeň - Česká Třebová | < > | Přelouč | Přelouč | 2023 | 2023 | 21 | 21 | 2023-05-24 | 0:00 | 2023-05-24 | 0:00 | 1 x 4 hours | Periodical | Signal |  | ST | [5 empty] | , X, X |  |  | zab. zař. SZZ. |  |  |  |  | 2022-12-15
SZCZ | V-008626/22 | Praha-Libeň - Česká Třebová | < > | Řečany nad Labem | Řečany nad Labem | 2023 | 2023 | 22 | 22 | 2023-05-31 | 0:00 | 2023-05-31 | 0:00 | 1 x 4 hours | Periodical | Signal |  | ST | [5 empty] | , X, X |  |  | zab. zař. SZZ. |  |  |  |  | 2022-12-15
SZCZ | V-008634/22 | Praha-Libeň - Česká Třebová | < > | Záboří nad Labem | Záboří nad Labem | 2023 | 2023 | 23 | 23 | 2023-06-07 | 0:00 | 2023-06-07 | 0:00 | 1 x 4 hours | Periodical | Signal |  | ST | [5 empty] | , X, X |  |  | zab. zař. SZZ. |  |  |  |  | 2022-12-15
SZCZ | V-008602/22 | Praha-Libeň - Česká Třebová | < > | Brandýs nad Orlicí | Choceň | 2023 | 2023 | 16 | 16 | 2023-04-18 | 0:00 | 2023-04-18 | 0:00 | 3 x 1 hours | Periodical | Signal |  | LT | [5 empty] | , X, X |  |  | zab. zař. TZZ. |  |  |  |  | 2022-12-15
SZCZ | V-008619/22 | Praha-Libeň - Česká Třebová | < > | Pardubice hlavní nádraží | Přelouč | 2023 | 2023 | 21 | 21 | 2023-05-23 | 0:00 | 2023-05-23 | 0:00 | 3 x 1 hours | Periodical | Signal |  | LT | [5 empty] | , X, X |  |  | zab. zař. TZZ. |  |  |  |  | 2022-12-15
SZCZ | V-008625/22 | Praha-Libeň - Česká Třebová | < > | Přelouč | Řečany nad Labem | 2023 | 2023 | 22 | 22 | 2023-05-30 | 0:00 | 2023-05-30 | 0:00 | 2 x 1 hours | Periodical | Signal |  | LT | [5 empty] | , X, X |  |  | zab. zař. TZZ. |  |  |  |  | 2022-12-15
SZCZ | V-008631/22 | Praha-Libeň - Česká Třebová | < > | Řečany nad Labem | Záboří nad Labem | 2023 | 2023 | 23 | 23 | 2023-06-06 | 0:00 | 2023-06-06 | 0:00 | 2 x 1 hours | Periodical | Signal |  | LT | [5 empty] | , X, X |  |  | zab. zař. TZZ. |  |  |  |  | 2022-12-15
SZCZ | V-008602/22 | Praha-Libeň - Česká Třebová | < > | Choceň | Choceň | 2023 | 2023 | 16 | 16 | 2023-04-18 | 0:00 | 2023-04-18 | 0:00 | 1 x 1 hours | Periodical | Signal |  | ST | [5 empty] | , X, X |  |  | zab. zař. SZZ. |  |  |  |  | 2022-12-15
SZCZ | V-008619/22 | Praha-Libeň - Česká Třebová | < > | Přelouč | Přelouč | 2023 | 2023 | 21 | 21 | 2023-05-23 | 0:00 | 2023-05-23 | 0:00 | 1 x 1 hours | Periodical | Signal |  | ST | [5 empty] | , X, X |  |  | zab. zař. SZZ. |  |  |  |  | 2022-12-15
SZCZ | V-008625/22 | Praha-Libeň - Česká Třebová | < > | Řečany nad Labem | Řečany nad Labem | 2023 | 2023 | 22 | 22 | 2023-05-30 | 0:00 | 2023-05-30 | 0:00 | 1 x 1 hours | Periodical | Signal |  | ST | [5 empty] | , X, X |  |  | zab. zař. SZZ. |  |  |  |  | 2022-12-15
SZCZ | V-008631/22 | Praha-Libeň - Česká Třebová | < > | Záboří nad Labem | Záboří nad Labem | 2023 | 2023 | 23 | 23 | 2023-06-06 | 0:00 | 2023-06-06 | 0:00 | 1 x 1 hours | Periodical | Signal |  | ST | [5 empty] | , X, X |  |  | zab. zař. SZZ. |  |  |  |  | 2022-12-15
SZCZ | V-008484/22 | Praha-Libeň - Česká Třebová | < > | Pardubice hlavní nádraží | Pardubice-Rosice nad Labem | 2023 | 2023 | 49 | 52 | 2023-12-10 | 0:00 | 2023-12-31 | 0:00 | 22 days | Continuous | Miscellaneous |  | LT | [8 empty] | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-008439/22 | Praha-Libeň - Česká Třebová | < > | Brandýs nad Orlicí | Brandýs nad Orlicí | 2023 | 2023 | 37 | 37 | 2023-09-14 18:00 | 0:00 | 2023-09-15 06:00 | 0:00 | 1 x 3 hours | Periodical | Track & Rail |  | ST | [8 empty] | záhlaví a zhlaví 1. TK směr Choceň; zhlaví a záhlaví 1. TK směr Bezpráví. |  |  |  |  | 2022-12-15
SZCZ | V-008438/22 | Praha-Libeň - Česká Třebová | < > | Brandýs nad Orlicí | Brandýs nad Orlicí | 2023 | 2023 | 36 | 36 | 2023-09-09 18:00 | 0:00 | 2023-09-10 06:00 | 0:00 | 1 x 3 hours | Periodical | Track & Rail |  | ST | [8 empty] | záhlaví a zhlaví 2. TK směr Choceň; zhlaví a záhlaví 2. TK směr Bezpráví. |  |  |  |  | 2022-12-15
SZCZ | V-008352/22 | Kolín - Brno-Maloměřice | < > | Kuřim | Brno-Královo Pole | 2023 | 2023 | 35 | 48 | 2023-09-01 | 0:00 | 2023-11-30 | 0:00 | 91 days | Continuous | Track & Rail |  | LT | [8 empty] | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-008352/22 | Kolín - Brno-Maloměřice | < > | Brno-Královo Pole | Brno-Královo Pole | 2023 | 2023 | 35 | 48 | 2023-09-01 | 0:00 | 2023-11-30 | 0:00 | 91 days | Continuous | Track & Rail |  | ST | [8 empty] | záhlaví a zhlaví 1. traťové koleje směr Kuřim. |  |  |  |  | 2022-12-15
SZCZ | V-008169/22 | Děčín - Kolín | < > | Sebuzín | Velké Žernoseky | 2023 | 2023 | 50 | 50 | 2023-12-16 | 0:00 | 2023-12-17 | 0:00 | 2 x 8 hours | Periodical | Catenary |  | LT | [8 empty] | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-008167/22 | Děčín - Kolín | < > | Velké Žernoseky | Sebuzín | 2023 | 2023 | 50 | 50 | 2023-12-14 | 0:00 | 2023-12-15 | 0:00 | 2 x 8 hours | Periodical | Catenary |  | LT | [8 empty] | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-008163/22 | Děčín - Kolín | < > | Sebuzín | Velké Žernoseky | 2023 | 2023 | 49 | 50 | 2023-12-09 18:00 | 0:00 | 2023-12-13 06:00 | 0:00 | 4 x 5 hours | Periodical | Others | T | LT | [5 empty] | , X, X |  |  | 1.,2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-008166/21 | Česká Třebová - Brno | < > | Brno-Královo Pole | Brno-Maloměřice | 2023 | 2023 | 51 | 52 | 2023-12-21 | 0:00 | 2023-12-31 | 0:00 | 11 days | Continuous | Miscellaneous |  | LT | [8 empty] | 1 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-008166/21 | Kolín - Brno-Maloměřice | < > | Brno-Královo Pole | Brno-Královo Pole | 2023 | 2023 | 51 | 52 | 2023-12-21 | 0:00 | 2023-12-31 | 0:00 | 11 days | Continuous | Miscellaneous |  | ST | [8 empty] | záhlaví a zhlaví 1. TK směr Brno-Maloměřice. |  |  |  |  | 2022-12-15
SZCZ | V-008165/21 | Kolín - Brno-Maloměřice | < > | Brno-Královo Pole | Kuřim | 2023 | 2023 | 48 | 51 | 2023-12-01 | 0:00 | 2023-12-20 | 0:00 | 20 days | Continuous | Miscellaneous |  | LT | [8 empty] | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-008165/21 | Kolín - Brno-Maloměřice | < > | Brno-Královo Pole | Brno-Královo Pole | 2023 | 2023 | 48 | 51 | 2023-12-01 | 0:00 | 2023-12-20 | 0:00 | 20 days | Continuous | Miscellaneous |  | ST | [8 empty] | záhlaví 2. TK směr Kuřim |  |  |  |  | 2022-12-15
SZCZ | V-008162/22 | Děčín - Kolín | < > | Velké Žernoseky | Sebuzín | 2023 | 2023 | 44 | 49 | 2023-11-04 | 0:00 | 2023-12-08 | 0:00 | 35 days | Continuous | Track & Rail |  | LT | [8 empty] | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-008149/22 | Děčín - Kolín | < > | Ústí nad Labem-Střekov | Ústí nad Labem západ | 2023 | 2023 | 40 | 42 | 2023-10-02 | 0:00 | 2023-10-21 | 0:00 | 20 days | Continuous | Bridge |  | LT | [8 empty] | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-008099/22 | Děčín - Kolín | < > | Sebuzín | Velké Žernoseky | 2023 | 2023 | 39 | 44 | 2023-09-30 | 0:00 | 2023-11-03 | 0:00 | 35 days | Continuous | Track & Rail |  | LT | [8 empty] | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-008097/22 | Děčín - Kolín | < > | Sebuzín | Velké Žernoseky | 2023 | 2023 | 39 | 39 | 2023-09-27 18:00 | 0:00 | 2023-09-29 06:00 | 0:00 | 2 x 8 hours | Periodical | Miscellaneous | T | LT | [5 empty] | , X, X |  |  | 1.,2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-008095/22 | Děčín - Kolín | < > | Sebuzín | Velké Žernoseky | 2023 | 2023 | 39 | 39 | 2023-09-25 | 0:00 | 2023-09-26 | 0:00 | 2 x 10 hours | Periodical | Miscellaneous |  | LT | [8 empty] | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-008093/22 | Děčín - Kolín | < > | Velké Žernoseky | Sebuzín | 2023 | 2023 | 38 | 38 | 2023-09-23 | 0:00 | 2023-09-24 | 0:00 | 2 x 10 hours | Periodical | Miscellaneous |  | LT | [8 empty] | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-008091/22 | Děčín - Kolín | < > | Sebuzín | Velké Žernoseky | 2023 | 2023 | 36 | 36 | 2023-09-04 | 0:00 | 2023-09-05 | 0:00 | 2 x 8 hours | Periodical | Catenary |  | LT | [8 empty] | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-008089/22 | Děčín - Kolín | < > | Velké Žernoseky | Sebuzín | 2023 | 2023 | 35 | 35 | 2023-09-02 | 0:00 | 2023-09-03 | 0:00 | 2 x 8 hours | Periodical | Catenary |  | LT | [8 empty] | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-008088/22 | Děčín - Kolín | < > | Velké Žernoseky | Litoměřice dolní nádraží | 2023 | 2023 | 33 | 33 | 2023-08-18 | 0:00 | 2023-08-18 | 0:00 | 1 x 8 hours | Periodical | Catenary |  | LT | [8 empty] | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-008085/22 | Děčín - Kolín | < > | Velké Žernoseky | Litoměřice dolní nádraží | 2023 | 2023 | 32 | 33 | 2023-08-13 18:00 | 0:00 | 2023-08-16 06:00 | 0:00 | 3 x 5 hours | Periodical | Catenary | T | LT | [5 empty] | , X, X |  |  | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-008084/22 | Děčín - Kolín | < > | Litoměřice dolní nádraží | Velké Žernoseky | 2023 | 2023 | 20 | 33 | 2023-05-16 | 0:00 | 2023-08-17 | 0:00 | 94 days | Continuous | Track & Rail |  | LT | [8 empty] | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-008074/22 | Děčín - Kolín | < > | Litoměřice dolní nádraží | Velké Žernoseky | 2023 | 2023 | 18 | 20 | 2023-05-06 | 0:00 | 2023-05-15 | 0:00 | 10 x 8 hours | Periodical | Catenary |  | LT | [8 empty] | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-008072/22 | Děčín - Kolín | < > | Litoměřice dolní nádraží | Velké Žernoseky | 2023 | 2023 | 18 | 18 | 2023-05-02 18:00 | 0:00 | 2023-05-04 06:00 | 0:00 | 2 x 5 hours | Periodical | Catenary | T | LT | [5 empty] | , X, X |  |  | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-008071/22 | Děčín - Kolín | < > | Velké Žernoseky | Litoměřice dolní nádraží | 2023 | 2023 | 9 | 18 | 2023-03-03 | 0:00 | 2023-05-05 | 0:00 | 64 days | Continuous | Track & Rail |  | LT | [8 empty] | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-008061/22 | Děčín - Kolín | < > | Velké Žernoseky | Litoměřice dolní nádraží | 2023 | 2023 | 8 | 9 | 2023-02-21 | 0:00 | 2023-03-02 | 0:00 | 10 x 8 hours | Periodical | Catenary |  | LT | [8 empty] | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-008044/22 | Děčín - Praha-Libeň | < > | Prackovice nad Labem | UNL hlavní nádraží jih | 2023 | 2023 | 20 | 20 | 2023-05-18 | 0:00 | 2023-05-20 | 0:00 | 3 days | Continuous | Track & Rail |  | LT | [5 empty] | , X, X |  |  | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-008043/22 | Děčín - Praha-Libeň | < > | UNL hlavní nádraží jih | Prackovice nad Labem | 2023 | 2023 | 20 | 20 | 2023-05-15 | 0:00 | 2023-05-17 | 0:00 | 3 days | Continuous | Track & Rail |  | LT | [5 empty] | , X, X |  |  | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-008042/22 | Děčín - Praha-Libeň | < > | Prackovice nad Labem | Lovosice | 2023 | 2023 | 19 | 19 | 2023-05-09 | 0:00 | 2023-05-12 | 0:00 | 4 days | Continuous | Track & Rail |  | LT | [5 empty] | , X, X |  |  | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007980/21 | Česká Třebová - Brno | < > | Adamov | Adamov | 2023 | 2023 | 15 | 15 | 2023-04-11 | 0:00 | 2023-04-12 | 0:00 | 2 days | Continuous | Miscellaneous |  | ST | [5 empty] | , X, X |  |  | lichá + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007976/21 | Česká Třebová - Brno | < > | Blansko | Adamov | 2023 | 2023 | 14 | 15 | 2023-04-06 | 0:00 | 2023-04-12 | 0:00 | 7 days | Continuous | Miscellaneous |  | LT | [5 empty] | , X, X |  |  | 1 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007976/21 | Česká Třebová - Brno | < > | Blansko | Blansko | 2023 | 2023 | 14 | 15 | 2023-04-06 | 0:00 | 2023-04-12 | 0:00 | 7 days | Continuous | Miscellaneous |  | ST | [5 empty] | , X, X |  |  | lichá + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007959/20 | Děčín - Praha-Libeň | < > | Kralupy nad Vltavou | Kralupy nad Vltavou | 2023 | 2023 | 37 | 38 | 2023-09-17 | 0:00 | 2023-09-18 | 0:00 | 2 days | Continuous | Catenary |  | ST | [8 empty] | zhlaví kolejí 105.,107.,109.,111.,113.,115.ze směru Libčice nad Vltavou. |  |  |  |  | 2022-12-15
SZCZ | V-007959/20 | Děčín - Praha-Libeň | < > | Kralupy nad Vltavou | Kralupy nad Vltavou | 2023 | 2023 | 37 | 38 | 2023-09-17 | 0:00 | 2023-09-18 | 0:00 | 2 days | Continuous | Catenary |  | ST | [8 empty] | zhlaví střední kolejí 105.,107.,109.,111.,113.,115.. |  |  |  |  | 2022-12-15
SZCZ | V-007958/20 | Děčín - Praha-Libeň | < > | Kralupy nad Vltavou | Kralupy nad Vltavou | 2023 | 2023 | 37 | 37 | 2023-09-15 | 0:00 | 2023-09-16 | 0:00 | 2 days | Continuous | Catenary |  | ST | [8 empty] | zhlaví kolejí 105.,107.,109.,111.,113.,115.ze směru Libčice nad Vltavou. |  |  |  |  | 2022-12-15
SZCZ | V-007958/20 | Děčín - Praha-Libeň | < > | Kralupy nad Vltavou | Kralupy nad Vltavou | 2023 | 2023 | 37 | 37 | 2023-09-15 | 0:00 | 2023-09-16 | 0:00 | 2 days | Continuous | Catenary |  | ST | [8 empty] | zhlaví střední kolejí 105.,107.,109.,111.,113.,115.. |  |  |  |  | 2022-12-15
SZCZ | V-007957/20 | Děčín - Praha-Libeň | < > | Kralupy nad Vltavou | Kralupy nad Vltavou | 2023 | 2023 | 37 | 37 | 2023-09-13 | 0:00 | 2023-09-14 | 0:00 | 2 days | Continuous | Catenary |  | ST | [8 empty] | zhlaví kolejí 105.,107.,109.,111.,113.,115.ze směru Libčice nad Vltavou. |  |  |  |  | 2022-12-15
SZCZ | V-007957/20 | Děčín - Praha-Libeň | < > | Kralupy nad Vltavou | Kralupy nad Vltavou | 2023 | 2023 | 37 | 37 | 2023-09-13 | 0:00 | 2023-09-14 | 0:00 | 2 days | Continuous | Catenary |  | ST | [8 empty] | zhlaví střední kolejí 105.,107.,109.,111.,113.,115.. |  |  |  |  | 2022-12-15
SZCZ | V-007955/20 | Děčín - Praha-Libeň | < > | Kralupy nad Vltavou | Kralupy nad Vltavou | 2023 | 2023 | 37 | 37 | 2023-09-11 | 0:00 | 2023-09-12 | 0:00 | 2 days | Continuous | Catenary |  | ST | [8 empty] | zhlaví kolejí 105.,107.,109.,111.,113.,115.ze směru Libčice nad Vltavou. |  |  |  |  | 2022-12-15
SZCZ | V-007955/20 | Děčín - Praha-Libeň | < > | Kralupy nad Vltavou | Kralupy nad Vltavou | 2023 | 2023 | 37 | 37 | 2023-09-11 | 0:00 | 2023-09-12 | 0:00 | 2 days | Continuous | Catenary |  | ST | [8 empty] | zhlaví střední kolejí 105.,107.,109.,111.,113.,115.. |  |  |  |  | 2022-12-15
SZCZ | V-007954/20 | Děčín - Praha-Libeň | < > | Kralupy nad Vltavou | Kralupy nad Vltavou | 2023 | 2023 | 36 | 36 | 2023-09-09 | 0:00 | 2023-09-10 | 0:00 | 2 days | Continuous | Catenary |  | ST | [8 empty] | zhlaví kolejí 105.,107.,109.,111.,113.,115.ze směru Libčice nad Vltavou. |  |  |  |  | 2022-12-15
SZCZ | V-007954/20 | Děčín - Praha-Libeň | < > | Kralupy nad Vltavou | Kralupy nad Vltavou | 2023 | 2023 | 36 | 36 | 2023-09-09 | 0:00 | 2023-09-10 | 0:00 | 2 days | Continuous | Catenary |  | ST | [8 empty] | zhlaví střední kolejí 105.,107.,109.,111.,113.,115.. |  |  |  |  | 2022-12-15
SZCZ | V-007953/20 | Děčín - Praha-Libeň | < > | Kralupy nad Vltavou | Kralupy nad Vltavou | 2023 | 2023 | 36 | 36 | 2023-09-07 | 0:00 | 2023-09-08 | 0:00 | 2 days | Continuous | Catenary |  | ST | [8 empty] | zhlaví kolejí 105.,107.,109.,111.,113.,115.ze směru Libčice nad Vltavou. |  |  |  |  | 2022-12-15
SZCZ | V-007953/20 | Děčín - Praha-Libeň | < > | Kralupy nad Vltavou | Kralupy nad Vltavou | 2023 | 2023 | 36 | 36 | 2023-09-07 | 0:00 | 2023-09-08 | 0:00 | 2 days | Continuous | Catenary |  | ST | [8 empty] | zhlaví střední kolejí 105.,107.,109.,111.,113.,115.. |  |  |  |  | 2022-12-15
SZCZ | V-007951/20 | Děčín - Praha-Libeň | < > | Kralupy nad Vltavou | Kralupy nad Vltavou | 2023 | 2023 | 35 | 35 | 2023-08-29 | 0:00 | 2023-08-31 | 0:00 | 3 days | Continuous | Catenary |  | ST | [8 empty] | zhlaví kolejí 105.,107.,109.,111.,113.,115.ze směru Libčice nad Vltavou. |  |  |  |  | 2022-12-15
SZCZ | V-007951/20 | Děčín - Praha-Libeň | < > | Kralupy nad Vltavou | Kralupy nad Vltavou | 2023 | 2023 | 35 | 35 | 2023-08-29 | 0:00 | 2023-08-31 | 0:00 | 3 days | Continuous | Catenary |  | ST | [8 empty] | zhlaví střední kolejí 105.,107.,109.,111.,113.,115.. |  |  |  |  | 2022-12-15
SZCZ | V-007950/22 | Děčín - Kolín | < > | Velké Žernoseky | Sebuzín | 2023 | 2023 | 35 | 35 | 2023-08-31 | 0:00 | 2023-09-03 | 0:00 | 4 days | Continuous | Track & Rail |  | LT | [8 empty] | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007950/20 | Děčín - Praha-Libeň | < > | Kralupy nad Vltavou | Kralupy nad Vltavou | 2023 | 2023 | 34 | 35 | 2023-08-27 | 0:00 | 2023-08-28 | 0:00 | 2 days | Continuous | Catenary |  | ST | [8 empty] | zhlaví kolejí 105.,107.,109.,111.,113.,115.ze směru Libčice nad Vltavou. |  |  |  |  | 2022-12-15
SZCZ | V-007950/20 | Děčín - Praha-Libeň | < > | Kralupy nad Vltavou | Kralupy nad Vltavou | 2023 | 2023 | 34 | 35 | 2023-08-27 | 0:00 | 2023-08-28 | 0:00 | 2 days | Continuous | Catenary |  | ST | [8 empty] | zhlaví střední kolejí 105.,107.,109.,111.,113.,115.. |  |  |  |  | 2022-12-15
SZCZ | V-007949/22 | Děčín - Kolín | < > | Sebuzín | Velké Žernoseky | 2023 | 2023 | 40 | 40 | 2023-10-02 | 0:00 | 2023-10-06 | 0:00 | 5 days | Continuous | Track & Rail |  | LT | [8 empty] | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007949/20 | Děčín - Praha-Libeň | < > | Kralupy nad Vltavou | Kralupy nad Vltavou | 2023 | 2023 | 34 | 34 | 2023-08-25 | 0:00 | 2023-08-26 | 0:00 | 2 days | Continuous | Catenary |  | ST | [8 empty] | zhlaví kolejí 105.,107.,109.,111.,113.,115.ze směru Libčice nad Vltavou. |  |  |  |  | 2022-12-15
SZCZ | V-007949/20 | Děčín - Praha-Libeň | < > | Kralupy nad Vltavou | Kralupy nad Vltavou | 2023 | 2023 | 34 | 34 | 2023-08-25 | 0:00 | 2023-08-26 | 0:00 | 2 days | Continuous | Catenary |  | ST | [8 empty] | zhlaví střední kolejí 105.,107.,109.,111.,113.,115.. |  |  |  |  | 2022-12-15
SZCZ | V-007948/22 | Děčín - Kolín | < > | Litoměřice dolní nádraží | Velké Žernoseky | 2023 | 2023 | 33 | 33 | 2023-08-16 | 0:00 | 2023-08-17 | 0:00 | 2 days | Continuous | Track & Rail |  | LT | [8 empty] | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007948/22 | Děčín - Kolín | < > | Litoměřice dolní nádraží | Litoměřice dolní nádraží | 2023 | 2023 | 33 | 33 | 2023-08-16 | 0:00 | 2023-08-17 | 0:00 | 2 days | Continuous | Track & Rail |  | ST | [8 empty] | sudá jen TV. záhlaví žernosecké 2. traťové koleje |  |  |  |  | 2022-12-15
SZCZ | V-007947/22 | Děčín - Kolín | < > | Polepy | Litoměřice dolní nádraží | 2023 | 2023 | 34 | 35 | 2023-08-26 | 0:00 | 2023-08-28 | 0:00 | 3 days | Continuous | Track & Rail |  | LT | [8 empty] | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007947/20 | Děčín - Praha-Libeň | < > | Kralupy nad Vltavou | Kralupy nad Vltavou | 2023 | 2023 | 33 | 33 | 2023-08-17 | 0:00 | 2023-08-18 | 0:00 | 2 days | Continuous | Catenary |  | ST | [8 empty] | zhlaví kolejí 117.,119.,121.,123.,125.,127.,129.,131.,133a ze směru Libčice nad Vltavou. |  |  |  |  | 2022-12-15
SZCZ | V-007947/20 | Děčín - Praha-Libeň | < > | Kralupy nad Vltavou | Kralupy nad Vltavou | 2023 | 2023 | 33 | 33 | 2023-08-17 | 0:00 | 2023-08-18 | 0:00 | 2 days | Continuous | Catenary |  | ST | [8 empty] | zhlaví střední kolejí 113.,115.,117.,119.,121.,123.,125.,127.,129.,131.,133b. |  |  |  |  | 2022-12-15
SZCZ | V-007946/22 | Děčín - Kolín | < > | Hoštka | Polepy | 2023 | 2023 | 34 | 34 | 2023-08-23 | 0:00 | 2023-08-25 | 0:00 | 3 days | Continuous | Track & Rail |  | LT | [8 empty] | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007946/20 | Děčín - Praha-Libeň | < > | Kralupy nad Vltavou | Kralupy nad Vltavou | 2023 | 2023 | 33 | 33 | 2023-08-15 | 0:00 | 2023-08-16 | 0:00 | 2 days | Continuous | Catenary |  | ST | [8 empty] | zhlaví kolejí 117.,119.,121.,123.,125.,127.,129.,131.,133a ze směru Libčice nad Vltavou. |  |  |  |  | 2022-12-15
SZCZ | V-007946/20 | Děčín - Praha-Libeň | < > | Kralupy nad Vltavou | Kralupy nad Vltavou | 2023 | 2023 | 33 | 33 | 2023-08-15 | 0:00 | 2023-08-16 | 0:00 | 2 days | Continuous | Catenary |  | ST | [8 empty] | zhlaví střední kolejí 113.,115.,117.,119.,121.,123.,125.,127.,129.,131.,133b. |  |  |  |  | 2022-12-15
SZCZ | V-007945/22 | Děčín - Kolín | < > | Štětí | Liběchov | 2023 | 2023 | 33 | 34 | 2023-08-20 | 0:00 | 2023-08-22 | 0:00 | 3 days | Continuous | Track & Rail |  | LT | [8 empty] | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007945/20 | Děčín - Praha-Libeň | < > | Kralupy nad Vltavou | Kralupy nad Vltavou | 2023 | 2023 | 32 | 33 | 2023-08-13 | 0:00 | 2023-08-14 | 0:00 | 2 days | Continuous | Catenary |  | ST | [8 empty] | zhlaví kolejí 117.,119.,121.,123.,125.,127.,129.,131.,133a ze směru Libčice nad Vltavou. |  |  |  |  | 2022-12-15
SZCZ | V-007945/20 | Děčín - Praha-Libeň | < > | Kralupy nad Vltavou | Kralupy nad Vltavou | 2023 | 2023 | 32 | 33 | 2023-08-13 | 0:00 | 2023-08-14 | 0:00 | 2 days | Continuous | Catenary |  | ST | [8 empty] | zhlaví střední kolejí 113.,115.,117.,119.,121.,123.,125.,127.,129.,131.,133b. |  |  |  |  | 2022-12-15
SZCZ | V-007944/20 | Děčín - Praha-Libeň | < > | Kralupy nad Vltavou | Kralupy nad Vltavou | 2023 | 2023 | 32 | 32 | 2023-08-11 | 0:00 | 2023-08-12 | 0:00 | 2 days | Continuous | Catenary |  | ST | [8 empty] | zhlaví kolejí 117.,119.,121.,123.,125.,127.,129.,131.,133a ze směru Libčice nad Vltavou. |  |  |  |  | 2022-12-15
SZCZ | V-007944/20 | Děčín - Praha-Libeň | < > | Kralupy nad Vltavou | Kralupy nad Vltavou | 2023 | 2023 | 32 | 32 | 2023-08-11 | 0:00 | 2023-08-12 | 0:00 | 2 days | Continuous | Catenary |  | ST | [8 empty] | zhlaví střední kolejí 113.,115.,117.,119.,121.,123.,125.,127.,129.,131.,133b. |  |  |  |  | 2022-12-15
SZCZ | V-007943/20 | Děčín - Praha-Libeň | < > | Kralupy nad Vltavou | Kralupy nad Vltavou | 2023 | 2023 | 32 | 32 | 2023-08-09 | 0:00 | 2023-08-10 | 0:00 | 2 days | Continuous | Catenary |  | ST | [8 empty] | zhlaví kolejí 117.,119.,121.,123.,125.,127.,129.,131.,133a ze směru Libčice nad Vltavou. |  |  |  |  | 2022-12-15
SZCZ | V-007943/20 | Děčín - Praha-Libeň | < > | Kralupy nad Vltavou | Kralupy nad Vltavou | 2023 | 2023 | 32 | 32 | 2023-08-09 | 0:00 | 2023-08-10 | 0:00 | 2 days | Continuous | Catenary |  | ST | [8 empty] | zhlaví střední kolejí 113.,115.,117.,119.,121.,123.,125.,127.,129.,131.,133b. |  |  |  |  | 2022-12-15
SZCZ | V-007942/20 | Děčín - Praha-Libeň | < > | Kralupy nad Vltavou | Kralupy nad Vltavou | 2023 | 2023 | 32 | 32 | 2023-08-07 | 0:00 | 2023-08-08 | 0:00 | 2 days | Continuous | Catenary |  | ST | [8 empty] | zhlaví kolejí 117.,119.,121.,123.,125.,127.,129.,131.,133a ze směru Libčice nad Vltavou. |  |  |  |  | 2022-12-15
SZCZ | V-007942/20 | Děčín - Praha-Libeň | < > | Kralupy nad Vltavou | Kralupy nad Vltavou | 2023 | 2023 | 32 | 32 | 2023-08-07 | 0:00 | 2023-08-08 | 0:00 | 2 days | Continuous | Catenary |  | ST | [8 empty] | zhlaví střední kolejí 113.,115.,117.,119.,121.,123.,125.,127.,129.,131.,133b. |  |  |  |  | 2022-12-15
SZCZ | V-007941/20 | Děčín - Praha-Libeň | < > | Kralupy nad Vltavou | Kralupy nad Vltavou | 2023 | 2023 | 31 | 31 | 2023-08-05 | 0:00 | 2023-08-06 | 0:00 | 2 days | Continuous | Catenary |  | ST | [8 empty] | zhlaví kolejí 117.,119.,121.,123.,125.,127.,129.,131.,133a ze směru Libčice nad Vltavou. |  |  |  |  | 2022-12-15
SZCZ | V-007941/20 | Děčín - Praha-Libeň | < > | Kralupy nad Vltavou | Kralupy nad Vltavou | 2023 | 2023 | 31 | 31 | 2023-08-05 | 0:00 | 2023-08-06 | 0:00 | 2 days | Continuous | Catenary |  | ST | [8 empty] | zhlaví střední kolejí 113.,115.,117.,119.,121.,123.,125.,127.,129.,131.,133b. |  |  |  |  | 2022-12-15
SZCZ | V-007940/20 | Děčín - Praha-Libeň | < > | Kralupy nad Vltavou | Kralupy nad Vltavou | 2023 | 2023 | 31 | 31 | 2023-08-03 | 0:00 | 2023-08-04 | 0:00 | 2 days | Continuous | Catenary |  | ST | [8 empty] | zhlaví kolejí 117.,119.,121.,123.,125.,127.,129.,131.,133a ze směru Libčice nad Vltavou. |  |  |  |  | 2022-12-15
SZCZ | V-007940/20 | Děčín - Praha-Libeň | < > | Kralupy nad Vltavou | Kralupy nad Vltavou | 2023 | 2023 | 31 | 31 | 2023-08-03 | 0:00 | 2023-08-04 | 0:00 | 2 days | Continuous | Catenary |  | ST | [8 empty] | zhlaví střední kolejí 113.,115.,117.,119.,121.,123.,125.,127.,129.,131.,133b. |  |  |  |  | 2022-12-15
SZCZ | V-007939/20 | Děčín - Praha-Libeň | < > | Kralupy nad Vltavou | Kralupy nad Vltavou | 2023 | 2023 | 31 | 31 | 2023-08-01 | 0:00 | 2023-08-02 | 0:00 | 2 days | Continuous | Catenary |  | ST | [8 empty] | zhlaví kolejí 117.,119.,121.,123.,125.,127.,129.,131.,133a ze směru Libčice nad Vltavou. |  |  |  |  | 2022-12-15
SZCZ | V-007939/20 | Děčín - Praha-Libeň | < > | Kralupy nad Vltavou | Kralupy nad Vltavou | 2023 | 2023 | 31 | 31 | 2023-08-01 | 0:00 | 2023-08-02 | 0:00 | 2 days | Continuous | Catenary |  | ST | [8 empty] | zhlaví střední kolejí 113.,115.,117.,119.,121.,123.,125.,127.,129.,131.,133b. |  |  |  |  | 2022-12-15
SZCZ | V-007928/22 | Děčín - Kolín | < > | Ústí nad Labem-Střekov | Velké Březno | 2023 | 2023 | 30 | 30 | 2023-07-26 | 0:00 | 2023-07-29 | 0:00 | 4 days | Continuous | Switch |  | LT | [8 empty] | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007920/22 | Děčín - Kolín | < > | Velké Březno | Ústí nad Labem-Střekov | 2023 | 2023 | 30 | 30 | 2023-07-24 | 0:00 | 2023-07-26 | 0:00 | 3 days | Continuous | Switch |  | LT | [8 empty] | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007905/22 | Děčín - Kolín | < > | Boletice nad Labem | Děčín východ | 2023 | 2023 | 25 | 25 | 2023-06-19 | 0:00 | 2023-06-21 | 0:00 | 3 days | Continuous | Track & Rail |  | LT | [8 empty] | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007904/22 | Děčín - Kolín | < > | Děčín východ | Boletice nad Labem | 2023 | 2023 | 24 | 24 | 2023-06-15 | 0:00 | 2023-06-17 | 0:00 | 3 days | Continuous | Track & Rail |  | LT | [8 empty] | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007903/22 | Děčín - Kolín | < > | Ústí nad Labem západ | Ústí nad Labem-Střekov | 2023 | 2023 | 24 | 24 | 2023-06-12 | 0:00 | 2023-06-14 | 0:00 | 3 days | Continuous | Track & Rail |  | LT | [8 empty] | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-007517/22 | Kolín - Brno-Maloměřice | < > | Řikonín | Vlkov u Tišnova | 2023 | 2023 | 26 | 28 | 2023-07-01 | 0:00 | 2023-07-14 | 0:00 | 14 days | Continuous | Signal |  | LT | [5 empty] | , X, X |  |  | zab. zař. TZZ. |  |  |  |  | 2022-12-15
SZCZ | V-007517/22 | Kolín - Brno-Maloměřice | < > | Vlkov u Tišnova | Vlkov u Tišnova | 2023 | 2023 | 26 | 28 | 2023-07-01 | 0:00 | 2023-07-14 | 0:00 | 14 days | Continuous | Signal |  | ST | [5 empty] | , X, X |  |  | zab. zař. SZZ celá. |  |  |  |  | 2022-12-15
SZCZ | V-007517/22 | Kolín - Brno-Maloměřice | < > | Vlkov u Tišnova | Křižanov | 2023 | 2023 | 26 | 28 | 2023-07-01 | 0:00 | 2023-07-14 | 0:00 | 14 days | Continuous | Signal |  | LT | [5 empty] | , X, X |  |  | zab. zař. TZZ. |  |  |  |  | 2022-12-15
SZCZ | V-019653/20 | Brno - Břeclav | < > | Brno hlavní nádraží | Brno-Černovice odb. | 2023 | 2023 | 12 | 13 | 2023-03-24 | 0:00 | 2023-03-30 | 0:00 | 7 days | Continuous | Track & Rail | T | LT | [8 empty] | traťová + TV. záhlaví Odb.Brno-Černovice od náv.BS po IS za výh.6 |  |  |  |  | 2022-12-15
SZCZ | V-019238/21 | Praha-Libeň - Česká Třebová | < > | Česká Třebová | Parník odb. | 2023 | 2023 | 38 | 39 | 2023-09-23 | 0:00 | 2023-09-27 | 0:00 | 5 days | Continuous | Track & Rail |  | LT | [8 empty] | 2. bez TV. |  |  |  |  | 2022-12-15
SZCZ | V-019238/21 | Praha-Libeň - Česká Třebová | < > | Česká Třebová | Parník odb. | 2023 | 2023 | 38 | 39 | 2023-09-23 | 0:00 | 2023-09-27 | 0:00 | 5 days | Continuous | Track & Rail |  | LT | [8 empty] | 2. jen TV. |  |  |  |  | 2022-12-15
SZCZ | V-019237/21 | Praha-Libeň - Česká Třebová | < > | Česká Třebová | Parník odb. | 2023 | 2023 | 38 | 38 | 2023-09-18 | 0:00 | 2023-09-22 | 0:00 | 5 days | Continuous | Track & Rail |  | LT | [8 empty] | 1. bez TV. |  |  |  |  | 2022-12-15
SZCZ | V-019237/21 | Praha-Libeň - Česká Třebová | < > | Česká Třebová | Parník odb. | 2023 | 2023 | 38 | 38 | 2023-09-18 | 0:00 | 2023-09-22 | 0:00 | 5 days | Continuous | Track & Rail |  | LT | [8 empty] | 1. jen TV. |  |  |  |  | 2022-12-15
SZCZ | V-009468/21 | Praha-Libeň - Česká Třebová | < > | Odb Bezpráví | Odb Bezpráví | 2023 | 2023 | 15 | 15 | 2023-04-11 18:00 | 0:00 | 2023-04-12 06:00 | 0:00 | 1 x 8 hours | Periodical | Track & Rail |  | ST | [5 empty] | , X, X |  |  | záhlaví 2. TK směr Ústí nad Orlicí od LIS v km 261,265 po náv. S2 |  |  |  |  | 2022-12-15
SZCZ | V-009468/21 | Praha-Libeň - Česká Třebová | < > | Brandýs nad Orlicí | Brandýs nad Orlicí | 2023 | 2023 | 15 | 15 | 2023-04-11 18:00 | 0:00 | 2023-04-12 06:00 | 0:00 | 1 x 8 hours | Periodical | Track & Rail |  | ST | [5 empty] | , X, X |  |  | záhlaví 2. TK směr Bezpráví |  |  |  |  | 2022-12-15
SZCZ | V-009467/21 | Praha-Libeň - Česká Třebová | < > | Odb Bezpráví | Odb Bezpráví | 2023 | 2023 | 10 | 10 | 2023-03-07 18:00 | 0:00 | 2023-03-08 06:00 | 0:00 | 1 x 12 hours | Periodical | Track & Rail |  | ST | [5 empty] | , X, X |  |  | záhlaví 2. TK směr Ústí nad Orlicí, záhlaví 2. TK směr Brandýs nad Orlicí |  |  |  |  | 2022-12-15
SZCZ | V-009466/21 | Praha-Libeň - Česká Třebová | < > | Odb Bezpráví | Odb Bezpráví | 2023 | 2023 | 5 | 5 | 2023-01-31 18:00 | 0:00 | 2023-02-01 06:00 | 0:00 | 1 x 8 hours | Periodical | Track & Rail |  | ST | [5 empty] | , X, X |  |  | záhlaví 2. TK směr Ústí nad Orlicí od náv. 2L po LIS v km 261,265 |  |  |  |  | 2022-12-15
SZCZ | V-009464/21 | Praha-Libeň - Česká Třebová | < > | Brandýs nad Orlicí | Brandýs nad Orlicí | 2023 | 2023 | 14 | 14 | 2023-04-03 | 0:00 | 2023-04-04 | 0:00 | 2 x 12 hours | Periodical | Miscellaneous |  | ST | [8 empty] | zhlaví 1. TK směr Bezpráví. |  |  |  |  | 2022-12-15
SZCZ | V-009463/21 | Praha-Libeň - Česká Třebová | < > | Brandýs nad Orlicí | Brandýs nad Orlicí | 2023 | 2023 | 12 | 12 | 2023-03-22 | 0:00 | 2023-03-23 | 0:00 | 2 days | Continuous | Miscellaneous |  | ST | [8 empty] | zhlaví 1. TK směr Bezpráví. |  |  |  |  | 2022-12-15
SZCZ | V-009462/21 | Praha-Libeň - Česká Třebová | < > | Brandýs nad Orlicí | Brandýs nad Orlicí | 2023 | 2023 | 11 | 11 | 2023-03-15 | 0:00 | 2023-03-17 | 0:00 | 3 days | Continuous | Miscellaneous |  | ST | [8 empty] | zhlaví 1. TK směr Bezpráví. |  |  |  |  | 2022-12-15
SZCZ | V-009459/21 | Praha-Libeň - Česká Třebová | < > | Odb Bezpráví | Odb Bezpráví | 2023 | 2023 | 14 | 15 | 2023-04-09 | 0:00 | 2023-04-11 | 0:00 | 3 x 12 hours | Periodical | Miscellaneous |  | ST | [5 empty] | , X, X |  |  | záhlaví 1. TK směr Ústí n. O. od náv. S1 po náv. 1L |  |  |  |  | 2022-12-15
SZCZ | V-006704/22 | Česká Třebová - Brno | < > | Brno-Maloměřice | Letovice | 2023 | 2023 | 14 | 16 | 2023-04-03 | 0:00 | 2023-04-20 | 0:00 | 8 x 7 hours | Periodical | Maintenance |  | LT | [13 empty] | 2022-12-15
SZCZ | V-006708/22 | Česká Třebová - Brno | < > | Brno-Maloměřice | Letovice | 2023 | 2023 | 19 | 38 | 2023-05-09 | 0:00 | 2023-09-21 | 0:00 | 43 x 7 hours | Periodical | Maintenance |  | LT | [13 empty] | 2022-12-15
SZCZ | V-006716/22 | Břeclav - Kúty | < > | Lanžhot st.hr. | Břeclav | 2023 | 2023 | 37 | 42 | 2023-09-11 | 0:00 | 2023-10-19 | 0:00 | 20 x 7 hours | Periodical | Maintenance |  | LT | [13 empty] | 2022-12-15
SZCZ | V-006732/22 | Brno - Břeclav | < > | Popice | Modřice | 2023 | 2023 | 40 | 40 | 2023-10-02 | 0:00 | 2023-10-05 | 0:00 | 20 x 7 hours | Periodical | Maintenance |  | LT | [13 empty] | 2022-12-15
SZCZ | V-006739/22 | Česká Třebová - Brno | < > | Letovice | Svitavy | 2023 | 2023 | 41 | 41 | 2023-10-09 | 0:00 | 2023-10-11 | 0:00 | 3 x 7 hours | Periodical | Maintenance |  | LT | [13 empty] | 2022-12-15
SZCZ | V-009457/21 | Praha-Libeň - Česká Třebová | < > | Odb Bezpráví | Odb Bezpráví | 2023 | 2023 | 12 | 13 | 2023-03-26 | 0:00 | 2023-03-27 | 0:00 | 2 x 12 hours | Periodical | Miscellaneous |  | ST | [5 empty] | , X, X |  |  | záhlaví 1. TK směr Ústí n. O. od náv. S1 po náv. 1L |  |  |  |  | 2022-12-15
SZCZ | V-009456/21 | Praha-Libeň - Česká Třebová | < > | Odb Bezpráví | Odb Bezpráví | 2023 | 2023 | 12 | 12 | 2023-03-20 | 0:00 | 2023-03-21 | 0:00 | 2 days | Continuous | Miscellaneous |  | ST | [5 empty] | , X, X |  |  | záhlaví 1. TK směr Ústí n. O. od náv. S1 po náv. 1L |  |  |  |  | 2022-12-15
SZCZ | V-009455/21 | Praha-Libeň - Česká Třebová | < > | Odb Bezpráví | Odb Bezpráví | 2023 | 2023 | 10 | 10 | 2023-03-10 | 0:00 | 2023-03-11 | 0:00 | 2 days | Continuous | Miscellaneous |  | ST | [5 empty] | , X, X |  |  | záhlaví 1. TK směr Ústí n. O. od náv. S1 po náv. 1L |  |  |  |  | 2022-12-15
SZCZ | V-009453/21 | Praha-Libeň - Česká Třebová | < > | Brandýs nad Orlicí | Brandýs nad Orlicí | 2023 | 2023 | 24 | 24 | 2023-06-12 | 0:00 | 2023-06-13 | 0:00 | 2 x 12 hours | Periodical | Miscellaneous |  | ST | [8 empty] | zhlaví 2. TK směr Bezpráví. |  |  |  |  | 2022-12-15
SZCZ | V-009452/21 | Praha-Libeň - Česká Třebová | < > | Brandýs nad Orlicí | Brandýs nad Orlicí | 2023 | 2023 | 22 | 22 | 2023-05-31 | 0:00 | 2023-06-01 | 0:00 | 2 days | Continuous | Miscellaneous |  | ST | [8 empty] | zhlaví 2. TK směr Bezpráví. |  |  |  |  | 2022-12-15
SZCZ | V-005647/22 | Česká Třebová - Brno | < > | Adamov | Blansko | 2023 | 2023 | 13 | 13 | 2023-04-01 | 0:00 | 2023-04-02 | 0:00 | 2 days | Continuous | Miscellaneous |  | LT | [5 empty] | , X, X |  |  | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-005647/22 | Česká Třebová - Brno | < > | Brno-Maloměřice stavědlo 6 | Adamov | 2023 | 2023 | 13 | 13 | 2023-04-01 | 0:00 | 2023-04-02 | 0:00 | 2 days | Continuous | Miscellaneous |  | LT | [5 empty] | , X, X |  |  | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-005647/22 | Česká Třebová - Brno | < > | Adamov | Adamov | 2023 | 2023 | 13 | 13 | 2023-04-01 | 0:00 | 2023-04-02 | 0:00 | 2 days | Continuous | Miscellaneous |  | ST | [5 empty] | , X, X |  |  | sudá + TV. |  |  |  |  | 2022-12-15
SZCZ | V-005623/22 | Česká Třebová - Brno | < > | Blansko | Adamov | 2023 | 2023 | 12 | 12 | 2023-03-25 | 0:00 | 2023-03-26 | 0:00 | 2 days | Continuous | Miscellaneous |  | LT | [5 empty] | , X, X |  |  | 1 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-005608/22 | Česká Třebová - Brno | < > | Adamov | Adamov | 2023 | 2023 | 12 | 13 | 2023-03-25 | 0:00 | 2023-03-31 | 0:00 | 7 days | Continuous | Miscellaneous |  | ST | [5 empty] | , X, X |  |  | lichá + TV. |  |  |  |  | 2022-12-15
SZCZ | V-005594/22 | Česká Třebová - Brno | < > | Adamov | Adamov | 2023 | 2023 | 13 | 14 | 2023-04-01 | 0:00 | 2023-04-05 | 0:00 | 5 days | Continuous | Miscellaneous |  | ST | [5 empty] | , X, X |  |  | sudá + TV. |  |  |  |  | 2022-12-15
SZCZ | V-005572/22 | Česká Třebová - Brno | < > | Adamov | Adamov | 2023 | 2023 | 12 | 12 | 2023-03-24 | 0:00 | 2023-03-26 | 0:00 | 3 days | Continuous | Miscellaneous |  | ST | [5 empty] | , X, X |  |  | lichá + TV. |  |  |  |  | 2022-12-15
SZCZ | V-005571/22 | Česká Třebová - Brno | < > | Adamov | Brno-Maloměřice stavědlo 6 | 2023 | 2023 | 10 | 11 | 2023-03-10 | 0:00 | 2023-03-14 | 0:00 | 5 days | Continuous | Miscellaneous |  | LT | [8 empty] | 1 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-005570/22 | Česká Třebová - Brno | < > | Adamov | Adamov | 2023 | 2023 | 11 | 12 | 2023-03-19 | 0:00 | 2023-03-21 | 0:00 | 3 days | Continuous | Miscellaneous |  | ST | [5 empty] | , X, X |  |  | sudá + TV. |  |  |  |  | 2022-12-15
SZCZ | V-005569/22 | Česká Třebová - Brno | < > | Brno-Maloměřice stavědlo 6 | Adamov | 2023 | 2023 | 9 | 10 | 2023-03-03 | 0:00 | 2023-03-07 | 0:00 | 5 days | Continuous | Miscellaneous |  | LT | [8 empty] | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-005568/22 | Česká Třebová - Brno | < > | Adamov | Adamov | 2023 | 2023 | 16 | 16 | 2023-04-18 | 0:00 | 2023-04-19 | 0:00 | 2 days | Continuous | Miscellaneous |  | ST | [5 empty] | , X, X |  |  | sudá + TV. |  |  |  |  | 2022-12-15
SZCZ | V-005566/22 | Česká Třebová - Brno | < > | Adamov | Blansko | 2023 | 2023 | 15 | 16 | 2023-04-13 | 0:00 | 2023-04-19 | 0:00 | 7 days | Continuous | Miscellaneous |  | LT | [5 empty] | , X, X |  |  | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-005566/22 | Česká Třebová - Brno | < > | Blansko | Blansko | 2023 | 2023 | 15 | 16 | 2023-04-13 | 0:00 | 2023-04-19 | 0:00 | 7 days | Continuous | Miscellaneous |  | ST | [5 empty] | , X, X |  |  | sudá + TV. |  |  |  |  | 2022-12-15
SZCZ | V-006970/22 | Brno - Břeclav | < > | Brno hlavní nádraží | Brno-Židenice | 2023 | 2023 | 17 | 17 | 2023-04-29 | 0:00 | 2023-04-29 | 0:00 | 1 x 5 hours | Periodical | Track & Rail |  | LT | [8 empty] | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-006970/22 | Brno - Břeclav | < > | Brno-Židenice | Brno-Židenice | 2023 | 2023 | 17 | 17 | 2023-04-29 | 0:00 | 2023-04-29 | 0:00 | 1 x 5 hours | Periodical | Track & Rail |  | ST | [8 empty] | zhlaví severní koleje číslo 905. |  |  |  |  | 2022-12-15
SZCZ | V-006969/22 | Brno - Břeclav | < > | Brno-Židenice | Brno hlavní nádraží | 2023 | 2023 | 17 | 17 | 2023-04-29 | 0:00 | 2023-04-29 | 0:00 | 1 x 3 hours | Periodical | Track & Rail |  | LT | [8 empty] | 1 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-004538/22 | Brno - Břeclav | < > | Vranovice | Pohořelice | 2023 | 2023 | 27 | 32 | 2023-07-07 | 0:00 | 2023-08-10 | 0:00 | 35 days | Continuous | Track & Rail | T | LT | [8 empty] | traťová bez TV. |  |  |  |  | 2022-12-15
SZCZ | V-004481/22 | Brno - Břeclav | < > | Vranovice | Šakvice | 2023 | 2023 | 19 | 20 | 2023-05-09 | 0:00 | 2023-05-18 | 0:00 | 10 days | Continuous | Track & Rail |  | LT | [8 empty] | 1 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-004323/22 | Praha-Libeň - Česká Třebová | < > | Přelouč nákladní nádraží | Přelouč nákladní nádraží | 2023 | 2023 | 28 | 29 | 2023-07-10 | 0:00 | 2023-07-21 | 0:00 | 12 days | Continuous | Track & Rail |  | ST | [5 empty] | , X, X |  |  | traťová bez TV. záhlaví směr Choltice |  |  |  |  | 2022-12-15
SZCZ | V-004176/22 | Kolín - Brno-Maloměřice | < > | Tišnov | Tišnov | 2023 | 2023 | 13 | 17 | 2023-03-31 | 0:00 | 2023-04-28 | 0:00 | 29 days | Continuous | Track & Rail |  | ST | [5 empty] | , X, X |  |  | záhlaví ze směru Nedvědice |  |  |  |  | 2022-12-15
SZCZ | V-003942/22 | Praha-Libeň - Česká Třebová | < > | Újezd u Chocně | Choceň | 2023 | 2023 | 25 | 25 | 2023-06-20 | 0:00 | 2023-06-22 | 0:00 | 3 days | Continuous | Signal |  | LT | [8 empty] | zab. zař. TZZ mezi dopravnami. |  |  |  |  | 2022-12-15
SZCZ | V-002881/22 | Kolín - Brno-Maloměřice | < > | Golčův Jeníkov | Sázavka | 2023 | 2023 | 17 | 17 | 2023-04-26 | 0:00 | 2023-04-27 | 0:00 | 4 x 7 hours | Periodical | Catenary |  | LT | [13 empty] | 2022-12-15
SZCZ | V-002889/22 | Kolín - Brno-Maloměřice | < > | Golčův Jeníkov | Sázavka | 2023 | 2023 | 41 | 41 | 2023-10-11 | 0:00 | 2023-10-12 | 0:00 | 4 x 7 hours | Periodical | Catenary |  | LT | [13 empty] | 2022-12-15
SZCZ | V-002887/22 | Kolín - Brno-Maloměřice | < > | Ostrov nad Oslavou | Vlkov u Tišnova | 2023 | 2023 | 21 | 21 | 2023-05-24 | 0:00 | 2023-05-25 | 0:00 | 4 x 7 hours | Periodical | Catenary |  | LT | [13 empty] | 2022-12-15
SZCZ | V-001898/22 | Děčín - Kolín | < > | Stará Boleslav | Stará Boleslav | 2023 | 2023 | 23 | 23 | 2023-06-05 | 0:00 | 2023-06-11 | 0:00 | 7 x 10 hours | Periodical | Catenary |  | ST | [8 empty] | záhlaví 1.TK ve směru Dřísy |  |  |  |  | 2022-12-15
SZCZ | V-001905/22 | Děčín - Kolín | < > | Stará Boleslav | Stará Boleslav | 2023 | 2023 | 25 | 26 | 2023-06-19 | 0:00 | 2023-06-29 | 0:00 | 11 x 10 hours | Periodical | Catenary |  | ST | [8 empty] | záhlaví 1.TK ve směru Dřísy |  |  |  |  | 2022-12-15
SZCZ | V-001895/22 | Děčín - Kolín | < > | Dřísy | Stará Boleslav | 2023 | 2023 | 22 | 23 | 2023-06-03 | 0:00 | 2023-06-11 | 0:00 | 9 x 10 hours | Periodical | Catenary |  | LT | [8 empty] | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-001905/22 | Děčín - Kolín | < > | Dřísy | Stará Boleslav | 2023 | 2023 | 25 | 26 | 2023-06-19 | 0:00 | 2023-06-29 | 0:00 | 11 x 10 hours | Periodical | Catenary |  | LT | [8 empty] | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-001895/22 | Děčín - Kolín | < > | Stará Boleslav | Stará Boleslav | 2023 | 2023 | 22 | 22 | 2023-06-03 | 0:00 | 2023-06-04 | 0:00 | 2 x 10 hours | Periodical | Catenary |  | ST | [8 empty] | lichá jen TV. záhlaví 1.TK ve směru Dřísy |  |  |  |  | 2022-12-15
SZCZ | V-001674/22 | Děčín - Kolín | < > | Stará Boleslav | Dřísy | 2023 | 2023 | 18 | 19 | 2023-05-02 | 0:00 | 2023-05-10 | 0:00 | 9 x 10 hours | Periodical | Catenary |  | LT | [8 empty] | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-001681/22 | Děčín - Kolín | < > | Stará Boleslav | Dřísy | 2023 | 2023 | 20 | 21 | 2023-05-18 | 0:00 | 2023-05-28 | 0:00 | 11 x 10 hours | Periodical | Catenary |  | LT | [8 empty] | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-001891/22 | Děčín - Kolín | < > | Stará Boleslav | Stará Boleslav | 2023 | 2023 | 18 | 18 | 2023-05-02 | 0:00 | 2023-05-03 | 0:00 | 2 x 10 hours | Periodical | Catenary |  | ST | [8 empty] | sudá jen TV. záhlaví 2. TK ze směru Dřísy |  |  |  |  | 2022-12-15
SZCZ | V-001674/22 | Děčín - Kolín | < > | Stará Boleslav | Stará Boleslav | 2023 | 2023 | 18 | 19 | 2023-05-04 | 0:00 | 2023-05-10 | 0:00 | 7 x 10 hours | Periodical | Catenary |  | ST | [8 empty] | záhlaví 2. TK ze směru Dřísy |  |  |  |  | 2022-12-15
SZCZ | V-001681/22 | Děčín - Kolín | < > | Stará Boleslav | Stará Boleslav | 2023 | 2023 | 20 | 21 | 2023-05-18 | 0:00 | 2023-05-28 | 0:00 | 11 x 10 hours | Periodical | Catenary |  | ST | [8 empty] | záhlaví 2. TK ze směru Dřísy |  |  |  |  | 2022-12-15
SZCZ | V-001787/22 | Děčín - Kolín | < > | Dřísy | Všetaty | 2023 | 2023 | 13 | 14 | 2023-04-02 | 0:00 | 2023-04-03 | 0:00 | 2 x 10 hours | Periodical | Catenary |  | LT | [8 empty] | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-001872/22 | Děčín - Kolín | < > | Dřísy | Všetaty | 2023 | 2023 | 15 | 15 | 2023-04-14 | 0:00 | 2023-04-14 | 0:00 | 1 x 10 hours | Periodical | Catenary |  | LT | [8 empty] | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-001867/22 | Děčín - Kolín | < > | Dřísy | Dřísy | 2023 | 2023 | 27 | 28 | 2023-07-08 | 0:00 | 2023-07-12 | 0:00 | 5 x 10 hours | Periodical | Catenary |  | ST | [8 empty] | sudá jen TV. záhlaví a zhlaví směr S. Boleslav od 2L po S2, S4. |  |  |  |  | 2022-12-15
SZCZ | V-001864/22 | Děčín - Kolín | < > | Dřísy | Dřísy | 2023 | 2023 | 15 | 15 | 2023-04-13 | 0:00 | 2023-04-13 | 0:00 | 1 x 10 hours | Periodical | Catenary |  | ST | [8 empty] | sudá jen TV. záhlaví 2. TK ze směru S. Boleslav |  |  |  |  | 2022-12-15
SZCZ | V-001865/22 | Děčín - Kolín | < > | Dřísy | Dřísy | 2023 | 2023 | 19 | 19 | 2023-05-11 | 0:00 | 2023-05-12 | 0:00 | 2 x 10 hours | Periodical | Catenary |  | ST | [8 empty] | sudá jen TV. záhlaví 2. TK ze směru S. Boleslav |  |  |  |  | 2022-12-15
SZCZ | V-001864/22 | Děčín - Kolín | < > | Stará Boleslav | Dřísy | 2023 | 2023 | 15 | 15 | 2023-04-13 | 0:00 | 2023-04-13 | 0:00 | 1 x 10 hours | Periodical | Catenary |  | LT | [8 empty] | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-001865/22 | Děčín - Kolín | < > | Stará Boleslav | Dřísy | 2023 | 2023 | 19 | 19 | 2023-05-11 | 0:00 | 2023-05-12 | 0:00 | 2 x 10 hours | Periodical | Catenary |  | LT | [8 empty] | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-001861/22 | Děčín - Kolín | < > | Dřísy | Dřísy | 2023 | 2023 | 15 | 15 | 2023-04-12 | 0:00 | 2023-04-12 | 0:00 | 1 x 10 hours | Periodical | Catenary |  | ST | [8 empty] | lichá jen TV. záhlaví staroboleslavské navazující na 1.TK |  |  |  |  | 2022-12-15
SZCZ | V-001862/22 | Děčín - Kolín | < > | Dřísy | Dřísy | 2023 | 2023 | 24 | 24 | 2023-06-12 | 0:00 | 2023-06-13 | 0:00 | 2 x 10 hours | Periodical | Catenary |  | ST | [8 empty] | lichá jen TV. záhlaví staroboleslavské navazující na 1.TK |  |  |  |  | 2022-12-15
SZCZ | V-001861/22 | Děčín - Kolín | < > | Dřísy | Stará Boleslav | 2023 | 2023 | 15 | 15 | 2023-04-12 | 0:00 | 2023-04-12 | 0:00 | 1 x 10 hours | Periodical | Catenary |  | LT | [8 empty] | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-001862/22 | Děčín - Kolín | < > | Dřísy | Stará Boleslav | 2023 | 2023 | 24 | 24 | 2023-06-12 | 0:00 | 2023-06-13 | 0:00 | 2 x 10 hours | Periodical | Catenary |  | LT | [8 empty] | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-001784/22 | Děčín - Kolín | < > | Všetaty | Dřísy | 2023 | 2023 | 12 | 13 | 2023-03-26 | 0:00 | 2023-03-27 | 0:00 | 2 x 10 hours | Periodical | Catenary |  | LT | [8 empty] | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-002044/22 | Děčín - Kolín | < > | Dřísy | Dřísy | 2023 | 2023 | 36 | 36 | 2023-09-04 | 0:00 | 2023-09-06 | 0:00 | 3 days | Continuous | Catenary |  | ST | [8 empty] | zhlaví všetatské od námezníku výhybky č. 17 po náv.L2 a L4. |  |  |  |  | 2022-12-15
SZCZ | V-006852/22 | Česká Třebová - Brno | < > | Letovice | Březová nad Svitavou | 2023 | 2023 | 26 | 26 | 2023-06-26 | 0:00 | 2023-06-30 | 0:00 | 5 days | Continuous | Signal |  | LT | [8 empty] | zab. zař. PZS v km 208,487 (P6819), PZS v km 210,738 (P6822). |  |  |  |  | 2022-12-15
SZCZ | V-005421/22 | Děčín - Praha-Libeň | < > | Nelahozeves | Nelahozeves | 2023 | 2023 | 34 | 34 | 2023-08-24 | 0:00 | 2023-08-26 | 0:00 | 3 days | Continuous | Track & Rail |  | ST | [8 empty] | záhlaví vraňanské navazující na 1.TK Vraňany - Nelahozeves |  |  |  |  | 2022-12-15
SZCZ | V-005421/22 | Děčín - Praha-Libeň | < > | Nelahozeves | Vraňany | 2023 | 2023 | 34 | 34 | 2023-08-24 | 0:00 | 2023-08-26 | 0:00 | 3 days | Continuous | Track & Rail |  | LT | [8 empty] | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-005421/22 | Děčín - Praha-Libeň | < > | Vraňany | Vraňany | 2023 | 2023 | 34 | 34 | 2023-08-24 | 0:00 | 2023-08-26 | 0:00 | 3 days | Continuous | Track & Rail |  | ST | [8 empty] | záhlaví nelahozevské navazující na 1.TK Vraňany - Nelahozeves |  |  |  |  | 2022-12-15
SZCZ | V-005420/22 | Děčín - Praha-Libeň | < > | Nelahozeves | Nelahozeves | 2023 | 2023 | 34 | 34 | 2023-08-21 | 0:00 | 2023-08-23 | 0:00 | 3 days | Continuous | Track & Rail |  | ST | [8 empty] | záhlaví vraňanské navazující na 2.TK Nelahozeves - Vraňany |  |  |  |  | 2022-12-15
SZCZ | V-005420/22 | Děčín - Praha-Libeň | < > | Nelahozeves | Vraňany | 2023 | 2023 | 34 | 34 | 2023-08-21 | 0:00 | 2023-08-23 | 0:00 | 3 days | Continuous | Track & Rail |  | LT | [8 empty] | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-005420/22 | Děčín - Praha-Libeň | < > | Vraňany | Vraňany | 2023 | 2023 | 34 | 34 | 2023-08-21 | 0:00 | 2023-08-23 | 0:00 | 3 days | Continuous | Track & Rail |  | ST | [8 empty] | záhlaví nelahozevské navazující na 2.TK Nelahozeves - Vraňany |  |  |  |  | 2022-12-15
SZCZ | V-005416/22 | Děčín - Praha-Libeň | < > | Nelahozeves | Nelahozeves | 2023 | 2023 | 33 | 33 | 2023-08-16 | 0:00 | 2023-08-20 | 0:00 | 5 days | Continuous | Track & Rail |  | ST | [8 empty] | záhlaví kralupské navazující na 1.TK Nelahozeves - Kralupy nad Vltavou |  |  |  |  | 2022-12-15
SZCZ | V-005416/22 | Děčín - Praha-Libeň | < > | Nelahozeves | Kralupy nad Vltavou | 2023 | 2023 | 33 | 33 | 2023-08-16 | 0:00 | 2023-08-20 | 0:00 | 5 days | Continuous | Track & Rail |  | LT | [8 empty] | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-005416/22 | Děčín - Praha-Libeň | < > | Kralupy nad Vltavou | Kralupy nad Vltavou | 2023 | 2023 | 33 | 33 | 2023-08-16 | 0:00 | 2023-08-20 | 0:00 | 5 days | Continuous | Track & Rail |  | ST | [8 empty] | záhlaví nelahozevské navazující na 1.TK Nelahozeves - Kralupy nad Vltavou |  |  |  |  | 2022-12-15
SZCZ | V-002043/22 | Děčín - Kolín | < > | Dřísy | Všetaty | 2023 | 2023 | 35 | 36 | 2023-09-02 | 0:00 | 2023-09-04 | 0:00 | 3 days | Continuous | Catenary |  | LT | [8 empty] | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-002039/22 | Děčín - Kolín | < > | Dřísy | Dřísy | 2023 | 2023 | 37 | 37 | 2023-09-12 | 0:00 | 2023-09-14 | 0:00 | 3 days | Continuous | Catenary |  | ST | [8 empty] | zhlaví staroboleslavské od námezníku výh.č.1 po náv. S1 a S3. |  |  |  |  | 2022-12-15
SZCZ | V-005415/22 | Děčín - Praha-Libeň | < > | Nelahozeves | Nelahozeves | 2023 | 2023 | 32 | 33 | 2023-08-11 | 0:00 | 2023-08-15 | 0:00 | 5 days | Continuous | Track & Rail |  | ST | [8 empty] | záhlaví kralupské navazující na 2.TK Kralupy nad Vltavou - Nelahozeves |  |  |  |  | 2022-12-15
SZCZ | V-005415/22 | Děčín - Praha-Libeň | < > | Kralupy nad Vltavou | Nelahozeves | 2023 | 2023 | 32 | 33 | 2023-08-11 | 0:00 | 2023-08-15 | 0:00 | 5 days | Continuous | Track & Rail |  | LT | [8 empty] | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-005415/22 | Děčín - Praha-Libeň | < > | Kralupy nad Vltavou | Kralupy nad Vltavou | 2023 | 2023 | 32 | 33 | 2023-08-11 | 0:00 | 2023-08-15 | 0:00 | 5 days | Continuous | Track & Rail |  | ST | [8 empty] | záhlaví nelahozevské navazující na 2.TK Kralupy nad Vltavou - Nelahozeves |  |  |  |  | 2022-12-15
SZCZ | V-005391/22 | Děčín - Praha-Libeň | < > | Libčice nad Vltavou | Libčice nad Vltavou | 2023 | 2023 | 27 | 27 | 2023-07-03 | 0:00 | 2023-07-07 | 0:00 | 5 days | Continuous | Track & Rail |  | ST | [8 empty] | záhlaví kralupské navazující na 2.TK Libčice nad Vltavou - Kralupy nad Vltavou |  |  |  |  | 2022-12-15
SZCZ | V-005391/22 | Děčín - Praha-Libeň | < > | Libčice nad Vltavou | Kralupy nad Vltavou | 2023 | 2023 | 27 | 27 | 2023-07-03 | 0:00 | 2023-07-07 | 0:00 | 5 days | Continuous | Track & Rail |  | LT | [8 empty] | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-005391/22 | Děčín - Praha-Libeň | < > | Kralupy nad Vltavou | Kralupy nad Vltavou | 2023 | 2023 | 27 | 27 | 2023-07-03 | 0:00 | 2023-07-07 | 0:00 | 5 days | Continuous | Track & Rail |  | ST | [8 empty] | záhlaví libčické navazující na 2.TK Libčice nad Vltavou - Kralupy nad Vltavou |  |  |  |  | 2022-12-15
SZCZ | V-005384/22 | Děčín - Praha-Libeň | < > | Roztoky u Prahy | Roztoky u Prahy | 2023 | 2023 | 31 | 32 | 2023-08-05 | 0:00 | 2023-08-10 | 0:00 | 6 days | Continuous | Track & Rail |  | ST | [8 empty] | záhlaví libčické navazující na 1.TK Libčice nad Vltavou - Roztoky u Prahy |  |  |  |  | 2022-12-15
SZCZ | V-005384/22 | Děčín - Praha-Libeň | < > | Libčice nad Vltavou | Roztoky u Prahy | 2023 | 2023 | 31 | 32 | 2023-08-05 | 0:00 | 2023-08-10 | 0:00 | 6 days | Continuous | Track & Rail |  | LT | [8 empty] | 1 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-005384/22 | Děčín - Praha-Libeň | < > | Libčice nad Vltavou | Libčice nad Vltavou | 2023 | 2023 | 31 | 32 | 2023-08-05 | 0:00 | 2023-08-10 | 0:00 | 6 days | Continuous | Track & Rail |  | ST | [8 empty] | záhlaví roztocké navazující na 1.TK Libčice nad Vltavou - Roztoky u Prahy |  |  |  |  | 2022-12-15
SZCZ | V-002037/22 | Děčín - Kolín | < > | Všetaty | Dřísy | 2023 | 2023 | 36 | 36 | 2023-09-08 | 0:00 | 2023-09-10 | 0:00 | 3 days | Continuous | Catenary |  | LT | [8 empty] | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-001930/22 | Děčín - Kolín | < > | Dřísy | Dřísy | 2023 | 2023 | 36 | 37 | 2023-09-10 | 0:00 | 2023-09-12 | 0:00 | 3 days | Continuous | Catenary |  | ST | [8 empty] | zhlaví staroboleslavské od námezníku výh.č.1 po náv. S1 a S3. |  |  |  |  | 2022-12-15
SZCZ | V-001929/22 | Děčín - Kolín | < > | Dřísy | Stará Boleslav | 2023 | 2023 | 36 | 36 | 2023-09-07 | 0:00 | 2023-09-08 | 0:00 | 2 days | Continuous | Catenary |  | LT | [8 empty] | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-001750/22 | Děčín - Kolín | < > | Stará Boleslav | Dřísy | 2023 | 2023 | 35 | 35 | 2023-09-01 | 0:00 | 2023-09-02 | 0:00 | 2 days | Continuous | Catenary |  | LT | [8 empty] | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-006701/22 | Česká Třebová - Brno | < > | Brno-Maloměřice | Česká Třebová | 2023 | 2023 | 1 | 9 | 2023-01-01 | 0:00 | 2023-02-28 | 0:00 | 59 days | Continuous | Signal |  | LT | [8 empty] | zab. zař. ETCS mezi dopravnami. |  |  |  |  | 2022-12-15
SZCZ | V-006676/22 | Kolín - Brno-Maloměřice | < > | Kuřim | Brno-Královo Pole | 2023 | 2023 | 30 | 30 | 2023-07-30 | 0:00 | 2023-07-30 | 0:00 | 1 x 12 hours | Periodical | Track & Rail | T | LT | [5 empty] | , X, X |  |  | 1.,2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-006675/22 | Kolín - Brno-Maloměřice | < > | Brno-Královo Pole | Kuřim | 2023 | 2023 | 27 | 27 | 2023-07-08 18:00 | 0:00 | 2023-07-09 06:00 | 0:00 | 1 x 8 hours | Periodical | Track & Rail |  | LT |  |  | X | [5 empty] | 1. jen TV, 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-006675/22 | Kolín - Brno-Maloměřice | < > | Brno-Královo Pole | Kuřim | 2023 | 2023 | 27 | 27 | 2023-07-08 18:00 | 0:00 | 2023-07-09 06:00 | 0:00 | 1 x 8 hours | Periodical | Track & Rail |  | LT |  |  | X | [5 empty] | zab. zař. TZZ 1. a 2. traťové koleje mezi dopravnami. |  |  |  |  | 2022-12-15
SZCZ | V-006674/22 | Kolín - Brno-Maloměřice | < > | Brno-Královo Pole | Kuřim | 2023 | 2023 | 26 | 27 | 2023-07-01 | 0:00 | 2023-07-05 | 0:00 | 5 days | Continuous | Track & Rail |  | LT | [8 empty] | 2. bez TV. |  |  |  |  | 2022-12-15
SZCZ | V-006645/21 | Praha-Libeň - Česká Třebová | < > | Přelouč nákladní nádraží | Pardubice hlavní nádraží | 2023 | 2023 | 23 | 24 | 2023-06-10 | 0:00 | 2023-06-12 | 0:00 | 3 days | Continuous | Signal |  | LT | [8 empty] | zab. zař. TZZ v 2. traťové koleji mezi dopravnami . |  |  |  |  | 2022-12-15
SZCZ | V-001740/22 | Děčín - Kolín | < > | Stará Boleslav | Dřísy | 2023 | 2023 | 32 | 32 | 2023-08-07 18:00 | 0:00 | 2023-08-08 06:00 | 0:00 | 1 x 5 hours | Periodical | Catenary | T | LT | [8 empty] | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-006644/21 | Praha-Libeň - Česká Třebová | < > | Přelouč nákladní nádraží | Pardubice hlavní nádraží | 2023 | 2023 | 23 | 23 | 2023-06-07 | 0:00 | 2023-06-09 | 0:00 | 3 days | Continuous | Signal |  | LT | [8 empty] | zab. zař. TZZ v 1. traťové koleji mezi dopravnami . |  |  |  |  | 2022-12-15
SZCZ | V-006447/22 | Dresden - Děčín | < > | Děčín východ | Děčín-Prostřední Žleb | 2023 | 2023 | 42 | 42 | 2023-10-21 | 0:00 | 2023-10-22 | 0:00 | 2 x 10 hours | Periodical | Track & Rail | T | LT | [8 empty] | traťová + TV. |  |  |  |  | 2022-12-15
SZCZ | V-006300/22 | Kolín - Brno-Maloměřice | < > | Šlapanov | Havlíčkův Brod | 2023 | 2023 | 6 | 6 | 2023-02-11 | 0:00 | 2023-02-12 | 0:00 | 2 x 7 hours | Periodical | Catenary | T | LT | [5 empty] | , X, X |  |  | traťová + TV. |  |  |  |  | 2022-12-15
SZCZ | V-006248/22 | Praha-Libeň - Česká Třebová | < > | Moravany | Uhersko | 2023 | 2023 | 21 | 21 | 2023-05-25 | 0:00 | 2023-05-27 | 0:00 | 3 days | Continuous | Signal |  | LT | [8 empty] | zab. zař. TZZ v 2. traťové koleji mezi dopravnami . |  |  |  |  | 2022-12-15
SZCZ | V-006245/22 | Praha-Libeň - Česká Třebová | < > | Moravany | Uhersko | 2023 | 2023 | 21 | 21 | 2023-05-22 | 0:00 | 2023-05-24 | 0:00 | 3 days | Continuous | Signal |  | LT | [8 empty] | zab. zař. TZZ v 1. traťové koleji mezi dopravnami . |  |  |  |  | 2022-12-15
SZCZ | V-006243/22 | Praha-Libeň - Česká Třebová | < > | Kostěnice | Moravany | 2023 | 2023 | 20 | 20 | 2023-05-18 | 0:00 | 2023-05-20 | 0:00 | 3 days | Continuous | Signal |  | LT | [8 empty] | zab. zař. TZZ v 2. traťové koleji mezi dopravnami . |  |  |  |  | 2022-12-15
SZCZ | V-006240/22 | Praha-Libeň - Česká Třebová | < > | Kostěnice | Moravany | 2023 | 2023 | 20 | 20 | 2023-05-15 | 0:00 | 2023-05-17 | 0:00 | 3 days | Continuous | Signal |  | LT | [8 empty] | zab. zař. TZZ v 1. traťové koleji mezi dopravnami . |  |  |  |  | 2022-12-15
SZCZ | V-001699/22 | Děčín - Kolín | < > | Dřísy | Stará Boleslav | 2023 | 2023 | 31 | 33 | 2023-08-01 | 0:00 | 2023-08-16 | 0:00 | 16 days | Continuous | Catenary |  | LT | [8 empty] | 1. + TV. záhlaví záhlaví 1TK ze směru Dřísy v ŽST S. Boleslav; záhlaví a zhlaví 1TK ze směru S. Boleslav v ŽST Dřísy |  |  |  |  | 2022-12-15
SZCZ | V-001694/22 | Děčín - Kolín | < > | Stará Boleslav | Dřísy | 2023 | 2023 | 27 | 29 | 2023-07-04 | 0:00 | 2023-07-19 | 0:00 | 16 days | Continuous | Catenary |  | LT | [8 empty] | 2. + TV. záhlaví záhlaví 2TK ze směru Dřísy v ŽST S. Boleslav; záhlaví a zhlaví 2TK ze směru S. Boleslav v ŽST Dřísy |  |  |  |  | 2022-12-15
SZCZ | V-006194/22 | Břeclav - Kúty | < > | Lanžhot st.hr. | Lanžhot | 2023 | 2023 | 1 | 24 | 2023-01-01 | 0:00 | 2023-06-16 | 0:00 | 167 days | Continuous | Miscellaneous |  | LT | [8 empty] | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-006165/22 | Brno - Břeclav | < > | Brno-Maloměřice stavědlo 3 | Brno-Židenice | 2023 | 2023 | 8 | 8 | 2023-02-21 18:00 | 0:00 | 2023-02-22 06:00 | 0:00 | 1 x 3 hours | Periodical | Catenary |  | LT | [8 empty] | 1K,2K + TV. |  |  |  |  | 2022-12-15
SZCZ | V-006165/22 | Česká Třebová - Brno | < > | Brno-Maloměřice stavědlo 6 | Brno-Židenice | 2023 | 2023 | 8 | 8 | 2023-02-21 18:00 | 0:00 | 2023-02-22 06:00 | 0:00 | 1 x 3 hours | Periodical | Catenary |  | LT | [8 empty] | 1.,2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-006161/22 | Brno - Břeclav | < > | Brno-Maloměřice stavědlo 3 | Brno-Židenice | 2023 | 2023 | 7 | 7 | 2023-02-18 | 0:00 | 2023-02-18 | 0:00 | 1 x 4 hours | Periodical | Catenary |  | LT | [8 empty] | 1K + TV. |  |  |  |  | 2022-12-15
SZCZ | V-006160/22 | Brno - Břeclav | < > | Brno-Židenice | Brno-Maloměřice stavědlo 3 | 2023 | 2023 | 7 | 7 | 2023-02-18 | 0:00 | 2023-02-18 | 0:00 | 1 x 4 hours | Periodical | Catenary |  | LT |  |  | X | [5 empty] | 2K + TV. |  |  |  |  | 2022-12-15
SZCZ | V-006159/22 | Brno - Břeclav | < > | Brno-Židenice | Brno-Maloměřice | 2023 | 2023 | 7 | 7 | 2023-02-14 | 0:00 | 2023-02-17 | 0:00 | 4 days | Continuous | Catenary |  | LT |  |  | X | [5 empty] | 8. jen TV. |  |  |  |  | 2022-12-15
SZCZ | V-006144/22 | Brno - Břeclav | < > | Brno-Židenice | Brno-Maloměřice stavědlo 3 | 2023 | 2023 | 5 | 6 | 2023-02-04 | 0:00 | 2023-02-07 | 0:00 | 4 days | Continuous | Catenary |  | LT |  |  | X | [5 empty] | 2K + TV. |  |  |  |  | 2022-12-15
SZCZ | V-006136/22 | Brno - Břeclav | < > | Brno-Maloměřice | Brno-Maloměřice | 2023 | 2023 | 5 | 5 | 2023-01-31 | 0:00 | 2023-02-03 | 0:00 | 4 days | Continuous | Catenary |  | ST |  |  | X | [5 empty] | záhlaví a zhlaví traťové koleje T6 směr Brno-Židenice. |  |  |  |  | 2022-12-15
SZCZ | V-006136/22 | Brno - Břeclav | < > | Brno-Židenice | Brno-Maloměřice | 2023 | 2023 | 5 | 5 | 2023-01-31 | 0:00 | 2023-02-03 | 0:00 | 4 days | Continuous | Catenary |  | LT |  |  | X | [5 empty] | 6. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-006133/22 | Brno - Břeclav | < > | Brno-Maloměřice | Brno-Maloměřice | 2023 | 2023 | 3 | 3 | 2023-01-17 | 0:00 | 2023-01-20 | 0:00 | 4 days | Continuous | Catenary |  | ST |  |  | X | [5 empty] | záhlaví a zhlaví traťové koleje směr Brno-Židenice. |  |  |  |  | 2022-12-15
SZCZ | V-006133/22 | Brno - Břeclav | < > | Brno-Maloměřice | Brno-Židenice | 2023 | 2023 | 3 | 3 | 2023-01-17 | 0:00 | 2023-01-20 | 0:00 | 4 days | Continuous | Catenary |  | LT |  |  | X | [5 empty] | 4. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-006130/22 | Brno - Břeclav | < > | Brno-Maloměřice stavědlo 3 | Brno-Židenice | 2023 | 2023 | 3 | 4 | 2023-01-21 | 0:00 | 2023-01-24 | 0:00 | 4 days | Continuous | Catenary |  | LT | [8 empty] | 1K + TV. |  |  |  |  | 2022-12-15
SZCZ | V-006078/22 | Brno - Břeclav | < > | Vranovice | Hrušovany u Brna | 2023 | 2023 | 34 | 35 | 2023-08-26 | 0:00 | 2023-09-01 | 0:00 | 7 days | Continuous | Track & Rail |  | LT | [5 empty] | , X, X |  |  | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-006077/22 | Brno - Břeclav | < > | Hrušovany u Brna | Vranovice | 2023 | 2023 | 33 | 34 | 2023-08-19 | 0:00 | 2023-08-25 | 0:00 | 7 days | Continuous | Track & Rail |  | LT | [5 empty] | , X, X |  |  | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-006076/22 | Brno - Břeclav | < > | Vranovice | Hrušovany u Brna | 2023 | 2023 | 17 | 18 | 2023-04-25 | 0:00 | 2023-05-01 | 0:00 | 7 days | Continuous | Track & Rail |  | LT | [5 empty] | , X, X |  |  | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-006075/22 | Brno - Břeclav | < > | Hrušovany u Brna | Vranovice | 2023 | 2023 | 16 | 17 | 2023-04-18 | 0:00 | 2023-04-24 | 0:00 | 7 days | Continuous | Track & Rail |  | LT | [5 empty] | , X, X |  |  | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-006072/22 | Brno - Břeclav | < > | Břeclav přednádraží | Podivín | 2023 | 2023 | 31 | 31 | 2023-08-02 18:00 | 0:00 | 2023-08-05 06:00 | 0:00 | 3 x 6 hours | Periodical | Catenary |  | LT |  |  | X | [5 empty] | 1. jen TV. |  |  |  |  | 2022-12-15
SZCZ | V-006071/22 | Brno - Břeclav | < > | Podivín | Břeclav přednádraží | 2023 | 2023 | 31 | 31 | 2023-07-31 | 0:00 | 2023-08-06 | 0:00 | 7 days | Continuous | Catenary |  | LT | [8 empty] | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-006070/22 | Brno - Břeclav | < > | Břeclav přednádraží | Podivín | 2023 | 2023 | 30 | 30 | 2023-07-24 | 0:00 | 2023-07-30 | 0:00 | 7 days | Continuous | Catenary |  | LT | [8 empty] | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-006063/22 | Brno - Břeclav | < > | Podivín | Břeclav přednádraží | 2023 | 2023 | 28 | 28 | 2023-07-10 | 0:00 | 2023-07-16 | 0:00 | 7 x 10 hours | Periodical | Catenary |  | LT | [8 empty] | 1. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-006056/22 | Brno - Břeclav | < > | Břeclav přednádraží | Podivín | 2023 | 2023 | 27 | 27 | 2023-07-03 | 0:00 | 2023-07-09 | 0:00 | 7 x 10 hours | Periodical | Catenary |  | LT | [8 empty] | 2. + TV. |  |  |  |  | 2022-12-15
SZCZ | V-005370/22 | Děčín - Praha-Libeň | < > | Praha-Bubeneč | Praha-Holešovice | 2023 | 2023 | 27 | 27 | 2023-07-08 | 0:00 | 2023-07-09 | 0:00 | 2 days | Continuous | Track & Rail |  | LT | [8 empty] | 1 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-005370/22 | Děčín - Praha-Libeň | < > | Praha-Holešovice | Praha-Holešovice | 2023 | 2023 | 27 | 27 | 2023-07-08 | 0:00 | 2023-07-09 | 0:00 | 2 days | Continuous | Track & Rail |  | ST | [8 empty] | záhlaví bubenečské navazující na 1.TK Praha Bubeneč - Praha Holešovice |  |  |  |  | 2022-12-15
SZCZ | V-005370/22 | Děčín - Praha-Libeň | < > | Praha-Bubeneč | Praha-Bubeneč | 2023 | 2023 | 27 | 27 | 2023-07-08 | 0:00 | 2023-07-09 | 0:00 | 2 days | Continuous | Track & Rail |  | ST | [8 empty] | záhlaví holešovické navazující na 1.TK Praha Bubeneč - Praha Holešovice |  |  |  |  | 2022-12-15
SZCZ | V-005370/22 | Děčín - Praha-Libeň | < > | Praha-Holešovice | Praha-Holešovice | 2023 | 2023 | 27 | 27 | 2023-07-08 | 0:00 | 2023-07-09 | 0:00 | 2 days | Continuous | Track & Rail |  | ST | [8 empty] | záhlaví bubenské navazující na 1.TK Praha Holešovice - Praha Bubny |  |  |  |  | 2022-12-15
SZCZ | V-005370/22 | Děčín - Praha-Libeň | < > | Praha-Holešovice | Praha-Bubny | 2023 | 2023 | 27 | 27 | 2023-07-08 | 0:00 | 2023-07-09 | 0:00 | 2 days | Continuous | Track & Rail |  | LT | [8 empty] | 1 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-005365/22 | Děčín - Praha-Libeň | < > | Praha-Holešovice | Praha-Bubeneč | 2023 | 2023 | 26 | 26 | 2023-07-01 | 0:00 | 2023-07-02 | 0:00 | 2 days | Continuous | Track & Rail |  | LT | [8 empty] | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-005365/22 | Děčín - Praha-Libeň | < > | Praha-Holešovice | Praha-Holešovice | 2023 | 2023 | 26 | 26 | 2023-07-01 | 0:00 | 2023-07-02 | 0:00 | 2 days | Continuous | Track & Rail |  | ST | [8 empty] | záhlaví bubenečské navazující na 2.TK Praha Holešovice - Praha Bubeneč |  |  |  |  | 2022-12-15
SZCZ | V-005365/22 | Děčín - Praha-Libeň | < > | Praha-Bubeneč | Praha-Bubeneč | 2023 | 2023 | 26 | 26 | 2023-07-01 | 0:00 | 2023-07-02 | 0:00 | 2 days | Continuous | Track & Rail |  | ST | [8 empty] | záhlaví holešovické navazující na 2.TK Praha Holešovice - Praha Bubeneč |  |  |  |  | 2022-12-15
SZCZ | V-005360/20 | Praha-Libeň - Česká Třebová | < > | Český Brod | Český Brod | 2023 | 2023 | 15 | 16 | 2023-04-15 | 0:00 | 2023-04-19 | 0:00 | 5 days | Continuous | Catenary |  | ST | [5 empty] | , X, X |  |  | záhlaví a zhlaví 1. traťové koleje ze směru Úvaly. |  |  |  |  | 2022-12-15
SZCZ | V-005358/20 | Praha-Libeň - Česká Třebová | < > | Český Brod | Český Brod | 2023 | 2023 | 10 | 13 | 2023-03-11 | 0:00 | 2023-03-30 | 0:00 | 20 days | Continuous | Catenary |  | ST | [5 empty] | , X, X |  |  | záhlaví a zhlaví 2. traťové koleje ze směru Úvaly. |  |  |  |  | 2022-12-15
SZCZ | V-005197/22 | Česká Třebová - Brno | < > | Rájec-Jestřebí | Skalice nad Svitavou | 2023 | 2023 | 21 | 22 | 2023-05-24 | 0:00 | 2023-05-30 | 0:00 | 7 days | Continuous | Track & Rail |  | LT | [8 empty] | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-005196/22 | Česká Třebová - Brno | < > | Skalice nad Svitavou | Rájec-Jestřebí | 2023 | 2023 | 20 | 21 | 2023-05-17 | 0:00 | 2023-05-23 | 0:00 | 7 days | Continuous | Track & Rail |  | LT | [8 empty] | 1 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-005195/22 | Česká Třebová - Brno | < > | Letovice | Březová nad Svitavou | 2023 | 2023 | 19 | 20 | 2023-05-10 | 0:00 | 2023-05-16 | 0:00 | 7 days | Continuous | Track & Rail |  | LT | [8 empty] | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-005194/22 | Česká Třebová - Brno | < > | Březová nad Svitavou | Letovice | 2023 | 2023 | 18 | 19 | 2023-05-03 | 0:00 | 2023-05-09 | 0:00 | 7 days | Continuous | Track & Rail |  | LT | [8 empty] | 1 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-005193/22 | Česká Třebová - Brno | < > | Skalice nad Svitavou | Letovice | 2023 | 2023 | 17 | 18 | 2023-04-26 | 0:00 | 2023-05-02 | 0:00 | 7 days | Continuous | Track & Rail |  | LT | [8 empty] | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-005193/22 | Česká Třebová - Brno | < > | Skalice nad Svitavou | Skalice nad Svitavou | 2023 | 2023 | 17 | 18 | 2023-04-26 | 0:00 | 2023-05-02 | 0:00 | 7 days | Continuous | Track & Rail |  | ST | [8 empty] | sudá jen TV. záhlaví a zhlaví 2. traťové koleje směr Letovice. |  |  |  |  | 2022-12-15
SZCZ | V-005192/22 | Česká Třebová - Brno | < > | Letovice | Skalice nad Svitavou | 2023 | 2023 | 16 | 17 | 2023-04-19 | 0:00 | 2023-04-25 | 0:00 | 7 days | Continuous | Track & Rail |  | LT | [8 empty] | 1 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-005192/22 | Česká Třebová - Brno | < > | Skalice nad Svitavou | Skalice nad Svitavou | 2023 | 2023 | 16 | 17 | 2023-04-19 | 0:00 | 2023-04-25 | 0:00 | 7 days | Continuous | Track & Rail |  | ST | [8 empty] | lichá jen TV. záhlaví a zhlaví 1. traťové koleje směr Letovice. |  |  |  |  | 2022-12-15
SZCZ | V-005110/22 | Břeclav - Wien | < > | Břeclav | Břeclav st.hr. | 2023 | 2023 | 3 | 3 | 2023-01-18 | 0:00 | 2023-01-19 | 0:00 | 2 x 8 hours | Periodical | Track & Rail |  | LT | [8 empty] | 1 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-005108/22 | Břeclav - Wien | < > | Břeclav st.hr. | Břeclav | 2023 | 2023 | 3 | 3 | 2023-01-16 | 0:00 | 2023-01-17 | 0:00 | 2 x 8 hours | Periodical | Track & Rail |  | LT | [8 empty] | 2 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-004915/22 | Břeclav - Wien | < > | Břeclav | Boří les | 2023 | 2023 | 36 | 36 | 2023-09-04 | 0:00 | 2023-09-04 | 0:00 | 1 x 7 hours | Periodical | Track & Rail | T | LT | [5 empty] | , X, X |  |  | traťová bez TV. |  |  |  |  | 2022-12-15
SZCZ | V-004664/22 | Břeclav - Wien | < > | Břeclav st.hr. | Břeclav | 2023 | 2023 | 41 | 42 | 2023-10-11 | 0:00 | 2023-10-20 | 0:00 | 10 days | Continuous | Track & Rail |  | LT | [8 empty] | 1 + TV. |  |  |  |  | 2022-12-15
SZCZ | V-004659/22 | Břeclav - Wien | < > | Břeclav st.hr. | Břeclav | 2023 | 2023 | 40 | 41 | 2023-10-02 | 0:00 | 2023-10-11 | 0:00 | 10 days | Continuous | Track & Rail |  | LT | [8 empty] | 2 + TV. |  |  |  |  | 2022-12-15
ŽSR | 56TT2212002 | Bratislava - Štúrovo | > | Palárikovo | Nové Zámky | 2023 | 2023 | 2 | 21 | 2023-01-09 | 0:00 | 2023-05-25 | 23:59 | 3288:00 | Continuous | Track & Rail |  | LT | [8 empty] | KRK |  |  |  |  | 2022-12-09
ŽSR | 56TT2212004 | Bratislava - Štúrovo | < | Trnovec nad Váhom | Tvrdošovce | 2023 | 2023 | 4 | 5 | 2023-01-24 | 8:00 | 2023-01-31 | 16:00 | 192:00 | Periodical | Track & Rail |  | LT | [8 empty] | KRK, koľ. č. 1, 2 |  |  | A14003 |  | 2022-12-09
ŽSR | 56TT2212005 | Bratislava - Štúrovo | > | Trnovec nad Váhom | Tvrdošovce | 2023 | 2023 | 2 | 4 | 2023-01-10 | 8:00 | 2023-01-23 | 16:00 | 336:00 | Periodical | Track & Rail |  | LT | [8 empty] | KRK, koľ. č. 1, 2 |  |  | A14003 |  | 2022-12-09
ŽSR | 56TT2212006 | Bratislava - Štúrovo | > | Trnovec nad Váhom | Tvrdošovce | 2023 | 2023 | 4 | 5 | 2023-01-24 | 8:00 | 2023-01-30 | 16:00 | 168:00 | Periodical | Track & Rail |  | LT | [8 empty] | KRK, koľ. č. 2 (nočné) |  |  | A14003 |  | 2022-12-09
ŽSR | 56TT2212007 | Bratislava - Štúrovo | < | Tvrdošovce | Tvrdošovce | 2023 | 2023 | 2 | 2 | 2023-01-14 | 8:00 | 2023-01-15 | 16:00 | 48:00 | Periodical | Track & Rail |  | ST | [8 empty] | KRK, koľ. č. 1, 2; trnovecké zhlavie, TV celé (nočné) |  |  | A14003 |  | 2022-12-09
ŽSR | 56TT2212008 | Bratislava - Štúrovo | > | Tvrdošovce | Tvrdošovce | 2023 | 2023 | 3 | 3 | 2023-01-21 | 8:00 | 2023-01-22 | 16:00 | 48:00 | Periodical | Track & Rail |  | ST | [8 empty] | KRK, koľ. č. 1, 2; tvrdošovecké zhlavie, TV celé |  |  | A14003 |  | 2022-12-09
ŽSR | 56TT2212009 | Bratislava - Štúrovo | > | Trnovec nad Váhom | Tvrdošovce | 2023 | 2023 | 5 | 27 | 2023-02-01 | 0:00 | 2023-07-09 | 23:59 | 3768:00 | Continuous | Track & Rail |  | LT | [8 empty] | KRK, koľ. č. 1, 2 |  |  | A14003 |  | 2022-12-09
ŽSR | 56TT2212010 | Bratislava - Štúrovo | < | Trnovec nad Váhom | Tvrdošovce | 2023 | 2023 | 28 | 48 | 2023-07-10 | 0:00 | 2023-11-30 | 23:59 | 3432:00 | Continuous | Track & Rail |  | LT | [8 empty] | KRK, koľ. č. 1, 2 |  |  | A14003 |  | 2022-12-09
ŽSR | 56TT2212011 | Bratislava - Štúrovo | < > | Tvrdošovce | Tvrdošovce | 2023 | 2023 | 23 | 23 | 2023-06-05 | 0:00 | 2023-06-07 | 23:59 | 72:00 | Continuous | Track & Rail |  | ST | [8 empty] | OKLV 3 v. j. |  |  |  |  | 2022-12-09
ŽSR | 56TT2212012 | Bratislava - Štúrovo | < > | Tvrdošovce | Tvrdošovce | 2023 | 2023 | 23 | 24 | 2023-06-08 | 0:00 | 2023-06-12 | 23:59 | 120:00 | Continuous | Track & Rail |  | ST | [8 empty] | OKLV 3 v. j. |  |  |  |  | 2022-12-09
ŽSR | 56TT2212033 | Štúrovo - Ferencváros | > | Štúrovo | Štúrovo št. hr. | 2023 | 2023 | 28 | 29 | 2023-07-10 | 0:00 | 2023-07-17 | 23:59 | 192:00 | Continuous | Bridge |  | LT | [8 empty] | Výmena mostníc (265 ks), MO km 203,394; TK 2 |  |  |  |  | 2022-12-09
ŽSR | 56TT2212034 | Bratislava - Rajka | < > | Bratislava ÚNS | Bratislava ÚNS | 2023 | 2023 | 32 | 33 | 2023-08-07 | 8:00 | 2023-08-18 | 16:00 | 144:00 | Periodical | Miscellaneous |  | ST | [8 empty] | OKLV |  |  |  |  | 2022-12-09
ŽSR | 56TT2212035 | Bratislava - Rajka | < > | Bratislava-Nové Mesto | Bratislava-Nové Mesto | 2023 | 2023 | 14 | 25 | 2023-04-03 | 0:00 | 2023-06-25 | 23:59 | 1032:00 | Continuous | Miscellaneous |  | ST | [8 empty] | OKLV + OKLK |  |  |  |  | 2022-12-09
ŽSR | 56TT2212036 | Bratislava - Rajka | > | Bratislava-Nové Mesto | Bratislava ÚNS | 2023 | 2023 | 31 | 52 | 2023-08-01 | 0:00 | 2023-12-31 | 23:59 | 3648:00 | Continuous | Track & Rail |  | LT | [8 empty] | KRŽZ; TK2 |  |  |  |  | 2022-12-09
ŽSR | 56TT2212037 | Nové Zámky - Komárom | < > | Komárno št. hr. | Komárno | 2023 | 2023 | 35 | 39 | 2023-09-01 | 0:00 | 2023-09-30 | 23:59 | 600:00 | Continuous | Bridge |  | LT | [8 empty] | Výmena mostníc (816 ks), MO km 3,021 |  |  |  |  | 2022-12-09
ŽSR | 56TT2212038 | Bratislava - Komárno | < > | Podunajské Biskupice | Bratislava-Nové Mesto | 2023 | 2023 | 23 | 28 | 2023-06-11 | 0:00 | 2023-07-11 | 23:59 | 744:00 | Continuous | Track & Rail |  | LT | [8 empty] | TIOP č. 7 Bratislava Vrakuňa |  |  | A14202 |  | 2022-12-09
ÖBB Infra | 81-57571 | Wien - Ebenfurth - Sopron | < > | Wampersdorf |  | 2022 | 2023 | 26 | 26 | 2022-07-01 | 8:00 | 2023-07-02 | 6:00 | 365 days + 22,0 h | Continuous | Others |  | ST | [6 empty] | 40 |  | Bf-Umbau |  | N |  |  | 2022-04-06
ÖBB Infra | 81-61537 | Wien - Ebenfurth - Sopron | < > | Wampersdorf |  | 2022 | 2023 | 26 | 36 | 2022-07-01 | 8:00 | 2023-09-04 | 4:30 | 430 days | Continuous | Others |  | ST | [6 empty] | 40 |  | Bf-Umbau |  | N |  |  | 2022-04-06
ÖBB Infra | 81-62661 | Wien - Hegyeshalom | < > | Gramatneusiedl |  | 2022 | 2023 | 35 | 36 | 2022-09-01 | 8:00 | 2023-09-04 | 4:30 | 368 days | Continuous | Others |  | ST | [8 empty] | Fahrleitungsumbau |  | N |  |  | 2022-05-01
ÖBB Infra | 81-62662 | Wien - Hegyeshalom | > | Gramatneusiedl |  | 2023 | 2023 | 5 | 9 | 2023-02-03 | 0:00 | 2023-03-05 | 24:00 | 31 days | Continuous | Others |  | ST | S | [5 empty] | 10 |  | Abtrag Personensteg und Bahnsteigneubau [Bauphase 6a - Bahnhofumbau Gramatneusiedl] |  | N |  |  | 2022-05-01
ÖBB Infra | 81-62663 | Wien - Hegyeshalom | > | Gramatneusiedl |  | 2023 | 2023 | 8 | 9 | 2023-02-24 | 22:30 | 2023-02-27 | 4:50 | 2 days + 6,3 h | Continuous | Others |  | ST | S |  |  | C |  | B | 10 |  | Einbau Weiche 60 [neu] (Bauphase 6a - Bahnhofumbau Gramatneusiedl) |  | N |  |  | 2022-11-03
ÖBB Infra | 81-62664 | Wien - Hegyeshalom | < > | Gramatneusiedl |  | 2023 | 2023 | 10 | 23 | 2023-03-07 | 0:00 | 2023-06-07 | 24:00 | 92 days + 23,0 h | Continuous | Others |  | ST | [8 empty] | Neuerrichtung Bgl 4+6 (Bauphase 6b - Bahnhofumbau Gramatneusiedl) |  | N |  |  | 2022-05-01
ÖBB Infra | 81-61071 | Wien - Hegyeshalom | < > | Kledering |  | 2023 | 2023 | 14 | 15 | 2023-04-08 | 9:00 | 2023-04-11 | 5:00 | 2 days + 20,0 h | Continuous | Others | T | ST | [8 empty] | Weichenneulage DKW 453/454 und DKW 455/456 |  | N |  |  | 2021-12-14
ÖBB Infra | 81-61071 | Wien - Ebenfurth - Sopron | < > | Kledering |  | 2023 | 2023 | 14 | 15 | 2023-04-08 | 9:00 | 2023-04-11 | 5:00 | 2 days + 20,0 h | Continuous | Others | T | ST | [8 empty] | Weichenneulage DKW 453/454 und DKW 455/456 |  | N |  |  | 2021-12-14
ÖBB Infra | 81-61059 | Wien - Hegyeshalom | < > | Abzww Zur | Wien Zvbf | 2023 | 2023 | 16 | 17 | 2023-04-17 | 7:00 | 2023-04-30 | 17:00 | 13 days + 10,0 h | Continuous | Others |  | LT | [8 empty] | Gleisneulage Bgl 323 |  | N |  |  | 2022-11-28
ÖBB Infra | 81-63887 | Wien - Hegyeshalom | < > | Abzww Zur | Wien Zvbf | 2023 | 2023 | 16 | 17 | 2023-04-17 | 7:00 | 2023-04-30 | 17:00 | 13 days + 10,0 h | Continuous | Others |  | LT | [8 empty] | Gleisneulage Bgl 324 |  | N |  |  | 2022-11-28
ÖBB Infra | 81-61059 | Wien - Ebenfurth - Sopron | < > | Abzww Zur | Wien Zvbf | 2023 | 2023 | 16 | 17 | 2023-04-17 | 7:00 | 2023-04-30 | 17:00 | 13 days + 10,0 h | Continuous | Others |  | LT | [8 empty] | Gleisneulage Bgl 323 |  | N |  |  | 2022-11-28
ÖBB Infra | 81-63887 | Wien - Ebenfurth - Sopron | < > | Abzww Zur | Wien Zvbf | 2023 | 2023 | 16 | 17 | 2023-04-17 | 7:00 | 2023-04-30 | 17:00 | 13 days + 10,0 h | Continuous | Others |  | LT | [8 empty] | Gleisneulage Bgl 324 |  | N |  |  | 2022-11-28
ÖBB Infra | 81-63047 | Wien - Hegyeshalom | < | Nickelsdorf |  | 2023 | 2023 | 21 | 22 | 2023-05-26 | 9:00 | 2023-05-30 | 4:00 | 3 days + 19,0 h | Continuous | Others |  | ST | S | [5 empty] | 30 |  | Gründliche Durcharbeitung, sowie Sanierung der EK in km 66,641 |  | N |  |  | 2022-11-03
ÖBB Infra | 81-56749 | Wien - Hegyeshalom | < > | Gramatneusiedl |  | 2023 | 2024 | 23 | 52 | 2023-06-08 | 0:00 | 2024-12-31 | 24:00 | 754 days | Continuous | Others |  | ST | [8 empty] | Bf-Umbau |  | Y |  |  | 2021-12-14
ÖBB Infra | 81-62667 | Wien - Hegyeshalom | < > | Gramatneusiedl |  | 2023 | 2023 | 23 | 26 | 2023-06-08 | 0:00 | 2023-07-02 | 6:00 | 24 days + 6,0 h | Continuous | Others | T | ST |  |  |  | C |  | B |  |  | Einbau Weiche 91,92 [neu], sowie Inbetriebnahme Gleis 4,6 [neu] (Bauphase 7a - Bahnhofumbau Gramatneusiedl) |  | N |  |  | 2022-05-01
ÖBB Infra | 81-56750 | Wien - Hegyeshalom | < > | Götzendorf | Abzww Str 11815 | 2023 | 2024 | 26 | 52 | 2023-07-01 | 0:00 | 2024-12-31 | 24:00 | 731 days | Continuous | Others |  | LT | [8 empty] | Bf-Umbau |  | Y |  |  | 2021-12-14
ÖBB Infra | 81-58206 | Wien - Ebenfurth - Sopron | < > | Münchendorf | Wampersdorf | 2023 | 2023 | 26 | 36 | 2023-07-01 | 23:20 | 2023-09-04 | 4:30 | 64 days + 5,2 h | Continuous | Others | T | LT |  |  |  | C |  | B |  |  | Anbindung Bf Ebreichdorf neu an Münchendorf und Wampersdorf |  | N |  |  | 2022-11-03
ÖBB Infra | 81-62668 | Wien - Hegyeshalom | < > | Gramatneusiedl |  | 2023 | 2023 | 26 | 27 | 2023-07-02 | 6:00 | 2023-07-09 | 6:00 | 7 days | Continuous | Others |  | ST | [8 empty] | Neuerrichtung Bypassgleis zwischen W63 und W92 (Bauphase 7b - Bahnhofumbau Gramatneusiedl) |  | N |  |  | 2022-05-01
ÖBB Infra | 81-61538 | Wien - Ebenfurth - Sopron | > | Wampersdorf |  | 2023 | 2023 | 26 | 50 | 2023-07-02 | 6:00 | 2023-12-11 | 4:30 | 161 days + 23,5 h | Continuous | Others |  | ST | [6 empty] | 40 |  | Bf-Umbau |  | N |  |  | 2022-05-01
ÖBB Infra | 81-61540 | Wien - Ebenfurth - Sopron | < > | Wampersdorf |  | 2023 | 2024 | 26 | 36 | 2023-07-02 | 6:00 | 2024-09-02 | 4:30 | 428 days | Continuous | Others |  | ST | [6 empty] | 40 |  | Bf-Umbau |  | N |  |  | 2022-05-01
ÖBB Infra | 81-62481 | Wien - Ebenfurth - Sopron | > | Wampersdorf | Sbl Wp 1 | 2023 | 2023 | 26 | 32 | 2023-07-02 | 6:00 | 2023-08-07 | 6:00 | 36 days | Continuous | Others |  | LT | S |  |  | C |  | B | 30 |  | Planumsverbesserung mit UGV, sowie Einbau der Weichen 2+3 in der Hst Pottendorf-L. |  | N |  |  | 2022-11-03
ÖBB Infra | 81-61018 | Wien - Hegyeshalom | > | Zurndorf | Nickelsdorf | 2023 | 2023 | 27 | 30 | 2023-07-04 | 8:00 | 2023-07-30 | 16:00 | 26 days + 8,0 h | Continuous | Others |  | LT |  |  |  | C |  | B | 20 |  | Gleisneulage mit Untergrundverstärkung |  | N |  |  | 2022-11-03
ÖBB Infra | 81-61019 | Wien - Hegyeshalom | < > | Zurndorf |  | 2023 | 2023 | 27 | 34 | 2023-07-04 | 8:00 | 2023-08-26 | 16:00 | 53 days + 8,0 h | Continuous | Others |  | ST | [6 empty] | 0 |  | Gleisneulage mit Bahnsteigerneuerung |  | N |  |  | 2022-11-03
ÖBB Infra | 81-62482 | Wien - Ebenfurth - Sopron | < | Wampersdorf | Sbl Wp 1 | 2023 | 2023 | 32 | 36 | 2023-08-07 | 6:00 | 2023-09-04 | 4:30 | 27 days + 22,5 h | Continuous | Others |  | LT | S |  |  | C |  | B | 30 |  | Planumsverbesserung mit UGV, sowie Einbau der Weichen 1+4 in der Hst Pottendorf-L. |  | N |  |  | 2022-11-03
ÖBB Infra | 81-62670 | Wien - Hegyeshalom | < > | Gramatneusiedl |  | 2023 | 2023 | 36 | 41 | 2023-09-04 | 4:30 | 2023-10-15 | 24:00 | 41 days + 19,5 h | Continuous | Others |  | ST | [8 empty] | Abtrag Bgl 5+7, sowie der Weichen 52-55 [alt], Einbau Weichen 51-54 [neu] (Bauphase 8 - Bahnhofumbau Gramatneusiedl) |  | N |  |  | 2022-05-22
ÖBB Infra | 81-59833 | Wien - Hegyeshalom | > | Himberg |  | 2023 | 2023 | 36 | 41 | 2023-09-09 | 7:00 | 2023-10-13 | 22:00 | 34 days + 15,0 h | Continuous | Others |  | ST |  |  |  | C |  | B | 30 |  | Unterbausanierung |  | Y |  |  | 2021-12-14
ÖBB Infra | 81-61070 | Wien - Hegyeshalom | < > | Wien Zvbf | Kledering | 2023 | 2023 | 36 | 37 | 2023-09-09 | 10:00 | 2023-09-15 | 17:00 | 6 days + 7,0 h | Continuous | Others |  | LT | [8 empty] | Gleisneulage |  | N |  |  | 2021-12-14
ÖBB Infra | 81-61070 | Wien - Ebenfurth - Sopron | < > | Wien Zvbf | Kledering | 2023 | 2023 | 36 | 37 | 2023-09-09 | 10:00 | 2023-09-15 | 17:00 | 6 days + 7,0 h | Continuous | Others |  | LT | [8 empty] | Gleisneulage |  | N |  |  | 2021-12-14
ÖBB Infra | 81-62671 | Wien - Hegyeshalom | < | Gramatneusiedl |  | 2023 | 2023 | 38 | 39 | 2023-09-22 | 22:30 | 2023-09-25 | 4:30 | 2 days + 6,0 h | Continuous | Others |  | ST | S |  |  | C |  | B | 10 |  | Abtrag der Weichen 56+57 [alt], Einbau Weichen 55+57 [neu] (Bauphase 8 - Bahnhofumbau Gramatneusiedl) |  | N |  |  | 2022-11-03
ÖBB Infra | 81-59834 | Wien - Hegyeshalom | > | Himberg | Gramatneusiedl | 2023 | 2023 | 41 | 43 | 2023-10-13 | 22:00 | 2023-10-25 | 22:00 | 12 days | Continuous | Others |  | LT |  |  |  | C |  | B | 30 |  | Anschwenkungen |  | Y |  |  | 2021-12-14
ÖBB Infra | 81-62673 | Wien - Hegyeshalom | < > | Gramatneusiedl |  | 2023 | 2023 | 42 | 42 | 2023-10-16 | 0:00 | 2023-10-22 | 24:00 | 7 days | Continuous | Others |  | ST | [8 empty] | Abtrag Bgl 11, sowie der Weiche 51 [alt], Einbau Weichen 31 [neu] (Bauphase 9 - Bahnhofumbau Gramatneusiedl) |  | N |  |  | 2022-05-01
ÖBB Infra | 81-62675 | Wien - Hegyeshalom | < > | Gramatneusiedl |  | 2023 | 2023 | 43 | 45 | 2023-10-23 | 0:00 | 2023-11-12 | 24:00 | 21 days + 1,0 h | Continuous | Others |  | ST | [8 empty] | Neuerrichtung Bgl 5-11 (Bauphase 10a - Bahnhofumbau Gramatneusiedl) |  | N |  |  | 2022-05-01
ÖBB Infra | 81-62676 | Wien - Hegyeshalom | < | Gramatneusiedl |  | 2023 | 2023 | 43 | 45 | 2023-10-23 | 0:00 | 2023-11-12 | 24:00 | 21 days + 1,0 h | Continuous | Others |  | ST | S | [5 empty] | 10 |  | Bahnsteigneubau (Bauphase 10a - Bahnhofumbau Gramatneusiedl) |  | N |  |  | 2022-05-01
ÖBB Infra | 81-59835 | Wien - Hegyeshalom | > | Lanzendorf-Rannersdorf | Gramatneusiedl | 2023 | 2023 | 43 | 44 | 2023-10-25 | 22:00 | 2023-11-01 | 1:00 | 6 days + 4,0 h | Continuous | Others |  | LT |  |  |  | C |  | B | 30 |  | Anschwenkungen Sgl 2 an Gleis 4-neu |  | Y |  |  | 2021-12-14
ÖBB Infra | 81-59836 | Wien - Hegyeshalom | < | Lanzendorf-Rannersdorf | Gramatneusiedl | 2023 | 2023 | 44 | 44 | 2023-11-01 | 6:00 | 2023-11-03 | 5:00 | 1 day + 23,0 h | Continuous | Others |  | LT |  |  |  | C |  | B | 30 |  | Einbau W 1-neu und anbinden an Bgl 2 |  | Y |  |  | 2021-12-14
ÖBB Infra | 81-59837 | Wien - Hegyeshalom | < | Himberg | Gramatneusiedl | 2023 | 2023 | 44 | 45 | 2023-11-01 | 6:00 | 2023-11-06 | 5:00 | 4 days + 23,0 h | Continuous | Others |  | LT |  |  |  | C |  | B | 30 |  | Anschwenken Bgl 2 an Sgl 1 Ri Gn |  | Y |  |  | 2021-12-14
ÖBB Infra | 81-59838 | Wien - Hegyeshalom | < | Himberg | Gramatneusiedl | 2023 | 2023 | 45 | 46 | 2023-11-06 | 5:00 | 2023-11-18 | 17:30 | 12 days + 12,5 h | Continuous | Others |  | LT |  |  |  | C |  | B | 30 |  | Hauptverkabelung |  | Y |  |  | 2021-12-14
ÖBB Infra | 81-62677 | Wien - Hegyeshalom | < > | Gramatneusiedl |  | 2023 | 2024 | 46 | 22 | 2023-11-13 | 0:00 | 2024-05-31 | 4:50 | 200 days + 3,8 h | Continuous | Others |  | ST | [8 empty] | Abtrag der Weichen 7-11 [alt], Einbau Weichen 4,7,8,10,11,13 [neu], Neuerrichtung Bgl 3-11 inkl. Einhub Personensteg (Bauphase 10b - Bahnhofumbau Gramatneusiedl) |  | N |  |  | 2022-05-01
ÖBB Infra | 81-62931 | Wien - Hegyeshalom | < > | Gramatneusiedl |  | 2023 | 2023 | 48 | 48 | 2023-12-01 | 19:00 | 2023-12-03 | 6:00 | 1 day + 11,0 h | Continuous | Others |  | ST |  |  |  | C |  |  |  |  | ESTW - Inbetriebnahme |  | N |  |  | 2022-11-03
GYSEV | 5512705 Deleted | Sopron - Győr | < > | Ikrény | Győr | 2023 | 2023 | 23 | 23 | 2023-06-05 | 7:30 | 2023-06-10 | 17:30 | 5 days + 10 h 0 min | Continuous | Others | T | [5 empty] | R |  |  |  | Total closure, re-routing necessary
GYSEV | 5512706 Deleted | Sopron - Győr | < > | Enese | Ikrény | 2023 | 2023 | 36 | 36 | 2023-09-04 | 7:30 | 2023-09-05 | 17:30 | 1 days + 10 h 0 min | Continuous | Track & Rail | T | [5 empty] | R |  |  |  | Total closure, re-routing necessary
GYSEV | 5512794 | Rajka - Hegyeshalom | < > | Rajka | Hegyeshalom | 2023 | 2023 | 15 | 15 | 2023-04-11 | 11:30 | 2023-04-11 | 18:00 | 1 day | Periodical | Catenary | T | [5 empty] | R | B | D |  | Total closure, re-routing necessary |  |  |  | 2023-02-20
GYSEV | 5512795 | Rajka - Hegyeshalom | < > | Rajka oh. | Rajka | 2023 | 2023 | 15 | 15 | 2023-04-11 | 11:30 | 2023-04-11 | 18:00 | 1 day | Periodical | Catenary | T | [5 empty] | R | B | D |  | Total closure, re-routing necessary |  |  |  | 2023-02-20
GYSEV | 5512796 | Rajka - Hegyeshalom | < > | Rajka | Hegyeshalom | 2023 | 2023 | 15 | 15 | 2023-04-12 | 11:30 | 2023-04-12 | 18:00 | 1 day | Periodical | Catenary | T | [5 empty] | R | B | D |  | Total closure, re-routing necessary |  |  |  | 2023-02-20
GYSEV | 5512797 | Rajka - Hegyeshalom | < > | Rajka oh. | Rajka | 2023 | 2023 | 15 | 15 | 2023-04-12 | 11:30 | 2023-04-12 | 18:00 | 1 day | Periodical | Catenary | T | [5 empty] | R | B | D |  | Total closure, re-routing necessary |  |  |  | 2023-02-20
GYSEV | 5512798 | Rajka - Hegyeshalom | < > | Rajka | Hegyeshalom | 2023 | 2023 | 15 | 15 | 2023-04-13 | 11:30 | 2023-04-13 | 18:00 | 1 day | Periodical | Catenary | T | [5 empty] | R | B | D |  | Total closure, re-routing necessary |  |  |  | 2023-02-20
GYSEV | 5512799 | Rajka - Hegyeshalom | < > | Rajka oh. | Rajka | 2023 | 2023 | 15 | 15 | 2023-04-13 | 11:30 | 2023-04-13 | 18:00 | 1 day | Periodical | Catenary | T | [5 empty] | R | B | D |  | Total closure, re-routing necessary |  |  |  | 2023-02-20
GYSEV | 5512800 | Sopron - Győr | < > | Sopron | Csorna | 2023 | 2023 | 16 | 16 | 2023-04-17 | 8:10 | 2023-04-17 | 18:40 | 1 day | Periodical | Track & Rail | T | [5 empty] | R | B | D |  | Total closure, re-routing necessary |  |  |  | 2023-02-20
GYSEV | 5512801 | Sopron - Győr | < > | Sopron | Csorna | 2023 | 2023 | 16 | 16 | 2023-04-18 | 8:10 | 2023-04-18 | 18:40 | 1 day | Periodical | Track & Rail | T | [5 empty] | R | B | D |  | Total closure, re-routing necessary |  |  |  | 2023-02-20
GYSEV | 5512802 | Sopron - Győr | < > | Sopron | Csorna | 2023 | 2023 | 16 | 16 | 2023-04-19 | 8:10 | 2023-04-19 | 18:40 | 1 day | Periodical | Track & Rail | T | [5 empty] | R | B | D |  | Total closure, re-routing necessary |  |  |  | 2023-02-20
GYSEV | 5512803 | Sopron - Győr | < > | Csorna | Győr | 2023 | 2023 | 16 | 16 | 2023-04-20 | 7:35 | 2023-04-20 | 17:35 | 1 day | Periodical | Track & Rail | T | [5 empty] | R | B | D |  | Total closure, re-routing necessary |  |  |  | 2023-02-20
GYSEV | 5512804 | Sopron - Győr | < > | Csorna | Győr | 2023 | 2023 | 16 | 16 | 2023-04-21 | 7:35 | 2023-04-21 | 17:35 | 1 day | Periodical | Track & Rail | T | [5 empty] | R | B | D |  | Total closure, re-routing necessary |  |  |  | 2023-02-20
GYSEV | 5512805 | Sopron - Győr | < > | Sopron | Csorna | 2023 | 2023 | 22 | 22 | 2023-05-30 | 3:00 | 2023-06-03 | 23:59 | 4 days | Continuous | Track & Rail | T | [5 empty] | R | B |  |  | Total closure, re-routing necessary |  |  |  | 2023-02-20
GYSEV | 5512806 | Sopron - Győr | < > | Csorna | Győr | 2023 | 2023 | 23 | 24 | 2023-06-11 | 3:00 | 2023-06-16 | 23:59 | 6 days | Continuous | Track & Rail | T | [5 empty] | R | B |  |  | Total closure, re-routing necessary |  |  |  | 2023-02-20
GYSEV | 5512807 | Sopron - Győr | < > | Sopron | Csorna | 2023 | 2023 | 28 | 28 | 2023-07-10 | 3:00 | 2023-07-16 | 23:59 | 7 days | Continuous | Track & Rail | T | [5 empty] | R | B |  |  | Total closure, re-routing necessary |  |  |  | 2023-02-20
MÁV | 5507001001 | Hegyeshalom - Ferencváros | > | Biatorbágy | Herceghalom | 2023 | 2023 | 1 | 1 | 2023-01-03 | 0:00 | 2023-01-08 | 23:59 | 6 Days | Continuous | Others |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507001002 | Hegyeshalom - Ferencváros | < | Biatorbágy | Herceghalom | 2023 | 2023 | 2 | 2 | 2023-01-09 | 0:00 | 2023-01-15 | 23:59 | 7 Days | Continuous | Others |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507001003 | Hegyeshalom - Ferencváros | > | Hegyeshalom | Mosonmagyaróvár | 2023 | 2023 | 12 | 13 | 2023-03-24 | 20:45 | 2023-03-27 | 1:00 | 2 day 4 h | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-12-01
MÁV | 5507001004 | Hegyeshalom - Ferencváros | < | Szárliget | Tatabánya | 2023 | 2023 | 13 | 13 | 2023-03-31 | 23:00 | 2023-04-01 | 22:00 | 23 h | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507001005 | Hegyeshalom - Ferencváros | > | Szárliget | Tatabánya | 2023 | 2023 | 13 | 13 | 2023-04-01 | 22:00 | 2023-04-02 | 21:00 | 23 h | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-12-01
MÁV | 5507001006 | Hegyeshalom - Ferencváros | < | Budaörs | Budapest-Kelenföld | 2023 | 2023 | 15 | 16 | 2023-04-14 | 23:30 | 2023-04-17 | 4:00 | 2 days 2 h 30 m | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507001007 | Hegyeshalom - Ferencváros | > | Tatabánya | Tata | 2023 | 2023 | 16 | 16 | 2023-04-21 | 22:00 | 2023-04-22 | 19:00 | 21 h | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507001008 | Hegyeshalom - Ferencváros | < | Bicske | Szárliget | 2023 | 2023 | 16 | 17 | 2023-04-22 | 22:00 | 2023-04-24 | 5:15 | 31 h 15 min | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507001009 Deleted | Hegyeshalom - Ferencváros | < | Öttevény | Győr | 2023 | 2023 | 18 | 28 | 2023-05-02 | 0:00 | 2023-07-15 | 23:59 | 75 days | Continuous | Bridge |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507001010 Deleted | Hegyeshalom - Ferencváros | > | Öttevény | Győr | 2023 | 2023 | 28 | 34 | 2023-07-16 | 0:00 | 2023-08-27 | 23:59 | 43 Days | Continuous | Bridge |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507001011 | Hegyeshalom - Ferencváros | < | Lébény-Mosonszentmiklós | Kimle-Károlyháza | 2023 | 2023 | 35 | 36 | 2023-09-01 | 23:00 | 2023-09-08 | 5:00 | 6 Days 6 h | Continuous | Bridge |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507001012 | Hegyeshalom - Ferencváros | > | Kimle-Károlyháza | Mosonmagyaróvár | 2023 | 2023 | 37 | 37 | 2023-09-11 | 22:00 | 2023-09-12 | 6:00 | 8 hours | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507001009 | Hegyeshalom - Ferencváros | < | Ferencváros | Kelenföld | 2023 | 2023 | 18 | 19 | 2023-05-05 | 22:00 | 2023-05-08 | 4:30 | 54 h 30 min | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation (closure of one track of a double track line) |  |  |  | 2023-02-01
MÁV | 5507001010 | Hegyeshalom - Ferencváros | < > | Ferencváros | Kelenföld | 2023 | 2023 | 18 | 18 | 2023-05-06 | 0:30 | 2023-05-06 | 4:30 | 4 h | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2023-02-01
MÁV | 5507001013 | Hegyeshalom - Ferencváros | < > | Ferencváros | Kelenföld | 2023 | 2023 | 18 | 18 | 2023-05-07 | 0:30 | 2023-05-07 | 4:30 | 4 h | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2023-02-01
MÁV | 5507001014 | Hegyeshalom - Ferencváros | > | Ferencváros | Kelenföld | 2023 | 2023 | 19 | 20 | 2023-05-12 | 22:00 | 2023-05-15 | 4:30 | 54 h 30 min | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation (closure of one track of a double track line) |  |  |  | 2023-02-01
MÁV | 5507001015 | Hegyeshalom - Ferencváros | < > | Ferencváros | Kelenföld | 2023 | 2023 | 19 | 19 | 2023-05-14 | 0:30 | 2023-05-14 | 4:30 | 4 h | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2023-02-01
MÁV | 5507001016 | Hegyeshalom - Ferencváros | < > | Ferencváros | Kelenföld | 2023 | 2023 | 20 | 20 | 2023-05-15 | 0:30 | 2023-05-15 | 4:30 | 4 h | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2023-02-01
MÁV | 5507001017 | Hegyeshalom - Ferencváros | < | Ferencváros | Kelenföld | 2023 | 2023 | 20 | 21 | 2023-05-19 | 22:00 | 2023-05-22 | 4:30 | 54 h 30 min | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation (closure of one track of a double track line) |  |  |  | 2023-02-01
MÁV | 5507001018 | Hegyeshalom - Ferencváros | < > | Ferencváros | Kelenföld | 2023 | 2023 | 20 | 20 | 2023-05-21 | 0:30 | 2023-05-21 | 4:30 | 4 h | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2023-02-01
MÁV | 5507001019 | Hegyeshalom - Ferencváros | < > | Ferencváros | Kelenföld | 2023 | 2023 | 21 | 21 | 2023-05-22 | 0:30 | 2023-05-22 | 4:30 | 4 h | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2023-02-01
MÁV | 5507001020 | Hegyeshalom - Ferencváros | < > | Ferencváros | Kelenföld | 2023 | 2023 | 21 | 21 | 2023-05-27 | 0:30 | 2023-05-27 | 4:30 | 4 h | Continuous | Others | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2023-02-01
MÁV | 5507001021 | Hegyeshalom - Ferencváros | < | Ferencváros | Kelenföld | 2023 | 2023 | 22 | 23 | 2023-06-02 | 22:00 | 2023-06-05 | 4:30 | 54 h 30 min | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation (closure of one track of a double track line) |  |  |  | 2023-02-01
MÁV | 5507001022 | Hegyeshalom - Ferencváros | < > | Ferencváros | Kelenföld | 2023 | 2023 | 22 | 22 | 2023-06-03 | 0:30 | 2023-06-03 | 4:30 | 4 h | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2023-02-01
MÁV | 5507001023 | Hegyeshalom - Ferencváros | < > | Ferencváros | Kelenföld | 2023 | 2023 | 22 | 22 | 2023-06-04 | 0:30 | 2023-06-04 | 4:30 | 4 h | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2023-02-01
MÁV | 5507001024 | Hegyeshalom - Ferencváros | > | Ferencváros | Kelenföld | 2023 | 2023 | 23 | 24 | 2023-06-09 | 22:00 | 2023-06-12 | 4:30 | 54 h 30 min | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation (closure of one track of a double track line) |  |  |  | 2023-02-01
MÁV | 5507001025 | Hegyeshalom - Ferencváros | < > | Ferencváros | Kelenföld | 2023 | 2023 | 23 | 23 | 2023-06-10 | 0:30 | 2023-06-10 | 4:30 | 4 h | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2023-02-01
MÁV | 5507001026 | Hegyeshalom - Ferencváros | < > | Ferencváros | Kelenföld | 2023 | 2023 | 23 | 23 | 2023-06-11 | 0:30 | 2023-06-11 | 4:30 | 4 h | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2023-02-01
MÁV | 5507001027 | Hegyeshalom - Ferencváros | < | Ferencváros | Kelenföld | 2023 | 2023 | 25 | 26 | 2023-06-23 | 22:00 | 2023-06-26 | 4:30 | 54 h 30 min | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation (closure of one track of a double track line) |  |  |  | 2023-02-01
MÁV | 5507001028 | Hegyeshalom - Ferencváros | < > | Ferencváros | Kelenföld | 2023 | 2023 | 25 | 25 | 2023-06-24 | 0:30 | 2023-06-24 | 4:30 | 4 h | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2023-02-01
MÁV | 5507001029 | Hegyeshalom - Ferencváros | < > | Ferencváros | Kelenföld | 2023 | 2023 | 25 | 25 | 2023-06-25 | 0:30 | 2023-06-25 | 4:30 | 4 h | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2023-02-01
MÁV | 5507001030 | Hegyeshalom - Ferencváros | < | Ferencváros | Kelenföld | 2023 | 2023 | 26 | 27 | 2023-06-30 | 22:00 | 2023-07-03 | 4:30 | 54 h 30 min | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation (closure of one track of a double track line) |  |  |  | 2023-02-01
MÁV | 5507001031 | Hegyeshalom - Ferencváros | < > | Ferencváros | Kelenföld | 2023 | 2023 | 26 | 26 | 2023-07-02 | 0:30 | 2023-07-02 | 4:30 | 4 h | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2023-02-01
MÁV | 5507001032 | Hegyeshalom - Ferencváros | < > | Ferencváros | Kelenföld | 2023 | 2023 | 27 | 27 | 2023-07-03 | 0:30 | 2023-07-03 | 4:30 | 4 h | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2023-02-01
MÁV | 5507001033 | Hegyeshalom - Ferencváros | < | Ferencváros | Kelenföld | 2023 | 2023 | 27 | 28 | 2023-07-07 | 22:00 | 2023-07-10 | 4:30 | 54 h 30 min | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation (closure of one track of a double track line) |  |  |  | 2023-02-01
MÁV | 5507001034 | Hegyeshalom - Ferencváros | > | Ferencváros | Kelenföld | 2023 | 2023 | 28 | 29 | 2023-07-14 | 22:00 | 2023-07-17 | 4:30 | 54 h 30 min | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation (closure of one track of a double track line) |  |  |  | 2023-02-01
MÁV | 5507001035 | Hegyeshalom - Ferencváros | > | Ferencváros | Kelenföld | 2023 | 2023 | 29 | 30 | 2023-07-21 | 22:00 | 2023-07-24 | 4:30 | 54 h 30 min | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation (closure of one track of a double track line) |  |  |  | 2023-02-01
MÁV | 5507001037 | Hegyeshalom - Ferencváros | > | Ferencváros | Kelenföld | 2023 | 2023 | 35 | 36 | 2023-09-01 | 22:00 | 2023-09-04 | 4:30 | 54 h 30 min | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation (closure of one track of a double track line) |  |  |  | 2023-02-01
MÁV | 5507001038 | Hegyeshalom - Ferencváros | > | Ferencváros | Kelenföld | 2023 | 2023 | 36 | 37 | 2023-09-08 | 22:00 | 2023-09-11 | 4:30 | 54 h 30 min | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation (closure of one track of a double track line) |  |  |  | 2023-02-01
MÁV | 5507001039 | Hegyeshalom - Ferencváros | < | Ferencváros | Kelenföld | 2023 | 2023 | 37 | 38 | 2023-09-15 | 22:00 | 2023-09-18 | 4:30 | 54 h 30 min | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation (closure of one track of a double track line) |  |  |  | 2023-02-01
MÁV | 5507001040 | Hegyeshalom - Ferencváros | > | Ferencváros | Kelenföld | 2023 | 2023 | 38 | 39 | 2023-09-22 | 22:00 | 2023-09-25 | 4:30 | 54 h 30 min | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation (closure of one track of a double track line) |  |  |  | 2023-02-01
MÁV | 5507001041 | Hegyeshalom - Ferencváros | < > | Ferencváros | Kelenföld | 2023 | 2023 | 38 | 38 | 2023-09-23 | 0:30 | 2023-09-23 | 4:30 | 4 h | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2023-02-01
MÁV | 5507001042 | Hegyeshalom - Ferencváros | < > | Ferencváros | Kelenföld | 2023 | 2023 | 38 | 38 | 2023-09-24 | 0:30 | 2023-09-24 | 4:30 | 4 h | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2023-02-01
MÁV | 5507001043 | Hegyeshalom - Ferencváros | < | Ferencváros | Kelenföld | 2023 | 2023 | 39 | 40 | 2023-09-29 | 22:00 | 2023-10-02 | 4:30 | 54 h 30 min | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation (closure of one track of a double track line) |  |  |  | 2023-02-01
MÁV | 5507001044 | Hegyeshalom - Ferencváros | < > | Ferencváros | Kelenföld | 2023 | 2023 | 39 | 39 | 2023-09-30 | 0:30 | 2023-09-30 | 4:30 | 4 h | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2023-02-01
MÁV | 5507001045 | Hegyeshalom - Ferencváros | < > | Ferencváros | Kelenföld | 2023 | 2023 | 39 | 39 | 2023-10-01 | 0:30 | 2023-10-01 | 4:30 | 4 h | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2023-02-01
MÁV | 5507001046 | Hegyeshalom - Ferencváros | > | Ferencváros | Kelenföld | 2023 | 2023 | 40 | 41 | 2023-10-06 | 22:00 | 2023-10-09 | 4:30 | 54 h 30 min | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation (closure of one track of a double track line) |  |  |  | 2023-02-01
MÁV | 5507001047 | Hegyeshalom - Ferencváros | < > | Ferencváros | Kelenföld | 2023 | 2023 | 40 | 40 | 2023-10-07 | 0:30 | 2023-10-07 | 4:30 | 4 h | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2023-02-01
MÁV | 5507001048 | Hegyeshalom - Ferencváros | < > | Ferencváros | Kelenföld | 2023 | 2023 | 40 | 40 | 2023-10-08 | 0:30 | 2023-10-08 | 4:30 | 4 h | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2023-02-01
MÁV | 5507001049 | Hegyeshalom - Ferencváros | < | Ferencváros | Kelenföld | 2023 | 2023 | 41 | 42 | 2023-10-13 | 22:00 | 2023-10-16 | 4:30 | 54 h 30 min | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation (closure of one track of a double track line) |  |  |  | 2023-02-01
MÁV | 5507001050 | Hegyeshalom - Ferencváros | < > | Ferencváros | Kelenföld | 2023 | 2023 | 41 | 41 | 2023-10-14 | 0:30 | 2023-10-14 | 4:30 | 4 h | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2023-02-01
MÁV | 5507001051 | Hegyeshalom - Ferencváros | < > | Ferencváros | Kelenföld | 2023 | 2023 | 41 | 41 | 2023-10-15 | 0:30 | 2023-10-15 | 4:30 | 4 h | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2023-02-01
MÁV | 5507001052 | Hegyeshalom - Ferencváros | > | Ferencváros | Kelenföld | 2023 | 2023 | 45 | 46 | 2023-11-10 | 22:00 | 2023-11-13 | 4:30 | 54 h 30 min | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation (closure of one track of a double track line) |  |  |  | 2023-02-01
MÁV | 5507001053 | Hegyeshalom - Ferencváros | > | Ferencváros | Kelenföld | 2023 | 2023 | 46 | 47 | 2023-11-17 | 22:00 | 2023-11-20 | 4:30 | 54 h 30 min | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation (closure of one track of a double track line) |  |  |  | 2023-02-01
MÁV | 5507001054 | Hegyeshalom - Ferencváros | < | Ferencváros | Kelenföld | 2023 | 2023 | 47 | 48 | 2023-11-24 | 22:00 | 2023-11-27 | 4:30 | 54 h 30 min | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation (closure of one track of a double track line) |  |  |  | 2023-02-01
MÁV | 5507001055 | Hegyeshalom - Ferencváros | > | Tata | Almásfüzitő-Felső | 2023 | 2023 | 22 | 22 | 2023-06-02 | 21:50 | 2023-06-03 | 5:00 | 7 h 10 min | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation (closure of one track of a double track line) |  |  |  | 2023-02-01
MÁV | 5507070001 | Štúrovo - Ferencváros | > | Verőce | Nagymaros | 2023 | 2023 | 7 | 7 | 2023-02-13 | 0:00 | 2023-02-19 | 23:59 | 7 Days | Continuous | Others |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507070002 | Štúrovo - Ferencváros | < | Verőce | Nagymaros | 2023 | 2023 | 8 | 8 | 2023-02-20 | 0:00 | 2023-02-26 | 23:59 | 7 Days | Continuous | Others |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507070003 | Štúrovo - Ferencváros | < | Nagymaros | Szob | 2023 | 2023 | 11 | 12 | 2023-03-17 | 23:20 | 2023-03-20 | 5:45 | 2 Days 6 h 25 min | Continuous | Others |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507070004 | Štúrovo - Ferencváros | > | Nagymaros | Szob | 2023 | 2023 | 12 | 12 | 2023-03-20 | 9:00 | 2023-03-24 | 22:00 | 4 Days 13 h | Continuous | Others |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507070005 | Štúrovo - Ferencváros | > | Nagymaros | Szob | 2023 | 2023 | 20 | 20 | 2023-05-15 | 9:00 | 2023-05-19 | 22:00 | 4 Days 13 h | Continuous | Others |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507070006 Deleted | Štúrovo - Ferencváros | > | Rákospalota-Újpest | Dunakeszi | 2023 | 2023 | 23 | 23 | 2023-06-09 | 22:00 | 2023-06-11 | 23:59 | 2 days 2 h | Continuous | Others |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507070007 Deleted | Štúrovo - Ferencváros | > | Rákosrendező | Rákospalota-Újpest | 2023 | 2023 | 25 | 26 | 2023-06-23 | 22:00 | 2023-06-27 | 3:50 | 3 Days 5 h 50 min | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507070008 Deleted | Štúrovo - Ferencváros | < > | Rákosrendező | Rákospalota-Újpest | 2023 | 2023 | 25 | 25 | 2023-06-24 | 0:20 | 2023-06-24 | 4:00 | 3 h 40 min | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507070009 Deleted | Štúrovo - Ferencváros | < > | Rákosrendező | Rákospalota-Újpest | 2023 | 2023 | 25 | 25 | 2023-06-25 | 0:20 | 2023-06-25 | 4:00 | 3 h 40 min | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507070010 Deleted | Štúrovo - Ferencváros | < | Rákosrendező | Rákospalota-Újpest | 2023 | 2023 | 26 | 27 | 2023-06-27 | 3:50 | 2023-07-08 | 23:59 | 11 H 20 h | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507070011 Deleted | Štúrovo - Ferencváros | < > | Rákosrendező | Rákospalota-Újpest | 2023 | 2023 | 26 | 26 | 2023-07-01 | 0:20 | 2023-07-01 | 4:00 | 3 h 40 min | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507070012 Deleted | Štúrovo - Ferencváros | < > | Rákosrendező | Rákospalota-Újpest | 2023 | 2023 | 26 | 26 | 2023-07-02 | 0:20 | 2023-07-02 | 4:00 | 3 h 40 min | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507070013 | Štúrovo - Ferencváros | > | Nagymaros | Szob | 2023 | 2023 | 32 | 32 | 2023-08-07 | 9:00 | 2023-08-11 | 22:00 | 4 Days 13 h | Continuous | Others |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507070014 | Štúrovo - Ferencváros | > | Nagymaros | Szob | 2023 | 2023 | 41 | 41 | 2023-10-09 | 9:00 | 2023-10-13 | 22:00 | 4 Days 13 h | Continuous | Others |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507082001 | Vác - Hatvan - Újszász | < > | Hatvan | Jászberény | 2023 | 2023 | 13 | 13 | 2023-03-27 | 0:00 | 2023-03-30 | 23:59 | 4 Days | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2022-08-28
MÁV | 5507082002 | Vác - Hatvan - Újszász | < > | Jászberény | Jászboldogháza-Jánoshida | 2023 | 2023 | 13 | 13 | 2023-03-31 | 0:00 | 2023-04-02 | 23:59 | 3 Days | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2022-08-28
MÁV | 5507082003 | Vác - Hatvan - Újszász | < > | Jászboldogháza-Jánoshida | Újszász | 2023 | 2023 | 14 | 14 | 2023-04-03 | 0:00 | 2023-04-05 | 23:59 | 3 Days | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2022-08-28
MÁV | 5507100001 Deleted | Ferencváros - Szajol (100) | > | Monor | Pilis | 2023 | 2023 | 11 | 18 | 2023-03-18 | 0:00 | 2023-05-05 | 23:59 | 49 Days | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507100002 Deleted | Ferencváros - Szajol (100) | < | Cegléd | Abony | 2023 | 2023 | 13 | 18 | 2023-04-01 | 0:00 | 2023-05-05 | 23:59 | 35 Days | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507100003 Deleted | Ferencváros - Szajol (100) | < | Monor | Pilis | 2023 | 2023 | 18 | 24 | 2023-05-06 | 0:00 | 2023-06-17 | 23:59 | 43 Days | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507100004 Deleted | Ferencváros - Szajol (100) | > | Cegléd | Abony | 2023 | 2023 | 18 | 24 | 2023-05-06 | 0:00 | 2023-06-17 | 23:59 | 42 Days | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507100005 | Ferencváros - Szajol (100) | < | Albertirsa | Ceglédbercel-Cserő | 2023 | 2023 | 24 | 26 | 2023-06-17 | 0:00 | 2023-07-01 | 1:30 | 13 Days | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507100006 | Ferencváros - Szajol (100) | > | Albertirsa | Ceglédbercel-Cserő | 2023 | 2023 | 26 | 28 | 2023-07-01 | 1:30 | 2023-07-15 | 2:00 | 14 Days | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507100007 | Ferencváros - Szajol (100) | < | Ceglédbercel-Cserő | Cegléd | 2023 | 2023 | 28 | 32 | 2023-07-15 | 0:00 | 2023-08-07 | 23:59 | 24 days | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507100008 | Ferencváros - Szajol (100) | > | Ceglédbercel-Cserő | Cegléd | 2023 | 2023 | 32 | 34 | 2023-08-08 | 0:00 | 2023-08-25 | 21:59 | 18 days | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507100009 | Ferencváros - Szajol (100) | > | Pilis | Albertirsa | 2023 | 2023 | 37 | 43 | 2023-09-11 | 4:00 | 2023-10-27 | 23:59 | 46 Days 20 h | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507100010 | Ferencváros - Szajol (100) | < | Pilis | Albertirsa | 2023 | 2023 | 43 | 49 | 2023-10-28 | 0:00 | 2023-12-08 | 23:59 | 42 Days | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507100001 | Ferencváros - Szajol (100) | < > | Albertirsa | Ceglédbercel-Cserő | 2023 | 2023 | 25 | 25 | 2023-06-23 | 23:25 | 2023-06-24 | 4:10 | 4 h 45 min | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2023-02-15
MÁV | 5507100002 | Ferencváros - Szajol (100) | < > | Albertirsa | Ceglédbercel-Cserő | 2023 | 2023 | 25 | 25 | 2023-06-24 | 23:25 | 2023-06-25 | 4:10 | 4 h 45 min | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2023-02-15
MÁV | 5507100003 | Ferencváros - Szajol (100) | < | Ceglédbercel-Cserő | Cegléd | 2023 | 2023 | 25 | 25 | 2023-06-24 | 23:25 | 2023-06-25 | 4:10 | 4 h 45 min | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation (closure of one track of a double track line) |  |  |  | 2023-02-15
MÁV | 5507100004 | Ferencváros - Szajol (100) | < > | Albertirsa | Ceglédbercel-Cserő | 2023 | 2023 | 26 | 26 | 2023-06-26 | 1:55 | 2023-06-26 | 3:10 | 1 h 25 min | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2023-02-15
MÁV | 5507100011 | Ferencváros - Szajol (100) | < | Ceglédbercel-Cserő | Cegléd | 2023 | 2023 | 26 | 26 | 2023-06-26 | 1:55 | 2023-06-26 | 3:10 | 1 h 25 min | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation (closure of one track of a double track line) |  |  |  | 2023-02-15
MÁV | 5507120027 | Ferencváros - Szolnok (120a) | < | Rákoshegy | Maglód | 2023 | 2023 | 10 | 11 | 2023-03-10 | 22:00 | 2023-03-13 | 4:00 | 2 day 6 h | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-12-01
MÁV | 5507120043 | Szajol - Curtici | < > | Békéscsaba | Lőkösháza Gr. | 2023 | 2023 | 15 | 15 | 2023-04-11 | 23:20 | 2023-04-12 | 3:20 | 4 h | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507120044 | Szajol - Curtici | < > | Békéscsaba | Lőkösháza Gr. | 2023 | 2023 | 15 | 15 | 2023-04-12 | 23:20 | 2023-04-13 | 3:20 | 4 h | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2022-08-28
MÁV | 5507120045 | Szajol - Curtici | < > | Békéscsaba | Lőkösháza Gr. | 2023 | 2023 | 15 | 15 | 2023-04-13 | 23:20 | 2023-04-14 | 3:20 | 4 h | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2022-08-28
MÁV | 5507120046 | Szajol - Curtici | < > | Békéscsaba | Lőkösháza Gr. | 2023 | 2023 | 15 | 15 | 2023-04-14 | 23:20 | 2023-04-15 | 3:20 | 4 h | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2022-08-28
MÁV | 5507120047 | Szajol - Curtici | < > | Békéscsaba | Lőkösháza Gr. | 2023 | 2023 | 15 | 15 | 2023-04-15 | 23:20 | 2023-04-16 | 3:20 | 4 h | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2022-08-28
MÁV | 5507120048 | Szajol - Curtici | < > | Békéscsaba | Lőkösháza Gr. | 2023 | 2023 | 15 | 16 | 2023-04-16 | 23:20 | 2023-04-17 | 3:20 | 4 h | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2022-08-28
MÁV | 5507120049 | Szajol - Curtici | < > | Békéscsaba | Lőkösháza Gr. | 2023 | 2023 | 16 | 16 | 2023-04-17 | 23:20 | 2023-04-18 | 3:20 | 4 h | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2022-08-28
MÁV | 5507120050 | Szajol - Curtici | < > | Békéscsaba | Lőkösháza Gr. | 2023 | 2023 | 16 | 16 | 2023-04-18 | 23:20 | 2023-04-19 | 3:20 | 4 h | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2022-08-28
MÁV | 5507120051 | Szajol - Curtici | < > | Békéscsaba | Lőkösháza Gr. | 2023 | 2023 | 16 | 16 | 2023-04-19 | 23:20 | 2023-04-20 | 3:20 | 4 h | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2022-08-28
MÁV | 5507120052 | Szajol - Curtici | < > | Békéscsaba | Lőkösháza Gr. | 2023 | 2023 | 16 | 16 | 2023-04-20 | 23:20 | 2023-04-21 | 3:20 | 4 h | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2022-08-28
MÁV | 5507120053 | Szajol - Curtici | < > | Békéscsaba | Lőkösháza Gr. | 2023 | 2023 | 16 | 16 | 2023-04-21 | 23:20 | 2023-04-22 | 3:20 | 4 h | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2022-08-28
MÁV | 5507120054 | Szajol - Curtici | < > | Békéscsaba | Lőkösháza Gr. | 2023 | 2023 | 16 | 16 | 2023-04-22 | 23:20 | 2023-04-23 | 3:20 | 4 h | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2022-08-28
MÁV | 5507120055 | Szajol - Curtici | < > | Békéscsaba | Lőkösháza Gr. | 2023 | 2023 | 16 | 17 | 2023-04-23 | 23:20 | 2023-04-24 | 3:20 | 4 h | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2022-08-28
máv | 5507120057 | Szajol - Curtici | < > | Békéscsaba | Lőkösháza Gr. | 2023 | 2023 | 17 | 17 | 2023-04-24 | 23:20 | 2023-04-25 | 3:20 | 4 h | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2022-08-28
MÁV | 5507120058 | Szajol - Curtici | < > | Békéscsaba | Lőkösháza Gr. | 2023 | 2023 | 17 | 17 | 2023-04-25 | 23:20 | 2023-04-26 | 3:20 | 4 h | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2022-08-28
MÁV | 5507120059 | Szajol - Curtici | < > | Békéscsaba | Lőkösháza Gr. | 2023 | 2023 | 17 | 17 | 2023-04-26 | 23:20 | 2023-04-27 | 3:20 | 4 h | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2022-08-28
MÁV | 5507120060 | Szajol - Curtici | < > | Békéscsaba | Lőkösháza Gr. | 2023 | 2023 | 17 | 17 | 2023-04-27 | 23:20 | 2023-04-28 | 3:20 | 4 h | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2022-08-28
MÁV | 5507120061 | Szajol - Curtici | < | Szajol | Tiszatenyő | 2023 | 2023 | 18 | 19 | 2023-05-02 | 6:00 | 2023-05-11 | 6:00 | 216 h | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation (closure of one track of a double track line) |  |  |  | 2023-02-15
MÁV | 5507120062 | Ferencváros - Szolnok (120a) | > | Nagykáta | Tápiószele | 2023 | 2023 | 23 | 23 | 2023-06-05 | 22:30 | 2023-06-06 | 5:00 | 6 h 30 min | Continuous | Others |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507120063 | Ferencváros - Szolnok (120a) | > | Nagykáta | Tápiószele | 2023 | 2023 | 23 | 23 | 2023-06-06 | 22:30 | 2023-06-07 | 5:00 | 6 h 30 min | Continuous | Others |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507120064 | Ferencváros - Szolnok (120a) | < | Nagykáta | Tápiószele | 2023 | 2023 | 23 | 23 | 2023-06-07 | 22:30 | 2023-06-08 | 5:00 | 6 h 30 min | Continuous | Others |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507120065 | Ferencváros - Szolnok (120a) | < | Nagykáta | Tápiószele | 2023 | 2023 | 23 | 23 | 2023-06-08 | 22:30 | 2023-06-09 | 5:00 | 6 h 30 min | Continuous | Others |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507120066 | Ferencváros - Szolnok (120a) | > | Újszász | Szolnok | 2023 | 2023 | 24 | 24 | 2023-06-12 | 22:30 | 2023-06-13 | 5:00 | 6 h 30 min | Continuous | Others |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507120067 | Ferencváros - Szolnok (120a) | > | Újszász | Szolnok | 2023 | 2023 | 24 | 24 | 2023-06-13 | 22:30 | 2023-06-14 | 5:00 | 6 h 30 min | Continuous | Others |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507120068 | Ferencváros - Szolnok (120a) | > | Újszász | Szolnok | 2023 | 2023 | 24 | 24 | 2023-06-14 | 22:30 | 2023-06-15 | 5:00 | 6 h 30 min | Continuous | Others |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507120069 | Ferencváros - Szolnok (120a) | < | Újszász | Szolnok | 2023 | 2023 | 24 | 24 | 2023-06-15 | 22:30 | 2023-06-16 | 5:00 | 6 h 30 min | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507120070 | Ferencváros - Szolnok (120a) | > | Újszász | Szolnok | 2023 | 2023 | 34 | 34 | 2023-08-25 | 21:00 | 2023-08-26 | 6:30 | 9 h 30 min | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507120071 | Ferencváros - Szolnok (120a) | < | Újszász | Szolnok | 2023 | 2023 | 34 | 34 | 2023-08-26 | 21:00 | 2023-08-27 | 6:30 | 9 h 30 min | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507120072 | Ferencváros - Szolnok (120a) | < | Újszász | Szolnok | 2023 | 2023 | 35 | 35 | 2023-09-01 | 21:00 | 2023-09-02 | 6:30 | 9 h 30 min | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507120073 | Ferencváros - Szolnok (120a) | > | Újszász | Szolnok | 2023 | 2023 | 35 | 35 | 2023-09-02 | 21:00 | 2023-09-03 | 6:30 | 9 h 30 min | Continuous | Track & Rail |  | LT | [6 empty] | D |  | Single line operation |  |  |  | 2022-08-28
MÁV | 5507101001 | Szajol - PL - Biharkeresztes | < > | Püspökladány | Biharkeresztes oh. | 2023 | 2023 | 29 | 31 | 2023-07-20 | 0:00 | 2023-08-05 | 23:59 | 16 days | Continuous | Track & Rail | T | LT | S | [5 empty] | D |  | Total closure |  |  |  | 2022-10-20
CFR | 5312707 | Simeria - Brasov | < > | Brașov | Stupini | 2023 | 2023 | 1 | 22 | 2023-01-01 | 0:00 | 2023-05-31 | 23:59 | 553d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312708 | Simeria - Brasov | < > | Brașov | Stupini | 2023 | 2024 | 22 | 52 | 2023-06-01 | 0:00 | 2024-12-31 | 23:59 | 1020d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312709 | Simeria - Brasov | < > | Stupini |  | 2023 | 2023 | 18 | 22 | 2023-05-02 | 0:00 | 2023-05-31 | 23:59 | 30d | Continuous | Track & Rail | T |  |  |  |  | C,, | R,, |  |  |  | Total closure
CFR | 5312710 | Simeria - Brasov | < > | Stupini | Bod | 2023 | 2023 | 1 | 22 | 2023-01-01 | 0:00 | 2023-05-31 | 23:59 | 553d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312711 | Simeria - Brasov | < > | Stupini | Bod | 2023 | 2024 | 22 | 3 | 2023-06-01 | 0:00 | 2024-01-15 | 23:59 | 229d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312712 | Simeria - Brasov | < > | Stupini | Bod | 2022 | 2023 | 30 | 24 | 2022-07-25 | 0:00 | 2023-06-14 | 23:59 | 325d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312713 | Simeria - Brasov | < > | Stupini | Bod | 2023 | 2023 | 18 | 22 | 2023-05-02 | 0:00 | 2023-05-31 | 23:59 | 30d | Continuous | Track & Rail | T |  |  |  |  | C,, | R,, |  |  |  | Total closure
CFR | 5312714 | Simeria - Brasov | < > | Stupini | Bod | 2023 | 2023 | 24 | 33 | 2023-06-14 | 0:00 | 2023-08-17 | 23:59 | 65d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312715 | Simeria - Brasov | < > | Stupini | Bod | 2023 | 2024 | 33 | 27 | 2023-08-18 | 0:00 | 2024-07-04 | 23:59 | 322d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312716 | Simeria - Brasov | < > | Bod | Feldioara | 2022 | 2023 | 30 | 33 | 2022-07-25 | 0:00 | 2023-08-17 | 23:59 | 389d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312717 | Simeria - Brasov | < > | Bod | Feldioara | 2023 | 2024 | 33 | 52 | 2023-08-18 | 0:00 | 2024-12-31 | 23:59 | 567d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312718 | Simeria - Brasov | < > | Bod | Feldioara | 2023 | 2023 | 18 | 22 | 2023-05-02 | 0:00 | 2023-05-31 | 23:59 | 30d | Continuous | Track & Rail | T |  |  |  |  | C,, | R,, |  |  |  | Total closure
CFR | 5312719 | Simeria - Brasov | < > | Bod | Feldioara | 2023 | 2024 | 22 | 30 | 2023-06-01 | 0:00 | 2024-07-28 | 23:59 | 424d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312720 | Simeria - Brasov | < > | Bod | Feldioara | 2023 | 2025 | 33 | 10 | 2023-08-18 | 0:00 | 2025-03-06 | 23:59 | 567d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312721 | Simeria - Brasov | < > | Feldioara | Apața | 2022 | 2023 | 47 | 24 | 2022-11-25 | 0:00 | 2023-06-14 | 23:59 | 202d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312722 | Simeria - Brasov | < > | Feldioara | Apața | 2023 | 2023 | 24 | 49 | 2023-06-14 | 0:00 | 2023-12-05 | 23:59 | 175d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312723 | Simeria - Brasov | < > | Feldioara | Apața | 2023 | 2024 | 49 | 52 | 2023-12-05 | 0:00 | 2024-12-31 | 23:59 | 458d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312724 | Simeria - Brasov | < > | Feldioara | Apața | 2023 | 2023 | 7 | 9 | 2023-02-15 | 0:00 | 2023-03-01 | 23:59 | 15d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312725 | Simeria - Brasov | < > | Feldioara | Apața | 2023 | 2024 | 9 | 29 | 2023-03-02 | 0:00 | 2024-07-20 | 23:59 | 507d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312726 | Simeria - Brasov | < > | Feldioara | Apața | 2023 | 2024 | 29 | 6 | 2023-07-21 | 0:00 | 2024-02-05 | 23:59 | 200d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312727 | Simeria - Brasov | < > | Feldioara | Apața | 2023 | 2024 | 49 | 52 | 2023-12-05 | 0:00 | 2024-12-31 | 23:59 | 458d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312728 | Simeria - Brasov | < > | Apata | Augustin | 2023 | 2023 | 1 | 45 | 2023-01-01 | 0:00 | 2023-11-08 | 23:59 | 938d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312729 | Simeria - Brasov | < > | Apata | Augustin | 2023 | 2024 | 46 | 46 | 2023-11-15 | 0:00 | 2024-11-15 | 23:59 | 367d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312730 | Simeria - Brasov | < > | Augustin | Racos | 2023 | 2024 | 17 | 23 | 2023-04-24 | 0:00 | 2024-06-07 | 23:59 | 411d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312731 | Simeria - Brasov | < > | Racos | Rupea | 2023 | 2024 | 1 | 32 | 2023-01-01 | 0:00 | 2024-08-05 | 23:59 | 700d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312732 | Simeria - Brasov | < > | Racos | Rupea | 2023 | 2024 | 1 | 32 | 2023-01-01 | 0:00 | 2024-08-07 | 23:59 | 884d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312733 | Simeria - Brasov | < > | Rupea | Cața | 2023 | 2023 | 35 | 45 | 2023-08-30 | 0:00 | 2023-11-09 | 23:59 | 72d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312734 | Simeria - Brasov | < > | Rupea | Cața | 2023 | 2023 | 35 | 41 | 2023-08-30 | 0:00 | 2023-10-09 | 23:59 | 41d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312735 | Simeria - Brasov | < > | Rupea | Cața | 2023 | 2024 | 45 | 51 | 2023-11-10 | 0:00 | 2024-12-16 | 23:59 | 403d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312736 | Simeria - Brasov | < > | Rupea | Cața | 2022 | 2023 | 22 | 19 | 2022-06-01 | 0:00 | 2023-05-11 | 23:59 | 345d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312737 | Simeria - Brasov | < > | Rupea | Cața | 2023 | 2024 | 5 | 3 | 2023-02-02 | 0:00 | 2024-01-16 | 23:59 | 349d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312738 | Simeria - Brasov | < > | Cața | Beia | 2023 | 2024 | 5 | 3 | 2023-02-02 | 0:00 | 2024-01-16 | 23:59 | 349d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312739 | Simeria - Brasov | < > | Cața | Beia | 2022 | 2023 | 22 | 19 | 2022-06-01 | 0:00 | 2023-05-11 | 23:59 | 345d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312740 | Simeria - Brasov | < > | Cața | Beia | 2023 | 2024 | 19 | 10 | 2023-05-12 | 0:00 | 2024-03-07 | 23:59 | 301d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312741 | Simeria - Brasov | < > | Cața | Beia | 2023 | 2024 | 19 | 10 | 2023-05-12 | 0:00 | 2024-03-07 | 23:59 | 301d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312742 | Simeria - Brasov | < > | Cața | Beia | 2023 | 2024 | 5 | 3 | 2023-02-02 | 0:00 | 2024-01-16 | 23:59 | 349d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312743 | Simeria - Brasov | < > | Beia | Mureni | 2023 | 2024 | 19 | 10 | 2023-05-12 | 0:00 | 2024-03-07 | 23:59 | 301d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312744 | Simeria - Brasov | < > | Beia | Mureni | 2023 | 2024 | 44 | 40 | 2023-10-30 | 0:00 | 2024-09-30 | 23:59 | 337d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312745 | Simeria - Brasov | < > | Beia | Mureni | 2023 | 2024 | 19 | 10 | 2023-05-12 | 0:00 | 2024-03-07 | 23:59 | 301d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312746 | Simeria - Brasov | < > | Beia | Mureni | 2023 | 2024 | 44 | 40 | 2023-10-30 | 0:00 | 2024-09-30 | 23:59 | 337d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312747 | Simeria - Brasov | < > | Mureni | Vânători | 2023 | 2024 | 42 | 52 | 2023-10-16 | 0:00 | 2024-12-31 | 23:59 | 523d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312748 | Simeria - Brasov | < > | Mureni | Vânători | 2022 | 2023 | 17 | 41 | 2022-05-01 | 0:00 | 2023-10-15 | 23:59 | 533d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312749 | Simeria - Brasov | < > | Mureni | Vânători | 2023 | 2024 | 42 | 52 | 2023-10-16 | 0:00 | 2024-12-31 | 23:59 | 523d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312750 | Simeria - Brasov | < > | Mureni | Vânători | 2023 | 2024 | 1 | 11 | 2023-01-01 | 0:00 | 2024-03-17 | 23:59 | 495d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312751 | Simeria - Brasov | < > | Mureni | Vânători | 2023 | 2024 | 42 | 52 | 2023-10-16 | 0:00 | 2024-12-31 | 23:59 | 523d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312752 | Simeria - Brasov | < > | Vânători | Albești | 2023 | 2024 | 42 | 40 | 2023-10-16 | 0:00 | 2024-10-01 | 23:59 | 352d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312753 | Simeria - Brasov | < > | Vânători | Albești | 2023 | 2024 | 24 | 11 | 2023-06-16 | 0:00 | 2024-03-17 | 23:59 | 276d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312754 | Simeria - Brasov | < > | Vânători | Albești | 2023 | 2023 | 1 | 24 | 2023-01-01 | 0:00 | 2023-06-15 | 23:59 | 788d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312755 | Simeria - Brasov | < > | Vânători | Albești | 2023 | 2024 | 24 | 11 | 2023-06-16 | 0:00 | 2024-03-17 | 23:59 | 276d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312756 | Simeria - Brasov | < > | Vânători | Albești | 2022 | 2023 | 39 | 41 | 2022-10-01 | 0:00 | 2023-10-15 | 23:59 | 380d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312757 | Simeria - Brasov | < > | Vânători | Albești | 2023 | 2024 | 42 | 40 | 2023-10-16 | 0:00 | 2024-10-01 | 23:59 | 352d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312758 | Simeria - Brasov | < > | Albești |  | 2023 | 2023 | 41 | 42 | 2023-10-12 | 0:00 | 2023-10-16 | 23:59 | 5d | Continuous | Track & Rail | T |  |  |  |  | C,, | R,, |  |  |  | Total closure
CFR | 5312759 | Simeria - Brasov | < > | Albești | Sighisoara | 2022 | 2023 | 39 | 6 | 2022-10-01 | 0:00 | 2023-02-10 | 23:59 | 133d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312760 | Simeria - Brasov | < > | Albești | Sighisoara | 2023 | 2023 | 1 | 24 | 2023-01-01 | 0:00 | 2023-06-15 | 23:59 | 788d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312761 | Simeria - Brasov | < > | Albești | Sighisoara | 2023 | 2024 | 24 | 49 | 2023-06-16 | 0:00 | 2024-12-07 | 23:59 | 541d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312762 | Arad - Simeria | < > | Barzava | Milova | 2022 | 2023 | 47 | 30 | 2022-11-25 | 0:00 | 2023-07-24 | 23:59 | 242d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312763 | Arad - Simeria | < > | Barzava | Milova | 2022 | 2023 | 47 | 34 | 2022-11-25 | 0:00 | 2023-08-25 | 23:59 | 274d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312764 | Arad - Simeria | < > | Barzava | Milova | 2023 | 2023 | 30 | 34 | 2023-07-24 | 0:00 | 2023-08-25 | 23:59 | 33d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312765 | Arad - Simeria | < > | Milova |  | 2023 | 2023 | 26 | 27 | 2023-07-02 | 0:00 | 2023-07-09 | 23:59 | 8d | Continuous | Track & Rail | T |  |  |  |  | C,, | R,, |  |  |  | Total closure
CFR | 5312766 | Arad - Simeria | < > | Milova | Radna | 2023 | 2023 | 1 | 30 | 2023-01-01 | 0:00 | 2023-07-24 | 23:59 | 809d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312767 | Arad - Simeria | < > | Milova | Radna | 2023 | 2023 | 30 | 34 | 2023-07-24 | 0:00 | 2023-08-25 | 23:59 | 33d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312768 | Arad - Simeria | < > | Radna |  | 2023 | 2023 | 33 | 34 | 2023-08-18 | 0:00 | 2023-08-25 | 23:59 | 8d | Continuous | Track & Rail | T |  |  |  |  | C,, | R,, |  |  |  | Total closure
CFR | 5312770 | Arad - Simeria | < > | Ilteu | Savarsin | 2023 | 2023 | 1 | 49 | 2023-01-01 | 0:00 | 2023-12-04 | 23:59 | 958d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312771 | Arad - Simeria | < > | Savarsin | Varadia | 2023 | 2023 | 1 | 31 | 2023-01-01 | 0:00 | 2023-08-01 | 23:59 | 774d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312772 | Arad - Simeria | < > | Savarsin | Varadia | 2023 | 2023 | 1 | 36 | 2023-01-01 | 0:00 | 2023-09-10 | 23:59 | 814d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312773 | Arad - Simeria | < > | Savarsin | Varadia | 2023 | 2024 | 36 | 36 | 2023-09-10 | 0:00 | 2024-09-04 | 23:59 | 361d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312774 | Arad - Simeria | < > | Varadia | Batuta | 2023 | 2024 | 1 | 36 | 2023-01-01 | 0:00 | 2024-09-06 | 23:59 | 2019d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312775 | Arad - Simeria | < > | Barzava | Barzava Noua | 2023 | 2024 | 1 | 36 | 2023-01-01 | 0:00 | 2024-09-06 | 23:59 | 1907d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312776 | Arad - Simeria | < > | Gurasada | Campuri Surduc | 2022 | 2023 | 30 | 30 | 2022-07-29 | 0:00 | 2023-07-28 | 23:59 | 365d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312777 | Arad - Simeria | < > | Campuri Surduc | Zam | 2022 | 2023 | 30 | 30 | 2022-07-25 | 0:00 | 2023-07-28 | 23:59 | 369d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312778 | Arad - Simeria | < > | Zam | Ilteu | 2023 | 2023 | 22 | 22 | 2023-05-31 | 0:00 | 2023-06-01 | 23:59 | 2d | Continuous | Track & Rail | T |  |  |  |  | C,, | R,, |  |  |  | Total closure
CFR | 5312779 | Arad - Simeria | < > | Simeria | Deva | 2023 | 2023 | 1 | 38 | 2023-01-01 | 0:00 | 2023-09-23 | 23:59 | 1249d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312780 | Arad - Simeria | < > | Simeria | Deva | 2023 | 2023 | 1 | 51 | 2023-01-01 | 0:00 | 2023-12-22 | 23:59 | 1339d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312781 | Arad - Simeria | < > | Simeria | Deva | 2023 | 2023 | 15 | 15 | 2023-04-11 | 0:00 | 2023-04-11 | 23:59 | 1d | Continuous | Track & Rail | T |  |  |  |  | C,, | R,, |  |  |  | Total closure
CFR | 5312782 | Arad - Simeria | < > | Simeria | Deva | 2023 | 2023 | 16 | 16 | 2023-04-23 | 0:00 | 2023-04-23 | 23:59 | 1d | Continuous | Track & Rail | T |  |  |  |  | C,, | R,, |  |  |  | Total closure
CFR | 5312783 | Arad - Simeria | < > | Deva | Mintia | 2023 | 2023 | 1 | 38 | 2023-01-01 | 0:00 | 2023-09-23 | 23:59 | 1555d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312784 | Arad - Simeria | < > | Deva | Mintia | 2023 | 2023 | 1 | 51 | 2023-01-01 | 0:00 | 2023-12-22 | 23:59 | 1645d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312785 | Arad - Simeria | < > | Branisca | Mintia | 2023 | 2023 | 16 | 17 | 2023-04-19 | 0:00 | 2023-04-25 | 23:59 | 7d | Continuous | Track & Rail | T |  |  |  |  | C,, | R,, |  |  |  | Total closure
CFR | 5312786 | Arad - Simeria | < > | Branisca | Mintia | 2023 | 2023 | 20 | 21 | 2023-05-20 | 0:00 | 2023-05-26 | 23:59 | 7d | Continuous | Track & Rail | T |  |  |  |  | C,, | R,, |  |  |  | Total closure
CFR | 5312787 | Arad - Simeria | < > | Branisca | Mintia | 2023 | 2023 | 17 | 38 | 2023-04-25 | 0:00 | 2023-09-23 | 23:59 | 152d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312788 | Arad - Simeria | < > | Branisca | Mintia | 2023 | 2023 | 21 | 51 | 2023-05-26 | 0:00 | 2023-12-22 | 23:59 | 211d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312789 | Arad - Simeria | < > | Ilia | Gurasada | 2022 | 2023 | 40 | 38 | 2022-10-03 | 0:00 | 2023-09-23 | 23:59 | 356d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312790 | Arad - Simeria | < > | Ilia | Gurasada | 2022 | 2023 | 46 | 51 | 2022-11-18 | 0:00 | 2023-12-22 | 23:59 | 400d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312792 | Biharkeresztes - Coslariu | < > | Episcopia Bihor | Cluj Napoca | 2023 | 2024 | 18 | 52 | 2023-05-01 | 0:00 | 2024-12-31 | 23:59 | 975d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312792 | Biharkeresztes - Coslariu | < > | Episcopia Bihor | Cluj Napoca | 2025 | 2025 | 1 | 52 | 2025-01-01 | 0:00 | 2025-12-31 | 23:59 | 975d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
CFR | 5312793 | Biharkeresztes - Coslariu | < > | Valea Florilor | Boju | 2023 | 2024 | 22 | 52 | 2023-06-01 | 0:00 | 2024-12-31 | 23:59 | 580d | Continuous | Track & Rail |  | LT | S | [7 empty] | one track closed and the other one with speed restriction
NRIC | 5212595 | Sofia - Promachon | < > | Volujak | Sofia | 2022 | 2023 | 49 | 49 | 2022-12-11 | 0:00 | 2023-12-09 | 0:00 | 1 year | Continuous | Maintenance |  | LT | S | [5 empty] | D |  | Full interuption of the traffic along one track |  |  |  | 2021-12-23
NRIC | 5212596 | Sofia - Plovdiv | < > | Sofia | Sofia | 2022 | 2023 | 49 | 49 | 2022-12-11 | 0:00 | 2023-12-09 | 0:00 | 1 year | Continuous | Maintenance |  | ST | [6 empty] | D |  | Partial interuptin of station tracks |  |  |  | 2021-12-23
NRIC | 5212597 | Sofia - Plovdiv | < > | Sofia | Iskar | 2022 | 2023 | 49 | 49 | 2022-12-11 | 0:00 | 2023-12-09 | 0:00 | 1 year | Continuous | Maintenance |  | LT | S | [5 empty] | D |  | Full interuption of the traffic along one track |  |  |  | 2021-12-23
NRIC | 5212598 | Sofia - Plovdiv | < > | Iskar | Elin Pelin | 2022 | 2023 | 49 | 49 | 2022-12-11 | 0:00 | 2023-12-09 | 0:00 | 1 year | Continuous | Maintenance |  | LT | S | [5 empty] | D |  | Full interuption of the traffic along one track |  |  |  | 2021-12-23
NRIC | 5212599 | Sofia - Plovdiv | < > | Verinsko | Kostenets | 2022 | 2023 | 49 | 49 | 2022-12-11 | 0:00 | 2023-12-09 | 0:00 | 1 year | Continuous | Maintenance |  | LT | S | [5 empty] | D |  | Full interuption of the traffic along one track |  |  |  | 2021-12-23
NRIC | 5212600 | Sofia - Plovdiv | < > | Belovo | Septemvri | 2022 | 2023 | 49 | 49 | 2022-12-11 | 0:00 | 2023-12-09 | 0:00 | 1 year | Continuous | Maintenance |  | LT | S | [5 empty] | D |  | Full interuption of the traffic along one track |  |  |  | 2021-12-23
NRIC | 5212601 | Plovdiv - Mihailovo | < > | Orizovo | Mihaylovo | 2023 | 2023 | 24 | 41 | 2023-06-15 | 0:00 | 2023-10-15 | 0:00 | 4 months | Continuous | Maintenance | T | [5 empty] | R |  | D |  | Full Interuption of the traffic |  |  |  | 2021-12-23 |  |  | Re: Plovdiv - Dimitrovgrad - Mihailovo
NRIC | 5212602 | Plovdiv - Mihailovo | < > | Lozarevo | Lozarevo | 2022 | 2023 | 49 | 49 | 2022-12-11 | 9:00 | 2023-12-09 | 16:00 | 7 hours | Periodical | Maintenance |  | LT | [6 empty] | D |  | 7-hour interruption of the traffic |  |  |  | 2021-12-23
NRIC | 5212603 | Stara Zagora - Dimitrovgrad | < > | Mihailovo | Mericleri | 2023 | 2023 | 9 | 11 | 2023-03-01 | 0:00 | 2023-03-15 | 0:00 | 15 days | Continuous | Maintenance | T | [5 empty] | R |  | D |  | Full Interuption of the traffic |  |  |  | 2021-12-23 |  |  | Simionovgrad-Nova Zagora
NRIC | 5212604 | Sofia - Promachon | < > | Blagoevgrad | Kresna | 2023 | 2023 | 31 | 33 | 2023-08-01 | 0:00 | 2023-08-20 | 0:00 | 20 days | Continuous | Maintenance | T | [9 empty] | Full Interuption of the traffic |  |  |  | 2021-12-23 |  |  | no capacity is available
NRIC | 5212605 | Vidin tovarna - Mezdra jug | < > | Brusarci | Vidin Tovarna | 2023 | 2023 | 31 | 32 | 2023-08-01 | 0:00 | 2023-08-10 | 0:00 | 10 days | Continuous | Maintenance | T | [7 empty] | D |  | Full Interuption of the traffic |  |  |  | 2021-12-23 |  |  | no capacity is available
NRIC | 5212606 | Karnobat - Nova Zagora | < > | Jambol | Zimnitsa | 2023 | 2023 | 35 | 44 | 2023-09-01 | 0:00 | 2023-10-30 | 0:00 | 2 months | Continuous | Maintenance | T | [7 empty] | D |  | Full Interuption of the traffic |  |  |  | 2021-12-23 |  |  | Re: Stara Zagora-Tulovo-Karnobat
NRIC | 5212607 | Nova Zagora - Simeonovgrad | < > | Nova Zagora | Simeonevgrad | 2023 | 2023 | 13 | 22 | 2023-04-01 | 0:00 | 2023-05-31 | 0:00 | 2 months | Continuous | Maintenance | T | [5 empty] | R |  | D |  | Full Interuption of the traffic |  |  |  | 2021-12-23 |  |  | Re: Nova Zagora - Stara Zagora Dimitrovgrad - Simeonovgrad
NRIC | 5212608 | Ruse - Karnobat | < > | Sindel | Junak | 2023 | 2023 | 34 | 37 | 2023-08-25 | 0:00 | 2023-09-15 | 0:00 | 21 days | Continuous | Maintenance | T | [5 empty] | R |  | D |  | Full Interuption of the traffic |  |  |  | 2021-12-23 |  |  | Re: Kaspican-Chumen-Komunari
NRIC | 5212609 | Videle - Ruse | < > | Ruse razpredelitelna | Giurgiu Nord | 2023 | 2023 | 22 | 39 | 2023-06-01 | 8:00 | 2023-09-30 | 16:00 | 8 hours | Periodical | Maintenance |  | LT | [6 empty] | D |  | 8-hour interruption of the traffic |  |  |  | 2021-12-23
NRIC | 5212610 | Ruse - Karnobat | < > | Ruse razpredelitelna | Kaspican | 2023 | 2023 | 9 | 48 | 2023-03-01 | 9:00 | 2023-11-30 | 16:00 | 7 hours | Periodical | Maintenance |  | LT | [6 empty] | D |  | 7-hour interruption of the traffic |  |  |  | 2021-12-23
NRIC | 5212611 | Ruse - Karnobat | < > | Obrazcov chiflik |  | 2023 | 2023 | 16 | 17 | 2023-04-20 | 0:00 | 2023-04-25 | 0:00 | 6 days | Continuous | Maintenance | T | [5 empty] | R |  | D |  | Full Interuption of the traffic |  |  |  | 2021-12-23 |  |  | Re: Ruse razpredelitelna-Gorna Orqhovica-Kaspican
NRIC | 5212612 | Ruse - Karnobat | < > | Vetovo |  | 2023 | 2023 | 25 | 26 | 2023-06-20 | 0:00 | 2023-06-26 | 0:00 | 7 days | Continuous | Maintenance | T | [5 empty] | R |  | D |  | Full Interuption of the traffic |  |  |  | 2021-12-23 |  |  | Re: Ruse razpredelitelna-Gorna Orqhovica-Kaspican
NRIC | 5212613 | Ruse - Karnobat | < > | Prostorno |  | 2023 | 2023 | 39 | 40 | 2023-09-29 | 0:00 | 2023-10-04 | 0:00 | 6 days | Continuous | Maintenance | T | [5 empty] | R |  | D |  | Full Interuption of the traffic |  |  |  | 2021-12-23 |  |  | Re: Ruse razpredelitelna-Gorna Orqhovica-Kaspican
NRIC | 5212614 | Ruse - Karnobat | < > | Samuil |  | 2023 | 2023 | 16 | 17 | 2023-04-20 | 0:00 | 2023-04-25 | 0:00 | 6 days | Continuous | Maintenance | T | [5 empty] | R |  | D |  | Full Interuption of the traffic |  |  |  | 2021-12-23 |  |  | Re: Ruse razpredelitelna-Gorna Orqhovica-Kaspican
NRIC | 5212615 | Ruse - Karnobat | < > | Samuil |  | 2023 | 2023 | 24 | 25 | 2023-06-15 | 0:00 | 2023-06-20 | 0:00 | 6 days | Continuous | Maintenance | T | [5 empty] | R |  | D |  | Full Interuption of the traffic |  |  |  | 2021-12-23 |  |  | Re: Ruse razpredelitelna-Gorna Orqhovica-Kaspican
NRIC | 5212616 | Ruse - Karnobat | < > | Visoka poliana |  | 2023 | 2023 | 39 | 40 | 2023-09-29 | 0:00 | 2023-10-04 | 0:00 | 6 days | Continuous | Maintenance | T | [5 empty] | R |  | D |  | Full Interuption of the traffic |  |  |  | 2021-12-23 |  |  | Re: Ruse razpredelitelna-Gorna Orqhovica-Kaspican
OSE | 7312791 | Promachon - Strymonas | < > | Promachon border | Strymonas | 2023 | 2023 | 1 | 40 | 2023-01-08 | 7:00 | 2023-10-04 | 18:00 | 10 months | Continuous | Maintenance |  | LT | [8 empty] | Total closure every week from Sunday 7:00 till Wednesday 18:00 |  |  |  | 2023-01-05
Update
Delete
Change
New
Undo change/delete
Publish
New
Changed
Deleted
Map
Show all

## Graphic Overview
RFC 7 Overview
[5 empty] | 2023 | January | [30 empty] | February | [27 empty] | March | [30 empty] | April | [29 empty] | May | [30 empty] | June | [29 empty] | July | [30 empty] | August | [30 empty] | September | [29 empty] | October | [30 empty] | November | [29 empty] | December
Capacity Restriction | Type | Date from | Date to | Duration | IM |  | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4 | [6 empty] | 5 | [6 empty] | 6 | [6 empty] | 7 | [6 empty] | 8 | [6 empty] | 9 | [6 empty] | 10 | [6 empty] | 11 | [6 empty] | 12 | [6 empty] | 13 | [6 empty] | 14 | [6 empty] | 15 | [6 empty] | 16 | [6 empty] | 17 | [6 empty] | 18 | [6 empty] | 19 | [6 empty] | 20 | [6 empty] | 21 | [6 empty] | 22 | [6 empty] | 23 | [6 empty] | 24 | [6 empty] | 25 | [6 empty] | 26 | [6 empty] | 27 | [6 empty] | 28 | [6 empty] | 29 | [6 empty] | 30 | [6 empty] | 31 | [6 empty] | 32 | [6 empty] | 33 | [6 empty] | 34 | [6 empty] | 35 | [6 empty] | 36 | [6 empty] | 37 | [6 empty] | 38 | [6 empty] | 39 | [6 empty] | 40 | [6 empty] | 41 | [6 empty] | 42 | [6 empty] | 43 | [6 empty] | 44 | [6 empty] | 45 | [6 empty] | 46 | [6 empty] | 47 | [6 empty] | 48 | [6 empty] | 49 | [6 empty] | 50 | [6 empty] | 51 | [6 empty] | 52
Wilhelmshaven - Bremen | [5 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Bremerhaven - Bremen | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 3 | 3 | 3 | 5 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 1 | 1 | 1 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 3 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 5 | 3
Bremen - Hannover | [52 empty] | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 3 | 3 | 3 | 5 | 5 | 3 | 5 | 5 | 3 | 3 | 3 | 3 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 5 | 5 | 5 | 1 | 1 | 1 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 5 | 5 | 1 | 1 |  |  | 5 | 5 | 5
Hannover - Magdeburg | [66 empty] | 5 | 5 |  | 3 | 3 |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | [13 empty] | 3 | 3 | 3 | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [14 empty] | 3 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 3 | 3 |  |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 2 | 2 | 2 | 1 | 1 |  |  | 5 | 5 | 5 | 5 | 2 | 5 | 5 | 2 | 2 | 2 | 3 | 3 | 3 | [9 empty] | 1 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 3 | 3 | 5 | 3 | 3 | [8 empty] | 2 | 2 | 2 | 2 | 2 | 1 |  | 2 | 2 | 2 | 2 | [9 empty] | 1 | 1 | 1 | 1 | 3 | 3 |  | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | [5 empty] | 3 |  | 3 | 3 | 3 | 3 | 5 | 3 | 3 | 3 | 5 | 3 |  |  | 5
Magdeburg - Falkenberg | [68 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 5 | 5 | 5 |  |  | 5 | [10 empty] | 1 | 1 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [8 empty] | 3 |  |  |  | 5 | [17 empty] | 3 | 5 | [5 empty] | 3 | 5 | [25 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | 3 | 5 | 3 | 5 |  | 5 | 5 | [10 empty] | 3 | 3 |  |  | 3 | 5 | 5 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 5 | [33 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 1
Falkenberg - Dresden | [5 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 3 | 3 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 3
Hamburg - Magdeburg | [5 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 3 | 5 | 3 | 3 | 3 | 3 | 5 | 5 | 3 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 4 | 5 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 3 | 3 | 3 | 3 | 3
Rostock - Berlin | [5 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 5 | 3 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 3 | 3 | 3 | 5 | 5 | 5 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 4 | 4 | 3 | 3 | 3 | 3 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 3 | 3 | 3 | 5 | 4 | 4 | 4 | 4 | 4 | 3 | 3
Berlin - Dresden | [53 empty] | 3 | 5 | 5 | 3 | [25 empty] | 3 | [18 empty] | 5 |  |  | 1 | 2 | 2 | 1 | 5 | 5 | 5 | 5 | [7 empty] | 5 | 5 | 5 | 5 |  |  |  | 3 | 4 | 2 | 5 | 3 | 3 | 3 | [11 empty] | 5 | 5 | 5 |  |  |  | 5 | 5 | 5 | 5 |  |  | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 3 | 5 | 5 | 5 | 5 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [6 empty] | 3 | 3 | [7 empty] | 5 | 5 | [26 empty] | 5 | 5 | [5 empty] | 5 | 5 | [14 empty] | 3 | 3 | 3 | 1 | 1 | 3 |  | 5 | 3 | 3 | 5 | 3 | 5 | 5 | 3 | 3 | 3 | 5 | 5 | [13 empty] | 5 | [21 empty] | 5 | 5 |  |  |  | 3 | [14 empty] | 3 | 3 | 3 | 3
Dresden - Děčín | [5 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 |  |  |  |  | 3 |  |  | 2 | 2 | 2 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Děčín - Kolín | [26 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1
Děčín - Praha-Libeň | [99 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [19 empty] | 3 | 3 | 3 |  |  |  |  | 3 | 3 | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | [41 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [19 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
Praha-Libeň - Česká Třebová | [5 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Kolín - Brno-Maloměřice | [31 empty] | 1 | 1 | [6 empty] | 1 | 1 | [5 empty] | 2 | 2 | [5 empty] | 1 | 1 | [5 empty] | 1 | 1 | [5 empty] | 1 | 1 | [5 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  |  | 1 | 1 | [26 empty] | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Česká Třebová - Brno | [5 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [17 empty] | 1 | 1 | 1 | [70 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Brno - Břeclav | [20 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [6 empty] | 3 | 3 | 3 | 3 | 1 |  |  | 1 | 1 | [29 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | [18 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [7 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [43 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [30 empty] | 1 | 1 | 1 | 1 |  | 5 | 5 | [23 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [26 empty] | 1 | 1 | 1 | 1
Břeclav - Wien | [19 empty] | 1 | 1 | 1 | 1 | [228 empty] | 2 | [27 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Gänserndorf - Devinska N.V.
Wien - Ebenfurth - Sopron | [5 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Gramatneusiedl - Wr. Neustadt
Wien - Wr. Neustadt
Wr. Neustadt - Sopron
Parndorf - Bratislava
Wien - Hegyeshalom | [5 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Břeclav - Kúty | [5 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Kúty - Bratislava
Bratislava - Rajka | [97 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [36 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Bratislava - Štúrovo | [12 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Nové Zámky - Komárom | [248 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Kúty - Galanta
Rajka - Hegyeshalom | [105 empty] | 2 | 2 | 2
Sopron - Győr | [111 empty] | 2 | 2 | 2 | 2 | 2 | [38 empty] | 5 | 5 | 5 | 5 | 5 | [7 empty] | 5 | 5 | 5 | 5 | 5 | 5 | [23 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5
Hegyeshalom - Ferencváros | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [68 empty] | 3 | 3 | 3 | 3 |  |  |  | 3 | 3 | 3 | [11 empty] | 3 | 3 | 3 | 3 |  |  |  | 3 | 3 | 3 | 3 | [10 empty] | 3 | 5 | 5 | 3 |  |  |  | 3 | 3 | 5 | 5 |  |  |  | 3 | 3 | 5 | 5 |  |  |  |  | 5 | [5 empty] | 3 | 5 | 5 | 3 |  |  |  | 3 | 5 | 5 | 3 | [10 empty] | 3 | 5 | 5 | 3 |  |  |  | 3 | 3 | 5 | 5 |  |  |  | 3 | 3 | 3 | 3 |  |  |  | 3 | 3 | 3 | 3 |  |  |  | 3 | 3 | 3 | 3 | [38 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  |  | 3 | 3 | 3 | 3 |  |  |  | 3 | 5 | 5 | 3 |  |  |  | 3 | 5 | 5 | 3 |  |  |  | 3 | 5 | 5 | 3 |  |  |  | 3 | 5 | 5 | 3 | [24 empty] | 3 | 3 | 3 | 3 |  |  |  | 3 | 3 | 3 | 3 |  |  |  | 3 | 3 | 3 | 3
Štúrovo - Ferencváros | [48 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [18 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [51 empty] | 3 | 3 | 3 | 3 | 3 | [51 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [20 empty] | 3 | 3 | 3 | 3 | 3 | [58 empty] | 3 | 3 | 3 | 3 | 3
Vác - Hatvan - Újszász | [90 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Ferencváros - Szajol (100) | [172 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [16 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Ferencváros - Szolnok (120a) | [73 empty] | 3 | 3 | 3 | 3 | [83 empty] | 3 | 3 | 3 | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | [69 empty] | 3 | 3 | 3 |  |  |  |  | 3 | 3 | 3
Szajol - Curtici | [105 empty] | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Szajol - PL - Biharkeresztes | [205 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Curtici - Arad
Arad - Timisoara
Timisoara - Craiova
Craiova - Vidin tovarna
Arad - Simeria | [5 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Simeria - Brasov | [5 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Braşov - Chitila
Chitila - Constanta
Simeria - Filiasi
Craiova - Videle
Videle - Chitila
Videle - Ruse | [156 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Biharkeresztes - Coslariu | [125 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Vidin tovarna - Mezdra jug | [217 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Mezdra jug - Sofia
Sofia - Promachon | [5 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Sofia - Plovdiv | [5 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Plovdiv - Dimitrovgrad
Plovdiv - Mihailovo | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Stara Zagora - Dimitrovgrad | [64 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Dimitrovgrad - Svilengrad
Ruse - Karnobat | [64 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 5 | 5 | 5 | 5 | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 5 | 5 | 5 | 5 | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Karnobat - Burgas
Karnobat - Nova Zagora | [248 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Nova Zagora - Simeonovgrad | [95 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Nova Zagora - Stara Zagora
Promachon - Strymonas | [11 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Thessaloniki - Strymonas
Thessaloniki - Athina
Svilengrad - Alexandroupolis
Alexandroupolis - Strymonas
Bratislava - Komárno | [166 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
g
f
Update
Total Capacity Restriction
All day
Day/Night
Partial Capacity Restriction
All day
Day/Night

## Help
This interactive map works only when macros are enabled.
If you don't have macros enabled you will see the security warning (as shown below) when opening the document for the first time. Click options and enable macros:
HELP
i
I can't click on the map!
To avoid this security warning everytime you open the document, you can enable macros permenantly. Follow these steps:
1. Click on Office button
2. Click on Excel options
3. Select Trust Center
4. Click on Trust Center Settings...
5. Select Macro Settings
6. Enable all macros
Legal Notice
In the present overview, the infrastructure managers concerned have published the planning status for infrastructure availability restrictions along the related Rail Freight Corridor. The published measures constitute a snapshot of the situation at the date of publication and are subject to constant changes. Please note that the information provided should be used for rough orientation purposes only and may not constitute the basis for any legal claim.
Publication of possessions does not substitute any national law or legislation and RUs/applicants must refer to national network Statements.

## Data (hidden)
IM |  | Section |  | Direction | Duration | ID value | Reason for restriction | Total Closure | Reduced Track Availability | Speed Restrictions | Weight, Length, Profile | Diesel only | Cancellation | Re-routing | Train replacement | Other | In yearly timetable | Classification | Status | Automatic process | Year | Week
DB Netz AG | 80 | Wilhelmshaven - Bremen | 1 | < > | Continuous | 12808 | Signal | T | LT | S | W | Do | C,, | R,, | ,B, | O,, | Y | Major | Planned | Y | 2022 | 1
SŽCZ | 54 | Bremerhaven - Bremen | 2 | > | Periodical |  | Switch |  | ST |  | L |  | ,C, | ,R, | ,,B | ,O, | N | High | Coordination | N | 2023 | 2
ŽSR | 56 | Bremen - Hannover | 3 | < | Periodical continuous |  | Catenary |  | LT+ST |  | P |  | ,,C | ,,R | ,B,B | ,,O |  | Medium | Consultation |  | 2024 | 3
ÖBB Infra | 81 | Hannover - Magdeburg | 4 |  |  |  | Track & Rail |  |  |  | W+L |  | C,C, | R,R, |  | O,O, |  | Minor | Published |  | 2025 | 4
MÁV | 55 | Magdeburg - Falkenberg | 5 |  |  |  | Tunnel |  |  |  | W+P |  | C,,C | R,,R |  | O,,O |  |  | Canceled |  |  | 5
GYSEV | 55 | Falkenberg - Dresden | 6 |  |  |  | Bridge |  |  |  | L+P |  | ,C,C | ,R,R |  | ,O,O | [5 empty] | 6
CFR | 53 | Hamburg - Magdeburg | 7 |  |  |  | Miscellaneous |  |  |  | W+L+P |  | C,C,C | R,R,R |  | O,O,O | [5 empty] | 7
NRIC | 52 | Rostock - Berlin | 8 |  |  |  | Maintenance | [14 empty] | 8
OSE | 73 | Berlin - Dresden | 9 |  |  |  | Others | [14 empty] | 9
|  | Dresden - Děčín | 10 | [18 empty] | 10
|  | Děčín - Kolín | 11 | [18 empty] | 11
|  | Děčín - Praha-Libeň | 12 | [18 empty] | 12
|  | Praha-Libeň - Česká Třebová | 13 | [18 empty] | 13
|  | Kolín - Brno-Maloměřice | 14 | [18 empty] | 14
|  | Česká Třebová - Brno | 15 | [18 empty] | 15
|  | Brno - Břeclav | 16 | [18 empty] | 16
|  | Břeclav - Wien | 17 | [18 empty] | 17
|  | Gänserndorf - Devinska N.V. | 18 | [18 empty] | 18
|  | Wien - Ebenfurth - Sopron | 19 | [18 empty] | 19
|  | Gramatneusiedl - Wr. Neustadt | 20 | [18 empty] | 20
|  | Wien - Wr. Neustadt | 21 | [18 empty] | 21
|  | Wr. Neustadt - Sopron | 22 | [18 empty] | 22
|  | Parndorf - Bratislava | 23 | [18 empty] | 23
|  | Wien - Hegyeshalom | 24 | [18 empty] | 24
|  | Břeclav - Kúty | 25 | [18 empty] | 25
|  | Kúty - Bratislava | 26 | [18 empty] | 26
|  | Bratislava - Rajka | 27 | [18 empty] | 27
|  | Bratislava - Štúrovo | 28 | [18 empty] | 28
|  | Nové Zámky - Komárom | 29 | [18 empty] | 29
|  | Kúty - Galanta | 30 | [18 empty] | 30
|  | Rajka - Hegyeshalom | 31 | [18 empty] | 31
|  | Sopron - Győr | 32 | [18 empty] | 32
|  | Hegyeshalom - Ferencváros | 33 | [18 empty] | 33
|  | Štúrovo - Ferencváros | 34 | [18 empty] | 34
|  | Vác - Hatvan - Újszász | 35 | [18 empty] | 35
|  | Ferencváros - Szajol (100) | 36 | [18 empty] | 36
|  | Ferencváros - Szolnok (120a) | 37 | [18 empty] | 37
|  | Szajol - Curtici | 38 | [18 empty] | 38
|  | Szajol - PL - Biharkeresztes | 39 | [18 empty] | 39
|  | Curtici - Arad | 40 | [18 empty] | 40
|  | Arad - Timisoara | 41 | [18 empty] | 41
|  | Timisoara - Craiova | 42 | [18 empty] | 42
|  | Craiova - Vidin tovarna | 43 | [18 empty] | 43
|  | Arad - Simeria | 44 | [18 empty] | 44
|  | Simeria - Brasov | 45 | [18 empty] | 45
|  | Braşov - Chitila | 46 | [18 empty] | 46
|  | Chitila - Constanta | 47 | [18 empty] | 47
|  | Simeria - Filiasi | 48 | [18 empty] | 48
|  | Craiova - Videle | 49 | [18 empty] | 49
|  | Videle - Chitila | 50 | [18 empty] | 50
|  | Videle - Ruse | 51 | [18 empty] | 51
|  | Biharkeresztes - Coslariu | 52 | [18 empty] | 52
|  | Vidin tovarna - Mezdra jug | 53
|  | Mezdra jug - Sofia | 54
|  | Sofia - Promachon | 55
|  | Sofia - Plovdiv | 56
|  | Plovdiv - Dimitrovgrad | 57
|  | Plovdiv - Mihailovo | 58
|  | Stara Zagora - Dimitrovgrad | 59
|  | Dimitrovgrad - Svilengrad | 60
|  | Ruse - Karnobat | 61
|  | Karnobat - Burgas | 62
|  | Karnobat - Nova Zagora | 63
|  | Nova Zagora - Simeonovgrad | 64
|  | Nova Zagora - Stara Zagora | 65
|  | Promachon - Strymonas | 66
|  | Thessaloniki - Strymonas | 67
|  | Thessaloniki - Athina | 68
|  | Svilengrad - Alexandroupolis | 69
|  | Alexandroupolis - Strymonas | 70
|  | Bratislava - Komárno | 71